## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
89876595-8ede-49b9-b899-8017947ed107 | checklist | 561464-DOW-ITP-PC-005 EF Welding | itp | 561464-DOW-ITP-PC-005 EF Welding
c1e30351-6b1f-45ec-8481-c8339bdfc3bf | section | SECTION 3 – RECEIVING INSPECTIONS
988da88b-faf5-4145-ba97-81d82ff16d9a | checkpoint | 3.1 - Material delivery
790bf116-eaaa-5eba-b908-f933f8fb168a | note | Inspection Point: Quality Control Activity - Each pipe welding location check pipes to be welded
5f8bcd0c-eb74-51ec-92f1-f63d32f8f1a5 | note | ○ Each EF fitting
d2ce81ad-3f2f-5534-aea3-f597558675bd | note | ○ Check bags undamaged and sealed
6dc51a14-d326-518d-a445-b6dca23f4e21 | note | Acceptance Criteria - Pipes shall be DN315 PE100 PN20
06bc52f0-ff0c-5755-afea-dc05f49e04f9 | note | ○ EF fittings correct size, SDR, PE100 and pressure rating.
31008a2e-bdb3-500c-a2d8-9006851303c5 | note | Verifying Document - Photo of markings and labels on pipe.
86df8768-a9d5-591a-ac4a-368d7cdfb472 | note | ○ Delivery docket/ packing slip
2ffeef06-a050-591a-b69a-530b24e9ba59 | note | ○ Scan bar code on fitting
8ebd2e55-b930-5ec0-888f-c2dbb77c1ca2 | note | Frequency - On delivery
9cb550b6-16a0-5899-b68b-b67b4d99ea7c | note | Inspection Type (Visual, other) - Visual
01d2e968-c310-58ae-b050-a83eff214715 | note | Inspection: Key - V
ce43b4c5-58da-5332-ae41-bcb64aac3659 | note | Inspection: By - CR, IP
626931a2-ce2e-4cd0-914c-cf45a678a40c | checkpoint | 3.2 - Certification of welding equipment
f2de90cd-3bfa-5846-8c55-54f17ee9f4c4 | note | Inspection Point: Quality Control Activity - Confirming just one EF welding machine in use during life of project.
da74ee92-4ce9-5bbc-83f9-7c7cc2d59abe | note | Acceptance Criteria - Accepted by Client as suitable for use
fa6d3d64-608b-5a91-8d4d-183a55585627 | note | Verifying Document - Current calibration certificate/service record
271446e8-bfc3-520a-9044-beb5e7af7714 | note | Frequency - Prior to commencement of works
031f3630-1122-5f8a-880c-e2f97bf69efc | note | Inspection Type (Visual, other) - Hold point
4371b285-885c-5ad7-9063-c6c38cefe0be | note | Inspection: Key - H
be32ca52-d0cd-55c0-a49e-a748bbdb82a6 | note | Inspection: By - IP
6189bc5e-2ec7-4c81-9969-427f017d032b | signoff | AUTHORITY HOLDPOINT
e971d1c7-b20a-4d56-b7b2-19c10b71f7bb | section | SECTION 4 – IN-PROCESS INSPECTIONS
396d9750-b6cb-4756-b39f-44eea7dfbfb6 | checkpoint | 4.1 - PE Welding – Operator and Equipment
4b7756c3-85f4-5f59-a4ae-5cd850d2b493 | note | Inspection Point: Quality Control Activity - Competency certificate of welder and certificate of fitness for welding equipment
e8c356dc-e91c-5f88-831e-d9f686e46b9c | note | ○ Generator capacity adequate for the EF fittings.
cf199ed1-54ef-5479-80f9-ac137fc955c3 | note | Acceptance Criteria - Have peel decohesion test of weld samples carried out by an IANZ accredited laboratory.
014f630c-35d3-5eae-868d-790dceb89fcd | note | Verifying Document - Current welding certificates of operatives
1b49e27b-b4e2-5e74-a330-e50ef9ab8437 | note | ○ Current calibration record of welding Equipment
f92e8b0c-e1e4-5b82-a6cf-466762ee8b60 | note | ○ Peel decohesion test results
9ccb1fa3-25d5-5b30-8bfe-4807dbd0d9cb | note | Frequency - During Installation
3b48a67e-72af-5962-9107-de64ff6d360a | note | Inspection Type (Visual, other) - Inspection, Examine
94c9eb18-472f-5a33-a5f6-a18c807322a6 | note | Inspection: Key - I, E
b82c6407-4232-52a3-b41b-f7dd3ca3db27 | note | Inspection: By - CR, IP
ea9cb44c-40ab-49c3-b024-4c0b9969038c | checkpoint | 4.2 - Test Sampling
cdc70a16-79de-5267-b2b2-3681248edf1f | note | Inspection Point: Quality Control Activity - one pre-qualification per operator, one pilot weld per machine/per DN.
9cdd8145-fec6-5b21-9b2f-d1e7c2d5ec32 | note | Acceptance Criteria - Pass/Fail
f9e7f615-5e0d-55c6-847d-2628dcaecd27 | note | ○ ISO 13953 (Testing)
9691a34c-49e2-560a-af89-d161cd5df70e | note | Verifying Document - Peel decohesion test results from Kiwi Mechanical Ltd
14829eb8-72cf-58dd-9978-3b64965861e7 | note | Frequency - Every 20 welds per operator (or as requested by Client).
355904ab-35b3-5059-9ce5-45b8ba3c6bba | note | ○ Test frequency to be reduced in response to consistent pass results, with Engineers approval.
19349b11-3f4a-5456-9d41-75d787343096 | note | Inspection Type (Visual, other) - Operation, Review
6a1ba33c-5b18-5e77-aea6-413ff578b72b | note | Inspection: Key - O, R
3ad715ca-16dd-5256-bb42-736c0cff98a9 | note | Inspection: By - WS/CR, IP
caf63ee8-3d6d-471e-9d9b-d69102ea28b9 | checkpoint | 4.3 - Weld Completion
f48c3e1d-f12d-5fa0-9cb1-9c137fb97db0 | note | Inspection Point: Quality Control Activity - Weld completed to required standard and specification.
96ef4892-7de2-5642-9927-5e5b787c8c00 | note | ○ Only move strings after EF’s have cooled!
d9d39a04-2d8d-5dc7-8c0c-e6229c138779 | note | Acceptance Criteria - Pass/Fail
21dd90ce-d95a-5ab3-a61a-d23dde56e35a | note | ○ PIPA POP001 version 8.1 2021 and POP014
e21bbae8-6855-5024-92bc-486319492605 | note | ○ EF controller printout for all EF joints
8990d69a-f1f6-511d-989a-feec0249e218 | note | Verifying Document - Power App or manual records
f881470e-c718-59a7-bbfa-b765d2775d15 | note | ○ Data log from welding equipment
6a5bc7c6-344b-5943-9e92-7614bbcd020f | note | ○ Photo Log
dad5ab20-fd46-5c6b-98ac-f369722756d4 | note | Frequency - Each weld
932425f7-f076-5264-a500-38cbf115a9bb | note | Inspection Type (Visual, other) - Check, Dimension Inspection
39180c62-44ad-5a86-9638-28a2cfa36ea1 | note | Inspection: Key - C, D, R
53e436e2-ea2e-5b4c-b168-6a5a61b8e33a | note | Inspection: By - WS/CR, IP
f76a43e5-c841-45a0-8de7-fe42284394af | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
c9eb3f10-4ec9-4f87-86d6-0444ab171484 | checkpoint | 5.1 - Completion of QA
125ab79b-aabf-5a14-a788-e0ca845c5f9b | note | Inspection Point: Quality Control Activity - Ensure QA package complete.
08bf1b7c-bde5-546b-8eaf-9912de178dd4 | note | Acceptance Criteria - all necessary documents including HDPE welding compiled and handed over to ER in completeness.
e4f7096c-eb81-500a-a658-5f1c1b08fa7f | note | Verifying Document - Excel spreadsheet exported from Power App, includes weld photos and weld date from weld equipment.
5710ba99-1c92-52d2-972c-472f518c7dfa | note | Frequency - Before practical completion
aa5d2773-c0b5-5669-9695-9279e2340d17 | note | Inspection Type (Visual, other) - Inspection, Monitor on Random Basis
cf7612c7-4d00-5c56-8ed8-ba5e9712d79c | note | Inspection: Key - I, M
73bb0bd1-8783-5207-ac22-181f100100f0 | note | Inspection: By - CR, IP