## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e4245192-4076-48e8-bd5c-3ae8dead3324 | checklist | Add Documents & Photos |  | Add Documents & Photos
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0e56f51a-898f-4c46-83e4-15f33021466a | checkpoint | Please upload the relevant document(s) / photos and press PASS.
51534b79-4a97-46d0-a4bc-980d914787e9 | checklist | ITP - Drainage Manholes | itp | ITP - Drainage Manholes
ce7eee14-637e-4040-8d69-4b632f2c74a9 | section | WW 1.0 - Wastewater Manhole Setout
91758b32-30d6-4b4e-9b0c-b80e7af63271 | checkpoint | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
03b57c0c-d2cf-5203-a030-870ec3a30b56 | note | Acceptance Criteria - CI
d7d85df6-3ad4-58c8-afcf-bb4cf6ab369a | note | Verifying Document - Current Plan and Longsection revisions being used to install
8e3505c5-d4c3-459f-902a-53e02859de14 | checkpoint | 1.2 - Confirm Datum for Survey Setout
13e53fd0-aae9-5efd-8825-89ad3eeba6e0 | note | Acceptance Criteria - CI
0bb40608-e342-562a-be38-3bdc3edb0c4c | note | Verifying Document - Correspondence of Datum to use
0cba13d1-8a51-48ff-b3e8-727f81a325ee | checkpoint | 1.3 - Confirm existing and proposed drainage locations
bc0fef71-0a00-5b21-a49b-42b826f2deb5 | note | Acceptance Criteria - CI
0c7d8ec7-ad72-545f-bb90-220d715cc413 | note | Verifying Document - Asbuilt of Existing Manholes
3f65c5b1-ef54-4880-926f-3cdcb17f9eda | checkpoint | 1.4 - All wastewater pipes and manholes shall be placed in accordance with Engineer's model and locations given in design drawings.
61e8c021-54ea-5c47-b660-72864f618517 | note | Spec Reference/Special Conditions - Prelet
0bf059bd-65c8-5fe0-97a1-5437fefa105b | note | Acceptance Criteria - CI
28bd81fe-9515-5012-9256-34162270e799 | note | Verifying Document - Drainage Models provided by Engineer
76b3dfce-157e-4f8c-8068-5a25ebf149b8 | checkpoint | 1.5 - Wastewater Connection Authorisation approval from Veolia for Tie-ins into existing
4374a3ee-fdb1-5b53-b02d-c44d94c46fd4 | note | Spec Reference/Special Conditions - Veolia Requirements
27020a4d-f076-5ed9-936d-542888b293b6 | note | Acceptance Criteria - HP
fd0818a9-e75e-5ac0-a743-b6aaa13a43d7 | note | Verifying Document - Signed Wastewater Connection Authorsiation form from Veolia
2549a3c8-0cc2-4991-b7a1-3a3abfd733c3 | signoff | HOLD POINT
00bdfd6b-bedf-4a67-8dba-542784e2636d | checkpoint | 1.6 - Complete council Kick-off meeting
418d1d44-eb3d-5d0f-90a0-8584245db8fe | note | Spec Reference/Special Conditions - Building Consent
c823d993-c1c6-5e62-b5d9-72b95c10bf12 | note | Acceptance Criteria - HP
245d9320-8ccc-5c24-8544-68e93db3d264 | note | Verifying Document - Council inspection report
a80a2bc7-2b4c-4041-a66a-68e8854bbdab | signoff | HOLD - Continue only if the above is signed off.
c68b38ae-0627-43db-8d38-50e71b845e51 | section | WW 2.0 - Wastewater Manhole Excavation
91746b14-81e4-41c1-bb99-ee1e091289d8 | checkpoint | 2.1 - Manhole shall be placed on firm natural ground
ed41001e-3c8d-5d2b-8d37-b354ad2b9595 | note | Spec Reference/Special Conditions - Watercare WW 9
85b24835-975f-5b57-b76d-29269ec06b82 | note | Acceptance Criteria - CI
392c5dd6-9d57-5910-9c51-e0e65c041bda | note | Verifying Document - Photos
ecbce37f-75cc-4638-b3c5-5b84d12799ec | checkpoint | 2.2 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
7408d17a-f212-52c8-97f7-b6403d989dd7 | note | Acceptance Criteria - HP
16e0fb0b-b2aa-522b-9bfa-459a5cbde7e6 | note | Verifying Document - Geotech signoff
2890fb5f-fab8-464b-9828-31fefc2e6ff7 | signoff | HOLD POINT
8ba711f0-17e3-46b4-a9bf-397f6694bb6f | checkpoint | 2.3 - Breakout to commence only once Client have issued a site instruction
cee6bfcc-931f-5947-b36f-5fadc402a39e | note | Acceptance Criteria - WP
d2c56d1e-2a45-52f9-a76b-ae31ec5fe5f1 | note | Verifying Document - H&R Site Instruction
b2bbabbc-ccb9-4f71-b210-a0923ac21a86 | signoff | HOLD - Continue only if the above is signed off.
dc8069c8-d2bb-44ca-b748-99016059a046 | section | WW 3.0 - Wastewater Manhole Installation
f074809f-53ae-46c4-b0ee-15da332383c2 | checkpoint | 3.1 - Manhole Base to be laid on minimum 100mm bed of Gap20
8301a863-2870-5352-b00a-ae8d6fecef6c | note | Spec Reference/Special Conditions - Watercare WW 9
25efab79-8415-5b64-b07f-a52a08cfba0b | note | Acceptance Criteria - CI
cb592cca-2338-55b6-ab27-3906687b39ba | note | Verifying Document - Photos
f3a4572f-6fdf-44a0-98d5-0f4b96ea229a | checkpoint | 3.2 - Hydrophilic Seal Starters to be used to connnect into manhole
7d588171-c16d-53f4-aa98-5255dccdff7e | note | Spec Reference/Special Conditions - Watercare WW 5
9f6f30b6-14d6-5d86-9c8e-b2edbfb185a8 | note | Acceptance Criteria - CI
3a2efb16-a6bf-5091-8ebe-a7c9a5912b1a | note | Verifying Document - Photos
e825dcf7-15a3-4398-9b0f-99f76ebda627 | checkpoint | 3.3 - Haunching to be done on all lines entering manhole
3f538249-f87d-5240-ae26-7dca4524b741 | note | Spec Reference/Special Conditions - Auckland Council Requirement
02ff03e0-be65-53b6-9ac8-479ede2fa32d | note | Acceptance Criteria - CI
db125588-4cb2-52cc-8e1e-8345ec0c00db | note | Verifying Document - Photos of Haunching outside manhole
e37fe727-b7a4-4eac-9521-1a236f906700 | checkpoint | 3.4 - Asbuilt of Manhole invert levels prior to Auckland Council Inspection
f9d03c3c-6a69-51e9-9f1a-448ca162b65e | note | Spec Reference/Special Conditions - Auckland Council Requirement
f4c057a5-2965-5e07-8baf-e79e2030c58b | note | Acceptance Criteria - CI
39a3518c-7ada-5ae5-a679-1031e7a26be4 | note | Verifying Document - Asbuilt Drawing
a166801b-2076-41ef-9cde-d729749c02e7 | checkpoint | 3.5 - The position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
682c603e-3285-507d-a3f3-a683711f8616 | note | Spec Reference/Special Conditions - Watercare C3.1.1
9c6d6999-b287-5681-9516-a7e7b2c17d16 | note | Acceptance Criteria - CI
d4dd2001-4943-5447-af9c-db8bc04c9ddd | note | Verifying Document - M&P manhole sheet
f2463372-8aad-4832-a4e3-b552ce08b982 | checkpoint | 3.5 - Allow Auckland Council opportunity to inspect manhole Haunching prior to backfill
cfc751d4-503e-5b67-9c3b-5be110f636bc | note | Spec Reference/Special Conditions - Auckland Council Requirement
ba6c0c87-2185-5cea-a3c0-27fa508eb8ac | note | Acceptance Criteria - CI
cc91e0e2-c22c-53de-890a-1c5eb74faf86 | note | Verifying Document - Council inspection report
81dae6e6-83a1-49b7-b2ee-8a64814feff3 | checkpoint | 3.6 - Allow Veolia opportunity to inspect Tie-in prior to backfill
638a3bf8-a411-5eed-921c-c944c2212d5f | note | Spec Reference/Special Conditions - Veolia Requirements
fb7571d8-9ce7-5d7c-958d-148da69f5740 | note | Acceptance Criteria - CI
784c9d8b-2a16-590a-bff6-b2cbafb68ff9 | note | Verifying Document - Correspondence from Veolia
1bc0e2be-68b7-444e-8a05-7a77c80d8ff6 | checkpoint | 3.7 - Backfill Manhole in 200mm layers and conduct Clegg Hammer Impact Tests for Hardfill achieving CIV 25
045cf984-c7b8-5171-af9f-fa9ecbf0e37e | note | Spec Reference/Special Conditions - Watercare C2.21 row 12
2ad57ffb-4fa6-591f-afb0-c6df24ef82a4 | note | Acceptance Criteria - CI
68f5810d-8399-545c-9f2d-a4f9f5b69adb | note | Verifying Document - Clegg Hammer Results Sheet
616f1e79-730c-461d-a59d-b929af35d070 | checkpoint | 3.8 - Backfill Manhole in 300mm layers and conduct Shearvanes for clay fill achieving average value not less than 150KPA
ff437c23-ecad-57f2-a3a3-8008d3b6dd8d | note | Spec Reference/Special Conditions - Engenium Excavation and Hardfil Spec. Item 2.4
937761d7-dd4d-5427-9c4b-c8bebe9eb8c6 | note | Acceptance Criteria - CI
f6dea6d2-da4b-54e6-95fe-dc56540ce195 | note | Verifying Document - Shear Vane Results Sheet
6f5c4a54-e10c-45d5-a101-e19cd0da6fd3 | checkpoint | 3.9 - Benching to be done with Half Round Channel pipe earthenware
60823845-6864-59f9-a365-592fd22c2176 | note | Spec Reference/Special Conditions - Watercare WW5, Watercare WW9
02a22777-d8c0-5c66-8531-e4e1f82a63f6 | note | Acceptance Criteria - CI
b045ec3e-1d3d-50ae-a49b-13f0d1c20c76 | note | Verifying Document - Photos
0b1ea7f5-7bc1-4bc9-a183-dcc51ac48bea | checkpoint | 3.10 - Steps to be installed, ensure that lid opening is orientated on sthe location of steps.
7a1f8304-9de4-58a2-8c89-0facd84018cb | note | Spec Reference/Special Conditions - Watercare WW 5
c92b0e63-39cf-5738-a7d8-aed0e9666fac | note | Acceptance Criteria - CI
c0c5cbff-ac7f-5250-a251-d2d1add061d4 | note | Verifying Document - Photos
8b1389af-2b23-4cd7-85d9-8351cbe45665 | checkpoint | 3.11 - Ensure full entry depth of throat is not greater than 450mm and that the finishing around it is complete.
55b82816-d8bf-5036-a951-58e10f12f99e | note | Spec Reference/Special Conditions - Watercare WW 6
ae73af5e-cbe5-5ce8-b716-5a7f78913552 | note | Acceptance Criteria - CI
a7552c79-ee1e-57a7-b1b8-f54fa6b6bf9a | note | Verifying Document - Photos
9e4e2c5c-f4bd-4672-b757-a8be8f80fd06 | checkpoint | 3.12 - Manhole covers in the road shall be constructed so that the cover hinge is facing the oncoming traffic, for all other covers the orientation should be so that the cover hinge is at 90 degrees from the ladder, either side.
a68acfe9-8bce-59ad-8671-90089aaaa23d | note | Spec Reference/Special Conditions - Watercare WW 6
9aa12375-8557-5c72-8087-6d31a59d4124 | note | Acceptance Criteria - CI
ecc40653-b4a7-5fc7-b957-8134d21bdd32 | note | Verifying Document - Photos
8b79ad7d-b94b-46cc-8412-5e687f48f06f | checkpoint | 3.13 - Safety Grille to be installed
e1ccc87d-2b2e-562b-b1a7-13959a32a148 | note | Spec Reference/Special Conditions - Watercare WW 7
be05798e-6626-5528-ad7e-6c28d06525ae | note | Acceptance Criteria - CI
ad459374-c52c-510e-b831-97789321c07a | note | Verifying Document - Photos
b6c73a6a-b80e-4bcf-b9a2-07ea4915ad5c | signoff | HOLD - Continue only if the above is signed off.
3a3a66cc-c24f-4427-8c0a-178146c40bdb | section | WW 4.0 - Handover to client with PS3
5da75e77-f10c-4940-8877-68b410a58d7f | checkpoint | 4.1 - Complete Council final drainage inspection
6f1ed252-3913-5f15-8d85-478c2539e6c1 | note | Acceptance Criteria - HP
32da468e-c4e2-56aa-9df4-b2d424e692de | note | Verifying Document - Council inspection report
f90e80dd-4b6c-4fab-bfd3-dc28852432b9 | signoff | HOLD POINT
5c83d780-85f1-4d8c-9fe3-081055321c00 | checkpoint | 4.2 - Complete Engineer final drainage inspection
79c42fd6-4739-55eb-ac84-49b02ee49e7e | note | Acceptance Criteria - HP
817f868f-867c-5376-8bdf-29c3e94f007e | note | Verifying Document - Correspondence Engineer
3e73b208-12cf-44b6-b212-d0288241a7d0 | signoff | HOLD POINT
bd009103-155c-47c0-a9be-03e8da128fa7 | checkpoint | 4.2 - As built all pipe invert levels in manholes and CP and lid levels
2742e72d-2a92-51fa-af0a-e30fdfde00e7 | note | Acceptance Criteria - HP
9c4fd508-93fc-50f0-8917-b9e00a69b004 | note | Verifying Document - As built report
100d8ca1-d50b-4d31-a615-38f1e3db48da | signoff | HOLD POINT
00607f39-1a0a-4a00-818f-1d1ff20611dc | checkpoint | 4.4 - Handover to client with CS3
852f2ac4-9d2a-57c0-90e0-7eb3b60a4bd8 | note | Spec Reference/Special Conditions - CS3 Drainage
c9a140d0-d1f5-5f19-ad9f-50c0740b7ac0 | note | Acceptance Criteria - HP
c372de91-d66e-5895-a847-a846bffc1fb7 | note | Verifying Document - Handover documents
b11fb0cd-3618-48eb-8ad6-1ca28ef88cec | signoff | HOLD POINT
12417cfa-bab5-45b0-8acf-acb8303e7acb | checkpoint | Comments / Required Actions:
72ca1ae9-d031-57a9-8a80-6975b4c0e349 | textbox | Rev. Status
ff81aaf4-cd7f-5e8e-be33-a19567f2635f | date | Date
b545ed73-d694-5fce-8b57-8802fd2ad50c | textbox | Reason for Rev.
95baf96b-3cb1-46af-9ded-5c3292e44317 | checkpoint | Signed by:
0fc25e08-23b6-55cb-a320-94859a987c9d | note | Contractors Representative
fe5d5b95-80f3-525b-9fc6-cf7066b7587e | textbox | Print:
181151fb-8d5b-547a-a957-c72f65fa4ddf | date | Date:
b20e2181-7339-5dd7-afec-573d24844999 | note | Clients Representative
f7914557-8c53-52a6-ae90-ace2efcfdde5 | textbox | Print:
52365a2e-e1d1-55f9-b7d1-fbda53c84828 | date | Date:
3ff949e6-1c14-4318-84f1-fedf54399f99 | signoff | Signatures:
9ab78db1-c7dc-44bc-bebf-f3213a6ba799 | checklist | ITP - HD Detention Tank | itp | ITP - HD Detention Tank
869f6599-baf1-4008-98b1-95bf9ae4e971 | section | SW 1.0 - Agreements Prior to Install
361872c3-28df-4877-99f1-0a3e3d8dd97a | checkpoint | 1.1 - Agree on materials to be used prior to install, GAP 20 and A19 Bidim
971bc333-16da-57f4-ac25-0297147b2d28 | note | Spec Reference Special Conditions - N/A
b5a925cc-5af9-572c-b9cc-5d442f886d17 | note | Acceptance Criteria - CI
25f1b751-ffb2-56a5-b675-143d95a64c15 | note | Verifying Document - Email Confirmation
f96d5874-b2d9-47ba-8126-5438003f48be | checkpoint | 1.2 - Confirm Drawings and any additional instructions
b55b08ff-c331-5894-a24d-7d5f8e6785b4 | note | Spec Reference Special Conditions - N/A
f839b889-4dd1-5a7d-a277-97ef5a61d333 | note | Acceptance Criteria - CI
9978ec95-ec5f-54b4-b60c-b655fba67987 | note | Verifying Document - Correspondence and Procore Drawings
9b100462-e268-4fe6-b11d-51e970489cce | section | SW 2.0 - Detention Tank Excavation
2ddc8dbf-b1fd-4a4b-a2a8-0be84917d1f5 | checkpoint | 2.1 - Subgrade Testing of Detention Tank
4b48dc0f-89af-52d8-96bd-c38eb5d7eeb8 | note | Spec Reference Special Conditions - C410 Rev 6
b1278d24-cf92-59fc-ac34-389790411bfc | note | Acceptance Criteria - CI
53d92000-693d-5138-a83b-93ed0abc50e5 | note | Verifying Document - Photos and Testing
f6d5ad6c-0e2c-4732-826a-ce5836a3d273 | checkpoint | 2.2 - Gap 20 Testing of Detention Tank beneath Tank
d11c8fc0-7d9b-5a8c-93e1-a7e7a832fc7e | note | Spec Reference Special Conditions - C410 Rev 6
f43aa0ac-f13f-58e1-9933-3c7ca54d0e75 | note | Acceptance Criteria - CI
9c830638-863f-53cc-8a4b-50cb8ae455b7 | note | Verifying Document - Photos and Testing
1d77854a-9dc0-4cf6-8178-cc3427b405a3 | checkpoint | 2.3 - Laying A19 Bidim
c4b80d08-066d-5a8a-9881-a44e7dfb3c43 | note | Spec Reference Special Conditions - C410 Rev 6
a58434ed-7afc-5626-b2ef-9e47a3594d09 | note | Acceptance Criteria - CI
477410fb-a6fb-58ef-9d6d-293b4bfeacaf | note | Verifying Document - Photos and Testing
52acda46-37cd-49e8-8798-967f78eedbf6 | section | SW 3.0 - Detention Tank Install
cc7e5ecf-d362-44eb-b136-11489c868874 | checkpoint | 3.1 - Tank Installation
60121d05-16b1-5079-bd58-4ba3450fe9bc | note | Spec Reference Special Conditions - N/A
9fb87be3-c0f3-5dc2-abaf-6cf01001d045 | note | Acceptance Criteria - CI
620985f2-5f91-5f3f-93d7-836bc1d1ab55 | note | Verifying Document - Photos
94a6562f-f39c-4d2e-bac5-c01da3b40925 | checkpoint | 3.2 - Tank Connections
59c5990f-d3cd-5c0c-9d9b-73ab080d160c | note | Spec Reference Special Conditions - N/A
269369fb-22dc-5ce5-b508-76e8a7dd2de8 | note | Acceptance Criteria - CI
d31bbb10-c8d4-5f28-9129-d03f74140886 | note | Verifying Document - Photos
13e7adbd-f787-4cf5-a92a-2f0f66ec6b92 | section | SW 4.0 - Detention Tank Backfill
08942754-d119-4543-b56b-ba8d09d58e01 | checkpoint | 4.1 - Backfill on Sides of Tank
0fb81937-10bc-59a1-9a6c-a66e23763c87 | note | Spec Reference Special Conditions - N/A
a2a105df-0a98-5f15-80ae-d6c2598905f9 | note | Acceptance Criteria - CI
810263d8-fe4f-549c-8389-fc1f7ab0e6b3 | note | Verifying Document - Photos with Clegg Results
d4079338-61a3-4a45-b269-bdc2300252d6 | checkpoint | 4.2 - Backfill on top tank with GAP 20
6a684a90-46c2-5c25-bc87-f3a58a6c0571 | note | Spec Reference Special Conditions - N/A
c46143a7-d54c-5ab7-b7df-cb1310731565 | note | Acceptance Criteria - CI
c39b1f33-7d33-555a-ae74-87434148677f | note | Verifying Document - Photos with Clegg Results inlieu of Nucs
0cea4aaf-d7fa-4b30-9cd0-5e35bdcbda00 | checkpoint | 4.3 - Backfill on top tank with DQ65 to Subgrade
34332c71-f980-5ff8-831f-6e16f090fded | note | Spec Reference Special Conditions - N/A
cd16a288-abd7-530e-a497-2d99da08fc38 | note | Acceptance Criteria - CI
692ecbb3-b959-59a1-aed3-ce38bbedd0d1 | note | Verifying Document - Photos with Clegg Results
8aa0c970-521f-4694-bed7-d2d901aba4bb | section | SW 5.0 - Signoffs
4cdc14db-aae1-438b-93f7-3721c198cf72 | checkpoint | 5.1 - Auckland Council Inspection
4a74c481-a91a-5944-b159-a31802f45ce1 | note | Spec Reference Special Conditions - N/A
a90820e4-eb95-5ec9-a680-b1ae4579182f | note | Acceptance Criteria - CI
74303150-d299-55a3-9549-292bdebaf563 | note | Verifying Document - Council inspection report
727be688-5bd7-41b2-84a7-c79c5b44f05d | checkpoint | 5.2 - ACO Sign off
193739ca-3356-5da3-8612-43289a191854 | note | Acceptance Criteria - CI
5ab27d75-6357-5c6d-a2ca-7c1b98e20e78 | note | Verifying Document - Email Confirmation or formal document
b8c5d45c-e6d5-4f2a-a7fb-e8337e9419fa | checkpoint | 5.3 - Contractor PS3
a67230f0-3588-56ab-aa12-4573cfa9cc67 | note | Acceptance Criteria - CI
5b8361c3-27a2-53cf-ac85-918922b61283 | note | Verifying Document - Producer Statement 3
116d2ceb-1e03-45af-b1a8-eb0414192afa | checkpoint | 5.4 - Handover to client
28b63585-7194-5b37-ae2f-5fd276e3882c | note | Acceptance Criteria - CI
a4dd1097-b79c-59ea-af68-c2c830c7ab66 | note | Verifying Document - Handover documents
e25878a1-998d-4880-b4a4-5dbb0eff489d | checkpoint | Comments / Required Actions:
2facdc6d-4eb1-50c2-af44-221d9550eeb0 | textbox | Rev. Status
0b359be6-f3d3-5644-a7fe-0c18f139b064 | date | Date
8d601cd3-97e7-522a-9632-fb2f9994dfd9 | textbox | Reason for Rev.
45d8e55c-1d44-43bc-a99e-9bfd22642ff7 | checkpoint | Signed by:
7faa1411-2ee7-5196-902b-48080a7b1944 | note | Contractors Representative
93a1d23d-d4c7-5522-a4a6-cf3149450db7 | textbox | Print:
e960c4ca-2749-5ede-a65a-9527aca5d0fd | date | Date:
54118296-b446-53d3-b1a0-406a802ba5bd | note | Clients Representative
a92dbed9-31a3-5030-894a-d0599bdfbd21 | textbox | Print:
beaa5c4f-af34-58b1-b350-f6bf565f3865 | date | Date:
3488af27-2460-457f-83cb-8a7c492d6899 | signoff | Signatures:
40555011-0758-4fa3-880a-04d3499a4546 | checklist | ITP - Stormwater Drainage Lines | itp | ITP - Stormwater Drainage Lines
7860d96b-0460-4fa3-a0c1-1ec553623a52 | section | SW 1.0 - Stormwater Line Setout
9627559b-6365-47ae-8460-988ec734bdcb | checkpoint | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
f119ea80-de97-5686-9637-4ed0d2eaeb0b | note | Acceptance Criteria - CI
9ce1d001-fb1a-5fd4-a5da-806132eea8ec | note | Verifying Document - Current Plan and Longsection revisions being used to install
582dbf58-cecd-4b00-ae16-b5430b031c80 | checkpoint | 1.2 - Confirm Datum for Survey Setout
6838b07c-407a-5306-8c18-b5583a167524 | note | Acceptance Criteria - CI
5c0f98fb-e0b3-5303-a3b1-155a1c4ce190 | note | Verifying Document - Correspondence of Datum to use
05fe8839-8aa4-4e6c-8134-7bd381a0e596 | checkpoint | 1.3 - Confirm existing and proposed drainage locations
45a6c551-56de-5bb0-babb-4c358dee32b6 | note | Acceptance Criteria - CI
58cb5a1c-8aa3-5e4c-95d2-051fabba35bb | note | Verifying Document - Asbuilt of Existing Manholes
d2507f49-a6b1-4660-8d49-1ad2c67241ca | checkpoint | 1.4 - All wastewater pipes and manholes shall be placed in accordance with Engineer's model and locations given in design drawings.
7e0b3669-b4a9-5966-a9e7-264da8ea62f9 | note | Spec Reference/Special Conditions - Prelet
0ee5086d-c446-5e9c-aeae-df5c9affb6fb | note | Acceptance Criteria - CI
e50853cf-a1ca-5c79-a03a-964c423d9315 | note | Verifying Document - Drainage Models provided by Engineer
de36abdf-63f7-4a00-b4b3-38c509751d9a | checkpoint | 1.5 - Complete council Kick-off meeting
544c5059-ad4a-5691-9d0f-c13281c19b18 | note | Spec Reference/Special Conditions - Building Consent
caf1c1bc-408c-5ca7-bd4d-3f774271aa74 | note | Acceptance Criteria - HP
b295da35-1396-5208-b90b-2336e1c5d048 | note | Verifying Document - Council inspection report
09c1555b-d5ba-4d20-aa90-dd79a3f799d3 | signoff | HOLD - Continue only if the above is signed off.
09047965-125a-40f8-8934-71a9fb40ca7f | section | 2.0 - Stormwater Line Excavation
84a1c1d7-2251-4583-8f9a-2079885e423a | checkpoint | 2.1 - Wastewater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth. Use trench shield if battered cannot be achieve.
b3e5ee17-83e6-5d55-b210-613140ff1180 | note | Spec Reference/Special Conditions - NZS 4404:2010, AS/NZS 2566.2, WorkSafe NZ – Good Practice Guidelines: Excavation Safety
5d3bdd4d-fd94-55f5-941a-d6e3e40a9e8d | note | Acceptance Criteria - CI
ff40607f-76a2-53a5-bb2c-53eee1407144 | note | Verifying Document - Photos
714b3a87-f05c-460d-a943-1fcad8b9ae5a | checkpoint | 2.2 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
ff44fe76-4979-5386-8a5f-1eedf7f1aaab | note | Acceptance Criteria - HP
eb07eec2-e976-56bd-9af5-1d2c365413bf | note | Verifying Document - Geotech signoff
09347849-b4fa-4f66-b334-ed6366c3fd32 | signoff | HOLD POINT
ff53bb40-67d1-4197-9188-e3f74de431cf | checkpoint | 2.3 - Breakout to commence only once Client have issued a site instruction
3141f490-4942-54d0-84db-276dd2a8dc21 | note | Acceptance Criteria - WP
65f46c0e-1910-54f4-b8fe-e9e8951b3ea1 | note | Verifying Document - H&R Site Instruction
4304b497-6aac-45c3-b4a2-21f2cbfdc9e9 | signoff | HOLD - Continue only if the above is signed off.
aff16f87-22b8-4a9c-8faf-8f6557dd3aae | section | SW 3.0 - Stormwater Line Installation
6b689ead-d654-40bd-9786-6c3580d2ded9 | checkpoint | 3.1 - The position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
a27ed81b-24f6-57d5-9071-878853b0b5ab | note | Spec Reference/Special Conditions - Watercare C3.1.1
20dabdce-4c41-5462-91c3-4b7a5ba39bf5 | note | Acceptance Criteria - CI
48c72b9a-9c03-5d12-bf0a-6afcd5aa4528 | note | Verifying Document - M&P longsection sheet
62b80528-e0d5-4bf1-a5d7-67e86bc1b6a3 | checkpoint | 3.2 - Ensure grade with digital spirit level matches design grade along pipe alignment
b97f9e4d-381a-589c-a101-b1e1499ce297 | note | Spec Reference/Special Conditions - Auckland Council Requirement
4871ad51-ca48-5157-8f12-71b50a4ae6e2 | note | Acceptance Criteria - CI
70e8a5f1-6fcf-566d-830a-254317391e8d | note | Verifying Document - Photos along alignment
d0da5ec4-dea8-41ac-913b-f94d209cf389 | checkpoint | 3.3 - Asbuilt of pipe invert levels prior to Auckland Council Inspection
4093fa6f-b498-5612-aa56-37c5b32686b4 | note | Spec Reference/Special Conditions - Auckland Council Requirement
082e22e1-77bc-5060-a621-3a30911c5bc2 | note | Acceptance Criteria - CI
2ace9bc7-e828-5ee8-a598-9514cf1969b8 | note | Verifying Document - Asbuilt Drawing
490a715d-d3d9-4022-b16e-9c80162a6df3 | checkpoint | 3.4 - Allow Auckland Council opportunity to inspect pipeline prior to backfill
4b62d1db-ad9c-5699-b157-adaf5378295d | note | Spec Reference/Special Conditions - Auckland Council Requirement
5f7edeef-6be1-5d18-9d70-8344155484bb | note | Acceptance Criteria - CI
85c5525e-5af8-5b82-a14c-4a3ec368059e | note | Verifying Document - Council inspection report
077199b2-0a74-4fae-8563-63e5b87e4c93 | checkpoint | 3.7 - Backfill line in 200mm layers and conduct Clegg Hammer Impact Tests for Hardfill achieving CIV 25
e773cb88-8339-504b-ab42-cc4fc3b66fad | note | Spec Reference/Special Conditions - Watercare C2.21 row 12
179c3618-31d1-5b33-847a-aead23a670da | note | Acceptance Criteria - CI
f90717d7-c53b-598f-a32b-de2bea4b2538 | note | Verifying Document - Clegg Hammer Results Sheet
1a9ecef8-b39a-4ae1-85a3-2fb95f8a433f | checkpoint | 3.8 - Backfill line in 300mm layers and conduct Shearvanes for clay fill achieving average value not less than 150KPA
fc760f7e-1f5b-5d46-8a3c-f9025d9750b4 | note | Spec Reference/Special Conditions - Engenium Excavation and Hardfil Spec. Item 2.4
bbbea72d-efb7-570d-a0a3-84738688f734 | note | Acceptance Criteria - CI
c812e939-15a6-5450-8062-1f24cced8b4f | note | Verifying Document - Shear Vane Results Sheet
7a2feda5-d404-4de2-96e3-46abf52c3f38 | checkpoint | 3.9 - Pipework shall be CCTV inspected for defects, in particular pipe joints and to identify ponding areas for correction in gravity systems
b2297a4f-d49b-55f1-8c33-daae0f9bec33 | note | Spec Reference/Special Conditions - SWCOP
fdcea458-774a-55da-b5d5-6bbe81e4bd89 | note | Acceptance Criteria - CI
49206a06-6da8-532b-a537-14ffd6da446c | note | Verifying Document - CCTV Footage and Reports
d555939b-45bc-4fa1-ac9a-62e50b4266d8 | signoff | HOLD - Continue only if the above is signed off.
2ede7171-a36d-496c-977f-f63619a28e46 | section | SW 4.0 - Handover to client with PS3
3f9e2b05-585c-4fe7-88b2-1d499502babe | checkpoint | 4.1 - Complete Council final drainage inspection
a97a3899-fc54-50de-8f21-6e167c11fe7b | note | Acceptance Criteria - HP
2d109146-7110-5752-9871-5096ad84debf | note | Verifying Document - Council inspection report
1bdd76ed-2e09-4ea2-b022-69b5e50e7627 | signoff | HOLD POINT
3ee8bab0-3b34-430b-8341-d9fbd4ce8a9d | checkpoint | 4.2 - Complete Engineer final drainage inspection
264f5277-dba1-5a2e-bbde-efa16d9a5638 | note | Acceptance Criteria - HP
cd58561c-34bb-523a-ae4c-db5140ad553b | note | Verifying Document - Correspondence Engineer
3570b631-a57a-4901-b4f6-b4426a6b6d12 | signoff | HOLD POINT
7a875ac4-e293-4908-bebf-a14ea104105f | checkpoint | 4.2 - As built all pipe invert levels in manholes and CP and lid levels
79dfa501-4a70-5d6e-909b-6c8bb1a18ef7 | note | Acceptance Criteria - HP
b1a26b00-ed92-5213-a4a8-d664a0767725 | note | Verifying Document - As built report
9ff88e86-3a78-4436-bf91-4041533670f5 | signoff | HOLD POINT
1fd31d78-efad-42b5-b5bf-0a8452371f05 | checkpoint | 4.4 - Handover to client with CS3
206cf5e3-5506-540c-a673-6caefbbd3a97 | note | Spec Reference/Special Conditions - CS3 Drainage
bbde8453-dbbb-5e04-89d0-574b8282b539 | note | Acceptance Criteria - HP
83497e6b-1142-531f-adee-c51b294d0bf8 | note | Verifying Document - Handover documents
7fb37d94-9f1b-44ed-b22d-2b9a3b0b6ca0 | signoff | HOLD POINT
40922735-4c02-426c-83a5-8855af870762 | checkpoint | Comments / Required Actions:
542a1c65-8812-581d-9f76-9f1846b56135 | textbox | Rev. Status
cd11cac1-21f5-5ed2-8033-4f1b43dbb83a | date | Date
37f32dbf-6fed-5955-9614-4ab8e42409d1 | textbox | Reason for Rev.
79c957ef-ebd2-4286-9473-623027f8f5e0 | checkpoint | Signed by:
85c3deef-46e3-5df1-81ec-d0da98437a22 | note | Contractors Representative
df05775e-ec11-5b77-8d4b-fccf0166eaad | textbox | Print:
4de1ec3a-b97b-51bb-a45a-9f8e8e477446 | date | Date:
f374d965-d951-5389-8ab3-0fb14f92706f | note | Clients Representative
10dfebf1-a3bc-5a0b-a819-478d877b6e77 | textbox | Print:
d0547a2f-d2ec-50cd-b6fd-9517d5bf699b | date | Date:
08fd766d-8283-4f55-ae48-863e24ac99c0 | signoff | Signatures:
29d87b3b-4e51-4314-b2de-1802ecaf82ef | checklist | ITP - Stormwater Manholes | itp | ITP - Stormwater Manholes
ed7aa129-5206-489b-8091-f7909fa1809f | section | SW 1.0 - Stormwater Manhole Setout
4cac976c-7353-4ef2-8a85-4ae2afa851d3 | checkpoint | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
cdb9ac13-0226-584d-988b-3ded28fbfe14 | note | Acceptance Criteria - CI
7c60e366-454c-585a-9d84-93bdc4eb3a33 | note | Verifying Document - Current Plan and Longsection revisions being used to install
53ba1638-fe14-40a0-8151-2675cdcc7d40 | checkpoint | 1.2 - Confirm Datum for Survey Setout
8c2bf068-a7f6-56da-a87f-b9d15dbe8470 | note | Acceptance Criteria - CI
377186b2-ef40-56c9-9731-df4a3ae9b67b | note | Verifying Document - Correspondence of Datum to use
180cad15-02d5-4cf6-a286-be692b58af1f | checkpoint | 1.3 - Confirm existing and proposed drainage locations
b8a41726-ad35-5407-ab43-8024ec5effc8 | note | Acceptance Criteria - CI
e39e2a85-0a84-599f-8176-6fd81b7f506b | note | Verifying Document - Asbuilt of Existing Manholes
8bb0b156-e022-41c3-a67d-6697db5b3ff2 | checkpoint | 1.4 - All wastewater pipes and manholes shall be placed in accordance with Engineer's model and locations given in design drawings.
85f9498f-72c1-5f36-80fa-6838b397ddec | note | Spec Reference/Special Conditions - Prelet
092ca48a-0505-5aee-bc36-f6008a9b26f7 | note | Acceptance Criteria - CI
0dbe5ca7-f1ba-524f-9950-242f070836f7 | note | Verifying Document - Drainage Models provided by Engineer
ab767c90-a4de-48b1-b7b2-9885bbe35830 | checkpoint | 1.5 - Complete council Kick-off meeting
cc476855-bb09-5cf7-8249-a208284b695a | note | Spec Reference/Special Conditions - Building Consent
df680a2f-0701-5424-85fd-7e517442565e | note | Acceptance Criteria - HP
98bde65a-f020-54f6-82dd-0e32f7f06938 | note | Verifying Document - Council inspection report
3838b391-a79c-4134-a832-39c891e5ae1b | signoff | HOLD - Continue only if the above is signed off.
fc18f848-9e23-420a-9225-a1f8edbfd037 | section | SW 2.0 - Stormwater Manhole Excavation
91a1d0ea-11e6-45f6-9cc0-6895631aeb12 | checkpoint | 2.1 - Manhole shall be placed on firm natural ground
4351116d-da42-5219-9e6e-679f0feda810 | note | Spec Reference/Special Conditions - SWCOP SW06
5070ba1c-5938-5ff9-95cf-5e8e295d236e | note | Acceptance Criteria - CI
f613739d-67ac-5992-a08f-09e96a9b5d3b | note | Verifying Document - Photos
270e4e57-de59-4ef1-9047-9ce454382867 | checkpoint | 2.2 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
e2f86057-b590-5a5f-8cbf-70b4f4378f46 | note | Acceptance Criteria - HP
d2c87c4b-5e5d-5c09-b42b-8e6064481662 | note | Verifying Document - Geotech signoff
ec7e2bf1-a59e-437c-886e-9b7e6153c0e0 | signoff | HOLD POINT
882d853a-55f7-4957-a56f-e0bf152f9a4e | checkpoint | 2.3 - Breakout to commence only once Client have issued a site instruction
70c474b4-3b82-5c6d-9153-8dd7244c6257 | note | Acceptance Criteria - WP
2e9b6bf3-b80f-5505-b115-275e7ba34263 | note | Verifying Document - H&R Site Instruction
4a9a642c-58b5-4301-a435-09cc73d64a8d | signoff | HOLD - Continue only if the above is signed off.
72c865aa-5a59-4bc3-bca4-3f1cebaf615c | section | SW 3.0 - Stormwater Manhole Installation
053f0081-3880-4bb8-ac9c-1ad36bb88e19 | checkpoint | 3.1 - Manhole Base to be laid on minimum 100mm bed of Gap20
b2259bb7-8a90-5389-896c-355562dceb61 | note | Spec Reference/Special Conditions - SWCOP SW05
49b4edde-575f-580d-8a9f-0ad6b1c1a480 | note | Acceptance Criteria - CI
7e51b994-bbd0-50b4-95d3-d9934f97baba | note | Verifying Document - Photos
15441d27-d5d4-433e-b059-a23b39c714c5 | checkpoint | 3.2 - 600mm max Starters to be used to connnect into manhole
2252a50c-ac40-5f58-9d88-ee3ed990ac2c | note | Spec Reference/Special Conditions - SWCOP SW04
a75e969f-8d1c-580e-a561-570e5628ca1f | note | Acceptance Criteria - CI
6d6883c0-6908-5b39-86fe-9e8ab7300ed8 | note | Verifying Document - Photos
44d3b888-80ec-4747-819e-cb47e751ebbb | checkpoint | 3.3 - Haunching to be done on all lines entering manhole
b833e391-3ac9-581a-8d33-e5cb60dd05c6 | note | Spec Reference/Special Conditions - Auckland Council Requirement
6d96479f-9870-5331-96c7-19c6098e7802 | note | Acceptance Criteria - CI
9744e08e-f101-5df6-a856-c31e1e55abaf | note | Verifying Document - Photos of Haunching outside manhole
5c0573e6-17b4-4945-8672-212779560b90 | checkpoint | 3.4 - Asbuilt of Manhole invert levels prior to Auckland Council Inspection
482a412e-f845-5586-a11c-9b96198f2994 | note | Spec Reference/Special Conditions - Auckland Council Requirement
8f60edd9-c04d-56dd-ac28-9b2459251c49 | note | Acceptance Criteria - CI
e2f0bde8-9af4-58ba-b7c8-d46cedec2cee | note | Verifying Document - Asbuilt Drawing
709fffa9-dfa5-4f56-80bd-c1d59448d4bd | checkpoint | 3.5 - The position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
2fca6201-2c05-594a-b793-46171e8cee53 | note | Spec Reference/Special Conditions - Watercare C3.1.1
ad19ace0-7be0-550a-8b08-4315551fd056 | note | Acceptance Criteria - CI
c8fa1e97-9533-5d80-82f3-27b4850ecb18 | note | Verifying Document - M&P manhole sheet
3b9d0da3-76f2-4496-bc88-5be88c26738e | checkpoint | 3.5 - Allow Auckland Council opportunity to inspect manhole Haunching prior to backfill
00ecbbe9-cf91-5e5b-8148-cb95f5b1fc84 | note | Spec Reference/Special Conditions - Auckland Council Requirement
05231f39-145e-54a5-bb95-3480e9baa45b | note | Acceptance Criteria - CI
3c8327f8-eb22-5255-bf7d-47b4c5b70369 | note | Verifying Document - Council inspection report
2190cda1-2643-4bf4-b825-b76a672b94cc | checkpoint | 3.6 - Allow Veolia opportunity to inspect Tie-in prior to backfill
f8e4f014-e431-5797-b2fb-f5acd04d136e | note | Spec Reference/Special Conditions - Veolia Requirements
b74d9c38-ec2c-5e16-b3cb-432dadb63fe0 | note | Acceptance Criteria - CI
2901f20b-4a93-5a60-b32b-de08e2df7573 | note | Verifying Document - Correspondence from Veolia
b1b0f7c9-7673-418c-9cb8-f79a900edf11 | checkpoint | 3.7 - Backfill Manhole in 200mm layers and conduct Clegg Hammer Impact Tests for Hardfill achieving CIV 25
a67e99ba-cb2e-554c-a04d-f4fa8d44250f | note | Spec Reference/Special Conditions - Watercare C2.21 row 12
3c92e32f-f950-50d2-a57f-de6c79d65846 | note | Acceptance Criteria - CI
9a26571e-f20e-5363-8293-302eff360bd8 | note | Verifying Document - Clegg Hammer Results Sheet
b0d9bfd0-55af-4bd3-85af-c1019866b096 | checkpoint | 3.8 - Backfill Manhole in 300mm layers and conduct Shearvanes for clay fill achieving average value not less than 150KPA
f731d3f3-21c5-5b18-822d-db74528b8424 | note | Spec Reference/Special Conditions - Engenium Excavation and Hardfil Spec. Item 2.4
92badd77-970b-5fc0-beea-b61d5e6533e2 | note | Acceptance Criteria - CI
27717760-83df-5bbb-a739-7970c093b66f | note | Verifying Document - Shear Vane Results Sheet
34201dff-25c6-406b-b496-159956a1fd45 | checkpoint | 3.9 - Benching to be done with Half Round Channel pipe concrete
a2870e90-e49a-5b79-83fc-f3b9a5e4d541 | note | Spec Reference/Special Conditions - SWCOP SW05
f41ea30e-77f6-5d12-96d5-cd248cf33ace | note | Acceptance Criteria - CI
90296c50-5763-54fc-a372-1ae556ca18c9 | note | Verifying Document - Photos
5aa0f802-9b85-4f88-b05f-f3ee69de80ab | checkpoint | 3.10 - Steps to be installed, ensure that lid opening is orientated on sthe location of steps.
c9e1934b-fe3a-5f80-8f5f-c8496637445c | note | Spec Reference/Special Conditions - SWCOP SW05
84465b89-0f67-56e5-9830-ab87767fe978 | note | Acceptance Criteria - CI
d2847f86-b3cd-599a-baac-ba3ef6b56bc6 | note | Verifying Document - Photos
1369c01d-1010-431e-9455-587619001c83 | checkpoint | 3.11 - Ensure full entry depth of throat is not greater than 450mm and that the finishing around it is complete.
23e96ea3-a7e7-5727-be18-af81dfebd4c8 | note | Spec Reference/Special Conditions - SWCOP SW05
61921e65-cb91-58ec-b829-23a1bd787032 | note | Acceptance Criteria - CI
7b95bb02-312b-5b35-a297-0c9e533503ac | note | Verifying Document - Photos
4e228120-a422-4bbe-b915-2d6d2f91ea71 | checkpoint | 3.12 - Manhole covers in the road shall be constructed so that the cover hinge is facing the oncoming traffic, for all other covers the orientation should be so that the cover hinge is at 90 degrees from the ladder, either side.
6ebd683e-7190-5149-ba1e-039929347c36 | note | Spec Reference/Special Conditions - Watercare WW 6
702034a6-3492-50a1-86bb-3d27f89864ba | note | Acceptance Criteria - CI
fe541b48-04d1-55e6-b072-77d81d6688d9 | note | Verifying Document - Photos
77b223e3-97d6-49db-9b7d-4ab3a1994f71 | signoff | HOLD - Continue only if the above is signed off.
c51c50f0-d396-4cf0-8a52-87f1d8fb3655 | section | SW 4.0 - Handover to client with PS3
93adbc42-6d2b-4ac3-9225-3a5eca4693e9 | checkpoint | 4.1 - Complete Auckland Council final drainage inspection
bb3b922a-c3ae-5807-8c4e-0f118e8f9d8b | note | Acceptance Criteria - HP
a05f88b6-019d-5fd5-bf39-46fe17d2dd14 | note | Verifying Document - Council inspection report
67a09e86-1001-4aa6-a8e8-bb6baf2659b0 | signoff | HOLD POINT
16622f82-500d-4301-9b9e-ab5dd7101a0d | checkpoint | 4.2 - Complete Engineer final drainage inspection
3ea65bb2-c168-5f1a-9194-eb1b37ab78b6 | note | Acceptance Criteria - HP
1fac613e-3353-5ff1-a895-8a02a453e41c | note | Verifying Document - Correspondence Engineer
5a177353-118d-47dd-a51d-4d310c615b6c | signoff | HOLD POINT
daba4f2e-2810-4b68-b9a7-4ba66346ee49 | checkpoint | 4.2 - As built all pipe invert levels in manholes and CP and lid levels
592783c4-e39b-5f4b-95b0-5f5e1f69dadc | note | Acceptance Criteria - HP
a65a0094-a9cc-59a7-bcd3-d36f989487f6 | note | Verifying Document - As built report
ee15a2f8-1cb7-47af-b6fd-f9754ad8dda4 | signoff | HOLD POINT
bba6745f-478c-4bc2-98cd-eadcb8277089 | checkpoint | 4.4 - Handover to client with CS3
388d178e-1e2c-5399-b6a7-cb12858aa0ed | note | Spec Reference/Special Conditions - CS3 Drainage
c3f197b6-3686-546f-b30c-20b685318692 | note | Acceptance Criteria - HP
5840e8c3-16bc-50fa-bd78-fac5d669527c | note | Verifying Document - Handover documents
0145d8f1-c169-422b-a8ef-3a198b1a21ac | signoff | HOLD POINT
2b9cce75-2375-4be5-a618-0064b5b9eb8f | checkpoint | Comments / Required Actions:
12be8cd8-c306-52dd-9c09-c7f195e800b3 | textbox | Rev. Status
2b9e2c57-8013-50e9-b57d-8e307e6f8029 | date | Date
082cc959-c9b3-5af6-bdf8-13709e354e4c | textbox | Reason for Rev.
ddbac294-4e09-4dc0-8d9a-fdf881e570b9 | checkpoint | Signed by:
ff682d29-78de-5e6b-b9b8-df0c666918cc | note | Contractors Representative
c198f19e-40b7-5540-9d72-a1f963b0e9bd | textbox | Print:
e9f298a1-2427-5550-b8ba-a33371deaff2 | date | Date:
b2deb89e-5674-540d-9ac4-125feb93a19b | note | Clients Representative
e107d6b0-10a7-531e-8b80-c6d393dc3bad | textbox | Print:
3f559dac-005c-5082-9cfa-6af879911979 | date | Date:
06801dd6-9759-4586-80c7-41b8c1047164 | signoff | Signatures:
b535061e-fb9a-4768-8f5a-356493ed0c31 | checklist | ITP - Wastewater Drainage Lines | itp | ITP - Wastewater Drainage Lines
d47b7f40-dab2-4e7c-9e14-077c139c784e | section | WW 1.0 - Wastewater Line Setout
86b39f46-bab2-43ef-83bc-98655a5b7f4b | checkpoint | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
65b157a3-fd26-57cf-bcb6-7cc21296c725 | note | Acceptance Criteria - CI
b3cad4bd-19e3-5f4c-a387-968950506674 | note | Verifying Document - Current Plan and Longsection revisions being used to install
14fd8f2f-47ac-4d10-8f53-7f69e3295504 | checkpoint | 1.2 - Confirm Datum for Survey Setout
a9f4d610-ac38-5d12-8440-c9f894d6e89d | note | Acceptance Criteria - CI
e1a55e45-a114-5876-bccc-fa471caaa4a0 | note | Verifying Document - Correspondence of Datum to use
b188d4c6-ecef-44e8-8121-3ca49382c9d9 | checkpoint | 1.3 - Confirm existing and proposed drainage locations
2b7bedd2-b906-5dd9-bf66-f78cc1415264 | note | Acceptance Criteria - CI
5eb19467-303b-51bd-a886-e9eeffbc68e0 | note | Verifying Document - Asbuilt of Existing Manholes
27cbf796-8e71-4f9e-a056-298cd8663e25 | checkpoint | 1.4 - All wastewater pipes and manholes shall be placed in accordance with Engineer's model and locations given in design drawings.
98e3b3b6-db40-5978-9b21-a787adbb7c71 | note | Spec Reference/Special Conditions - Prelet
84d26bd0-75cd-5655-91ff-5a36ac558de2 | note | Acceptance Criteria - CI
6a976be0-3d6b-5b82-ad3c-4723a4c32679 | note | Verifying Document - Drainage Models provided by Engineer
3c61507b-9d4e-4a4d-b6ea-3fedd5186676 | checkpoint | 1.5 - Wastewater Connection Authorisation approval from Veolia for Tie-ins into existing
eb43db2a-18bb-5dc6-937b-f5f7e0881a8f | note | Spec Reference/Special Conditions - Veolia Requirements
3deb3bb2-1719-576c-8d75-d800cec92f7d | note | Acceptance Criteria - HP
3e0f37cd-bac1-5850-b157-c86f335988ed | note | Verifying Document - Signed Wastewater Connection Authorsiation form from Veolia
b17d119c-e6b2-47fa-9819-c9e9f976f7a3 | signoff | HOLD POINT
f7b72be5-d899-4968-be6f-aa745ca670cb | checkpoint | 1.6 - Complete council Kick-off meeting
ad48bcbb-88a2-5fcf-834c-3ffee1446254 | note | Spec Reference/Special Conditions - Building Consent
509441a5-11ab-5f67-a516-10bfe85a68de | note | Acceptance Criteria - HP
507592b3-f6bb-5b91-972f-1cea460d4d08 | note | Verifying Document - Council inspection report
a0f29172-2b86-4326-b7d5-08ce16c906d0 | signoff | HOLD - Continue only if the above is signed off.
d008c326-aa8f-4e29-b149-2028cb543d51 | section | WW 2.0 - Wastewater Line Excavation
8e280b08-2bad-4500-a1cc-e80c3f29418d | checkpoint | 2.1 - Wastewater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth. Use trench shield if battered cannot be achieve.
be5dbaa1-b1af-5819-b1e5-cb245a7307be | note | Spec Reference/Special Conditions - NZS 4404:2010, AS/NZS 2566.2 WorkSafe NZ – Good Practice Guidelines: Excavation Safety
611348a9-8812-5678-962a-03b0fea5dded | note | Acceptance Criteria - CI
aa9440c7-b879-5c9a-ad32-46c03be06283 | note | Verifying Document - Photos
6c0abec4-ce1e-49f2-8044-69ba71efd1f3 | checkpoint | 2.2 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
2c9a4ba6-9c93-57bd-93b0-f2331f9a54bc | note | Acceptance Criteria - HP
768c89f9-d660-5f6e-989f-db6c633b61d0 | note | Verifying Document - Geotech signoff
d37cbc55-23a9-4657-b788-bbc01a377b3e | signoff | HOLD POINT
c7e4c5fa-8856-487f-b39d-b8bca6cbb0c6 | checkpoint | 2.3 - Breakout to commence only once Client have issued a site instruction
ca5fd019-68b3-526d-959d-954c0618682b | note | Acceptance Criteria - WP
4f4e4099-88da-512e-a654-45b314b65237 | note | Verifying Document - H&R Site Instruction
dae6e3d0-d742-488a-8ae2-150a3ba4458a | signoff | HOLD - Continue only if the above is signed off.
a842d35e-c26f-4e31-9fd0-7f1d5e1d56af | section | WW 3.0 - Wastewater Line Installation
5e7111fb-f14d-4648-92e3-2f5124c63c91 | checkpoint | 3.1 - The position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
6af8f7fe-3866-553b-aa76-7c7e0a4e9580 | note | Spec Reference/Special Conditions - Watercare C3.1.1
0e92c489-37cd-5e62-aa5f-2335bddb16c0 | note | Acceptance Criteria - CI
2ba27367-6c48-537f-a2ef-35caa20e3722 | note | Verifying Document - M&P longsection sheet
d4551945-404a-45f2-a862-71e50d918c1e | checkpoint | 3.2 - Ensure grade with digital spirit level matches design grade along pipe alignment
5f7f8459-0fb2-50de-969d-8a65fd9d6a03 | note | Spec Reference/Special Conditions - Auckland Council Requirement
68b86e3a-3b07-5601-9411-66c7940ed7c5 | note | Acceptance Criteria - CI
1677dcd9-209c-5ebf-b290-ae22e781d112 | note | Verifying Document - Photos along alignment
36ff0a4e-4351-4016-82ff-d7812803b224 | checkpoint | 3.3 - Asbuilt of pipe invert levels prior to Auckland Council Inspection
2d495ed6-8724-57f7-a894-8f9347c51bff | note | Spec Reference/Special Conditions - Auckland Council Requirement
6ca29513-a967-571f-b702-a0a64a11d076 | note | Acceptance Criteria - CI
1431b16f-0fdc-5339-a3b3-27d525c411da | note | Verifying Document - Asbuilt Drawing
30dffd0e-0cfa-48ab-81fa-6f7d24da2d6d | checkpoint | 3.4 - Allow Auckland Council opportunity to inspect pipeline prior to backfill
0864de45-3f24-5744-8428-48aee3ef1631 | note | Spec Reference/Special Conditions - Auckland Council Requirement
6d7eaf47-664b-5861-b3bd-f15ac7ca2b19 | note | Acceptance Criteria - CI
713333cc-2661-5a47-935c-fc3e7731f37c | note | Verifying Document - Council inspection report
f9f2b597-3e8e-4223-b46e-00cb911ae6cb | checkpoint | 3.6 - Allow Veolia opportunity to inspect Tie-in prior to backfill
bf340dfb-960c-5fe9-9f6b-fc133b083899 | note | Spec Reference/Special Conditions - Veolia Requirements
fbcb492d-c94c-51d2-9fb3-6f17474529fd | note | Acceptance Criteria - CI
6c71f439-3c8f-5989-9d08-563cff44d3a5 | note | Verifying Document - Correspondence from Veolia
f89ce300-6a76-447d-bc09-4a98fc85c3db | checkpoint | 3.7 - Backfill line in 200mm layers and conduct Clegg Hammer Impact Tests for Hardfill achieving CIV 25
3f959049-ae30-54ae-a544-2c4be91cc2d8 | note | Spec Reference/Special Conditions - Watercare C2.21 row 12
9bf892bb-37c7-5a3a-b4d7-70f3180c883b | note | Acceptance Criteria - CI
e9dd5409-0186-5a14-ad8a-08de2629f07a | note | Verifying Document - Clegg Hammer Results Sheet
57659c69-2b4c-4d30-994c-6af583ae2e78 | checkpoint | 3.8 - Backfill line in 300mm layers and conduct Shearvanes for clay fill achieving average value not less than 150KPA
58d4c54a-c755-5a8e-9e2f-4dfab05032cb | note | Spec Reference/Special Conditions - Engenium Excavation and Hardfil Spec. Item 2.4
2fab6f26-79e3-576f-ae03-4094ffb258ba | note | Acceptance Criteria - CI
42a6864f-5f4a-5fa9-9909-a472d03b0518 | note | Verifying Document - Shear Vane Results Sheet
bcebfd20-104e-4def-aab6-f1bfa8af48f5 | checkpoint | 3.9 - Pipework shall be CCTV inspected for defects, in particular pipe joints and to identify ponding areas for correction in gravity systems
437fe9a4-2fa4-5d31-8e69-afaf66aa6d2d | note | Spec Reference/Special Conditions - Watercare General Civil Construction Standard C3.1j
ca51199f-ffa9-5db8-97d3-5df16d76aaef | note | Acceptance Criteria - CI
5b5b92bd-7d6a-5888-bbfd-29aa76c864ad | note | Verifying Document - CCTV Footage and Reports
3ae42310-43a1-4edf-bbd4-8859f65bbbd1 | checkpoint | 3.10 - Watertightness Testing in presence of Auckland Council and Engineer
4727eeab-3995-53ae-9ea3-e7431910404d | note | Spec Reference/Special Conditions - Watercare General Civil Construction Standard C10.5.1
c29996ad-f42d-51d4-af26-92cd47cbadc1 | note | Acceptance Criteria - CI
5c9e6913-a9b8-546d-bd95-e2d18cdb6edc | note | Verifying Document - Council inspection report and Engineer Correspondence
acc3c0b6-7ce6-43a7-b2c9-96218d99af0d | section | WW 4.0 - Handover to client with PS3
0fdad1a0-003a-4fc6-be2a-ef580f98a271 | checkpoint | 4.1 - Complete Council final drainage inspection
5aafe0eb-5cfb-5de5-bc48-ef44efc1c1ac | note | Acceptance Criteria - HP
b3993e41-197f-53a6-ac44-69bfca6aff40 | note | Verifying Document - Council inspection report
778f3ddf-4a27-4567-93a7-b5a07598b675 | signoff | HOLD POINT
fa231236-8095-418b-bd42-fb3515f8397a | checkpoint | 4.2 - Complete Engineer final drainage inspection
696356f6-ae2f-5fd3-8ca4-7fdc3134a6cb | note | Acceptance Criteria - HP
e68860fd-54c7-5e7f-8016-a3a3296f00b9 | note | Verifying Document - Correspondence Engineer
5dd6e377-18b4-46d8-b736-bae870d687c3 | signoff | HOLD POINT
8a5d9805-d543-4ed4-a5a2-73e5bc5e6deb | checkpoint | 4.2 - As built all pipe invert levels in manholes and CP and lid levels
5a68f2ad-52aa-5fd0-bd07-f9cc7fd1069f | note | Acceptance Criteria - HP
f4d537b0-825a-5def-9f68-c8d8ca92dac6 | note | Verifying Document - As built report
9013b5bb-ab03-4ea3-814d-dfc38977f83c | signoff | HOLD POINT
95a08041-9756-4411-af06-233bafaf5c5c | checkpoint | 4.4 - Handover to client with CS3
6c1c88d1-27a3-5dfe-b766-19a8a45ce987 | note | Spec Reference/Special Conditions - CS3 Drainage
2fe425ea-86ec-5c3f-9fae-7c7e6acf15e5 | note | Acceptance Criteria - HP
037f77bc-cbd3-5b84-9b72-22e714d8a3d7 | note | Verifying Document - Handover documents
b5204706-631a-44ba-a9fe-a84304799949 | signoff | HOLD POINT
ba054061-f325-470a-94cd-ef8072d3fb54 | checkpoint | Comments / Required Actions:
4be5fac8-5cd3-5d9f-9482-030776acdc36 | textbox | Rev. Status
ff9d1861-123b-58ee-8ddc-92fb41d363f3 | date | Date
74a1a987-0cbc-54a2-81fe-b742b2ec9d8d | textbox | Reason for Rev.
00b8a262-8fc7-41bd-9b63-ed82c0ff066c | checkpoint | Signed by:
5e3e48ff-ffdf-51a1-8d2d-aaa3e3fea408 | note | Contractors Representative
f6eb9eed-b38b-5323-9a59-acbc16847694 | textbox | Print:
1a9fea27-d109-5b25-b272-eb1c10b4f616 | date | Date:
73a8231b-6721-5e0a-a13d-81b14ad0e76b | note | Clients Representative
1951a0cc-b7aa-5326-9f73-39612283a240 | textbox | Print:
94e0e574-9dcd-5552-8de3-64497518a801 | date | Date:
41553b56-3731-4bdb-a640-95d416c710ed | signoff | Signatures: