## Table 1
Project Name: |  | 2159- Senex QGP EOLF Earthworks - SENENE |  | Document No.: | OPS-MIMP-QA-ITP-040 | Legend |  | Legend |  | Legend
Contractor Name: |  | RSA |  | Revision: | 0 | HP | HOLD POINT | TP | Third Party | CHK |  | Check
Client Name: |  | SENEX ENERGY |  | Revision Date: | 2025-07-07 | WP | WITNESS POINT | SUR | Surveyor | R |  | Review
Contract No: |  |  |  | Prepared By: | Justine John | RE | REVIEW | TST | Test | INS |  | Inspect
Work Package: |  |  |  | Checked By: | Von Jones | D | DOCUMENT | VIS | Visual
Property Name: |  |  |  | Approved By (Client): |  | M | MONITOR | ITC | Inspection & Test Checklist
ITP Start Date: |  |  |  | Status: |  | I | INSPECTION | RSA | RSA Contractors
Inspection and Test Plan Details
Item | Activity / Inspection / Test Point | Work By | Applicable Spec/Doc Ref | Acceptance Criteria / Frequency | Frequency | Records | RSA Verification |  |  |  | Senex verification & Approval
[7 empty] | Requirement | Authority | Date & Signature | NCR / RFI | Requirement | Authority | Date & Signature
1 | Preliminary
1.1 | Survey and Setout | RSA | n/a | The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works | Prior to commencement | ITC | HP | RSA |  |  | HP | Senex
1.2 | Material Procurement | RSA | n/a | RSA shall provide Senex with a copy of QA documentation that demonstrates compliance with material properties of each unit outlined in the SOW prior to commencing the work. |  | ITC | HP | RSA |  |  | HP | Senex
1.3 | Survey benchmark | Principal | n/a | No material will be excavated until a joint survey of the existing surface has been performed by the contractor and the client. | Prior to commencement | ITC | HP | RSA |  |  | HP | Senex
2 | Clear and Grub and Topsoil Strip
2.1 | Clearing grubbing | RSA | OPS-MIMP-CS- GAR-014 | Extent of clearing and grubbing to be confirmed with Senex. Roots and vegetation cleared shall be stockpiled at a location specified in the ESC plan | 1/Lot | ITC | VIS | RSA |  |  | VIS | Senex
2.2 | Topsoil Sripping | RSA | OPS-MIMP-CN- SOW-0009_1- MIMP Civil Earthwors Construction SoW | Application of gypsum before topsoil strip (0.5kg/m2/100mm layer). 150mm of Topsoil shall be stripped such that all organic-rich soil and roots/ rootlets have been removed from the foundation of the embankment and internal borrow areas. | 1/Lot | ITC | HP | RSA |  |  | HP | Senex
2.3 | Stockpile of Materials | RSA | OPS-MIMP-CS- GAR-014 | Topsoil is to be placed in a loose, non-compacted state, to a maximum height of 3 metres, with batter slopes no greater than 1v:6H. The stockpile area must be clear of earthworks, drainage structures, obstructions, and other permanent works and must be free draining. Stripped topsoil shall be stockpiled where directed by the superintendent for reuse. Weed-contaminated soil is to be separated from non-contaminated soil stockpiles to prevent cross-contamination. | 1/Lot | ITC | HP | RSA |  |  | HP | Senex
2.4 | Survey after topsoil removal | RSA | OPS-MIMP-CS- GAR-014 | As-constructed survey has been completed to record the surface levels on completion of topsoil stripping. | As required | ITC | CHK | RSA |  |  | CHK | Senex
3 | Foundation Preparation
3.1 | Ground Surface Treatment | RSA | Technical Specification | The top 150mm below foundation surface level shall be scarified, watered, and compacted to a density ratio of not less than 100% of SMDD to AS 1289.5.1.1. Inspection being conducted befor proof rolling | 1/2500 m3 | ITC | HP | RSA |  |  | HP | Senex
3.2 | Proof Roll | RSA | Technical Specification | The contractor shall proof roll the entire exposed foundation surface within 24 hours of ground surface treatment to identify any soft or loose material. Proof rolling shall be undertaken with a fully loaded water cart or similar equipment, which has a minimum ground bearing pressure of 400 kPa. The rear axle of the fully laden water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres. Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone | 1/Lot | ITC | WP/HP | RSA |  |  | WP/HP | Senex
3.3 | Foundation Survey | RSA | Technical Specification | Survey of the excavated foundation surface shall be undertaken prior to placement of general fill. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
4 | Earth Work Construction
4.1 | Lot Identification | RSA | Technical Specification | Location of works identified by the project technical specification. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
4.2 | Underlying Lot Conforms | RSA | Technical Specification | Foundation preparation works completed in the underlying lot. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
4.3 | General Fill Material Requirement | RSA | Technical Specification | Grading Requirements 75mm sieve passing - 100 % 37.5mm sieve passing - 80-100 % 9.5mm sieve passing - 60-100 % 4.75mm sieve passing - 40-100 % 0.425mm sieve passing - 20-95 % 0.075mm sieve passing - 10-85 % Indicator Requirements Plasticity plots: above the 'A'- line Weighted Plasticity Index - <3200 Emersion Crumb: ≥ 3 Compaction standard: ≥ 95% SMDD Moisture content: Moisture conditioned at or near OMC | 1/Lot | Laboratory test Certificate | CHK | RSA |  |  | CHK | Senex | Signature
4..4 | Compaction Trials | RSA | Technical Specification | Compaction trials must be undertaken to assess the equipment and work methods which will achieve the necessary moisture content and compaction requirements. The trials must be continued until at least four out of every five consecutive tests taken conform to the specification in respect of grading, moisture content, and relative density. | 1/Lot | Laboratory test Certificate | HP | RSA |  |  | HP | Senex
4.5 | Fill placement | RSA | Technical Specification | Placed in continuous, approximately horizontal layers for the full width of the area, under level 1 supervision in layers not exceeding 250mm loose depth. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm before the placement of the next layer. Each layer of general fill material must be compacted with equipment determined appropriate by compaction trials, or as approved by the Senex representative. Adjacent to structures, pipes, and other services, the operation of heavy mobile equipment must be restricted. In such instances, special compaction using mechanical tampers or other equivalent methods as approved by the Engineer must be adopted. ≥ 100 % standard MDD placed as near as OMC Under level 1 supervision | 1/Lot | Level 1 compaction Certificate | CHK | RSA |  |  | CHK | Senex
4.6 | Proof Roll | RSA | Technical Specification | The contractor shall proofroll the general fill layer to identify any soft or loose material. Proof rolling shall be undertaken with a fully loaded water cart or similar equipment, which has a minimum ground bearing pressure of 400 kPa. The rear axle of the fully laden water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres. Areas of general fill layer identified by the superintendent as unsuitable shall be excavated and replaced with material conforming to the requirements of the overlying fill zone | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
4.7 | Testing | RSA | Technical Specification | General Fill Density Ration Particle Size Distribution Atterberg Limits CBR Testing Emersion Crumb Dispersion | 1/Lot | Laboratory test Certificate | CHK | RSA |  |  | CHK | Senex
4.8 | Survey | RSA | Technical Specification | The contractor should carry out a general survey of the finished general fill layer. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
5 | Hardstand Construction
5.1 | Lot Identification | RSA | Technical Specification | Location of works identified by the project technical specification. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
5.2 | Material Requirement | RSA | Technical Specification | The gravel used should be of Type 2.3 | 1/Stockpile | Material supplier specification letter | CHK | RSA |  |  | CHK | Senex
5.3 | Proof roll of subgrade | RSA | Technical Specification | The contractor shall proofroll the general fill layer to identify any soft or loose material. Proof rolling shall be undertaken with a fully loaded water cart or similar equipment, which has a minimum ground bearing pressure of 400 kPa. The rear axle of the fully laden water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres. Areas of general fill layer identified by the superintendent as unsuitable shall be excavated and replaced with material conforming to the requirements of the overlying fill zone | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex | Signature
5.4 | Placement of material | RSA | Technical Specification | Placed in continuous, approximately horizontal layers for the full width of the area, under level 1 supervision in layers not exceeding 250mm loose depth by AS3798. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm before the placement of the next layer. Each layer of general fill material must be compacted with equipment determined appropriate by compaction trials, or as approved by the Senex representative. ≥ 100 % standard MDD Under level 1 supervision | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex | Signature
5.5 | Material Testing | RSA | Technical Specification | Hard stand should be tested for material characteristics and compaction. ≥ 100 % standard MDD | 1/Lot | Laboratory test Certificate | CHK | RSA |  |  | CHK | Senex
5.6 | As built Survey | RSA | Technical Specification | Finished levels checked for vertical and horizontal tolerances as required. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
6 | Surface Water Runoff Management
6.1 | Lot Identification | RSA | Technical Specification | Location of works identified by the project technical specification. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
6.2 | Finished trimmed surface inspection | RSA | Technical Specification | The finished trimmed surface shall be inspected by the Senex prior to topsoil placement. | 1/Lot | ITC | HP | RSA |  |  | HP | Senex
6.3 | Gypsum application | RSA | Technical Specification | The finished trimmed surface shall be cross-ripped to 200mm. Topsoil shall be ameliorated with agricultural gypsum (MRTS 16b) at 10kg/loose m3 or 1kg/m2/100mm layer of soil OR (10t/ha/100mm). The gypsum mixing methodology should be submitted to the Senex representative for approval. | 1/Lot | ITC | HP | RSA |  |  | HP | Senex
6.4 | Finished surface Amelioration | RSA | Technical Specification | Finished surface should be ameliorated with fertilizer at 2.5kg/100m2. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
6.5 | Stock pile survey | RSA | Technical Specification | Topsoil within existing stockpiles shall be verified prior to topsoil placement to estimate the volume. | 1/Lot | ITC | HP | RSA |  |  | HP | Senex
6.6 | Placement of topsoil | RSA | Technical Specification | Topsoil shall be spread to a minimum thickness of 150mm. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
6.7 | Seeding/Hydro mulch | RSA | Technical Specification | The finished surfaces are to be stabilised by seeding using quality organic conditioner hydromulch with seed or compost at 12mm thick with seed. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
7 | Erosion and Sediment Control installation
7.1 | Lot Identification | RSA | Technical Specification | Location of works identified by the project technical specification. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
7.2 | Sediment Fence installation | RSA | Technical Specification | Fabric, Fabrick reinforcement and support posts should be installed according to the technical specification | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
7.3 | Coir Logs | RSA | Technical Specification | A 200 to 250mm jute, coir, or straw roll should be installed after discussing with the Senex representative. | 1/Lot | ITC | CHK | RSA |  |  | CHK | Senex
7.4 | Dumped Rock Protection | RSA | Technical Specification | The finished surface shall be inspected by the Senex representative prior to the placement of BIDIMA34 geotextile. The dumped rock using should be D50=200MM. Grading Paricle Size 400mm : 100 % Passing 200mm : < 50 % 100mm : <10 % Plasticity density : ≥ 2.6 t/m3 Water absorption: ≤ 2.0 % LAV : ≤ 35 % UCS : ≥ 50MPa% Sodium Sulphate soundness average loss ≤ 9 % | 1/Stockpile | Material supplier specification letter | CHK | RSA |  |  | CHK | Senex | Signature
Completed By | [10 empty] | Approved By |  | Signature
| Contractor Representative Senex Construction Representative | [8 empty] | Client Representative
| Name: |  | Name: | [7 empty] | Name:
| Position: |  | Position: | [7 empty] | Position:
| Company: |  | Company: | Senex | [6 empty] | Company: | Senex
| Signature |  | Signature | [7 empty] | Signature
| Date: |  | Date: | [7 empty] | Date:
NOTE: All fields are to be completed and initialled as appropriate. Any non-applicable fields shall state “N/A”.