## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | OPS-MIMP-QA-ITP-040 | itp
section | 1 - Preliminary
checkpoint | 1.1 - Survey and Setout
label | Work By - RSA
label | Applicable Spec/Doc Ref - n/a
label | Acceptance Criteria / Frequency - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
label | Frequency - Prior to commencement
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 1.2 - Material Procurement
label | Work By - RSA
label | Applicable Spec/Doc Ref - n/a
label | Acceptance Criteria / Frequency - RSA shall provide Senex with a copy of QA documentation that demonstrates compliance with material properties of each unit outlined in the SOW prior to commencing the work.
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 1.3 - Survey benchmark
label | Work By - Principal
label | Applicable Spec/Doc Ref - n/a
label | Acceptance Criteria / Frequency - No material will be excavated until a joint survey of the existing surface has been performed by the contractor and the client.
label | Frequency - Prior to commencement
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
section | 2 - Clear and Grub and Topsoil Strip
checkpoint | 2.1 - Clearing grubbing
label | Work By - RSA
label | Applicable Spec/Doc Ref - OPS-MIMP-CS- GAR-014
label | Acceptance Criteria / Frequency - Extent of clearing and grubbing to be confirmed with Senex. Roots and vegetation cleared shall be stockpiled at a location specified in the ESC plan
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - VIS
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - VIS
label | Senex verification & Approval: Authority - Senex
checkpoint | 2.2 - Topsoil Sripping
label | Work By - RSA
label | Applicable Spec/Doc Ref - OPS-MIMP-CN- SOW-0009_1-MIMP Civil Earthwors Construction SoW
label | Acceptance Criteria / Frequency - Application of gypsum before topsoil strip (0.5kg/m2/100mm layer). 150mm of Topsoil shall be stripped such that all organic-rich soil and roots/ rootlets have been removed from the foundation of the embankment and internal borrow areas.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 2.3 - Stockpile of Materials
label | Work By - RSA
label | Applicable Spec/Doc Ref - OPS-MIMP-CS- GAR-014
label | Acceptance Criteria / Frequency - Topsoil is to be placed in a loose, non-compacted state, to a maximum height of 3 metres, with batter slopes no greater than 1v:6H. The stockpile area must be clear of earthworks, drainage structures, obstructions, and other permanent works and must be free draining. Stripped topsoil shall be stockpiled where directed by the superintendent for reuse.
label | ○ Weed-contaminated soil is to be separated from non-contaminated soil stockpiles to prevent cross-contamination.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 2.4 - Survey after topsoil removal
label | Work By - RSA
label | Applicable Spec/Doc Ref - OPS-MIMP-CS- GAR-014
label | Acceptance Criteria / Frequency - As-constructed survey has been completed to record the surface levels on completion of topsoil stripping.
label | Frequency - As required
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
section | 3 - Foundation Preparation
checkpoint | 3.1 - Ground Surface Treatment
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The top 150mm below foundation surface level shall be scarified, watered, and compacted to a density ratio of not less than 100% of SMDD to AS 1289.5.1.1.
label | ○ Inspection being conducted befor proof rolling
label | Frequency - 1/2500 m3
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 3.2 - Proof Roll
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The contractor shall proof roll the entire exposed foundation surface within 24 hours of ground surface treatment to identify any soft or loose material. Proof rolling shall be undertaken with a fully loaded water cart or similar equipment, which has a minimum ground bearing pressure of 400 kPa.
label | ○ The rear axle of the fully laden water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres.
label | ○ Areas of subgrade identified by the superintendent as unsuitable material shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - WP/HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - WP/HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 3.3 - Foundation Survey
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Survey of the excavated foundation surface shall be undertaken prior to placement of general fill.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
section | 4 - Earth Work Construction
checkpoint | 4.1 - Lot Identification
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Location of works identified by the project technical specification.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 4.2 - Underlying Lot Conforms
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Foundation preparation works completed in the underlying lot.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 4.3 - General Fill Material Requirement
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Grading Requirements
label | ○ 75mm sieve passing - 100 %
label | ○ 37.5mm sieve passing - 80-100 %
label | ○ 9.5mm sieve passing - 60-100 %
label | ○ 4.75mm sieve passing - 40-100 % 0.425mm sieve passing - 20-95 % 0.075mm sieve passing - 10-85 %
label | ○ Indicator Requirements Plasticity plots: above the 'A'- line Weighted Plasticity Index - <3200 Emersion Crumb: ≥ 3
label | ○ Compaction standard: ≥ 95% SMDD
label | ○ Moisture content: Moisture conditioned at or near OMC
label | Frequency - 1/Lot
label | Records - Laboratory test Certificate
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 4.4 - Compaction Trials
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Compaction trials must be undertaken to assess the equipment and work methods which will achieve the necessary moisture content and compaction requirements. The trials must be continued until at least four out of every five consecutive tests taken conform to the specification in respect of grading, moisture content, and relative density.
label | Frequency - 1/Lot
label | Records - Laboratory test Certificate
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 4.5 - Fill placement
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Placed in continuous, approximately horizontal layers for the full width of the area, under level 1 supervision in layers not exceeding 250mm loose depth. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm before the placement of the next layer.
label | ○ Each layer of general fill material must be compacted with equipment determined appropriate by compaction trials, or as approved by the Senex representative.
label | ○ Adjacent to structures, pipes, and other services, the operation of heavy mobile equipment must be restricted. In such instances, special compaction using mechanical tampers or other equivalent methods as approved by the Engineer must be adopted.
label | ○ ≥ 100 % standard MDD placed as near as OMC Under level 1 supervision
label | Frequency - 1/Lot
label | Records - Level 1 compaction Certificate
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 4.6 - Proof Roll
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The contractor shall proofroll the general fill layer to identify any soft or loose material. Proof rolling shall be undertaken with a fully loaded water cart or similar equipment, which has a minimum ground bearing pressure of 400 kPa. The rear axle of the fully laden water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres.
label | ○ Areas of general fill layer identified by the superintendent as unsuitable shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 4.7 - Testing
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - General Fill
label | ○ Density Ration
label | ○ Particle Size Distribution Atterberg Limits
label | ○ CBR Testing
label | ○ Emersion Crumb Dispersion
label | Frequency - 1/Lot
label | Records - Laboratory test Certificate
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 4.8 - Survey
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The contractor should carry out a general survey of the finished general fill layer.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
section | 5 - Hardstand Construction
checkpoint | 5.1 - Lot Identification
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Location of works identified by the project technical specification.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 5.2 - Material Requirement
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The gravel used should be of Type 2.3
label | Frequency - 1/Stockpile
label | Records - Material supplier specification letter
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 5.3 - Proof roll of subgrade
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The contractor shall proofroll the general fill layer to identify any soft or loose material. Proof rolling shall be undertaken with a fully loaded water cart or similar equipment, which has a minimum ground bearing pressure of 400 kPa. The rear axle of the fully laden water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres.
label | ○ Areas of general fill layer identified by the superintendent as unsuitable shall be excavated and replaced with material conforming to the requirements of the overlying fill zone
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 5.4 - Placement of material
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Placed in continuous, approximately horizontal layers for the full width of the area, under level 1 supervision in layers not exceeding 250mm loose depth by AS3798. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm before the placement of the next layer.
label | ○ Each layer of general fill material must be compacted with equipment determined appropriate by compaction trials, or as approved by the Senex representative.
label | ○ ≥ 100 % standard MDD Under level 1 supervision
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 5.5 - Material Testing
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Hard stand should be tested for material characteristics and compaction.
label | ○ ≥ 100 % standard MDD
label | Frequency - 1/Lot
label | Records - Laboratory test Certificate
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 5.6 - As built Survey
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Finished levels checked for vertical and horizontal tolerances as required.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
section | 6 - Surface Water Runoff Management
checkpoint | 6.1 - Lot Identification
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Location of works identified by the project technical specification.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 6.2 - Finished trimmed surface inspection
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The finished trimmed surface shall be inspected by the Senex prior to topsoil placement.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 6.3 - Gypsum application
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The finished trimmed surface shall be cross-ripped to 200mm. Topsoil shall be ameliorated with agricultural gypsum (MRTS 16b) at 10kg/loose m3 or 1kg/m2/100mm layer of soil OR (10t/ha/100mm).
label | ○ The gypsum mixing methodology should be submitted to the Senex representative for approval.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 6.4 - Finished surface Amelioration
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Finished surface should be ameliorated with fertilizer at 2.5kg/100m2.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 6.5 - Stock pile survey
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Topsoil within existing stockpiles shall be verified prior to topsoil placement to estimate the volume.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - HP
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - HP
label | Senex verification & Approval: Authority - Senex
holdpoint | HOLD POINT
checkpoint | 6.6 - Placement of topsoil
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Topsoil shall be spread to a minimum thickness of 150mm.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 6.7 - Seeding/Hydro mulch
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The finished surfaces are to be stabilised by seeding using quality organic conditioner hydromulch with seed or compost at 12mm thick with seed.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
section | 7 - Erosion and Sediment Control installation
checkpoint | 7.1 - Lot Identification
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Location of works identified by the project technical specification.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 7.2 - Sediment Fence installation
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - Fabric, Fabrick reinforcement and support posts should be installed according to the technical specification
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 7.3 - Coir Logs
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - A 200 to 250mm jute, coir, or straw roll should be installed after discussing with the Senex representative.
label | Frequency - 1/Lot
label | Records - ITC
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
checkpoint | 7.4 - Dumped Rock Protection
label | Work By - RSA
label | Applicable Spec/Doc Ref - Technical Specification
label | Acceptance Criteria / Frequency - The finished surface shall be inspected by the Senex representative prior to the placement of BIDIMA34 geotextile.
label | ○ The dumped rock using should be D50=200MM.
label | Grading
label | ○ Paricle Size 400mm : 100 % Passing
label | ○ 200mm : < 50 %
label | ○ 100mm : <10 %
label | ○ Plasticity density : ≥ 2.6 t/m3 Water absorption: ≤ 2.0 % LAV : ≤ 35 %
label | ○ UCS : ≥ 50MPa%
label | ○ Sodium Sulphate soundness average loss ≤ 9 %
label | Frequency - 1/Stockpile
label | Records - Material supplier specification letter
label | RSA Verification: Requirement - CHK
label | RSA Verification: Authority - RSA
label | Senex verification & Approval: Requirement - CHK
label | Senex verification & Approval: Authority - Senex
section | To be completed upon completion of all work activities
checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
label | Completed By:
textbox | Contractor Representative - Name:
textbox | Contractor Representative - Position:
textbox | Senex Construction Representative - Name:
textbox | Senex Construction Representative - Position:
label | Approved By:
textbox | Client Representative - Name:
textbox | Client Representative - Position:
date | Date:
holdpoint | Add Signature