## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
323a5029-f861-5b49-bbd0-0fa90f1c44fa | checklist | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform |  | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform
14709687-ca49-585c-9e2d-bc7e071165a5 | section | Prior to Reinforcement
03ca3302-54ea-5fe6-9601-628d70a483a5 | checkpoint | Confirm Jump No Seq and bottom and top RLs of proposed pour
fc09e239-cb41-5229-8b1b-6ae5ce6205f1 | textbox | Jump No Sequence
75617b45-fc0d-579f-9246-d6705d97d9f2 | textbox | Bottom of Proposed Wall RL
8179fb56-38cc-5e32-9066-d62c3cd214d9 | textbox | Top of Proposed Wall RL
0131d1e5-9829-5ae5-9777-fddd091bd9c3 | checkpoint | Surveyor to complete survey of concrete walls below to confirm if walls need to be adjusted. Attach confirmation survey has been issued to formwork contractor via Aconex
acbaf781-9d79-57fa-9ed0-83bbeccd16c1 | textbox | Aconex Correspondence No.
6a2d26db-eb97-5c65-a2e2-59d27a2d77cc | checkpoint | Lift Requirements - Review formwork blockouts for lift openings and door thresholds in accordance with architectural elevations and lift shop drawings
de1cd537-8464-507e-bdff-c0f2bb8184ed | checkpoint | Formwork Requirements - Confirm that all reboxes, couplers, shear key pockets and cast in plates to internal shutter as per structural engineer detail
f46aa660-47cf-5320-90a6-461ec8d60422 | checkpoint | Attach Sign Off from form worker contractor confirming all works completed and clear access for handover to steel fixers
4f585971-b5f0-56eb-b5ac-e2aa9bea7876 | section | Prior to Closing Shutters
b338461b-2c19-59cb-a2e4-51dea582f0c8 | checkpoint | Lift Requirements - Confirm any block out / penetrations required for lift buttons and indicators has been cast in by Form Worker
2b333bef-1ef0-5309-abc8-11acba4f56a3 | checkpoint | Confirm all outside reboxes & couplers are installed to required SSL + cover levels
9e2abf08-bc49-568e-8b0d-cbdcc6b231e1 | checkpoint | Attach electrical contractors ITP to confirm any required conduit cast ins are completed
91f28ca2-219c-5bfa-ae71-27cf862a43a7 | checkpoint | Attach reinforcement installer’s ITP
3bc44e94-e608-5f08-81cb-7f38d623571a | checkpoint | Reinforcement Checks (Refer Structural Engineers Drawings for Reference):
3aabcaef-75b7-543f-9097-8ce3fe8da03c | note | Reinforcement cover sufficient
5db9e275-7014-5d2c-9883-66249edf6d5d | note | Lap Length of bars sufficient
c270377a-5ff0-5bff-85ee-fcbf436be1aa | note | Starter bar length to next pour correct
6e0fdbe0-6e0e-59e1-8ef2-ce14ae5842d5 | note | Lace bars installed to reboxes
92f8ba57-613d-5704-9f76-19ec4029f68d | checkpoint | Attach structural engineer’s inspection report
fd9cd6d6-111d-5ff3-89b0-16611eaa843d | checkpoint | Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
9fc82d7a-a558-562f-8736-c7d4f3eda8d6 | checkpoint | Attach photos of all works completed prior to closing shutters
a59e4763-4d27-52b9-87a4-635cae6dd022 | section | During Concrete Pouring
01bd6b09-ae5a-5128-9a4b-c5752317b4a2 | checkpoint | Confirm Concrete ordered is correct
69fee95c-c606-5464-a090-2d97dcf397c7 | textbox | MPa/mix design
cef213ee-84d7-51dd-9b80-b97468219d61 | checkpoint | Confirm pour height with concrete Contractor prior to pouring
a2ee5ee3-3a15-5d47-b73c-131915c9e0af | checkpoint | Attach form worker’s jumpform ITP
8eeb1ec6-cfd7-5ec3-98f0-cde5b6a70494 | checkpoint | Attach concrete place contractor’s ITP
da3045fb-c496-52e3-b307-9e695cad6a1a | checkpoint | Confirm concrete tester onsite to take samples and ensure correct pour location is recorded
0301ea4b-308b-5297-9f96-80e10dd13369 | section | Prior to Jumping
fb529313-bcdb-57c7-845e-f762c5e663f9 | checkpoint | Attach concrete test result to confirm min 15 MPa has been reached
4cce810a-f264-5392-86d8-62229acfe779 | checkpoint | Attach form worker’s Permit to Energise Jumpform.
2ed66936-a16d-5a74-b215-f797fe5c331a | note | Note exclusion zone below and all penetrations to be blocked up and secure and any temporary services (hydraulic/electrical/static line) disconnected inside trailing decks
16ebbe46-fe50-59f6-96e4-8c3f6085cb39 | section | After Jumping
6fc758a6-7e52-591e-8798-f956b4171a46 | checkpoint | Form Worker to ensure that all z bar holes and jumpform pockets within the lift shaft has been patched and infilled in accordance with structural engineer drawings
a5de8e97-6d7d-504d-90dc-7763000f1b77 | checkpoint | Attach concrete test results 28d and confirm compliance with engineer requirements
9c4d0f4e-3eb0-5a30-8ef8-9432339f53a8 | checkpoint | Permit to Re-seat jumpform received (attach to ITP)
7791678c-beec-5f8b-abd9-6119ac21c60c | checkpoint | Surveyor to survey finished concrete walls (attach as-built to ITP)
3543a7eb-a7dc-52c4-a19a-4f7f8f5b4e0e | signoff | Final ITP Review & Sign-off by Project Engineer
cce6bd62-a47d-5a2b-9438-30dd37d000e2 | checklist | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals |  | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
5ba4bfda-bc99-56cf-8b8b-2996c4f9926f | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
be34bdae-f703-5862-8415-cd17d0848cba | textbox | Architectural Drawings
98c3cdb3-0c8d-5188-bc6f-4dbea03affac | textbox | Structural Drawings
535fe087-6741-5432-99b5-8b5bd1d668f1 | checkpoint | Ensure survey of column/wall positions are completed prior to commencing formwork
83678975-8dac-5a3c-9344-1bc226ae18a7 | note | Attach surveyors as-built records to ITP
67880d0a-c7c0-503a-8574-c26af3170bd4 | checkpoint | Reinforcement - Check Starter bars from previous pour installed in correct position (compare against survey points)
6fa61a94-96db-5ff6-a543-755820891e1a | checkpoint | Reinforcement - Check for correct bar sizes and lap lengths between starter bars (top & bottom)
3902c60f-0f95-575f-a26e-2703689b150c | checkpoint | Cast-in Services - Electrical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design. Attach Contractors ITP
025eba38-756a-5f48-81d5-b24cbee885c5 | checkpoint | Cast-in Services - Hydraulics subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
c2d57c76-36ed-5a08-8267-6e7225fc89ac | checkpoint | Cast-in Services - Mechanical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
18de01a4-f42c-5901-afdf-25618335b566 | checkpoint | Cast-in Services - Fire Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
8f061269-5e8f-57f9-a105-62da81d836df | checkpoint | Cast-in Services - Security Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design
55bcc9e7-4508-50c4-999a-66d8c5c4c9aa | checkpoint | Confirm strength and mix design of concrete ordered with subcontractor prior to pour
83416d4e-588a-5834-bfc7-cca8d9297375 | textbox | Concrete Mix Design:
e502b10d-edc8-544c-b0eb-c56a1aad439f | checkpoint | Structural Engineer Sign-off - Foreman and subcontractor to sign off engineer’s report to verify that all work to be rectified was checked for compliance prior to pour
c4b3574e-3e4d-5d2d-9f51-2682acf11262 | note | Attach engineers inspection report and verification of rectification items being closed out.
e8a4bcc9-d32e-5f1d-ac6b-949038bf6b85 | checkpoint | Formwork Compliance - Confirm formwork is checked to achieve Class 2 finish to concrete:
1c7ffae4-da3d-5f41-9776-0dc689ab6e2a | tickbox | Formwork is clean and free of debris
9e437d63-5f9b-56ad-849a-dc1f97c98f02 | tickbox | No lipping of formwork between sheets
cc5eedd9-562a-5a3c-bbf8-35089fa64818 | tickbox | Fillets installed at all corners
f3d9af63-113f-5fa7-a734-818ad2f60b11 | tickbox | Form ties are installed at even spacing
6b22574f-5639-5df7-bb94-dd6682f5e4e7 | tickbox | Check for correct reo cover at shutters
c78823d8-b08f-5d92-b36a-9adb285dda2f | tickbox | Splayed columns are at correct degrees per Architectural/Structural drawings
a023a578-da63-5c4c-9d10-904381e00fd9 | checkpoint | Area cleaned of all excess formwork, sawdust at base of columns, reo, and debris prior to pour
d26c5200-b798-5a1b-8336-ba20b6936d9c | checkpoint | Attach formworkers ITP for column and wall formworking
a996aa4a-fd5b-5dc7-9d9f-1d40416795b1 | checkpoint | Attach Steelfixers ITP for Column and wall reinforcement
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
a996b133-8d9b-53cc-af5e-c4d995eba206 | checkpoint | Concrete Placement Checklist
ef0d10f5-ca0a-5fbc-b5a2-88bcb5fc011a | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
4d43f38a-5927-5625-9cee-50b55ef49554 | tickbox | Confirm Delivery Docket References correct mix design
6afa1aba-7909-5a62-8e46-39ab8780b801 | tickbox | Plant and Equipment checklist completed on concrete pump and lines
75c379bc-ae8f-53e8-84f9-d4849bf5d7c7 | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
8eae3c07-4137-513b-83dc-1b73460911d1 | note | 7, 28 & 56 day compressive test results to be issued by batch plant
0ba68840-1f2c-5ee0-8575-28464266daca | note | Batch plant to issue monthly dry shrinkage test results
b73bee09-e61c-5e56-8b55-431389362db1 | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
cfa21684-6574-52b3-ac38-ddba1bcb52d1 | tickbox | Form Worker
f0f49649-9514-5fe7-8657-bb359e1b359f | tickbox | Electrician
aab7c095-1bf7-539c-8343-065ddf77ee46 | tickbox | Plumber
045bea43-ef93-5c37-a70b-d767e5e3c0c3 | checkpoint | Ensure only rubber tipped vibrators are used and care is taken not to damage shutters
1b98fc0c-6352-5fbe-9adb-d3da0b8f3f8c | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of walls, immediately after pour for off form finishes.
77a27c32-7ee6-590f-8452-e5ff1e97b5c6 | checkpoint | Attach Concrete Place contractors ITP
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
9fb23d0e-0d1e-57cc-9c15-048ba7235eb7 | checkpoint | Curing - Approved curing compound to be applied to columns following removal of formwork as required.
1f774416-47c1-5414-ad4e-41fec77d84f0 | checkpoint | Confirm tolerance of finished concrete surfaces:
bef63090-e05d-52a2-9126-1efb628a4c99 | note | 5mm+/- in correct position
97bd183b-4da4-5ec2-82e7-5e9c5d97eab4 | note | 5mm +/- from 3.0m straight edges.
0e3449f9-ff48-5dad-aaa5-565606e686e0 | note | 5mm +/- from plumb.
54d3cdd2-0c38-5c30-8a62-c92cc82fbdde | checkpoint | As-Built Survey - Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As Built Survey Plan
234214fc-15c4-57c6-93e1-2a16b3f5124f | checkpoint | Concrete Test Results - Obtain all concrete test results. Confirm strength achieved after:
cd3ad7e9-18da-54e4-a3e6-dad00be42a1c | textbox | 7 Days MPa
27a71ddb-793f-5e8c-a11c-83069ad213c8 | textbox | 28 Days MPa
10ab75ae-4cdd-5660-a6b6-1d88aadbe99b | textbox | 56 Days MPa
35ac4bcc-f65d-56f1-9972-e66071f55c23 | checkpoint | All non-conformances closed out
95da422e-fade-5c59-b042-7bc47be521a6 | signoff | Final ITP Review & Sign-off by Project Engineer
829ea393-4911-51df-bdc1-4b02ca0b501b | checklist | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works |  | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
53a4e09b-da64-5382-9972-a06d81e557e3 | checkpoint | Confirm bottom, mid & top of stair RL's on Architectural Concrete Outlines.
e8432eb9-d3bf-54c0-ab3c-5666ea19e365 | textbox | Bottom Landing RL
522ca3ff-d379-52e2-a9ab-3283d628ca54 | textbox | Mid Landing RL
1f24f4ff-b86c-5894-b788-58006e9dca4d | textbox | Top Landing RL
1070e070-8762-52b5-8163-d97616889960 | checkpoint | Confirm Re-boxes/cast-in bars are installed to correct heights at landings, based on nominated design RL's.
a5d8848b-99b7-5ce5-bc68-b8d9d6f2968e | checkpoint | Confirm any starter bars on landings for dividing walls, etc… are installed as per Structural Drawings
678ad173-8ebb-532b-ab4c-6a7ef4eff6b6 | checkpoint | Check for reinforcement cover as per Structural Drawings.
efda221b-4598-5123-8e20-9290008eb0dc | note | Cover requirement generally 30mm
0bcac4cd-00c8-5ec5-af47-92b4b9e2bd9c | checkpoint | Confirm all cast in elements installed (eg, stair handrails, etc…)
caa37a77-0509-5eb0-8e63-66cd29d4e003 | checkpoint | Confirm all formwork is clean and free of debris.
008f933d-b076-578b-85e3-18ee9c16226c | checkpoint | Confirm any conventional parts of stairs have been formed in accordance with the relevant shop drawings and standards.
939e6cf6-de24-5941-9f7b-742819c18525 | note | Statutory Requirements (Dimensions in mm): Riser: Min. 115, Max. 190 Going: Min. 240, Max. 355 Ensure consistency
17ec3654-8c20-5f06-bb0c-3208a041b0b0 | checkpoint | Confirm cast-in of anti-slip items if required (eg, carborundum powder, stair nosings, etc…);
4685b9e2-81f4-54b7-8f57-70d5cd7089d2 | checkpoint | Obtain certificate from Structural Engineer prior to concrete pour and attached completed Inspection Report.
6626c3ce-5d25-5a28-a138-c902250b1eac | checkpoint | Confirm MPa, slump and agg. size of concrete prior to ordering.
cd6146d1-2ebb-56b4-9646-825e787cf64d | textbox | Concrete Mpa/Mix Design
37255657-064d-553e-8a7e-c073495e2932 | checkpoint | Obtain subcontractors ITP (Steel Fixer) & attach to ITP
7405efd4-e864-533b-bdb8-4e36a2df192d | checkpoint | Obtain subcontractors ITP (Form Worker) & attach to ITP
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
695edd83-2bbc-520b-927e-901f85d80a14 | checkpoint | If the stairs are being used as access to a leading deck, ensure alternative access is established prior to pouring.
0ebd1812-9009-5f0c-a6df-e4b64203a568 | checkpoint | Confirm concrete tester onsite during concrete pour, and the following tests have been requested.
061bea70-3313-5d8d-aec5-01c437d7de85 | note | 7 Day
362ef73f-a50c-537b-9a30-8b523e267b2c | note | 28 Day
cec00985-e38f-58cf-b784-74ea822c451f | note | Ensure concrete tester is aware of pour locations
b73bee09-e61c-5e56-8b55-431389362db1 | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
31fa7557-407d-52d8-a95f-0c8ea6e688a3 | tickbox | Form Worker
c3976a82-9072-5fb6-9178-4fea09025f3a | tickbox | Electrician
7d8cbc69-dd58-5e21-aabf-06c1380565c3 | tickbox | Plumber / Fire services
84260027-4fbc-5c5f-aafc-ae9858443195 | checkpoint | Ensure concreters have correct finishing tools (eg, carborundum powder, etc…).
03eaaf7a-25a4-5c60-abf8-0d3245aaa038 | checkpoint | Ensure only rubber tipped vibrators are used to prevent formwork damage.
2f58ffd1-86f9-5c30-b991-1c4c1f94d0de | checkpoint | Obtain Subcontractors ITP (Concretor) & attach to this ITP
9f644f6a-af2c-5b5b-a395-8bb6784abc9d | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of stairs, immediately after pour.
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
1f774416-47c1-5414-ad4e-41fec77d84f0 | checkpoint | Confirm tolerance of finished concrete surfaces:
0d39ffe8-ee98-52fa-b9f2-bc81f956f666 | note | 6mm +/- from design RL
6ba58a59-474a-533c-8221-6387e7075c24 | note | 6mm +/- from 3.0m straight edges.
6f0b642b-097f-5dd1-a01a-8fb6189a8529 | checkpoint | If an as-built survey is required, confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan
22a9295a-a3fb-5647-8476-347469c13ca7 | checkpoint | Obtain all concrete tests at 7 days. Attach to ITP
24390ce6-c799-50dc-918a-2e7ec4d213e2 | checkpoint | Obtain all concrete tests at 28 days. Attach to ITP
00237665-de82-5d74-8b32-4d8f3713f8cc | signoff | Final ITP Review & Sign-off by Project Engineer
08f1bafc-5b78-501b-95a0-f80d05307c0c | checklist | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab |  | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab
295f5594-f977-5cf3-a95e-1b914b0e80c5 | section | Prior to Formwork Deck Handover
5ba4bfda-bc99-56cf-8b8b-2996c4f9926f | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
71577392-12c1-515b-a87b-92b6737e8527 | textbox | Architectural Drawings
35391470-e1ca-5251-ae7d-50a6f778b833 | textbox | Structural Drawings
2dbeafe4-65f8-590f-a07c-dd1d8baa5d09 | checkpoint | Concrete Mix Design
aa0b26bf-fcf3-566e-823c-bba049b0a821 | textbox | Confirm Mix Design
41c99b98-0067-5b53-98db-86509393965f | checkpoint | Set-out - Surveyor set out slab grids to allow formwork construction
bf140f59-99b4-5b36-96dd-09ee09530581 | checkpoint | Survey & Set-out of formwork correct. Check correct heights for formwork soffit, Top of Concrete (TOC) and falls
7e92b3f4-2de1-5ce1-87ec-7db3a674d241 | note | Attach Surveyor Formwork As-Built to ITP
8e1a66ad-611f-5f80-9a67-1faca5fe1a19 | checkpoint | Site Instructions - Copies of design changes, emails and site advices and the like to be attached.
100f5dfe-8ec5-59b9-910c-f68c280a8190 | checkpoint | Bondek (where applicable) - Back propping installed for pre pour and deflection & gaps sealed to prevent dripping
e0fe376b-a421-5e7a-882b-8c272a18b689 | checkpoint | Structural Steel Sign off from Steel installer and Structural Engineer (where applicable for bondek slabs)
1a7b7757-785d-5271-a047-9317f30cb7cc | checkpoint | Formwork Sign-off - Area cleaned of all excess formwork, sawdust, reo and debris prior to pour. Safe Access to deck available.materials before handover deck
41e7a28f-8521-5b18-a4e6-d67e7a5df259 | note | Attach formworkers ITP (referencing all hobs, steps, cast-ins, HDB's, bearing strips, polystyrene, fillets, etc… installed correctly)
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
dfa84113-61be-5071-a599-4bfa7da4d22e | checkpoint | Structural Compliance - Engineers approval for concrete placement required with list of defects to be completed
9e61c242-2c12-584a-ab33-a3a588135238 | note | Attach structural engineers inspection report and evidence of close-out
718b0a37-0bd9-5d17-b022-13f4506ee88c | checkpoint | Formwork Engineers Sign-off - Attach Sign-off
bc6540fd-d9b4-5bb0-903f-90a9e8eb0ee3 | checkpoint | Post Tensioning - Check Subcontractor ITP complete, and attach to this ITP.
14d9e1fd-3501-5226-a3bc-f01df740ab71 | checkpoint | Screen Needle Cast-in's - Inspect all screen needles are installed in accordance with relevant shop drawings
528ef2fc-3f99-53f3-a276-ddcef0e4da30 | note | Attach sign-off from Formworker
5e6c0c26-c34c-5155-82d8-95ade4979701 | checkpoint | Curtain Wall Bracket Cast-in's - Inspect all Curtain wall brackets/rebates are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
48245463-11d7-5676-8374-8cb3d0502001 | note | Attach Curtain Wall subcontractors sign-off & ITP from formworker
fbf3fa70-7e97-51f1-84c5-a73c5ecf2ebb | checkpoint | Crane/Hoist Bracket Cast-in's - Inspect all hoist and crane brackets are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
4c3b3f45-78b0-55bc-9628-c84b2cacceae | note | Hoist and Crane contractor to inspect and sign-off cast-in position.
fb2866ee-56ac-59c4-8bf3-33914cc7ebf4 | checkpoint | Temporary Penetrations - Inspect formwork penetrations in accordance with temporary works design. Surveyor to confirm locations are correct.
4e806b36-cb1b-5334-8aab-68cb0e0307f4 | note | Temporary Penetrations may include: formwork hoist, concrete boom, etc…
adb4d0e8-65a6-5de3-ac58-c795f4505cad | checkpoint | In-Slab Services - Electrical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
20504b08-0515-5b97-8bbb-92856bce0c8c | checkpoint | In-Slab Services - Hydraulic subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
09a073b7-597f-507f-a4c5-18c36fd14628 | checkpoint | In-Slab Services - Mechanical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
712acdc7-b4a7-52f0-a901-c68540c44cdc | checkpoint | In-Slab Services - Fire Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
236453d7-a578-5c50-93a0-18a68dbd4dc6 | checkpoint | In-Slab Services - Security Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
57f69192-958a-57f3-8f3c-a9e497f8f688 | checkpoint | Formwork Cast-ins - All timber fillets, drip grooves, Rebates, and proprietary shear connectors installed as required
c7e06a37-79f9-5353-8059-3f145d6d5f46 | checkpoint | Starter Bars - Confirm all starter bars for walls and columns installed as required per structural and architectural drawings and survey pins
d00e631c-e50c-574a-9aa3-68412fd9553a | checkpoint | Water Stops - Confirm installation of any proprietary water stops as required (ie; at CJ’s, etc…)
855ff8fa-6730-557a-8e52-d106ec75c5bb | checkpoint | Reinforcement Cover - Check top RLs for all reinforcement, ensuring adequate concrete cover. Confirm with Concreter. Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits.
d514d25d-afda-56c2-8c36-6209bbcfd564 | checkpoint | Attach Reinforcement contractors ITP
dcb336a8-fd09-5bfa-873f-07af8cbbf30f | checkpoint | Concrete Falls - Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary
0c708f08-397b-5649-92f4-d4d6c37335ab | note | Cross-check the following drawings: See Hydraulic, Architectural Concrete Outlines and Structural drawings
37c28923-04ce-5966-8fbd-571b16e9c359 | checkpoint | Cleaning of Deck - Clean off decks and beams prior to pour and ensure all exposed off-form soffits are free of any dust, stains, and rust marks. Hose down if necessary.
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
a996b133-8d9b-53cc-af5e-c4d995eba206 | checkpoint | Concrete Placement Checklist
7913c179-94c9-519d-a948-d0a9c94253c5 | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
79922c4d-a7b3-5475-9417-7a5ba8f297fa | tickbox | Confirm Delivery Docket References correct mix design
3c0e5aa6-2340-5e95-b8cf-be49dd705115 | tickbox | Plant and equipment checklist completed on concrete pump and lines
931fdd79-290f-5785-802c-dba7dfd82152 | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
248d7a4c-044f-5752-bebe-bb2ab35d27b9 | note | 1, 4, 7, 28 & 56 day compressive test results to be issued by batch plant
f8f5594c-c38c-5d78-a8b6-38ab0fa98b6c | checkpoint | Concrete Finish - Ensure concrete contractor is aware of required concrete surface finish.
c1e85569-9cbf-50e3-9b95-e4470c2fbcbc | checkpoint | Slab Curing - Check cured when bleed water stops and able to access slab without marking and also amount used complies
14e178fb-fe69-52a0-91f6-30076e8b4f0a | checkpoint | Concrete Falls - Confirm concrete has falls to drainage points in slab.
e1d73840-aa9f-57a4-b903-c73dee258910 | checkpoint | Attach Concrete Place Contractors ITP
a2dc03bb-a611-5d28-91e4-bf1fb10f9020 | checkpoint | Trade Representatives - Ensure a representative from each of the following is on site and witnessing the pour:
274596a9-8284-55c2-a562-3a463c31a7f4 | tickbox | Form Worker
6e693d5b-96b7-5efd-a753-91817e4b9749 | tickbox | Electrician
4d76e6fc-1f2c-55c3-a91d-791136188cdf | tickbox | Plumber
a671c5d5-4c08-5660-a9d1-8999d27af5cf | tickbox | Post Tensioner
2192aa73-f6ba-58af-8c61-4895a7d428fb | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry.
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
08728e08-995c-50af-a2ec-d7e14671870a | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan.
f886350e-a086-5135-9a70-b777886af386 | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
22ed6f70-72b8-5528-9059-0ffa3d38f35d | note | 6mm +/- from design RL
74023c59-165d-53fa-bcb2-6f6223d28ae6 | note | 6mm +/- from 3.0m straight edges
1495d922-a480-534f-b717-6368bad185b9 | checkpoint | Exposed Concrete Finish - Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610 (Class 1, 2 or 3)
73a62edd-f785-5a3d-9a66-3aa541d7b88b | checkpoint | Concrete Test Results - Note test results on ITP and attach:
a1ddf03f-e21d-552c-b850-a1e687cafdac | textbox | 1 Day
fe30e90a-5fb4-5064-a514-5f52dfe6511f | textbox | 4 Day
8becb43c-e7d2-5896-bc57-4c3a4c1c9126 | textbox | 7 Day
f9ca7c0a-9042-5d98-bf73-7ed0fad33737 | textbox | 28 Day
d3436848-b341-5571-8ded-d3c90f10030f | textbox | 56 Day
a376cbd5-1e22-5251-a5f8-f870a953ef4e | checkpoint | Initial Stressing - Concrete has achieved required strength MPa (10 MPa and confirmed by Concrete contractor)
c63b12e5-d21d-5ebd-a6d0-4bbcbc26a6ec | note | Concrete Contractor must issue Concrete test results, verbal not accepted
41f18e67-7d4a-5d5a-bb7e-80b7411ea4ea | checkpoint | Final Stressing - Concrete has achieved required strength Mpa (22 Mpa and confirmed by concrete contractor)
1188e90e-ee7d-54b8-b59d-1a0cd8f0a55d | note | Concrete Contractor must issue Concrete test results, verbal not accepted
14b415dd-206b-51ad-b6fb-ce3037f86b3e | checkpoint | Stressing Sign-off - Before stripping can commence final stress complete, Ducts grouted and PT supervisor issues verification records
fff3426b-83cc-50f5-8e4a-d67a41db9099 | note | Attach Post Tension Contractors ITP
77c98c2f-53b9-58f0-b5d3-8207838ca4b1 | checkpoint | Extension Records Approval - Engineer approval of extension records following final stress
2c04992a-3395-5768-9381-56b23470d61c | textbox | Record date when props were removed if not given approval by engineer
9d87b967-2d49-5717-80ce-42ebdedfe8b2 | checkpoint | All non-conformances closed out and accepted by Structural Engineer and Architect.
d36b933e-9fa1-5bbc-9958-546e8775e762 | signoff | Final ITP Review & Sign-off by Project Engineer
23b80200-b5f4-59be-bf57-229c7a195a32 | checklist | 101C-SDC-TMP-CON-ITP-015 - 2 - Facade Curtain Wall | itp | 101C-SDC-TMP-CON-ITP-015 - 2 - Facade Curtain Wall
dee87330-edfd-5152-b514-90ed76f1359a | section | PRIOR TO CURTAIN WALL INSTALL WORKS
18a683b7-0dcd-56aa-8ef4-a1c42559600c | checkpoint | Shop Drawings
ee2eddcc-cf79-5e37-b150-5f8a3a578835 | note | REFERENCE: Aconex – Façade Drawings
594481c3-7c9d-5675-a169-b742354783db | note | ACCEPTANCE CRITERIA: Confirm correct For Construction Shop drawings available for the installation with the contractor. Refer to Plan located at core walls for approved reference (SDC site engineer to install reference plan)
b2bb5465-a81c-57e5-9da0-0836522d32ea | note | INSPECTIONS & VERIFICATION - BY: SE/FN
222c1ad5-6e34-5dcb-a88e-4b0017ac64c2 | note | INSPECTIONS & VERIFICATION - TYPE OF: Witness
c3c06fb6-0a8c-585f-9ef5-a036b4c37dc3 | textbox | COMMENTS / RECORDS: Record Shop Drawings available at time of installation from subcontractor.
14cbfa09-9205-55d1-9da2-e76ed2eab224 | checkpoint | Survey & Site Measures (1)
f4ff205a-ce7b-50ba-8932-9b384c11e053 | note | ACCEPTANCE CRITERIA: Check minimum survey requirements provided for the installation (ie; intersecting grids and benchmarks).
d1b2abc3-b993-578d-a3c6-0499e077ca53 | note | INSPECTIONS & VERIFICATION - BY: FN
c4035beb-bbb6-5944-87ed-f3ae9c5b998a | note | INSPECTIONS & VERIFICATION - TYPE OF: Hold
17c2079d-c153-567c-bec3-e2a338124f29 | note | COMMENTS / RECORDS: Attach Photos of grids and benchmarks provided.
b156e66d-9022-5ce3-a5cd-c4e89b8a62d9 | signoff | HOLD POINT
09ab0f08-1880-59f5-9409-8fcdd01e1700 | checkpoint | Survey & Site Measures (2)
d764f81e-00a2-5db0-8dfb-b58bc955d316 | note | ACCEPTANCE CRITERIA: Confirm opening sizes (widths and heights) correct per shop drawings. Check also that hobs & set down are level.
de17def3-b35d-5133-992c-45a0ab64f796 | note | INSPECTIONS & VERIFICATION - BY: FN
f3c55b85-58ce-525d-aa72-503f0d490ed6 | note | INSPECTIONS & VERIFICATION - TYPE OF: Witness
e4787fed-f5de-5feb-80ec-ea8a71adfecd | textbox | COMMENTS / RECORDS: Record as-built slab/hob/set-down SSL on install floor and floor/soffit above for reference (Surveyor As-built).
5c00771e-ec7e-5f18-93d0-3a24747c23ba | checkpoint | Storage/Installation Area
d99064ec-7d44-521b-b07b-e56c4db496e9 | note | ACCEPTANCE CRITERIA: Confirm curtain wall storage/staging area is available and ready. Confirm installation zones available and ready from previous trades.
24d8ffb3-8e33-55ad-878b-c48dc3146f31 | note | INSPECTIONS & VERIFICATION - BY: FN
3fc7c661-3b11-5d5d-a17a-405ac2a6fb8a | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
165343b7-4d39-5e94-a8b0-8e7ab5257c24 | note | COMMENTS / RECORDS: Note: storage/staging and installation zones may be across multiple floors (ie; panel install on 1st floor, floor above to be panel laydown, 3rd floor for crane). Ensure plywood installed across set-downs for pallet trolley movements.
b40699d5-a744-5d75-921c-a1cdc8a5b5a3 | checkpoint | Product Review (1)
17b38847-52e2-5e55-b306-11f677130854 | note | REFERENCE: Aconex – Façade Drawings
d1301c6e-bbd2-5d00-81b2-8fc390cf975b | note | ACCEPTANCE CRITERIA: Confirm all curtain wall panels are free from damages prior to installation.
7f664da9-ac59-50b2-ba02-7453e3c4700a | note | INSPECTIONS & VERIFICATION - BY: FN/SE
355e41b3-3473-5f33-8fad-6cdeed3b7f64 | note | INSPECTIONS & VERIFICATION - TYPE OF: Witness
eff08195-5878-50a7-9f93-0617f153acb8 | textbox | COMMENTS / RECORDS: Take photos and record any damages prior to install with specific panels (reference shop drawings for panel identification). Panel sign-off walk to occur to after each shift to record damages (if required)
fa54a783-7195-5842-8914-18b98c7bf614 | checkpoint | Product Review (2)
111aeb59-e15e-50ca-a4f1-8f7dea213a21 | note | REFERENCE: Aconex – Façade Drawings
08a628bd-7e5b-535d-876d-483cdec42da5 | note | ACCEPTANCE CRITERIA: Confirm panels are correct for the floor/area being installed, including colour, grade and thicknesses.
4cca5ae6-5c88-51e4-b8fc-153344d409ad | note | INSPECTIONS & VERIFICATION - BY: FN
ea5d30ea-d921-59d6-a698-053f18b5d216 | note | INSPECTIONS & VERIFICATION - TYPE OF: Witness
a95805c3-6c9c-5bfb-a63a-090bf0a49a20 | textbox | COMMENTS / RECORDS: Record photos of panel identification marks on packaging for reference. Compare against install plan on Core Walls.
c81cf52d-eda9-5a1e-ab0b-58f7ecd36c38 | checkpoint | Cast-in Façade Channel
3b854c85-0487-5fc5-84b2-577f8faaf604 | note | REFERENCE: Façade Contractor ITP
c385ff1d-0e64-543f-a1a1-79ee7beb38d6 | note | ACCEPTANCE CRITERIA: Confirm façade channel installed per agreed detail and in correct locations per shop drawings.
00ec3c85-d5bc-540c-aa49-a8da5ffc92de | note | INSPECTIONS & VERIFICATION - BY: FN/SE
ed92485a-73e7-5182-ba6d-110ff8fbdf8a | note | INSPECTIONS & VERIFICATION - TYPE OF: Hold
af43ac98-4c56-55b8-bbb9-069df42bdbac | note | COMMENTS / RECORDS: Attached façade contractor pre-pour inspection ITP for cast-in façade channel.
44881ea3-d3c1-5e12-9a28-9c11f2f7fa12 | signoff | HOLD POINT
3f48d143-af83-4262-ac49-a94eec06f226 | checkpoint | Cast-in Façade Channel
824d830b-97e7-5826-aaa7-08951e6e2063 | note | REFERENCE: Façade Contractor ITP
790ea204-b407-5e43-9cc1-cc214bd92cb6 | note | ACCEPTANCE CRITERIA: Confirm Channel pull out testing has been conducted on cast-in elements prior to curtain wall installation.
ae6cb88b-1f7e-5989-83f2-d96b759f1291 | note | INSPECTIONS & VERIFICATION - BY: SE
26f8896f-b755-5e24-a248-dcb056eced92 | note | INSPECTIONS & VERIFICATION - TYPE OF: Hold
e58e64ea-232d-52f9-ad5f-dcd8015e6c7f | note | COMMENTS / RECORDS: Attached façade channel testing report showing compliance of brackets.
e2b66205-0f0e-5792-925d-e8ff0c1fb81e | signoff | HOLD POINT
931224d7-2051-5d43-b064-dddfe231a55e | checkpoint | Weatherproofing Pre-Works
8c9692a3-991b-5a77-8588-47ef0984433f | note | REFERENCE: AS 3740
93176d3b-c445-52cd-ac09-c27b1c8ab3c8 | note | ACCEPTANCE CRITERIA: Ensure all sub-structure has membrane installed and signed-off prior to curtain wall installation.
f2bfd53d-5d19-5a03-9418-74d5bbc873c3 | note | INSPECTIONS & VERIFICATION - BY: FN
417d64e1-1706-5b11-90ac-88434dc4f305 | note | INSPECTIONS & VERIFICATION - TYPE OF: Hold
64d03ed7-6044-5163-8e75-3c242b6bebd8 | note | COMMENTS / RECORDS: Ensure to check areas such as: hobs for starter panels, vertical interfaces such as curtain wall to core wall junctions, balcony set downs, etc. Attach waterproofing contractors ITP.
587a4168-092b-5747-8dcd-db59b1c7b06a | signoff | HOLD POINT
f67bf10d-91a8-5459-8352-b2f1c0b62773 | section | DURING CURTAIN WALL INSTALL WORKS
b415af50-21c9-587b-a3b7-bde434229227 | checkpoint | Benchmark RL for Installation
c5271b9a-cf6b-534c-b334-cebb5eb869b1 | note | REFERENCE: Site Survey Marks
9a58e666-a8e7-5db2-84ba-bdfd00c7e77f | note | ACCEPTANCE CRITERIA: Verify with curtain wall install contractor that they are working from the agreed benchmark to set panel positions/heights.
0741f7be-5d36-53f2-af85-c1298abdc592 | note | INSPECTIONS & VERIFICATION - BY: FN
46c9f937-e141-5b22-8b22-79d98e57b76d | note | INSPECTIONS & VERIFICATION - TYPE OF: Hold
aa30a30b-e448-5b05-a67c-be4959896921 | textbox | COMMENTS / RECORDS: Record agreed benchmark:
b1720a54-4f70-5e8b-a2a8-643f5bed1ac6 | signoff | HOLD POINT
a27b160d-13eb-52a4-9b3a-76248c8a5d2f | checkpoint | Installation / Operation Checks (1)
feec6a50-4009-5230-ae4a-ac13ffd03bc0 | note | ACCEPTANCE CRITERIA: Review curtain wall panels installed plumb and level with panels below and adjacent.
6c809070-3dfe-5bc3-8061-04686a588ef1 | note | INSPECTIONS & VERIFICATION - BY: FN
7fa6890f-f660-5e78-b7d1-67a42823928f | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
b85ed309-1088-5457-85f3-26387fc45231 | note | COMMENTS / RECORDS: Spot check 5 panels per floor and complete general visual check.
30aa61d4-4e0c-55a4-9ca4-3fef1ba03402 | checkpoint | Installation / Operation Checks (2)
112300ef-7b8f-55c2-8f90-0fb31e7825e7 | note | ACCEPTANCE CRITERIA: Ensure curtain wall installed to the design façade line. Tolerance permissible is + / - 5mm per façade specification.
40e0a910-dd30-5c64-9afc-c70d4ae703a8 | note | INSPECTIONS & VERIFICATION - BY: FN
899c22dd-aabc-5724-8315-dc73686d347a | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
6196f3d1-45f9-5db9-8ee8-8e2883235b75 | note | COMMENTS / RECORDS: Check measure off grid as required, use level on panels to check plumb. Spot check 5 panels per floor and complete general visual check.
f9520e9f-d837-5bc7-aa0b-016531257147 | checkpoint | Installation / Operation Checks (3)
52a8f1ac-b7bc-5b17-ae5c-5ab7c3839d1e | note | ACCEPTANCE CRITERIA: Check to ensure correct type of glass or non-vision panels, etc… installed per shop drawings.
191e38aa-14fa-58ed-83f9-289f92230bb8 | note | INSPECTIONS & VERIFICATION - BY: FN
f9180e4b-09fd-5325-9e3b-c9f70d5010cd | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
fbabe895-c1d3-5d24-ade4-5882dc9160d5 | note | COMMENTS / RECORDS: Refer to shop drawings installed on core walls (curtain wall general arrangement & typical panel details) for reference.
8cb22098-0691-5721-89a2-f48cd7d2c1db | checkpoint | Installation / Operation Checks (4)
56f12cd2-0fd4-5172-9129-5b6e234d5c66 | note | ACCEPTANCE CRITERIA: Review sub-head and sub-jamb installation to ensure required gap left for movement per shop drawings (ie; approx. 20-30mm).
ca72866f-0d91-5533-a26a-d27bda1b4541 | note | INSPECTIONS & VERIFICATION - BY: FN
771bb1db-8bca-5495-a362-766a01622d0a | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
1f30d6fa-79ab-5eab-bd02-f22447a5b3c4 | note | COMMENTS / RECORDS: Ensure to check wintergarden balcony panels (sub-head) and panels adjacent to core walls (sub-jamb). Spot check 5 panel per floor, attach photos with tape measure.
bed905a3-0376-56c5-a643-a8edda4e9082 | checkpoint | Installation / Operation Checks (5)
659baacb-1165-53fd-930d-7bb550692745 | note | ACCEPTANCE CRITERIA: Review sub-sill installation, ensure caulking to mechanical fixings where penetrating membrane installations.
3ba04033-defb-5705-ae3d-67bcb1058d98 | note | INSPECTIONS & VERIFICATION - BY: FN
ffa49b0d-0f34-5f20-8a3d-b4233f5aeca6 | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
ee2e691b-b890-5f31-801c-e43903c15511 | note | COMMENTS / RECORDS: All Mechanical anchors to be sealed. Spot check 5 panels per floor, attach photos of sealant works.
060e2243-fb53-5e0c-b928-003dfd2ef237 | checkpoint | Installation / Operation Checks (6)
a9c02f38-c8eb-59bf-8b88-5bfcde926cda | note | ACCEPTANCE CRITERIA: Check installation of smoke flashing and required fire rated insulation (CSR Bradford Fire Seal Curtain Wall Batt) at slab to panel interface. Ensure insulation install to depth of slab. Ensure no gaps present in flashings.
e0c0bcc1-1e82-5e17-a3cf-46c061659c05 | note | INSPECTIONS & VERIFICATION - BY: FN
63e8046c-e6b2-5798-b2a1-0f7fe7358f64 | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
7adf18ac-0c90-537d-b144-7704b5cc8a23 | note | COMMENTS / RECORDS: Spot check 5 panels per floor. Attach photos to ITP prior to insulation being covered over. Attach photos of finished smoke flashing.
727d4db2-b3b3-54ec-af50-8c71076bad03 | checkpoint | Installation / Operation Checks (7)
c33bdea1-9116-52f1-b48c-fe3d1dbec6e6 | note | REFERENCE: Façade Specification
7b707dfc-448f-524f-bb18-1f6dc7c83ad3 | note | ACCEPTANCE CRITERIA: Review fixings to ensure stainless steel per description noted below from façade specification.
3824c538-326d-5929-9bd8-8837c084f482 | note | Fixings and Hardware:
620ba6b2-5c09-5d6a-b5f2-4bf86af9c602 | note | ○ Within panels to be grade 304 stainless steel
527e1daa-5859-50a5-afc8-3c402416b3e5 | note | ○ Internal fixings (including to structure) to be grade 304 stainless steel
929569b4-b21d-5076-99cb-0ab381362641 | note | ○ External and visible fixings to be grade 316 stainless steel
f79bce5e-23bc-5d31-83e5-0f0e1aa132ae | note | INSPECTIONS & VERIFICATION - BY: FN
b10cfe5f-8520-5613-ac12-1f6b2bf06bab | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
5ec329ec-fe20-5ad2-86e5-1072fae6d792 | note | COMMENTS / RECORDS: Spot check for each floor installation the panels and subcontractor supplies being used on-site.
d63e4d90-1991-5239-8c3f-53462c7b45a0 | checkpoint | Installation / Operation Checks (8)
97466eb4-facd-529d-80f1-48970747b045 | note | REFERENCE: FJC façade details
a3e32111-8842-50df-aa62-88b626713287 | note | ACCEPTANCE CRITERIA: Check secure installation of weatherproof sill flashings and membrane works completed accordingly per architect details. Check any pressure seals installed correctly.
f9738523-83ff-5c69-af7c-196b197dc783 | note | COMMENTS / RECORDS: Review against each interface.
adeca8ab-1593-503d-a61b-bdcc76fccb27 | checkpoint | Installation / Operation Checks (9)
333c40f9-e3d5-5fd9-814b-adb93fb12d08 | note | ACCEPTANCE CRITERIA: Check secure installation of any façade sun hoods or louvre elements to panels during install. Check bolts have been secured to required torque (xxx)
ae8d37eb-431d-5314-b9a8-2ab63165be04 | note | INSPECTIONS & VERIFICATION - BY: FN
e8190f51-54f8-51ef-b084-0b983cc154a5 | note | INSPECTIONS & VERIFICATION - TYPE OF: Witness
f2c8b726-cdf0-56cb-8933-f81086703c7b | note | COMMENTS / RECORDS: Spot check at least 2 panels per floor and attach photos of torque measurements.
bb26f3f6-e52e-535b-91a7-9b548f11ce41 | checkpoint | Installation / Operation Checks (10)
5dcaec85-a5cf-5554-a254-0091e11777f1 | note | ACCEPTANCE CRITERIA: Check all operable parts are working correctly (ie; sliding doors/windows, window winders/restrictors, door locks and hardware, etc…).
90d79525-6ba6-5740-9d70-17f506458e07 | note | INSPECTIONS & VERIFICATION - BY: FN
628ce031-1254-56b6-a465-79e408dd10ff | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
d39487cf-bea5-5c66-918d-e34ba95e2d28 | note | COMMENTS / RECORDS: Specific Checks (2 full apartments per floor):
60c37349-e7ba-58e4-9c5a-aed7efa44a92 | note | ○ Manual awning windows are restricted to 125mm.
1d86ce69-0254-5517-8b25-f451a3da6ba8 | note | ○ Check auto awning windows have cables pulled out and accessible & operating correctly.
8e301941-2094-51d5-8e84-192116d7ed3f | note | ○ Check sash windows to wintergardens and balcony sliding doors are operating smoothly.
fba7da13-1313-5395-83aa-bc26995ea5cd | note | ○ Check awning window and sliding door handle hardware engaging correctly.
455c1464-60a9-5b80-950c-1c1f3c9290e1 | note | ○ Swinging doors – check handle operation and restrictors to hold open door are working correctly.
3625b7cb-1ef4-5517-92db-f032cc5ec68c | checkpoint | Installation / Operation Checks (11)
69cd965a-360b-5d51-bfbd-68f2aabbf08a | note | REFERENCE: Acrylic Sash Handles
59ea0ed9-160c-592a-ae3d-05e04280d111 | note | ACCEPTANCE CRITERIA: Check acrylic handle to sash window installed at 1900mm AFFL, level and to centre of panels. Check also that adhesive is free from bubbles
731b1183-37c4-5c08-88c9-7a6425092c43 | note | INSPECTIONS & VERIFICATION - BY: FN
ded419ac-5727-5ee7-85e8-288489b1953e | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
aa5d1b50-5528-5760-849d-c001ae52ca95 | note | COMMENTS / RECORDS: Complete full check of 2 apartments per floor.
21bf6c0f-6897-52df-8dc2-0620f27f203a | checkpoint | Installation / Operation Checks (12)
6927da0c-6d21-564a-b7dc-8d8a40604e2b | note | ACCEPTANCE CRITERIA: Check all silicone/caulking installed on-site is as per approved sample.
68fbfb03-a6f7-565f-a048-ebe8b96717a6 | note | INSPECTIONS & VERIFICATION - BY: FN
73f71ba3-2b4b-5c28-9264-6bece0637132 | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
e1705831-ecac-573d-b621-35be29b2334b | note | COMMENTS / RECORDS: Product approved: Sikaflex-PRO (Concrete Grey Colour) – 961737. Spot check subcontractor supplies per floor installation.
d88ee8d5-9057-5e30-a472-beb20aa7a99d | checkpoint | Services – Mechanical (Kitchen/Toilet Exhaust)
14709f93-9d77-5e2f-8a29-a48ddc4ddfd2 | note | REFERENCE: Mechanical Shop Drawings & Curtain Wall Shop Drawings
d2d57d42-8b26-526a-8b41-29f6f398b527 | note | ACCEPTANCE CRITERIA: Review for adequate installation and sealant of the mechanical ductwork to the curtain wall panels.
f5b3dc92-d508-54eb-985c-fe518cea877a | note | INSPECTIONS & VERIFICATION - BY: FN
d52e6023-b8de-5288-8482-ba00b49534a8 | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
eafa8f9c-2d7d-5c50-8a47-6887fcfa8031 | textbox | COMMENTS / RECORDS: Record photos for reference.
9dc7e65e-15f5-5266-9a43-b632cb1ec54f | note | ○ NOTE: Flexible ductwork connections to backpan to be installed prior to panel installation and checked to ensure adequately sealed.
ee0e3916-d38c-5e66-bc9e-a51657e5c5f5 | note | ○ Check all instances of mechanical interfaces per floor.
1a712984-5552-525d-a890-9d3edd420e68 | checkpoint | Balcony Services – Hydraulic/Fire (Water/Gas & Sprinkler Lines)
2576930f-739e-557c-af29-c1ee28fedfe4 | note | REFERENCE: Hydraulic/Fire Shop Drawings & Curtain Wall Shop Drawings
538963de-c754-5fde-8b94-7e2f26d093c0 | note | ACCEPTANCE CRITERIA: Review correct placement of water/gas lines at sub-head zone and ensure adequately sealed for weathertightness & Acoustics.
b27e5e4c-702c-5144-b18c-ef4de19be293 | note | INSPECTIONS & VERIFICATION - BY: FN
add36c87-feca-5806-a628-bc7040940265 | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
f79563b4-285b-5936-8088-e9b8e1f2b779 | note | COMMENTS / RECORDS: Refer to curtain wall shop drawing: XXX for installation details. Check all apartments to ensure details installed correctly.
e2e6ee6e-8d79-5ae4-b2f4-0c60a3f0dbb4 | checkpoint | Balcony Services – Hydraulic (Overflows)
b895f6f1-8960-56be-95ca-1349f591d39b | note | REFERENCE: Hydraulic Shop Drawings & Curtain Wall Shop Drawings
2195abbe-e740-598d-a6cb-79568d7c57b1 | note | ACCEPTANCE CRITERIA: Check overflows installed below slab and adequately sealed to curtain wall facade by hydraulic contractor.
30df3773-0b66-5858-988a-f5a1da338b34 | note | INSPECTIONS & VERIFICATION - BY: FN
0f562eaf-475f-52ec-825d-36b2c26f9c0e | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
560468ab-25f5-55f7-9dcf-a00d7146ec45 | note | COMMENTS / RECORDS: Attach typical photos showing installations – check all balconies per floor (x2 overflow installations per balcony).
61b06fef-eac6-50a5-bcaf-6204f9ad5186 | checkpoint | Curtain Wall Defects (Pre-Installation)
27eb9212-b00a-5188-91eb-85dfb3eac23d | note | ACCEPTANCE CRITERIA: Ensure all protection removed from external face of curtain wall panels pre-installation and review aluminium and glass to ensure free from surface defects.
189549e5-31c3-5750-85db-377eef0bbdcd | note | INSPECTIONS & VERIFICATION - BY: FN
fbf32f99-a742-5de0-beb6-4df4ca7234af | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
5f6c6595-84cd-5047-bbb1-06f2aca85453 | textbox | COMMENTS / RECORDS: Record any defect photos as part of ITP.
cc25c546-bfdf-5e0c-821d-0815ea11af42 | note | ○ Check 10 panels per floor (approx. 10%)
bbc71ce6-1b14-502f-a2a1-a8acef07767b | checkpoint | Curtain Wall Defects (Post-Installation)
86da0a0e-f291-56fd-9d02-413112fd9d48 | note | ACCEPTANCE CRITERIA: Ensure all protection removed from internal face of curtain wall panels post-installation and review aluminium and glass to ensure free from surface defects.
0ae66e53-38b0-55fd-8187-3906770fa821 | note | INSPECTIONS & VERIFICATION - BY: FN
d1cb2ae0-4138-5a79-8318-9a6c9331242c | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
4dc17c70-9e68-547a-bf20-7074c9ecdf2c | textbox | COMMENTS / RECORDS: Record any defect photos as part of ITP.
6daf7ac0-cddf-519e-a0c9-7519bb65a441 | note | ○ Check 10 panels per floor (approx. 10%)
8393fe1b-2be5-5eda-ba8d-531028959c07 | checkpoint | Façade Access Elements
8648d212-6696-5296-b003-183d633e4f19 | note | REFERENCE: Façade Access Shop Drawings
f2b38c41-c018-561b-a4fa-02803f149797 | note | ACCEPTANCE CRITERIA: Where relevant levels, review and ensure façade access elements are attached to curtain wall installation per shop drawings (ie; raptor rails & pig tails, etc…).
6e087470-41ce-5a6a-92a3-4049e26916c3 | note | INSPECTIONS & VERIFICATION - BY: FN
760c5d39-eeb9-5dc3-99b5-ca3ef8e4ab44 | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
e955a4dc-db45-5dbb-9cc6-47e7bf8e0cac | note | COMMENTS / RECORDS: Location References: Level 30 sunshade (raptor rails), Level 31 – 35 sunshades (pig tails).
9a2513b6-e289-5dab-94ee-14a7e4107054 | note | ○ Attach install and certification documentation from façade access contractor as required.
e2bb2b54-8d0f-5f1b-bfc1-028b6c443742 | note | ○ Attached typical photos of the installation for reference.
319dcc8c-11af-5f13-8f74-46d809cb3a68 | checkpoint | Grouting to Façade Pockets
d00c29be-cbe9-5dc5-8bd1-df197eee8631 | note | ACCEPTANCE CRITERIA: Ensure grouting to façade pockets completed as per detail in shop drawings.
c2ca206e-60f8-51c7-982c-64b67b49f12b | note | INSPECTIONS & VERIFICATION - BY: FN
4d9ff5c4-c15e-56a7-92ea-0a1176f5e70c | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
e0cb1f89-cea2-592c-b332-13f4d3f38dfb | note | COMMENTS / RECORDS: Obtain sign-off from curtain wall contractor that brackets have been checked prior to infilling pockets. Check all pockets are filled by formwork contractor.
45dbcca2-8595-535a-87e5-b62d7d986332 | section | POST CURTAIN WALL INSTALL WORKS
4d3919aa-4e09-5997-9e8e-6e14df4ba2e6 | checkpoint | Contractors ITP
390a60cb-aded-5164-96b8-caceeec659c2 | note | ACCEPTANCE CRITERIA: Attach façade contractors’ installation ITPs (Façade curtain wall & Window Walls (Balcony panels) & terrace awnings).
554db7cc-dc41-548a-b46e-a2ac6d203ef8 | note | INSPECTIONS & VERIFICATION - BY: FN
6babac0b-5f58-5983-bdd2-75c033bf559e | note | INSPECTIONS & VERIFICATION - TYPE OF: Hold
eed564a0-eccd-55f0-98f5-42934a6a145e | note | COMMENTS / RECORDS: ITP required to be obtained per floor and prior to handover of level to subsequent trades.
92088df8-2db8-56dd-a522-bc920cce77fd | signoff | HOLD POINT
8f6be928-ded4-5ec2-9751-723d96580790 | checkpoint | Design Deviations
914f12c6-9a23-5bc5-8b2f-d0ceaa882c14 | note | ACCEPTANCE CRITERIA: Attach any correspondence related to design deviations as required to show approval from relevant consultants.
f94e0574-53db-5b1a-b37c-5d628443286e | note | INSPECTIONS & VERIFICATION - BY: SE
87d41414-0f83-51b8-b110-94d5a1c746fb | note | INSPECTIONS & VERIFICATION - TYPE OF: Surveillance
0ba225b9-08c4-59ce-b677-77e25bab4d0e | note | COMMENTS / RECORDS: Track with design manager as required and review inline with DBPA
9c479b1b-1f95-539d-86eb-d971b7dba01e | checkpoint | Façade Engineer Inspection
73ddc7d9-56f6-52fc-bc91-82d7897f312a | note | ACCEPTANCE CRITERIA: Attach façade engineer inspection report/sign-off as required.
abe7f4ce-7e7a-50b1-b03c-33b25a100c38 | note | INSPECTIONS & VERIFICATION - BY: SE
dc23acab-bf83-52f7-b82c-927b318e2552 | note | INSPECTIONS & VERIFICATION - TYPE OF: Witness
745d9fe4-4dc8-5dff-8523-fbd5173f5ed3 | note | COMMENTS / RECORDS: Ensure façade engineer inspects whole installation of first floor curtain wall (Lv14) – cast-in brackets, curtain wall installation, smoke flashings, window walls, etc. Ensure periodic inspections there after (every 3 floors) and any new installation details.
340d6c79-0600-5343-bde3-ca1a769a3f70 | checkpoint | Curtain Wall Protection
19b6d657-711c-5425-a4eb-3b327a6d5364 | note | ACCEPTANCE CRITERIA: Ensure protection installed to curtain wall glazing as required to prevent scratches during construction.
e0811bc3-629a-5192-a975-2ee51506abef | note | INSPECTIONS & VERIFICATION - BY: FN
ec5f73fe-bdaa-58c7-990b-bbea862adba0 | note | INSPECTIONS & VERIFICATION - TYPE OF: Hold
f5778d8e-7d5d-51a7-a180-35ecf1cf3f8a | note | COMMENTS / RECORDS: Ensure protection (coreflute) is installed on every floor, to every panel prior to handover to subsequent trades.
23e3a12e-2a94-58da-b9c7-7465d1e7b69d | signoff | HOLD POINT
311e7fae-cf06-444f-984e-307e1a5006e7 | checklist | Apartment Finishes ITP | itp | Apartment Finishes
cb835373-39b5-47a2-93b7-9bf739acede8 | section | Timber Floor
bd7e501b-6c2e-405a-9ce5-470884b35d86 | checkpoint | Measure Floor to Ceiling Height to ensure correct build up.
fb80a914-69e8-5ffc-be99-a69885031e36 | note | *Spot Check throughout apartment*
1c03eab3-da38-4353-9105-0f7a0e3ce520 | checkpoint | Ensure Acoustic Underlay has been installed.
e618ce75-f31f-4da8-912c-41ad7f29fd39 | checkpoint | Ensure Correct Setout
1bf00e06-8d08-4ea7-a56a-6a3fa3d6dce1 | checkpoint | Ensure boards being installed are the correct colour scheme.
db75fdc7-b4a1-5e04-9435-b745d4694fa6 | textbox | List colour scheme and board colour:
e6218425-8a4c-4dc8-a23e-d97f2901a361 | checkpoint | Check any expantion joints have been installed in the correct loction.
0664709d-8d04-46af-8756-ee658573400b | checkpoint | Check any purchaser upgrades have been installed
2d6915c5-3a54-488c-ba70-16f28d4bd219 | checkpoint | Ensure finished floor surface in within Mamimum deviation torerance.
1ea705f4-6536-5857-b164-d71ed3d219d1 | note | *3mm from a 3m staightedge laid in any direction*
5190ba9a-dcf0-442f-b3e4-bdd6cdadeb35 | checkpoint | Ensure threshold Setout is correct at all door ways.
29d37f5d-4d78-404b-a746-8aa8e3a6b73a | checkpoint | Ensure even distribution of board colour tones throughout apartment.
73e37ff7-4afb-4f6a-a545-344ec4c3e3f7 | checkpoint | Ensure Angles have been installed as per plans
f122ef0f-617c-47ac-91b6-db0ca4fd4f3c | checkpoint | Ensure correct caulking colour has been used, and confirm caulking has been installed in required locations.
876d53b6-3297-43cb-80fd-4b42d1171ca5 | checkpoint | Record product batch/serial number for tracking of any future defects
643e56dc-cfa8-50c7-9bf0-16855825a74a | textbox | Batch/Serial Numbers:
5501c17d-68bf-444c-a158-64b84fe06683 | checkpoint | Record photos of floor
59b40eec-8172-4e0c-a878-e2437fff145c | section | Carpet
d871dd14-3eb2-4280-b871-42268541091c | checkpoint | Ensure Acoustic Underlay has been installed.
97826c27-b86c-4b4f-9e2f-7f5f2f032768 | checkpoint | Confirm correct carpet colour has been installed
3e7dc61b-3d63-401f-8460-52c00515eebe | checkpoint | Ensure carpet seams have been installed neatly and in corrrect locations as per plans.
a749473f-277e-4056-b196-183bad590090 | checkpoint | Ensure Carpet levels at door thresholds.
d2d5ed96-8908-481c-8aef-04cb1e28f14c | checkpoint | Check for any imperfections in the carpet
103bd739-4a89-5868-9543-5516be88eb0a | note | *Including any ruff spots in the under the carpet*
d2a6f37f-e385-4687-974a-a6329a1da32e | checkpoint | Record Photos of Carpet
ac4dede5-2298-4014-a528-682af129b0ca | section | Skirting
12b6307c-63fb-41eb-9391-eb317b46c989 | checkpoint | Confirm all Skirting is installed as per plans
944f79b9-5a03-4fc2-8708-9f6750729e31 | checkpoint | Ensure all skirting intersection are neat
50a1a9ef-cb13-494d-a47d-af28e9b7e0e0 | checkpoint | Ensure there are not visible joints in skirting
68f6f00a-6167-487e-8b14-30f1b860224f | checkpoint | Ensure caulking under skirting is neat to the floor.
2a529e82-7f3c-48bf-9f39-b4980911efba | checkpoint | Ensure skirting rebate is cleanly installed
99d4fc36-1d83-4004-be4b-d496f34f4277 | checkpoint | Ensure there's no bowing in the skirting
25404baa-b8f6-451d-aa5a-258af258f069 | checkpoint | Confirm skirting is installed with correct gap for expanation joint (2-3mm) - Only if expanition joint is required.
0ad09607-c096-49b4-9897-5a3b1b14c5a5 | checkpoint | Record photos of skirting
af164ea8-adee-46ab-82e4-28a25dacdd21 | section | Paint
7be47d7c-476a-4f55-b5b1-29ff34d9ff8f | checkpoint | Ensure wall substrate is set and sanded correctly
042faa81-e95b-409d-b702-b8a66caf1fce | checkpoint | Ensure paint colour is correct in each area
dde98014-2c58-41bc-8588-061e2aaeeea5 | checkpoint | Ensure paint is the correct finish
f4a16ae4-89a7-4fbf-9740-572bf46b3689 | checkpoint | Check that black paint has been appied to required areas. i.e behind bulkhead grills
cb1e51fc-7e1d-4b4f-95d1-f9cf838aa8de | checkpoint | Check to ensure 5 class wall were installed to area's exposed to direct sunlight.
b327b49c-a6e2-478b-abed-00cc95f64c28 | checkpoint | Ensure top's and bottoms of doors in wet areas have been painted.
4f1ec874-8307-461d-8c6c-39c8137bfcda | checkpoint | Confirm there is no paint on other elements
76a816c3-4fd5-4705-b2ab-896ef7b61639 | checkpoint | Ensure there are no divots in paint
1ba1f4bb-9b9f-4f6d-ad0c-e8d0450c9e46 | checkpoint | Ensure there are no visible brush strokes
04c14baa-3160-4514-8358-091c95597a26 | checkpoint | Confirm all required coats have been applied
ad31ab40-e273-4614-aa7e-c72c625a57f3 | checkpoint | Record Photos of Painted Walls
43a235d6-77c7-43d6-97fd-4ce2fde9fdf7 | section | Fixtures and Fittings
70ae946c-b29c-4966-93ee-0d4cf12d3841 | checkpoint | Laundry, Bathroom, Kitchen
bac9cca1-517a-4c46-adf6-87248d9064f0 | checkpoint | Ensure all Fittings and Fixtures are installed as per architectural Plans
298f683c-bd16-5220-a666-6335653fe56a | note | * Refer to Architectural RCP, Bathroom/Kitchen Elevations.*
3c599199-e8f2-5ca7-ab75-b419f4bbc74f | tickbox | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
5772ff40-f403-4773-9257-a30993a3df34 | checkpoint | Confirm any functional Fixtures/ Fittings are in working order
4ac15ba7-5a61-5cef-a918-1f60f13f102a | tickbox | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
fab1bfda-3234-4d41-adaf-d16e1ce8d6ba | checkpoint | Confirm correct quantities of all Fittings and Fixtures have been installed as per architectural RCP drawings
2a8378a1-487c-5591-941c-e56359a214a3 | tickbox | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
3eca5a0b-f2bf-4d70-951e-404d3996adbd | checkpoint | Confirm all fittings and Fixtures are the correct colour/ Finish.
4cdf4042-87d0-576d-ada9-5817dfd5b22c | tickbox | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
ff2ea0cc-e264-4242-a59a-b25d699fc8e4 | section | Sign-off
fd646ac6-dbc5-4836-8fea-56180f2158d1 | checkpoint | Subcontractor Signoff
45dd68cd-0c70-433c-8347-7b86ea54e951 | signoff | Subcontractor Sign-off
a210f335-9ce2-4431-bafb-004b8828aaac | checkpoint | SDC Signoff
7bb4578f-1506-485d-8fbb-bedcf462ddef | signoff | SDC Sign-off
0b201768-9013-5d87-a4fd-5a69e04455ae | checklist | Framing/Sheeting |  | Framing/Sheeting
1530de07-be34-5ea4-9be0-034b905e4913 | section | Survey/Wall Framing
23e408dd-5135-5585-8838-3938629743f7 | checkpoint | Confirm set-out of walls in correct locations & cross check with surveyors grids.
bf593cf7-e545-5d09-9b0b-ec0e6373d66f | textbox | Confirm wall set-out plan/revision used for set-out
a16d87db-338a-538f-a086-c2dff04f4e24 | checkpoint | Confirm that 1m benchmark has been reviewed and agreed. Ensure it is marked on most relevant permanent structure.
172e069e-c65b-54dc-b5a7-1c15435da685 | note | Attach photo of 1m benchmark for reference.
9d89ff1b-c508-5ac3-bd00-4946b21dcaac | checkpoint | Review wall types are installed correctly per architectural wall type details.
b3289e54-f7f4-5040-ae16-579651fe5a19 | checkpoint | Review wet area framing to ensure square and plumb to take tiling.
2475c618-869c-5955-91b7-ed342460614d | checkpoint | Strengthening Requirements - Confirm all noggins, trimming blocks and struts have been appropriately installed to support the following items (Min. 12mm structural plywood). Ensure to cross check relevant drawings:
2c5a047b-960f-5c5f-aa3a-0cb88c8cc8cb | note | Appliances (Wall mounted dryers, etc…)
c1b1f60c-6dc9-5f9a-8745-995ef2938d45 | note | Bathroom Accessories (Robe hooks, towel rails, shower shelves, toilet roll holders, adaptable handrails, etc…)
925b3429-826e-5c1e-b9d5-42f3bd35a048 | note | Bathroom Furniture (Mirror Cabinets, Vanity Basins, shower roses, etc…)
3d0db52b-01eb-5cce-8cbf-3a3679aa89de | note | Services (pendant lighting, display screens, TV areas, etc…)
adce8afe-bf59-540f-a059-012355501f0e | checkpoint | Adaptable Apartments - Check blocking installed to cater for post adaptation layouts
1f6ff53a-205c-5f4d-9e46-ea4d22ee9c5f | checkpoint | Confirm that all framing is square at corners (check top, middle & bottom of frame junctions)
08416204-8429-568e-afd7-c9fa6e7deb30 | checkpoint | Confirm studs not bridging or touching hydraulic pipes, mechanical units, columns in intertenancy walls or lift shaft walls to ensure vibration is not transferred through walls
f50e86d9-dd83-5f11-aa50-b871c9ce3f96 | checkpoint | Deflection Requirements - Ensure gap is present (10-15mm) at top of stud inside head track
7dc97a50-13d3-5d72-a8a4-3e023ea7fc7a | checkpoint | Joinery Openings - check gaps between framing to joinery + wall finishes will fit (5mm tolerance)
a9f86b22-e357-52ed-8b42-f7e8c3cec071 | checkpoint | Stud Spacing - Spot check studwork is spaced at 600mm maximum per Architectural Specification. Check additional studwork reinforcement at openings (ie; double studwork).
39866e90-f81a-57a8-a328-13140080c264 | note | Staggered Studs (if required) - to be installed at 300mm centres alternating per architectural specification
800c99ae-fb54-518e-8b80-7904c5f20f9d | checkpoint | Movement Joints - check walls are discontinued where they pass over building movement joints.
0fb9cac1-74f6-5835-97fe-e2f3275bfea0 | checkpoint | Services Risers - Ensure stud and trackwork is kept a minimum of 20mm away from vertical services within risers per acoustic specification
7b5c79f8-64ee-516a-84e0-855baefc7c2d | checkpoint | Engineered Designs - Spot check any engineered framing designs and attached engineers review and sign-off on system.
62a0e57d-2239-53a4-ac18-f77d094f5587 | section | Wall Sheeting
120a946f-ec6f-599e-bb9b-b8960ce99ed1 | checkpoint | Confirm acoustic/thermal insulation installed to achieve design ratings
9214adb6-d2ff-5660-8c6b-148031b3d64c | note | Cross check product ratings against architectural insulation plans
89c41d83-a979-5103-9f52-baa51290c96e | checkpoint | Confirm there is a minimum of 45mm cavity (or 20mm where double sheeted with recessed skirting shown both sides of wall) between the residential intertenancy wall studwork per Acoustic Details/Wall type Plans
4dd07011-91a4-5458-83e3-bb6a7828e05b | checkpoint | Confirm door frames are installed vertical and plumb and at correct height.
6dd1553e-b07f-5f38-8ad6-7ad960f7ad18 | note | Check metal door frames in wet areas are outside of membrane zone (ie; notched accordingly).
fdf1f2cb-3f25-5dac-8ad1-e2d57b621fdf | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting walls
cf6a3ad0-9bac-535e-bb27-643a2e2def4c | signoff | Review & Sign-off by Acoustic Consultant
3406cd78-db00-5dcb-bfaa-92bc3b90dba2 | checkpoint | Check plasterboard sheets installed with 10-15mm gap at top and bottom to allow for deflection and fire sealant.
f70875dd-ec8f-5405-a8b4-37e1f96d5b9a | checkpoint | Control Joints - Ensure controls joints installed in wall runs larger than 12m in length.
ac438481-ab6e-51d7-9fcb-8324a93b993c | checkpoint | Check correct plasterboard linings installed (type and thickness) per architectural wall types
3ffd3315-cf0c-5aa2-a990-9022ef15a0b5 | checkpoint | Ensure sheets are staggered on multiple sheet layer walls. Stagger all sheet joints by minimum 200mm per architectural specification.
1fcf115e-b487-5f8b-8f9d-3eb3e9c1ee8a | checkpoint | Confirm plasterboard lining installed to wet areas are sealed up to concrete soffit on both sides of wall where adjacent to habitable rooms.
9736503d-c21f-51e6-96ba-c5b04f89b1fc | checkpoint | Confirm all services penetrations through wet area walls adjacent to habitable rooms are sealed and caulked for acoustic performance.
2e46ccf7-7f4f-5172-a94e-48007bf168d3 | note | Check that mechanical flex ducts are not passing through walls - to be rigid ductwork or sleave installed over.
1eaaba03-6b1a-5154-a302-05cc6d20387e | checkpoint | Check intertenancy walls extend to façade panels, leave 10-15mm gap and caulked with fire sealant.
94b691b9-1b0d-4444-897c-1b43735b54b4 | checkpoint | Check that Durasteel Fire Board and Rockwool insulation is installed around perimeter at soffit at façade bracket locations as per agreed fire engineering detail (ie; 500mm long board with 2x fixings and 120mm of rockwool either side of the bracket).
ee010fbd-1046-56c5-b493-1d37862a0f5a | section | Sheeting Ceilings
1f688c69-de7d-5db6-9592-47ca2fce1731 | checkpoint | Confirm ceiling insulation complete where applicable
94e08ce9-c2d6-58ed-a243-14d3407f27c2 | checkpoint | Confirm provisions made in ceiling framing for access panels and air grilles were required by architectural RCP
7fdffaac-406b-5801-bef2-6361fc7b31f7 | note | Spot check access panels installed to allow access to fire dampers and mechanical fans
036d84fe-11bd-5ad9-ab55-b8fa4ef58f5a | checkpoint | Confirm ceiling framing bulkheads are square and level
4e88e007-6712-548b-af61-90634071bf08 | checkpoint | Confirm furring channels do not clash with other services (eg; downlights, access panels, mechanical exhaust, sprinkler heads, etc…).
6d815a4b-f7ea-50d6-8d30-a42333b3b1fe | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
82729cd5-dd85-5ad5-8e66-822a52f5bab6 | signoff | Review & Sign-off by Acoustic Consultant
e217164f-af7e-5616-bd19-3343bb541cc7 | checkpoint | HOLD POINT - Confirm BCA consultant inspection of services penetrations through fire rated walls prior to sheeting ceilings
894062ba-2286-5c42-97a3-5edb7e8965e2 | signoff | Review & Sign-off by BCA consultant
f2dee40a-a9fb-576d-a20a-9675ba9b5e42 | checkpoint | Confirm Plasterboard fixings are at correct intervals
47cc8396-5364-55eb-8c95-5ebafa007f1a | note | For painted surfaces, screw fixing onto sheeted frames should be max 400mm spacing. Refer to Manufacturer’s Installation guide
53c9c7bc-564d-5ce9-8daa-a26dc6b32637 | checkpoint | Confirm Villaboard/FC (wet area) fixings are of the correct intervals
be026fdc-1154-5e26-8d0d-16328c8b72b7 | note | For 9mm Villaboard/FC: Tiled wall screw fixings must be max 150mm spacing. Stud centres to be 400mm. Refer to Manufacturer’s Installation guide
49327a45-bf8d-5b9f-bcb8-d2eef0571ecf | checkpoint | Control Joints - Ensure ceiling bays are not larger than 12m without a joint or wall break.
1f79f360-0ac1-56e2-8b33-690dce63e2a6 | checkpoint | Attach Subcontractor ITP for the Works
c76b51ab-6264-5b4b-ab7d-fd597107fe72 | checkpoint | HOLD POINT - OK to proceed to painting
b4d64f56-0ea4-5b50-a1c8-90071a066939 | note | All defects completed?
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
9e8734e8-4a92-4091-b5a4-baa1562c86e0 | checklist | Joinery & Stone - ITP | itp | Joinery & Stone
10882068-b6eb-4a68-96dc-b83771b26efa | section | Kitchen Butler’s Pantry
7c333d19-f22b-4cc1-9f0e-873af1d792b2 | checkpoint | Shop Drawing (overarching)
f34d7490-0ba4-5b13-a0a8-607396ed6533 | note | Attach latest revision of approved shop drawings
28b385cb-8ac4-4b01-9599-5674f8b17351 | checkpoint | Colour scheme
4d1bc511-bab6-5b8a-b01e-c95b282aee94 | button | Correct colour scheme installed | Yes,No
02891d8a-ef8a-4ef7-ad9e-573821a1c7a3 | checkpoint | Visual finish check
d79dbb85-90fe-5310-96eb-7e3ad15283a6 | button | Free of damages, chips, or defects to veneers & panels | Yes,No
fa804913-c354-5121-abf2-327ad8a87313 | button | Even spacing observed in shadowlines | Yes,No,N/A
38a77ba8-a70d-52fb-a316-ae0091152b8c | button | LED/reed switch installed in nominated locations on shop drawings | Yes,No,N/A
383b16f7-e2d9-594b-9e47-ec1508abbf7b | note | Ensure correct anxiliary fittings are installed
c2fe7843-ae29-5a3f-9bbb-dd8f01e6b010 | tickbox | Cutlery drawer
01707ede-c83c-58af-a287-13deca8c6ac9 | tickbox | Bins
fc9a25f6-33d4-554b-9e16-735c4d9988da | button | Correct spec of handles are installed | Yes,No,N/A
d851c1a5-05e9-4c0d-b05c-a8c4b7e49be1 | checkpoint | Doors/drawers/compartments
defe3409-91ac-5b9b-bb1d-25e514241f61 | button | Arrangement as per approved shop drawing | Yes,No
233395f6-1e90-587b-bc4e-7d3f67db7834 | button | Dimensions of doors/drawers/compartments as per shop drawings | Yes,No
126b0373-58df-5d88-b747-451c23e2521f | button | Internal colour as per approved shop drawing | Yes,No
c4e0ace5-744c-5922-abdf-c8731fe5e9eb | button | Correctly aligned and square | Yes,No
dd734585-3467-5c1a-ab08-464bd0c93a30 | note | Note: Tolerances from Architectural Spec
d7911419-8bbb-5c0d-ae39-4745a347fffa | note | — Plumb and level 1:800
3acfbb3e-44ee-548c-acdf-24152c9ec24e | note | — Offsets in flush adjoining surfaces 0.5mm
dc0d3863-8c96-5837-9b78-7db4625cd1e9 | note | — Alignment of adjoining doors 0.5mm
01493049-fe7f-5a36-82f0-6e4858cd8cd7 | note | — Difference in scribe thickness for joinery items centred between walls 2mm
2738c298-a289-5ded-af88-9a362d307fda | note | — Doors centred in openings 0
334c4e8e-947d-5002-9571-764876bc72b8 | note | — Joints in finished surfaces 0
ff606243-f08a-581b-9bf0-7c2c2501978e | button | Doors/drawer hardware operating smoothly as intended | Yes,No
d9278297-2d0f-569b-a57a-dc14d0bb0efa | button | Check required access panels are incorporated | Yes,No,N/A
94e19fa1-d6cb-47dd-824f-6f87d5a69052 | checkpoint | Appliance
5fcf22b3-6ef2-555f-9c2b-39f873f1c34c | note | Correct appliance models installed as per room data sheet
85c22082-6e97-5471-82f6-133fdb624817 | tickbox | Fridge
f7231009-edf6-5e36-84a8-4617615b19eb | tickbox | Cooktop
14d61582-aa86-5a89-90cb-211c7fdbcf8b | tickbox | Microwave
fc8f0473-fd98-56ac-9bb4-69355920b3ca | tickbox | Wine fridge
dcbba3c2-ba9d-5864-94f0-401f40bdf6e4 | tickbox | Dish washer
e26e1260-2c43-58cb-8733-48429816c563 | tickbox | Rangehood
f3be05d4-691d-51dc-b902-477cd790e7a4 | tickbox | Oven
732009fb-5f9a-52a6-a11e-9e8c31d07c0a | button | Appliance fitting correctly in designated compartment | Yes,No
e83b0080-fcd6-5bdb-9c63-9f1d7eca950e | button | Appliance free of defects, chips & scratches | Yes,No
cc9f65aa-682c-441b-ae6c-c406473b2514 | checkpoint | Stone benchtop & splashback
dcb71581-6cdc-574e-bd8f-fee016f37663 | button | Correct stone type installed | Yes,No
a5d42671-bd8d-5c0d-8dc6-b659bf9b69e1 | button | Stone level/square | Yes,No
dc6ae56a-ca6c-5f9f-9e4d-2acbbec9d43e | button | Joints neatly caulked | Yes,No
e4e98075-bb46-5fea-8218-c910d8fbddec | button | Check exposed edges of all porcelin stone is polished | Yes,No
a3366ad4-e046-5f2a-a186-6db8f2fd843c | button | No cracks and chips | Yes,No
80286419-cf02-5ce9-a804-8612eeb9b1c7 | button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
986cf957-bec1-448f-9c29-91bdbcbc6c78 | checkpoint | Island bench stone
be811a99-e653-582e-b482-ec28775669b2 | button | Correct stone type installed | Yes,No,N/A
0aca2fe2-6348-55c4-b1ae-dd98bfb1dbcb | button | Stone level/square | Yes,No,N/A
f0bb52ba-2b53-5823-81e3-f48a76c832d0 | button | Joints neatly caulked | Yes,No,N/A
655d463a-3564-5d93-ac49-8d93b3e32e0e | button | GPO cutout completed with even gap all around | Yes,No,N/A
8bb24d3f-7be0-59d0-a856-0b285442cec9 | button | Shadowline detail completed with even gaps all around | Yes,No,N/A
8b2757ab-d3b5-54b9-ace0-bb4419d2965a | button | Sink & setdown dimensions as per approved shop drawings | Yes,No,N/A
734b7f95-24ab-58b8-8be2-c8e6a5eac010 | button | No cracks and chips | Yes,No,N/A
913219d6-225b-5477-83bd-238643c60fd7 | button | Check top edge of joinery panels aligns with stone rebate | Yes,No,N/A
9e247373-5fc8-5fa9-a746-df0a2813c636 | button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
20b83f95-11b9-520c-8e95-7827cb84b6ed | button | For benches over 3m, check the joint is in the correct location as per approved shop drawings | Yes,No,N/A
847e5a60-8741-4ca3-a05f-818644302839 | checkpoint | PVR
b40bf68f-60de-541b-bf33-6582b71381f6 | button | Purchaser request implemented | Yes,No,N/A
bbc64396-9797-47a3-a7e1-f6a66b906508 | checkpoint | Photos
2e015c33-a3ab-5af8-9ee4-daac5ab3d879 | note | Attach photos of completed joinery/stone at time of inspection
b77fb326-e076-4d8e-abfe-830c86ad3738 | section | Wardrobe
2da53386-1687-4c4c-bf4e-9697eb8ba287 | checkpoint | Colour scheme
c53828b5-9289-5909-b52e-55451792563e | button | Correct colour scheme installed | Yes,No
be91c943-c855-4f6e-af0d-71b447e86e6b | checkpoint | Visual finish check
45263ac3-bec2-5987-9ccd-a5e4177679d0 | button | Free of damages, chips, or defects to veneers & panels | Yes,No
39f9694d-0087-570b-acfb-a9560e611f69 | button | Even spacing observed in shadowlines | Yes,No,N/A
b9afc519-ff4b-5954-b9f3-20fa7c21bb5a | button | LED/reed switch installed in nominated locations | Yes,No,N/A
e4409022-fe21-596c-951a-5702183b6c9d | button | Glass shelves free of scratches/defects | Yes,No,N/A
438e94a9-cdeb-5177-a153-61e031f9fe57 | button | Correct felt is installed in jewelery module | Yes,No,N/A
f5fe48cf-4877-50a9-ae46-5b348120fc82 | button | Correct spec of handles are installed | Yes,No,N/A
89a41e16-9668-48e7-adb1-33c64474b8b0 | checkpoint | Doors/drawers/compartments
b1603bd3-6146-525e-87d5-de64821635f9 | button | Arrangment as per approved shop drawing | Yes,No
795914ca-9304-5fa2-a443-d8c95b4092eb | button | Internal colour as per approved shop drawing | Yes,No
021b194e-24cc-5969-ad3d-8139d182d152 | button | Correctly aligned and square | Yes,No
9992dcd6-8368-50b0-b4f6-656bdc1d6bb8 | note | Note: Tolerances from Architectural Spec
550c8db4-eaf2-5bdd-954f-950220f5559c | note | — Plumb and level 1:800
6d72c558-5d1a-5506-ae03-ef7794495fdd | note | — Offsets in flush adjoining surfaces 0.5mm
63d647c9-f72b-5275-82b6-c0e454fe4185 | note | — Alignment of adjoining doors 0.5mm
2afcb762-05c6-5b00-941c-999a183dfc6e | note | — Difference in scribe thickness for joinery items centred between walls 2mm
aeaeb792-83ee-5119-b4ae-34c4aee66559 | note | — Doors centred in openings 0
524a88f2-fd92-5b5b-90bd-9a91432d2a8f | note | — Joints in finished surfaces 0
427f007f-2577-5a26-8989-f83c66ab1fed | button | Doors/drawer hardware operating smoothly as intended | Yes,No
26ceaa41-90dc-5a19-9870-793724b337bd | button | Hanging rails securely installed with correct spacing | Yes,No
56a612ad-1572-5c25-a510-a1f3004c7b82 | button | Check access panels are installed in correct location | Yes,No
42469146-f9ec-4d60-8e0b-6e4ceb3112d9 | checkpoint | PVR
c5e223cd-7120-59df-a366-f5bc75e8858f | button | Purchaser request implemented | Yes,No,N/A
5b9aaa9a-9fed-4111-b4a7-38ad4ae22240 | checkpoint | Photos
064b58cd-672b-51c7-b191-fcd79deecec7 | note | Attach photos of completed joinery at time of inspection
ce161a2a-ac76-4bc9-8d95-0faf2d8fbff0 | section | Storage
15c660ea-752d-47a9-8db9-cf4f641dae88 | checkpoint | Colour scheme
9aca7d13-aeab-53d8-aa73-07ce0a4cf091 | button | Correct colour scheme installed | Yes,No
1f73b24d-bdce-406f-8111-d8e1911d86ed | checkpoint | Visual finish check
aa493cf2-112c-5f09-ab5c-4f3e4615ebc4 | button | Free of damages, chips, or defects to veneers & panels | Yes,No
c1f9a506-42e0-5598-9cc0-0fc2d72ac49b | button | Even spacing observed in shadowlines | Yes,No,N/A
d585eb88-ba7a-54ab-81be-b134f4476fd7 | button | LED/reed switch installed in nominated locations | Yes,No,N/A
d758d36a-9fad-568d-82a6-5d2dabe35f6e | button | Correct spec of handles are installed | Yes,No,N/A
d433bcc2-7e46-4baa-87b1-37d9b0f96afe | checkpoint | Doors/drawers/compartments
a02cc5ab-8698-58c2-a292-6bcefc664141 | button | Arrangment as per approved shop drawing | Yes,No
b8febc58-b534-5d79-9c95-e3306cd4fd47 | button | Internal colour as per approved shop drawing | Yes,No
be90fa64-6e9f-5fd8-8bf0-9b9d6d764838 | button | Correctly aligned and square | Yes,No
ebc1b3e8-42c4-50ef-9312-a661eb40abd7 | note | Note: Tolerances from Architectural Spec
54cc5662-6217-5d9d-8145-2de2c7de414d | note | — Plumb and level 1:800
9297d1e5-5a3b-57c0-89b4-43d2b8d9a69f | note | — Offsets in flush adjoining surfaces 0.5mm
e9e61443-2609-546b-801b-edca7c085ae1 | note | — Alignment of adjoining doors 0.5mm
b667290a-2ad1-552b-b78f-246bcc54b86a | note | — Difference in scribe thickness for joinery items centred between walls 2mm
2e685ff6-56d9-554c-bdb9-37cbc8147f99 | note | — Doors centred in openings 0
4bb08797-8065-5cbe-bdf3-40942d26025b | note | — Joints in finished surfaces 0
1e8b2849-252b-5240-a098-4a242b6a21e1 | button | Doors/drawer hardware operating smoothly as intended | Yes,No
b60ace29-4c7a-5ce1-8534-222ebc137e76 | button | Vent grille neatly installed | Yes,No
b36ba896-b15c-4cfd-9520-6106a8eaacc6 | checkpoint | PVR
fd5e41bb-d9a3-5cfd-9037-09fc044e7b59 | button | Purchaser request implemented | Yes,No,N/A
c9af107a-bcda-42b8-af53-975a39b39b73 | checkpoint | Photos
57c83dba-c160-56ca-92b1-2e5ab4121743 | note | Attach photos of completed joinery at time of inspection
ebddcf99-8cc2-43cb-a0b2-842f800d0025 | section | Bathroom
af903dce-6207-42e3-ad56-540ebddd86b7 | checkpoint | Colour scheme
85a85c8e-d7b7-5787-9e00-a0f9f213baef | button | Correct colour scheme installed | Yes,No
258b166f-9366-45b2-b1c5-91902a112979 | checkpoint | Visual finish check
fe074b84-f32c-54c5-ac54-cc3e92cab487 | button | Free of damages, chips, or defects to veneers/panels/mirror | Yes,No
7dccf066-9693-5ae3-ab2e-9d218fabec65 | button | Even spacing observed in shadowlines | Yes,No,N/A
8c2adb51-0ff9-5577-8075-513cc3f130e2 | button | No distortion in mirror | Yes,No,N/A
21a86dca-0ef7-5acc-a500-22c5868b4378 | button | Check GPO/thermostat is installed in the correct location | Yes,No,N/A
4159a6ea-2b39-47f5-86da-1164fce191c4 | checkpoint | Doors/drawers/compartments
1a848c49-a51b-5519-88b3-c16d90a962f5 | button | Arrangment as per approved shop drawing | Yes,No
f9a0dae4-b6be-5ab9-89a3-2a2ebcc76495 | button | Internal colour as per approved shop drawing | Yes,No
8af2200a-67ae-550e-ae86-2037c80c8fb0 | button | Correctly aligned and square | Yes,No
adb100cc-b660-5c27-b33e-73dfc6820a5d | note | Note: Tolerances from Architectural Spec
200df294-5f5f-53eb-9c0d-9f3b6440271d | note | — Plumb and level 1:800
dea229ba-7967-59f0-a177-065a9754522c | note | — Offsets in flush adjoining surfaces 0.5mm
b258cbaa-afa5-5d11-aab4-851cb25af158 | note | — Alignment of adjoining doors 0.5mm
6a269c51-5cd4-5eaa-8c61-d9e5add105be | note | — Difference in scribe thickness for joinery items centred between walls 2mm
b3e1430f-0f7f-546c-925f-16c8d4c03eb2 | note | — Doors centred in openings 0
d50152f6-12e1-5fc1-b539-d49e4f28373a | note | — Joints in finished surfaces 0
7908c528-b8b8-5508-a612-166e1a4c6280 | button | Doors/drawer hardware operating smoothly as intended | Yes,No
907bc94b-2110-49e3-a569-f887ad9ba1d4 | checkpoint | Stone Vanity Top
919e172d-0266-5e94-a23f-d67923eca6a5 | button | Correct stone type installed | Yes,No
965df843-b02b-5383-bf1e-bcef259eedd4 | button | Stone level/square | Yes,No
35003b1f-d219-51f6-93fa-8347624427e3 | button | Joints neatly caulked | Yes,No
fdbc914d-f76b-57bc-ac06-350f52d469db | button | No cracks and chips | Yes,No
76c3b0d6-8788-45a7-8036-606b267e6a24 | checkpoint | PVR
838b3395-ca81-54aa-9828-07260673a32c | button | Purchaser request implemented | Yes,No,N/A
a3d94e16-4890-493f-bb69-3efeccf5e512 | checkpoint | Photos
e9e9684d-86dc-5dcf-b57e-c5b05f76cbc4 | note | Attach photos of completed joinery at time of inspection
cb76a883-de0d-4197-9f50-d0da9874dde1 | section | Laundry
6d105542-d192-4602-8cd8-a82d7508666e | checkpoint | Colour scheme
62b3f443-3caa-51a4-843c-c103cbe34358 | button | Correct colour scheme installed | Yes,No
41d7aada-e3fa-4f0e-94c0-89d0689909f4 | checkpoint | Visual finish check
b494bb83-234b-5ce2-9252-bdcc3a8ad8fc | button | Free of damages, chips, or defects to veneers & panels | Yes,No
476ab5ab-f353-5b46-ac3c-158ff82958de | button | Even spacing observed in shadowlines | Yes,No,N/A
b4d818a2-0c26-48fa-92d0-1a2512076289 | checkpoint | Doors/drawers/compartments
0fff9288-1ef5-5247-9fee-3fa3f8832c66 | button | Arrangement as per approved shop drawing | Yes,No
93e6041a-6779-56fe-863f-0b40fdff5b69 | button | Internal colour as per approved shop drawing | Yes,No
511f5151-8db5-570b-b4ce-ab9672dc8e3a | button | Correctly aligned and square | Yes,No
db3366ee-1e59-58ad-bae1-086500b54f37 | note | Note: Tolerances from Architectural Spec
51e15bfe-354a-5ab7-9d03-075b0048bcd7 | note | — Plumb and level 1:800
ff541c5c-0022-5795-a962-e86d4d0fea57 | note | — Offsets in flush adjoining surfaces 0.5mm
887d1551-c6d2-5234-818f-4be1fd955ade | note | — Alignment of adjoining doors 0.5mm
668920c1-7c06-53d9-b86d-51a899e0f53b | note | — Difference in scribe thickness for joinery items centred between walls 2mm
ebeeea1c-a709-583b-b66b-dc4ca9977e82 | note | — Doors centred in openings 0
46e201c3-2554-5e4d-9fce-b81f0e5d95f4 | note | — Joints in finished surfaces 0
f63469e0-0d12-5215-9ca1-0d792cf04c1e | button | Doors/drawer hardware operating smoothly as intended | Yes,No
190d7b68-e114-5ab1-92fd-15cab745c29c | button | Check 20mm undercut under the door | Yes,No,N/A
f459e345-8eb3-43f8-9c63-db5d0b815de5 | checkpoint | Appliance
44719134-15cf-51f5-844a-04012b499509 | note | Correct washer/dryer model installed
cf4d7db6-ea3c-508f-b7e6-64661ac1e10f | tickbox | Washer
f431ecfc-3c71-5b26-a26d-d9b9180f1f46 | tickbox | Dryer
0ed3aa2a-e057-4a56-af80-ba1b38c713c3 | checkpoint | Stone benchtop
70046006-365f-5b01-a25d-10dc0d089909 | button | Correct stone type installed | Yes,No
f040ec3a-1718-50d1-900c-595bbc55e757 | button | Stone level/square | Yes,No
fded73af-5427-5a8a-844a-868da9060bec | button | Joints neatly caulked | Yes,No
03249bd0-8f80-51e5-87a9-eaeea11e14d7 | button | Check exposed edges of all porcelin stone is polished | Yes,No
2dbe1338-079d-5f92-bfac-1ee1ef839d30 | button | No cracks and chips | Yes,No
f28b4f38-5ec5-585b-91fa-e5af341ab8fa | button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
b2a3cf29-b084-479e-9c29-832b986e1187 | checkpoint | PVR
a34d59dc-11b3-56c5-804d-cd468dd7bc9e | button | Purchaser request implemented | Yes,No,N/A
ca54bccf-cc51-45de-94d5-5189b79fd663 | checkpoint | Photos
e9e533a8-eff0-5609-9269-1febc9b5aca8 | note | Attach photos of completed joinery at time of inspection
e6e38f3a-7cca-4125-ac07-d81fd57813a4 | section | PVR Joinery Items
05739b72-0c68-41d8-b1d3-3109df91fec6 | checkpoint | PVR Joinery Items
dd8623a9-e500-56e2-b542-0fce4e7fac5b | button | Additional PVR joinery elements within this apartment? | Yes,No
70aa184a-c493-5c92-930b-0e06ed691449 | textbox | If Y, expand to selection below:
a0fed7d2-a391-4cf1-94c5-e8862c47a1f4 | checkpoint | Shop Drawing (overarching)
b8c6a2fc-dd71-5d69-89ae-5fe0b977437c | note | Attach latest revision of approved shop drawings
c4d2837b-7fe3-44fa-96a6-c48925dd1d83 | checkpoint | Colour scheme
3148e4df-417e-5589-9042-ab85889fccb7 | button | Correct colour scheme installed | Yes,No
13e5c8db-d800-4fdc-887f-f56289b78d08 | checkpoint | Visual finish check
978faec7-c234-56f1-ad6a-6a2547ec7056 | button | Free of damages, chips, or defects to veneers & panels | Yes,No
20c62033-edc3-538f-bb79-d356672e2b4f | button | Even spacing observed in shadowlines | Yes,No,N/A
8716b8ee-4646-51a2-8a2a-56eb044b618b | button | LED/reed switch installed in nominated locations on shop drawings | Yes,No,N/A
8cf014d0-b85f-5c9a-8197-50537322b99d | button | Ensure correct anxiliary fittings are installed | Yes,No,N/A
c20f980d-0c59-404d-a774-5b251a717999 | checkpoint | Doors/drawers/compartments
243b2e6e-a2de-53af-b401-ec552a2beddc | button | Arrangement as per approved shop drawing | Yes,No
f4f24b13-2cef-5c16-8bc9-9ce748f5daad | button | Dimensions of doors/drawers/compartments as per shop drawings | Yes,No
9244c14f-e8b2-5634-824d-a4fb40b48e2c | button | Internal colour as per approved shop drawing | Yes,No
e15c1cdf-882c-57c7-bff3-8790765448f6 | button | Correctly aligned and square | Yes,No
fee780d7-3d8c-5fa7-a75f-4a5f3240a787 | note | Note: Tolerances from Architectural Spec
aa1e743e-c680-5c0e-9b8f-91d491cd0237 | note | — Plumb and level 1:800
198486ca-3fe7-575f-bb7d-551613f46897 | note | — Offsets in flush adjoining surfaces 0.5mm
cf114990-62d4-503e-9ea5-6ac8408c2a66 | note | — Alignment of adjoining doors 0.5mm
f965a236-dbfa-5a85-9a92-03b4cee5524f | note | — Difference in scribe thickness for joinery items centred between walls 2mm
37902c21-2b5e-5955-98fc-8e08a519126a | note | — Doors centred in openings 0
924d05a1-4dd5-5c99-83f2-ab14f03ea568 | note | — Joints in finished surfaces 0
870e6fa6-726a-5e01-8a20-15250c812673 | button | Doors/drawer hardware operating smoothly as intended | Yes,No,N/A
cbaeec3d-53ae-51b5-a55a-16365ec8e2a0 | button | Check required access panels are incorporated | Yes,No,N/A
91fb4c27-cbf2-4f85-814e-aa1d93403f50 | checkpoint | Appliance
b3d012e0-f575-50da-8a40-6f249965092b | button | Correct appliance models installed as per room data sheet | Yes,No,N/A
e609b123-68e7-5299-a63d-0675107a6c8b | button | Appliance fitting correctly in designated compartment | Yes,No,N/A
fede0437-416a-5801-bacb-ee0bb984f206 | button | Appliance free of defects, chips & scratches | Yes,No,N/A
5b1a5628-02a4-40f5-b07b-6f29e014e1f2 | checkpoint | Stone
5102941f-22f6-5713-907d-4703ff94b3bf | button | Stone elements part of PVR joinery? | Yes,No
c9bae4a4-9caf-5729-b0ba-9ff0485898b0 | textbox | If Y, expand selection below:
6d5eab5a-04dd-446f-a914-1b789237e5ec | checkpoint | Stone
ef92f352-a244-5d23-95c3-7e87024d4c32 | button | Correct stone type installed | Yes,No,N/A
8de4233c-8276-5fa5-b77c-9748d9ead22b | button | Stone level/square | Yes,No,N/A
8cf01d86-7474-5788-85c5-5cdd941587c3 | button | Joints neatly caulked | Yes,No,N/A
f513486e-e070-55ee-bc30-32a467081afd | button | Check exposed edges of all porcelin stone is polished | Yes,No,N/A
5e003957-fc80-5d86-80a9-a5c4ff5455b8 | button | No cracks and chips | Yes,No,N/A
0efec0b3-416a-58fb-b4ca-3af4956a846a | button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
ef8c127b-a34f-4ec9-8c6a-3a2114961f02 | checkpoint | Photos
650def58-0b3b-5f6c-8544-a36c131c26cb | note | Attach photos of completed joinery/stone at time of inspection
731c5a83-9e8c-56bc-8a93-11110847dcef | checklist | Level Compliance |  | Level Compliance
a41e79a4-7f72-5f55-8786-436198c5996a | section | Fire Rated Plasterboard Compliance
7c6e7729-f341-5150-9cf6-7f5a10583dba | checkpoint | Attach Manufacturer Inspection Report for the level
19c4b854-f4c7-533d-ad9e-d27db011ed47 | checkpoint | Confirm all outstanding items have been closed out
1dcf1d61-3fff-5e6b-9d6d-1ac14ad15322 | signoff | HOLD POINT - Attach Close-out Confirmation & Photos
36938e10-e0fc-5dc3-bb4d-2631c4ef88a1 | section | BCA Compliance
d8990e0a-d3a7-5776-b5ac-a53f996c067a | checkpoint | Attach BCA consultant fire compliance inspection report for the level
028143a9-05e6-4f56-8b42-828de2f1b2fd | checkpoint | Confirm all outstanding items have been closed out
7c21d0d2-f5ce-5b18-8292-98b478286372 | signoff | HOLD POINT - Attach Close-out Confirmation & Photos
f1cc1083-7799-5321-92f5-429a392ffd2f | section | Acoustic Compliance
47609e99-82df-5220-a259-29403d261744 | checkpoint | Attach Acoustic Consultant Inspection Report for the level
79702705-5f84-4627-9b0e-4aebb1ce426c | checkpoint | Confirm all outstanding items have been closed out
4e032bbd-0dfd-5979-bb50-a7b9c9df9f95 | signoff | HOLD POINT - Attach Close-out Confirmation & Photos
68578234-762e-519f-bcca-532b1d0b8897/2 | checklist | SDC-TMP-CON-CHK-013 - B - Void-Riser Closures |  | SDC-TMP-CON-CHK-013 - B - Void-Riser Closures
674045f6-1811-58fe-b909-b838b50d6fb9 | section | Area Information
8111ace1-1386-5c1f-8290-3df28e3c8d3f | checkpoint | Details
0a851e7e-9fdc-54c0-9d78-75a3866dfd6d | textbox | Location of works
8e64d65d-5cf5-5996-89f3-35729946d8bc | textbox | Floor/Level
bff878db-f23f-5638-8dae-2729d422ddec | textbox | Apartment/Area Reference
53dfffaa-c1b2-5070-99f6-9d8e42b3fdae | section | PRE-CLOSURE
5eda8520-35b8-5b64-bcfb-e05834aab6c0 | checkpoint | Electrical
ed3ca5bd-ca61-538e-be9c-a80ace300a77 | note | ACTIVITY: Electrical services
bb0c17f0-d6a4-582d-accc-334baa7f7dd5 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
ca261955-6124-5a29-9307-680aa333ac8f | signoff | Subcontractor/Consultant Signoff
4626e0e9-f132-5211-8a3b-572771fd2c23 | checkpoint | Mechanical
7e3d5c21-721c-5f10-93d9-dd56dfd04598 | note | ACTIVITY: Mechanical services
b3e4112c-9522-527a-8312-43aeec0d7484 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
63c06ab2-385a-5295-833e-d1cc808390bf | signoff | Subcontractor/Consultant Signoff
8cde4215-2128-5176-88bf-1b9292e62799 | checkpoint | Plumbing
6ff207e2-9ad8-5526-8abf-90b30fcf37f0 | note | ACTIVITY: Plumbing services
045af96b-848d-5bab-978c-0113707bb246 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
1114a46a-5773-5910-b2ac-ab04f9c5c75f | signoff | Subcontractor/Consultant Signoff
6fcc9299-d65a-579a-a73a-5cd4b959f824 | checkpoint | Fire Dampers
18e56a68-aee2-53d9-a697-32c104067a95 | note | ACTIVITY: Fire dampers installed
be09255d-6f5d-58f3-a218-a2cea0d666fb | note | REQUIREMENT: Fire dampers have been installed in accordance with Australian Standards, drawings and specification
021d7010-f484-5f0e-88fa-b23d9464758f | signoff | Subcontractor/Consultant Signoff
ef955797-bb0d-581e-ad8f-cdcccec5167f | checkpoint | Fire Services
0c745462-c39c-54b7-abb5-33fb98f49c2c | note | ACTIVITY: Fire services
5d1e275a-ff8c-583b-845e-d1cf8d6592e8 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
6bd8de6a-ef2c-5d36-bcb3-274d42be31d4 | signoff | Subcontractor/Consultant Signoff
74ec88cb-324f-562b-8366-92adfb76bc5a | checkpoint | Plasterboard Trade
2def0b4e-2bec-515d-98c9-13173f4d9f86 | note | ACTIVITY: Framing/Sheeting Works
35347ca0-8b1f-5ab4-9415-7cf9029382e6 | note | REQUIREMENT: Plasterboard construction and sealing has been completed in accordance with the drawings and manufactures guidelines
90a26ca7-975f-5f6d-8640-4ffd09a22101 | signoff | Subcontractor/Consultant Signoff
a0698adb-adac-5ae4-8135-6a0b50fb8bf7 | checkpoint | Passive Fire
e64d72fb-ddd5-54a6-9613-704512de951c | note | ACTIVITY: Fire Spray/Passive Fire Protection - Take Photos for Record"
fb8c9aa0-1238-5dda-a666-911a2c1b88a2 | note | REQUIREMENT: Has been completed in accordance with the drawings and specifications to services & structural elements
893c336f-97f9-5b70-a5ac-37df76fa1c47 | signoff | Subcontractor/Consultant Signoff
fd26e2a4-96f8-5680-878b-9a0801bf78e5 | checkpoint | Structural
a2c00c59-cf34-5f19-806c-68c227ae2a64 | note | ACTIVITY: AECOM Engineer
cc68cd98-5c3e-5560-8096-c8dfdde71c0a | note | REQUIREMENT: New Structural elements have been inspected and signed off prior to closing void/riser
eb5406d9-514d-5f55-9f7f-8f3a06a9cb5f | signoff | Subcontractor/Consultant Signoff
bb881818-3c86-5830-bce8-defa8a1d3906 | checkpoint | SDC Builder
15c6061f-90b6-5485-b44c-135fe0e72143 | note | ACTIVITY: Pre-Closure Photos
89559dcb-7f86-598b-a980-04c685aaf080 | note | REQUIREMENT: Attach photos for record of walls and ceilings pre-sheeting.
23f868fa-85d2-5e62-a476-c053d0679cbb | signoff | Subcontractor/Consultant Signoff
6f9b39eb-4c79-44ad-98b9-a678cb37b884 | checkpoint | Window Actuators
2d9ac95a-263f-5ded-b53d-148095b7e839 | note | ACTIVITY: Window Actuator Wiring and Controller Sign-Off
4db9a88e-76cd-520f-92a3-f2b67a50fdaa | note | REQUIREMENT: Confirm that window actuator wiring is completed, and controllers have been tested and working prior to sheeting ceilings
10ee8ef6-ac3c-4f2e-9313-5a3d8e30cf45 | signoff | Subcontractor/Consultant Signoff
0641b5bd-4539-5e41-86c8-d846851f2be2 | section | POST-CLOSURE
7e86647e-3212-52e6-82b4-bc6467720616 | checkpoint | Acoustic
211af32d-80ed-510f-a856-6ee94198847a | note | ACTIVITY: Inspection
46e95309-96ad-57de-817e-5e7ed55650c7 | note | REQUIREMENT: Acoustic inspection carried out where required. Attach report.
e511fa89-ebbb-52a8-ba59-9855dd3ef121 | signoff | Subcontractor/Consultant Signoff
855621a4-2f21-5aef-a16f-6e7f0dee9f12 | checkpoint | BCA
be310d74-87d8-58cd-b53b-5ed627b5a624 | note | ACTIVITY: Inspection
b9f72734-ac01-5ef3-b049-e350f84491b2 | note | REQUIREMENT: BCA Compliance inspection carried out on construction and services penetrating where required. Attach report.
86c98323-cbad-5472-b985-dadb4ad96b9a | signoff | Subcontractor/Consultant Signoff
51cd79a8-35c2-557c-a9d3-b3abeb51ec76 | checkpoint | Scentre Group Consultants
b28506f4-68d2-5626-a5b1-b1dc1dc3af57 | note | ACTIVITY: Defects
bf893f0e-a776-5eb6-9773-cef955ac1b5d | note | REQUIREMENT: All defects identified during SDC and consultant inspections have been rectified
82bd51c3-ea41-5971-984a-2ad0b7160a09 | signoff | Subcontractor/Consultant Signoff
036eb850-7bf1-591d-aeba-77b443cf9716 | checkpoint | Final SDC Review & Sign-off:
56eae728-9f58-599a-9ef2-8e79a5ba9d92 | note | The Wall/Ceiling cannot be closed off until ALL sections above have signed off
fa35e456-d74b-5039-adb6-ba057493523d | textbox | Name:
4c7943a6-7231-507c-a580-0ba6fded9705 | date | Date:
1223a7af-ece6-5d8a-b4d8-512c3c67f999 | signoff | Signature:
0ead2e01-1da6-4196-a345-f4be489208ae | checklist | SDC-TMP-CON-CHK-013 - B - Wall/Ceiling Closure Checklist |  | SDC-TMP-CON-CHK-013 - B - Wall/Ceiling Closure Checklist
1eac476c-b321-45bc-9aee-3442fd328842 | section | Area Information
762e1f51-40d0-4ca7-8de8-2f87450d3f9a | checkpoint | Details
823026c1-ca16-5188-8f86-729ec3fc9db7 | textbox | Location of works
9b581f0a-1930-5c18-8239-64373b44d90a | textbox | Floor/Level
d9e3ef0a-7a9a-56de-9cce-0e0645619d49 | textbox | Apartment/Area Reference
7948ef07-0133-4828-a94f-0d39470eda88 | section | PRE-CLOSURE
5ba4e16d-58be-40a7-b3f8-83bd7ff8593b | checkpoint | Electrical
051948b6-389b-5a1f-bb80-a8d4b4af1d2c | note | ACTIVITY: Electrical services
4a412a90-314f-5626-b9f1-fbcb8e08d506 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
d7acc258-b382-4da5-9fc9-554eccc31bdc | signoff | Subcontractor/Consultant Signoff
8ae6743b-1115-49ef-a24a-3a01108f40a1 | checkpoint | Mechanical
ebe8f95e-6139-5bce-bdc0-4f0d19915165 | note | ACTIVITY: Mechanical services
d332cfbf-cc46-5c0f-9b73-3507bd80c673 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
f60b6b4f-c0dd-4a5b-ab47-0b1e66cd4e6a | signoff | Subcontractor/Consultant Signoff
974356e4-5280-4571-b02b-266286b994e1 | checkpoint | Plumbing
46b1db48-69e6-5b8e-a4eb-b625ba249aff | note | ACTIVITY: Plumbing services
a7087fc2-d428-5007-a804-b673843bf0d1 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
1630a608-e35c-483f-9b96-56e203fa3c68 | signoff | Subcontractor/Consultant Signoff
cb75f375-f66d-4216-938e-3cd6768de24c | checkpoint | Fire Dampers
f9cfd8c8-5e32-589e-98bf-6d1248bff2a0 | note | ACTIVITY: Fire dampers installed
ad9b8db7-4ef6-54f3-bf7d-4cf79b9ea32c | note | REQUIREMENT: Fire dampers have been installed in accordance with Australian Standards, drawings and specification
534cfb0e-ad5a-4e57-95cb-308846163bcd | signoff | Subcontractor/Consultant Signoff
c4defe7b-fd87-4739-b6f8-9999dc4d40e0 | checkpoint | Fire Services
b044fed9-9eac-5846-9f43-479daa9e5fbb | note | ACTIVITY: Fire services
8dcfd02a-c66e-5deb-8971-efb1a13551e2 | note | REQUIREMENT: Have been completed in accordance with the drawings and specifications
1bf24ac7-6e40-4b75-a031-e8da7363495b | signoff | Subcontractor/Consultant Signoff
8e997720-d324-4cac-be95-ad540724eeea | checkpoint | Plasterboard Trade
db62aa60-4906-5cf0-bafe-bb5c27b865c5 | note | ACTIVITY: Framing/Sheeting Works
3d1be7b5-922f-5c92-9ef3-fabdd641472a | note | REQUIREMENT: Plasterboard construction and sealing has been completed in accordance with the drawings and manufactures guidelines
15822eda-7612-4ae6-a19e-41a408f7a49e | signoff | Subcontractor/Consultant Signoff
fdecb69f-8336-4a02-8add-7803a4b16dc1 | checkpoint | Passive Fire
5e6ebf39-d0e1-5f7f-875f-d4a4026a0a49 | note | ACTIVITY: Fire Spray/Passive Fire Protection - Take Photos for Record"
73d2be0b-a13c-52aa-9147-1bfc8061fcdb | note | REQUIREMENT: Has been completed in accordance with the drawings and specifications to services & structural elements
a8440880-e099-40fa-a221-6171838ba2aa | signoff | Subcontractor/Consultant Signoff
52753582-822b-4712-9b77-2136f87c220d | checkpoint | Structural
e2ced4d7-527a-5d1b-b301-2519dc64d1c0 | note | ACTIVITY: AECOM Engineer
cded0481-de43-5076-bd7e-5bfae09f97d7 | note | REQUIREMENT: New Structural elements have been inspected and signed off prior to closing void/riser
e00b8992-1427-427d-9c7d-c739c558cea2 | signoff | Subcontractor/Consultant Signoff
f47936b8-230c-40ef-8933-e53e42b0626f | checkpoint | SDC Builder
dfab27f5-eb88-585e-baef-3f24bdd112a5 | note | ACTIVITY: Pre-Closure Photos
27e0a07e-66f2-515e-98ad-08b5597dce93 | note | REQUIREMENT: Attach photos for record of walls and ceilings pre-sheeting.
3ff3eedf-0ecd-4265-bcb9-66a03acf0663 | signoff | Subcontractor/Consultant Signoff
da323dc0-1ed9-4b04-864b-bd61f1200362 | checkpoint | Window Actuators
40be76e0-504f-5a27-a668-c2fcc63172f5 | note | ACTIVITY: Window Actuator Wiring and Controller Sign-Off
2a5138b8-d0d3-5977-abab-6217211138ca | note | REQUIREMENT: Confirm that window actuator wiring is completed, and controllers have been tested and working prior to sheeting ceilings
87e1c297-ce36-45d6-964f-c39328c52b5a | signoff | Subcontractor/Consultant Signoff
5c97ca53-12d3-4d97-9e67-b5503ab5f79d | section | POST-CLOSURE
11e59620-0ecf-4a76-aef8-5dd296d29a4d | checkpoint | Acoustic
42f5a6ab-ee47-54cd-a2c4-a0ae88405213 | note | ACTIVITY: Inspection
bb10fdc2-6906-5d64-a176-c394a1355c32 | note | REQUIREMENT: Acoustic inspection carried out where required. Attach report.
93d6130a-06f8-4f11-b519-840a2768c659 | signoff | Subcontractor/Consultant Signoff
258da80f-c884-4023-a099-71621dc8df53 | checkpoint | BCA
3d79e9af-642b-525c-a5a1-b817d2d01b97 | note | ACTIVITY: Inspection
1ca4e25f-c2f9-5d19-8701-fcf980d7f0a2 | note | REQUIREMENT: BCA Compliance inspection carried out on construction and services penetrating where required. Attach report.
67891caf-a10e-40fb-8768-0a85357f65fa | signoff | Subcontractor/Consultant Signoff
35a31cab-ac38-46b5-8e1c-07845d000074 | checkpoint | Scentre Group Consultants
53deb6b2-c1c9-54df-a016-a8b7fc1b7a9e | note | ACTIVITY: Defects
221b5794-7379-5cf7-9211-2fc81ce32830 | note | REQUIREMENT: All defects identified during SDC and consultant inspections have been rectified
2ed548e0-100f-4c08-bdce-cbbc9e12d53d | signoff | Subcontractor/Consultant Signoff
968ad440-5129-40f9-a5c3-55d7e072af74 | checkpoint | Final SDC Review & Sign-off:
67fd9b6a-ca35-5c26-bbfe-a89bd9bf5c20 | note | The Wall/Ceiling cannot be closed off until ALL sections above have signed off
b3e13ffc-b44c-511d-a048-afcd131e2413 | textbox | Name:
9a0a8fdd-5f9a-513f-b99d-d3333299139c | date | Date:
5b8e87d9-9143-49e9-ab36-be039f923c94 | signoff | Signature:
5d9eac43-a20a-58d4-bb7e-7572843c389d | checklist | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings |  | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings
2f9bce0e-f342-5d28-97b0-6393c8a55b69 | checkpoint | Prior to Concrete Pour - Attach markup structural plan identifying footings relevant to this ITP
5cbc8690-cff0-55e9-8cca-b705cdef437a | checkpoint | Prior to Concrete Pour - Confirm surveyor has provided setout for pad footing excavation (attach survey setout plan)
5436674b-8e8a-5e6b-b10c-cba6a6bf7fb7 | checkpoint | Prior to Concrete Pour - Attach Geotech engineer bearing certification confirming approval of substrate complying with engineer’s requirements
1c991607-4f56-555a-89b1-9b45f1738387 | checkpoint | Prior to Concrete Pour - Confirm that either pre- applied membrane or Forecoin plastic has been installed to comply with electrolysis study (attach photos)
56029564-4096-5e57-9d07-bdb38a0b4660 | checkpoint | Prior to Concrete Pour - Confirm excavation is free of debris and loose materials to walls and floor prior to handover (attach photos)
0d58d1b2-c79f-5215-88e2-0cc362dfda8d | checkpoint | Prior to Concrete Pour - Attach reinforcement contractors ITP (incl AEFAC Accredited installer signoff of any drill and epoxy bars to comply with structural engineer details)
c4c66113-3c19-5714-af47-52d082b8f135 | checkpoint | Prior to Concrete Pour - Confirm wall starter bars have been installed in accordance with surveyor setout and architectural outline drawings.
b7a7ce8f-94bd-564f-a988-100948dba2c9 | checkpoint | Prior to Concrete Pour - Attach signoff from CFT Column contractor inspection approval of starter bars, castins and hold down bolts
689e3c27-65a8-5151-9c67-3d9e745f6bd1 | checkpoint | Prior to Concrete Pour - Attach waterproofing contractors ITP confirm tanking waterproofing and PVC water bar has been installed(attach waterproofing ITP)
5b05355e-515b-50fd-a85f-da522e94e86f | checkpoint | Prior to Concrete Pour - Confirm that waterproofing consultant has inspected works and defects closed out
393b9469-2ff9-5e2c-a713-4c2800a8b1d1 | checkpoint | Prior to Concrete Pour - Attach hydraulic contractor's ITP confirming completion of any cast in as per hydraulic drawings
36c2f93a-d172-5030-ac87-a7b742d72372 | checkpoint | Prior to Concrete Pour - Attach formwork ITP/Signoff that all formwork to kicker has been completed (sump, hobs, edge boards etc)
23f9823d-9165-5cbc-b486-45bec2c97cb3 | checkpoint | Prior to Concrete Pour - Attach structural engineer’s inspection report
0bae1477-c557-5713-9c1c-ab264bc81b77 | checkpoint | Prior to Concrete Pour - Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
03664712-ddd0-5227-a828-de0e778194e9 | checkpoint | Prior to Concrete Pour - Confirm concrete place contractor's order complies with engineer's strength of concrete, waterproofing additive and testing requirements
705f0048-4a1b-55cf-a516-2c79242e1568 | checkpoint | Prior to Concrete Place - Attach photo of formwork setting the level for concrete place contractor
a40d7920-2900-5a09-9d3a-c075149f15fb | checkpoint | Prior to Concrete Pour - Attach concrete place contractor’s ITP
ecfe7831-c974-5fc6-a6c6-a2bc6ff39ff0 | checkpoint | After Concrete Pour - Confirm RL of poured footing complies with design RLs
18b2f80b-a9dc-5dc5-84fc-4ef33e8b2fac | checkpoint | After Concrete Pour - Confirm integrals falls have been completed in concrete to sump
d1268640-08dd-5ff8-831f-cfa97381e791 | checkpoint | After Concrete Pour - Attach concrete test results and confirm compliance with engineer requirements
137abde5-83cd-5168-8e4e-54503cda813f | checkpoint | Signoffs - Site Engineer to signoff ITP has been completed
1c58e575-642e-591d-a72e-03542ab08ffd | signoff | Signoff by Site Engineer
82b25620-11d2-5998-81ad-7c3846b7c749 | checkpoint | Signoffs - Project Engineer to review and confirm ITP has been completed
df67adf2-4fc5-5a7f-a46c-4c434bcbae4c | signoff | Signoff by Project Engineer
ab703c7d-344b-55a2-b416-d63f349afedd | checklist | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade |  | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade
1016cafd-6acf-571f-ac71-3cb8a976bf9e | checkpoint | Prior to Reinforcement: Attach Markup to confirm proposed pour zone
c746958f-18c2-5b88-9267-282c5f2ff901 | checkpoint | Prior to Reinforcement: Ensure detailed excavation is complete (Attach Excavation Contractor’s ITP)
f3366dfd-be73-517e-88c1-d99b51a3b6bf | checkpoint | Prior to Reinforcement: Confirm inground drainage and pit works has been completed and backfilled (Attach photos/confirmation)
5d52083a-02b1-5f2c-b7d9-29acec531ac3 | checkpoint | Prior to Reinforcement: Confirm that substation earthing rods have been drilled, as AS Built red line survey (If applicable)
d0ddcecc-e0ad-532b-bc76-5e76697c7162 | checkpoint | Prior to Reinforcement: Confirm min 100mm subsoil drainage has been installed as per geotechnical requirements (attach contractor’s ITP)
157ad683-bed3-56ab-97ef-51297160451f | checkpoint | Prior to Reinforcement: Confirm Surveyor has provided set outs/ benchmarks (Attach survey)
836f1ac7-3a33-5e1f-a567-3bc0592b1dae | checkpoint | Prior to Reinforcement: Confirm vapor barrier installed over subbase (Attach photos and confirm signed off by concrete place ITP)
4e697d51-962b-566c-bcd0-d76b289fb6e2 | checkpoint | Prior to Concrete Pour: Attach formwork contractor’s ITP (including setdowns, hobs, Construction/key/movement joints, ect.)
a70fb6bd-eaf5-505a-99e2-58527cbe5552 | checkpoint | Prior to Concrete Pour: Attach Structural Engineers inspection report
7afc412e-ba5c-52a8-97ea-0b5df4b87d47 | checkpoint | Prior to Concrete Pour: Attach Verification that structural engineer’s inspection report has been closed out to allow concrete pour (Attach Photos)
cd89edb7-fd58-5b38-94c8-3f0b6b2a3fda | checkpoint | Prior to Concrete Pour: Attach reinforcement contractor’s ITP
6d802568-2619-55e4-aac7-1cf8c6aca57c | checkpoint | Prior to Concrete Pour: Attach Hydraulic ITP (inground drainage and pipework)
d8dcf4a0-b680-5249-8a34-a308ac4896b2 | checkpoint | Prior to Concrete Pour: Attach Electrical ITP (Cast in conduits – if applicable)
78bdbd68-2c65-59de-ba08-e001107f40e0 | checkpoint | During Concrete Pour: Attach Concrete place contractor’s ITP (including Ableflex)
139a7b0b-3f18-5520-9495-79eb677d9440 | checkpoint | After Concrete Pour: Confirm falls have been completed in concrete pour in accordance to architectural drawings
099c4975-b6b9-5b67-af16-0ea6e4436487 | checkpoint | After Concrete Pour: Attach Concrete test results and confirm compliance with engineer requirements
68778255-61cf-56c8-81ab-23491075806f | checkpoint | After Concrete Pour: Confirm saw cuts installed as per engineer’s drawings
e3e5caf5-ca8b-5cac-8f12-0107ce5f41d6 | checkpoint | Signoffs: Site Engineer to signoff ITP has been completed
65719930-6c62-5d71-b865-8649e3555c77 | signoff | Signoff by Site Engineer
8c89fabc-4a87-55c4-80f0-00a867ff6e56 | checkpoint | Signoffs: Project Engineer to review and confirm ITP has been completed
8e6f285f-0a26-541f-a696-99853c5fa269 | signoff | Signoff by Project Engineer
3e0719b4-ae33-5910-bae0-91e410868a37 | checklist | Services Rough-in - Electrical |  | Services Rough-in - Electrical
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
4e3ce8a8-9ce9-5cef-a656-11fa8be01a3c | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
fd9c3fdc-76d2-53ee-846b-a52118975b88 | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
760c0529-6ae4-5c7f-9580-2e3ba34f0f77 | checkpoint | Confirm any cable/conduit penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around cable/penetration)
c2b705f5-5c03-5b9e-bd89-7c3455bfdba1 | checkpoint | Confirm at least 100mm separation between cables/conduits and any other services (200mm form fire dampers) where passing through a fire rated wall.
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
385345a0-a743-5d42-83ba-477a94a07c5e | tickbox | Ensure fixings at 200mm centres and washers are visible
9dafebea-a33a-55cf-9b8a-b5889507b074 | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
02706e39-ed99-5d49-85bc-15945a9790c1 | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
bdae01cc-e8a8-5eb2-8465-207f66b75b77 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
d853ec94-3817-5672-9c36-d3168d73d544 | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
df6e5841-5ce9-5f8c-b11e-7827512350e5 | checkpoint | Fire Rated GPO Boxes - Check installation within fire rated walls is compliant
07bb1f9a-1649-54b7-89cd-670771e3b598 | note | Max 3mm gap allowed between plasterboard lining and edge of box. Ensure gap is sealed with fire rated caulking.
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
514ad138-da5b-5416-8092-cb6eba8038b1 | section | Electrical Services
6902eb34-5ec2-5ee1-9ac9-8c8b7458143b | checkpoint | Confirm Latest Electrical Lighting & Power Plans are being used with Contractor (Refer Aconex)
c936bcc2-fc62-515b-bdfa-2fbd6b8a63ab | textbox | Record Plan numbers and revisions
908a5fde-b2ed-5833-86fd-d7faf4cdb8e1 | checkpoint | Typical Electrical Services Rough-in Heights - Spot check each room as follows (centre line of fitting):
e38d88b2-f6cc-527d-89cd-dfd95231f469 | note | Internal GPO's/TV/DATA Points - 300mm AFFL
83e1d7ae-d1af-5e22-b3e0-c27aefbb90c3 | note | Internal Light Switches - 1000mm AFFL
05194d08-8822-5c8d-b757-fd1dd2386673 | note | Home Automation Screen - 1500mm AFFL
07ae4def-0457-5657-b758-168ebf2a3f9e | note | External Balcony GPO - 650mm AFFL
f1026381-e22b-551b-8691-8ddf10fed91d | note | External Balcony Lights - 2100mm AFFL
90b73c89-f861-5dd9-af22-f2a8ced377ba | note | Interface with Joinery Elements - Check against joinery shop drawings to ensure correct location/height
13cca90b-b37e-5196-ad7e-be3a4894a604 | textbox | Record any deviations from typical heights and reasons why.
cd2f5312-0555-550f-8a29-a3242120ee52 | checkpoint | Services Installations - Complete visual check that all wiring for GPO/DATA/TV Points & Light Switches are installed
dd35c79b-b8fb-5014-9cc0-cd387c0be03a | textbox | Record any deviations from plans and reasons why.
368ff721-b597-5c97-9b4d-867418284612 | checkpoint | Confirm correct allocation of lighting quantities per architectural RCP drawings and rough-in installed
a5763d0e-2372-5a5a-9aa1-9043b9c9a92a | checkpoint | Confirm NBN cables have been roughed in to correct location & no 90 degree bends in conduit, sweeping bends only.
18507d56-0560-51cf-99c9-eabb0fa51ada | checkpoint | Confirm distribution board has been roughed in to correct location
889e914f-640a-5532-a03e-368f0d9a9e13 | checkpoint | Confirm intercom & home automation wiring in place
53b1d202-ae64-5edd-b5ba-37d89cfaa022 | checkpoint | Confirm power provisions to all kitchen appliances per kitchen shop drawings
2ca74d80-5715-5457-948f-ff4406d5f631 | checkpoint | Confirm minimum 50mm separation between power and data cables (or physical insulated barrier installed). Check minimum 25mm separation between power and gas/water services.
f8c78140-3b73-5c36-8903-057d5f38afae | checkpoint | Confirm Installation of earthquake bracing as required by standard
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
84a3209d-f36c-5120-86b0-9900349d9ea1 | signoff | HOLD POINT - Confirm Inspection items closed & Photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
36ab9cdd-4023-5d8f-b305-71e796eb2535 | checklist | Services Rough-in - Fire |  | Services Rough-in - Fire
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
702975bf-4441-551f-9e5a-f03921e79336 | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
d41cbda9-7f15-564f-97ee-294853e4f51a | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
5669f247-c260-5896-9a08-9146627fe462 | checkpoint | Confirm any cables penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around cables)
2d854f48-63e3-50d7-a158-47f97621e00d | checkpoint | Confirm at least 100mm separation between fire services and any other services (200mm form fire dampers) where passing through a fire rated wall.
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
e0baf51d-b07b-5442-ae76-1856584df488 | tickbox | Ensure fixings at 200mm centres and washers are visible
a2281e37-fa0f-5c19-8425-231cb9c42e3b | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
5a6bed70-a200-5eaf-bf7b-205c6f1ffa14 | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
dbfb4beb-48c9-5956-b6e5-7d2155627076 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
bb5fbef9-4589-5fc5-837b-002ef8b45356 | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
8158399f-f65f-5649-93cc-fd1097fdc58d | checkpoint | Check copper or steel pipes penetrating fire walls have fire wrap installed with at least 3 stainless cable ties.
38cab4e9-51ce-5fd5-b296-706c0eca953c | note | Ensure fire caulking is used to close any gaps around the pipe (coned) at the wall penetration prior and post wrap installation.
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
ef955797-bb0d-581e-ad8f-cdcccec5167f | section | Fire Services
cd2f3467-7930-5634-887c-0ec718c363b5 | checkpoint | Confirm Latest Wet & Dry Fire Plans are being used with Contractor (Refer Aconex)
e0608021-f10c-55a7-9330-e0e9747b8568 | textbox | Record Plan numbers and revisions
4625eb51-35a4-545b-9b40-7a32192eb49f | checkpoint | Service Installations - Complete visual check to confirm all Wet & Dry fire services rough-in is installed per plans (also reference Architectural RCP).
59ac44f3-5e35-5ffa-9952-45a611fec6e6 | textbox | Record any deviations from plans and reasons why.
161d880d-9376-5765-bf7f-f15814012a9f | checkpoint | Confirm all fire sprinkler pipes are charged so any leaks can be identified now and in the future.
01ab428e-7546-5a14-b126-17edfddb0a1a | checkpoint | Confirm any sprinkler pipes penetrating to the balcony are sealed at the external wall/window subhead.
561f6b53-979e-5f25-87a9-1bc152989b20 | checkpoint | Review sprinkler head and detector placement to ensure there are no obstructions to coverage.
21799f0d-c206-50fa-b132-29399a13071e | checkpoint | Confirm that pipework pressure, choke and hydrostatic testing has been completed.
62133283-1757-5944-b36f-444d94e0e94a | note | Pipes should be left under test for a minimum of 2hrs at 1400kPa. Provide time stamped before and after photos where relevant of pressure gauges.
dc069644-1ad7-500f-842d-eaf3269b30ba | signoff | HOLD POINT - Contractor to sign off on testing. Attach test sheet
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
fdf94e49-1b18-5bf5-9f85-87dfcc6402cd | signoff | HOLD POINT - Confirm Inspection items closed & photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
25bfb85c-956a-52d5-ba4a-48dfa27f99c8/3 | checklist | Services Rough-in - Hydraulic |  | Services Rough-in - Hydraulic
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
6d45aecf-5f00-53c7-acce-1a9ad270aa4b | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
67875932-c3f7-5c83-a864-e1e0307faf26 | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
42d308e3-033b-506d-bf73-ec0b8dacc9f4 | checkpoint | Confirm any PEX pipes penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around pipe)
e969e220-bf31-512a-81de-da2e530242e0 | checkpoint | Confirm at least 100mm separation between hydraulic services and any other services (200mm form fire dampers) where passing through a fire rated wall.
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
694aa2e0-d35e-57eb-b45c-2c331dfbfa8b | tickbox | Ensure fixings at 200mm centres and washers are visible
15e0764b-848b-51c5-98e9-bfdfd0d9d0c5 | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
dee391c5-a54f-5cca-9904-9b23adf2415f | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
c94f9e47-69db-51ea-a11f-00ff3f3c2998 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
b5851776-5b36-542b-b003-70123a8ffb63 | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
8158399f-f65f-5649-93cc-fd1097fdc58d | checkpoint | Check copper or steel pipes penetrating fire walls have fire wrap installed with at least 3 stainless cable ties.
a9611b02-81c4-511f-903f-89d2ab3ccd57 | note | Ensure fire caulking is used to close any gaps around the pipe (coned) at the wall penetration prior and post wrap installation.
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
a02749e8-d080-5a42-a5f6-01bc24ed22a8 | section | Hydraulic Services
5f08cc99-08e7-505e-8af3-256e7c528509 | checkpoint | Confirm Latest Hydraulic drainage and pressure Plans are being used with Contractor (Refer Aconex)
39db0f5a-035c-56b6-9f92-21237ebc4955 | textbox | Record Plan numbers and revisions
48e410e7-62dd-53e0-9d05-6396f5c05137 | checkpoint | Service Installations - Complete visual check to confirm all hydraulic drainage and pressure services are installed per plans.
4400c46f-7192-5e04-9924-7bba77b0d0b0 | textbox | Record any deviations from plans and reasons why.
46abcb0e-9bf4-523d-8c46-74ac0c78bf9a | checkpoint | Typical Hydraulic Services Rough-in Heights - Spot check each room as follows (centre line of fitting):
e11d0c11-c07d-5afe-8b40-b9be6bcf0f05 | note | External Balcony Tap - 450mm AFFL
8b574fcd-6cbd-5a16-9f25-6cbf4ae4367c | note | External Balcony Gas Point - 450mm AFFL
7eed5040-46b3-5ba6-87a7-69933ff20abd | note | Bathroom & Kitchens - Refer to apartment specific plans to confirm correct rough-in heights
fcc3b18c-557c-5c98-8621-14065b2c90f9 | textbox | Record any deviations from typical heights and reasons why.
a0fb0d86-d8d9-5385-8000-1827f3cf3dd0 | checkpoint | Review hot water supply is on the left hand side and cold water supply on the right hand side to:
8b967af4-0b78-5c94-98e5-a3fa24ebe97a | tickbox | Kitchen
875eaa89-aff1-562a-8727-9daf9c65e277 | tickbox | Bathrooms
9fbe428c-7f78-537c-9aa3-7c9b8ae160d9 | tickbox | Laundry
b28034ce-4274-5a04-a25a-005fe1d08527 | checkpoint | Confirm A/C tundish location has been supplied and trap prefilled
6c77e616-37de-5756-b051-b6a66ae30a87 | checkpoint | Confirm all in-wall hydraulic PC items installed (ie; in-built cisterns, mixer bodies, etc…)
66a72e52-e99a-584f-ba5f-33e9e0cef746 | checkpoint | Confirm all supply pipes are charged so any leaks can be identified now and in the future.
21799f0d-c206-50fa-b132-29399a13071e | checkpoint | Confirm that pipework pressure, choke and hydrostatic testing has been completed.
052af9f2-485c-526e-abf8-00e5c4fbb245 | note | Pipes should be left under test at 1500kPa (where applicable) for a minimum of 30min per the Australian Standards. Provide time stamped before and after photos where relevant of pressure gauges.
dc069644-1ad7-500f-842d-eaf3269b30ba | signoff | HOLD POINT - Contractor to sign off on testing. Attach test sheet
a74725a6-d237-5e00-bfa5-acd5a4cd160a | checkpoint | Check minimum 25mm separation between gas/water services and power.
7bddcb0b-4ee0-5ab2-b5ec-7e17e6a8c398 | checkpoint | Check that any operable valves or equipment (ie; PAPA Valve or TMV) behind walls or ceilings have a suitable access panel installed adjacent.
96f8dcdf-f000-573a-b1cc-85c36b636126 | checkpoint | Geberit Supertube - Complete visual check to ensure correct fittings are being used (search website link below for fitting types and install location reference). Review any horizontal pipe runs with 0% fall do not exceed 6m (which is the max. allowed by system).
2279818c-3a25-5e17-bc98-45bb28d352a9 | note | Website Link: https://www.geberit.com.au/products/piping-systems-for-building-drainage/geberit-supertube/
cc8d2f26-deda-574b-8a1e-6654aa1be324 | checkpoint | Confirm drainage points are capped off prior to fit-out trades commencing to prevent blockages from construction debris.
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
fdf94e49-1b18-5bf5-9f85-87dfcc6402cd | signoff | HOLD POINT - Confirm Inspection items closed & photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
52f1a2fe-7101-5616-8138-9d86de7a62b9 | section | Hydraulic Services - Acoustic Requirements
9a35aee1-b96d-50b0-b407-7afefae21d50 | checkpoint | Confirm PEX pipes running through studwork have gromets or silcone installed locally to prevent water hammer noise and damages.
9142f893-8ee6-5cde-a093-67d097714ed1 | checkpoint | Confirm no pipework is fixed to plasterboard or bridging cavities - should be fixed to studwork or blocking timbers.
45fd8307-17d0-5d6a-99aa-ba940d80b9fa | checkpoint | Review pipe clamps to ensure they have resilient foam sleeves installed to prevent vibration and noise transfer to structure.
b569fd29-a6e1-57ff-a844-4dfecf715911 | checkpoint | Pipe Lagging - Complete checks as listed below:
26d6e0bd-598f-56d2-8088-2f558342c532 | tickbox | Review all waste and stormwater pipes located in risers and ceilings are lagged.
5fc15055-55f5-55fe-8eb5-c595cad4bc70 | tickbox | Pipes running within 1.5m of A/C return air grille locations are to be double lagged.
11c3aee9-b758-5f3d-ac7e-693ff23f9a15 | tickbox | Review pipework lagging is overlapped 50mm at lagging joints.
abd2e7a9-d1fb-5216-b320-4b98cc90bfba | tickbox | Where lagged pipes penetrate slabs, walls and risers, ensure lagging is flanged with 50mm overlap where it meets the penetrating surface.
ac7a9501-22f0-59f7-962c-7549efde62d9 | tickbox | Review lagging around pipes is clear of any part of the structure (ie; walls, ceilings, slabs, framework, other services, etc…).
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
b7c49faa-a31f-5310-9323-48f90edcf9d9 | checklist | Services Rough-in - Mechanical |  | Services Rough-in - Mechanical
3528a5e7-cde5-54eb-b84e-652dd8e9ec14 | section | Fire Rating
b336a5cc-1f0b-5508-8087-99deabab0b3e | checkpoint | Check 1m benchmark has been set and agreed for services installation heights
579f9123-3374-5836-ac43-fe5a828138a3 | note | Attach Photo of benchmark for reference
4f146de2-db5d-5e8f-8220-8d0f600dad4e | checkpoint | Ensure services are installed neatly through fire rated walls
397a683d-d621-5e20-b423-4f27b3e40358 | note | Sheet areas of wall where services are to penetrate first (ie; above entry door), then install services to avoid non-compliances with sheeting.
5414dd65-1f33-5e6d-8269-602db51aed83 | checkpoint | Confirm any Mechanical cable/conduit penetrating the fire rated walls are sealed on both sides with intumescent fire mastic (conned around cable/penetration)
9ca51392-c28a-5230-ba38-02b634107fc8 | checkpoint | Confirm at least 100mm separation between mechanical cables/conduits and any other services (200mm form fire dampers) where passing through a fire rated wall.
37275155-b700-5805-8946-15fc5ad2468f | checkpoint | Fire Damper Checklist:
ac10f03a-aa17-55e5-a529-80e3147b66ab | tickbox | Ensure fire dampers installed at least 200mm away from other services where penetrating a fire rated wall
db700811-8eb9-53e5-a2a0-13d2fb4ca159 | tickbox | Ensure inside of damper penetration is lined ans sealed with fire rated plasterboard prior to damper installation
654871d3-603a-5c2e-a267-129c343c87d3 | tickbox | Ensure two layers of fire rated plasterboard installed each side of wall for damper installation (if not install additional layer locally as required)
15e12a42-5deb-5286-8333-b3de7844e62a | tickbox | Ensure provision for access (panels) installed for future damper inspection (both within ceiling and connecting ductwork)
2662999a-56ca-50a5-8632-cbb37034b936 | tickbox | Ensure flanges installed around all 4 sides of damper and no gaps visible.
2b0e251f-2475-5730-a7c5-bf73830ffe37 | tickbox | Fire Damper Approval - Check installation against data sheet/test report from contractor
9683530d-6b5f-5110-a473-ae71c785e5e8 | tickbox | Attach photos of compliant installation
058cee0a-42e2-5230-8e5e-d947f7b1c68b | checkpoint | Intubatt (Fibre Board Products) used with services
9ea5ae42-c65f-54a8-85ad-655436c59b47 | tickbox | Ensure fixings at 200mm centres and washers are visible
87be9ee9-3198-5fd4-8a87-3dd44ee53223 | tickbox | Ensure exposed edges of the board are covered with sealant to prevent deterioration over time
0b0f6c01-e457-551f-8547-d314db186ee1 | tickbox | Ensure where service penetrates the board that fire wrap and sealant are used to close any gaps
dc6fbf24-21e9-5b9e-a598-c61a9a880cd3 | tickbox | Attach photos of compliant installation
c59a31dc-26a0-5b0d-b6ad-6f2b88229aaa | checkpoint | Retro-Fit Fire Collars - Ensure correct size collar for service and that hole around services is sealed (coned) with fire rated sealant prior to installation.
d0f85ae5-ba43-5e5c-ae2e-7ee29560690a | note | Ensure an Acrylic Sealant is used (not intumescent sealant) when installing around fire collars
7f9c2cfd-9728-54bf-beac-2e2b433b369f | checkpoint | Confirm statuatory fire labels are installed adjacent services prior to sheeting. Attach photos for record.
5f3005de-2df6-566a-b171-ae1b623eab6e | section | Mechanical Services
d6472393-0551-5722-9126-3f5b6524a4d6 | checkpoint | Confirm Latest Mechanical Plans are being used with Contractor (Refer Aconex)
61c46027-bcc9-5900-987f-5e08ddaf35a6 | textbox | Record Plan numbers and revisions
72a73587-3b83-5f9e-85ee-ee3be815180f | checkpoint | Complete visual check that all flexible and ridgid ductwork has been installed per plans (also reference architectural RCP for future grille locations).
026f863d-ed5a-5289-a8e6-afe5e5077462 | note | Review to ensure no damages - take photos for record.
bec36726-f912-5ca6-890f-fb002a04b6d0 | note | Review support straps to flexible ductwork are installed evenly to prevent restrictions
943134e1-1399-55cb-9087-a3e835e04ffe | textbox | Record any deviations from plans and reasons why.
822228f0-71cc-5d29-af10-8af352773365 | checkpoint | Confirm wiring of AC controls are located per architectural requirements
0bcfc15d-bdd1-53f1-915d-0c958bfbebd1 | note | Refer to drawing: FJMT-A-61500 & specific apartment plan on Aconex for guidance
d3ec89ab-3a31-551d-a995-084c29f763ff | checkpoint | Typical Mechanical Services Rough-in Heights - Spot check each room as follows:
0b78e874-7ab3-5117-b88d-0d11639e552e | note | A/C Control & Thermostat - 75mm below home automation unit to top of controller where applicable
28539a7a-b4aa-5295-bf65-3db6d2d97474 | note | A/C Control & Thermostat - 75mm above light switch to bottom of controller where applicable
e1ffc51b-695e-514e-bd82-e1b6c96fd28b | textbox | Record any deviations from typical heights and reasons why.
2d9dbbf1-2689-5880-9ef9-e1dd7e755f63 | checkpoint | Review connections between flexible and ridgid ducting to ensure mechanically fixed and sealed.
522969ae-aedd-5442-b3f0-d6043d16c136 | checkpoint | Review connection between ductwork and façade to ensure mechanically fixed, sealed and a canvas connection is used to allow movement.
c30828b9-ccf2-561b-a60a-bd1f9928dce2 | note | Plenum box should be installed to curtain wall panel prior to installation to ensure properly sealed
6dc2b7df-404c-5901-90df-d10777b7f08d | checkpoint | Review Electrical Panel and Filter locations to FCUs to ensure they are not blocked and are accessible.
20a96969-3ade-56cb-a869-fad84b0759b0 | checkpoint | Review condensate drains and trays have been connected to hydraulic drainage and water tested to check for leaks.
3548a6c0-4a34-5780-8f3a-82ae8f90f256 | note | Check that condensate drain pipes have positive fall all the way to tundish point & 25mm air gap above tundish visible. Attach photos for record.
e6f0fed3-78c4-5897-be70-f78db9068a8d | checkpoint | Confirm refrigerant testing of lines completed prior to sheeting to check for leaks.
f1e07d8d-0791-5d9a-83d1-12fd1ba2ed38 | signoff | HOLD POINT - Contractor to sign off on testing. Attach test sheet
cc6da23b-6e42-5500-8801-e1cadf4d4431 | checkpoint | Review thermal insulation installed on refrigerant lines from the riser all the way to the FCU connection point.
f8c78140-3b73-5c36-8903-057d5f38afae | checkpoint | Confirm Installation of earthquake bracing as required by standard
74e43698-3c35-571c-b024-9b935a9fbfc3 | checkpoint | Confirm adaptable apartment future provisons installed if applicable
6d5e73eb-71d6-5ebb-a7d2-6890e280a7d1 | checkpoint | Services Checking Consultant Inspection Completed prior to Sheeting
84a3209d-f36c-5120-86b0-9900349d9ea1 | signoff | HOLD POINT - Confirm Inspection items closed & Photos attached
b18fcc20-250c-59ee-8c63-45e5fedab012 | checkpoint | Attach Subcontractor ITP
3e3fe827-5274-5883-80c1-21d7537e0434 | section | Mechanical Services - Acoustic Requirements
b9e59725-b5c3-5537-991f-18b37ca8037c | checkpoint | Confirm flexible ductwork is acoustically rated (ie. Inner flex is perforated and insulation lining between inner and outer flex).
86efce0a-7c20-5bac-854f-91fc56998cce | checkpoint | Review AC Fan Coil Unit (FCU) has vibration isolation (rubber) mounts or springs installed
00b74992-f637-5637-b12d-b5fab0f7a1a9 | checkpoint | Review Toilet/Laundry/Kitchen Exhaust fans have vibration islation (rubber) mounts or springs installed
1225cb5f-c4d7-58ae-bb3d-d732e059bfe5 | checkpoint | Review where flexible ductwork passes through full height acoustic walls (eg. Wet areas) - ensure wrapped in sheet metal and caulked (max. 10-15mm gap around service)
a6b3f612-f213-5429-ac4d-b021759f3611 | checkpoint | Review ductwork joints to ensure sealed properly (with "Emer-seal" joint sealant) to prevent noise resulting from air leakage
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
a019caed-13bb-57cc-8c19-e1532e4780be | checklist | SYS - Columns/Shear Walls |  | Columns/Shear Walls
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
5ba4bfda-bc99-56cf-8b8b-2996c4f9926f | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
be34bdae-f703-5862-8415-cd17d0848cba | textbox | Architectural Drawings
98c3cdb3-0c8d-5188-bc6f-4dbea03affac | textbox | Structural Drawings
535fe087-6741-5432-99b5-8b5bd1d668f1 | checkpoint | Ensure survey of column/wall positions are completed prior to commencing formwork
83678975-8dac-5a3c-9344-1bc226ae18a7 | note | Attach surveyors as-built records to ITP
67880d0a-c7c0-503a-8574-c26af3170bd4 | checkpoint | Reinforcement - Check Starter bars from previous pour installed in correct position (compare against survey points)
6fa61a94-96db-5ff6-a543-755820891e1a | checkpoint | Reinforcement - Check for correct bar sizes and lap lengths between starter bars (top & bottom)
3902c60f-0f95-575f-a26e-2703689b150c | checkpoint | Cast-in Services - Electrical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design. Attach Contractors ITP
025eba38-756a-5f48-81d5-b24cbee885c5 | checkpoint | Cast-in Services - Hydraulics subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
c2d57c76-36ed-5a08-8267-6e7225fc89ac | checkpoint | Cast-in Services - Mechanical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
18de01a4-f42c-5901-afdf-25618335b566 | checkpoint | Cast-in Services - Fire Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
8f061269-5e8f-57f9-a105-62da81d836df | checkpoint | Cast-in Services - Security Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design
55bcc9e7-4508-50c4-999a-66d8c5c4c9aa | checkpoint | Confirm strength and mix design of concrete ordered with subcontractor prior to pour
83416d4e-588a-5834-bfc7-cca8d9297375 | textbox | Concrete Mix Design:
e502b10d-edc8-544c-b0eb-c56a1aad439f | checkpoint | Structural Engineer Sign-off - Foreman and subcontractor to sign off engineer’s report to verify that all work to be rectified was checked for compliance prior to pour
c4b3574e-3e4d-5d2d-9f51-2682acf11262 | note | Attach engineers inspection report and verification of rectification items being closed out.
e8a4bcc9-d32e-5f1d-ac6b-949038bf6b85 | checkpoint | Formwork Compliance - Confirm formwork is checked to achieve Class 2 finish to concrete:
1c7ffae4-da3d-5f41-9776-0dc689ab6e2a | tickbox | Formwork is clean and free of debris
9e437d63-5f9b-56ad-849a-dc1f97c98f02 | tickbox | No lipping of formwork between sheets
cc5eedd9-562a-5a3c-bbf8-35089fa64818 | tickbox | Fillets installed at all corners
f3d9af63-113f-5fa7-a734-818ad2f60b11 | tickbox | Form ties are installed at even spacing
6b22574f-5639-5df7-bb94-dd6682f5e4e7 | tickbox | Check for correct reo cover at shutters
c78823d8-b08f-5d92-b36a-9adb285dda2f | tickbox | Splayed columns are at correct degrees per Architectural/Structural drawings
a023a578-da63-5c4c-9d10-904381e00fd9 | checkpoint | Area cleaned of all excess formwork, sawdust at base of columns, reo, and debris prior to pour
d26c5200-b798-5a1b-8336-ba20b6936d9c | checkpoint | Attach formworkers ITP for column and wall formworking
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
a996b133-8d9b-53cc-af5e-c4d995eba206 | checkpoint | Concrete Placement Checklist
ef0d10f5-ca0a-5fbc-b5a2-88bcb5fc011a | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
4d43f38a-5927-5625-9cee-50b55ef49554 | tickbox | Confirm Delivery Docket References correct mix design
6afa1aba-7909-5a62-8e46-39ab8780b801 | tickbox | Plant and Equipment checklist completed on concrete pump and lines
75c379bc-ae8f-53e8-84f9-d4849bf5d7c7 | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
8eae3c07-4137-513b-83dc-1b73460911d1 | note | 7, 28 & 56 day compressive test results to be issued by batch plant
0ba68840-1f2c-5ee0-8575-28464266daca | note | Batch plant to issue monthly dry shrinkage test results
b73bee09-e61c-5e56-8b55-431389362db1 | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
cfa21684-6574-52b3-ac38-ddba1bcb52d1 | tickbox | Form Worker
f0f49649-9514-5fe7-8657-bb359e1b359f | tickbox | Electrician
aab7c095-1bf7-539c-8343-065ddf77ee46 | tickbox | Plumber
045bea43-ef93-5c37-a70b-d767e5e3c0c3 | checkpoint | Ensure only rubber tipped vibrators are used and care is taken not to damage shutters
1b98fc0c-6352-5fbe-9adb-d3da0b8f3f8c | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of walls, immediately after pour for off form finishes.
c2833c5a-a36d-5c23-89e2-ab93946ee01b | checkpoint | Record of Pour - Marked up drawing available to record location of each batch of concrete
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
9fb23d0e-0d1e-57cc-9c15-048ba7235eb7 | checkpoint | Curing - Approved curing compound to be applied to columns following removal of formwork as required.
1f774416-47c1-5414-ad4e-41fec77d84f0 | checkpoint | Confirm tolerance of finished concrete surfaces:
bef63090-e05d-52a2-9126-1efb628a4c99 | note | 5mm+/- in correct position
97bd183b-4da4-5ec2-82e7-5e9c5d97eab4 | note | 5mm +/- from 3.0m straight edges.
0e3449f9-ff48-5dad-aaa5-565606e686e0 | note | 5mm +/- from plumb.
54d3cdd2-0c38-5c30-8a62-c92cc82fbdde | checkpoint | As-Built Survey - Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As Built Survey Plan
234214fc-15c4-57c6-93e1-2a16b3f5124f | checkpoint | Concrete Test Results - Obtain all concrete test results. Confirm strength achieved after:
cd3ad7e9-18da-54e4-a3e6-dad00be42a1c | textbox | 7 Days MPa
27a71ddb-793f-5e8c-a11c-83069ad213c8 | textbox | 28 Days MPa
10ab75ae-4cdd-5660-a6b6-1d88aadbe99b | textbox | 56 Days MPa
35ac4bcc-f65d-56f1-9972-e66071f55c23 | checkpoint | All non-conformances closed out
95da422e-fade-5c59-b042-7bc47be521a6 | signoff | Final ITP Review & Sign-off by Project Engineer
2f99e6e8-0697-55c3-a87d-4dccbd1a216e | checklist | SYS - PT Slabs |  | PT Slabs
295f5594-f977-5cf3-a95e-1b914b0e80c5 | section | Prior to Formwork Deck Handover
5ba4bfda-bc99-56cf-8b8b-2996c4f9926f | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
71577392-12c1-515b-a87b-92b6737e8527 | textbox | Architectural Drawings
35391470-e1ca-5251-ae7d-50a6f778b833 | textbox | Structural Drawings
2dbeafe4-65f8-590f-a07c-dd1d8baa5d09 | checkpoint | Concrete Mix Design
aa0b26bf-fcf3-566e-823c-bba049b0a821 | textbox | Confirm Mix Design
41c99b98-0067-5b53-98db-86509393965f | checkpoint | Set-out - Surveyor set out slab grids to allow formwork construction
bf140f59-99b4-5b36-96dd-09ee09530581 | checkpoint | Survey & Set-out of formwork correct. Check correct heights for formwork soffit, Top of Concrete (TOC) and falls
7e92b3f4-2de1-5ce1-87ec-7db3a674d241 | note | Attach Surveyor Formwork As-Built to ITP
8e1a66ad-611f-5f80-9a67-1faca5fe1a19 | checkpoint | Site Instructions - Copies of design changes, emails and site advices and the like to be attached.
100f5dfe-8ec5-59b9-910c-f68c280a8190 | checkpoint | Bondek (where applicable) - Back propping installed for pre pour and deflection & gaps sealed to prevent dripping
e0fe376b-a421-5e7a-882b-8c272a18b689 | checkpoint | Structural Steel Sign off from Steel installer and Structural Engineer (where applicable for bondek slabs)
1a7b7757-785d-5271-a047-9317f30cb7cc | checkpoint | Formwork Sign-off - Area cleaned of all excess formwork, sawdust, reo and debris prior to pour. Safe Access to deck available.materials before handover deck
41e7a28f-8521-5b18-a4e6-d67e7a5df259 | note | Attach formworkers ITP (referencing all hobs, steps, cast-ins, HDB's, bearing strips, polystyrene, fillets, etc… installed correctly)
e895f0c4-445d-5222-83aa-ee6b071b56fa | section | Prior to Concrete Pour
dfa84113-61be-5071-a599-4bfa7da4d22e | checkpoint | Structural Compliance - Engineers approval for concrete placement required with list of defects to be completed
9e61c242-2c12-584a-ab33-a3a588135238 | note | Attach structural engineers inspection report and evidence of close-out
718b0a37-0bd9-5d17-b022-13f4506ee88c | checkpoint | Formwork Engineers Sign-off - Attach Sign-off
bc6540fd-d9b4-5bb0-903f-90a9e8eb0ee3 | checkpoint | Post Tensioning - Check Subcontractor ITP complete, and attach to this ITP.
14d9e1fd-3501-5226-a3bc-f01df740ab71 | checkpoint | Screen Needle Cast-in's - Inspect all screen needles are installed in accordance with relevant shop drawings
528ef2fc-3f99-53f3-a276-ddcef0e4da30 | note | Attach sign-off from Formworker
5e6c0c26-c34c-5155-82d8-95ade4979701 | checkpoint | Curtain Wall Bracket Cast-in's - Inspect all Curtain wall brackets/rebates are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
48245463-11d7-5676-8374-8cb3d0502001 | note | Attach Curtain Wall subcontractors sign-off & ITP from formworker
fbf3fa70-7e97-51f1-84c5-a73c5ecf2ebb | checkpoint | Crane/Hoist Bracket Cast-in's - Inspect all hoist and crane brackets are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
4c3b3f45-78b0-55bc-9628-c84b2cacceae | note | Hoist and Crane contractor to inspect and sign-off cast-in position.
fb2866ee-56ac-59c4-8bf3-33914cc7ebf4 | checkpoint | Temporary Penetrations - Inspect formwork penetrations in accordance with temporary works design. Surveyor to confirm locations are correct.
4e806b36-cb1b-5334-8aab-68cb0e0307f4 | note | Temporary Penetrations may include: formwork hoist, concrete boom, etc…
adb4d0e8-65a6-5de3-ac58-c795f4505cad | checkpoint | In-Slab Services - Electrical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
20504b08-0515-5b97-8bbb-92856bce0c8c | checkpoint | In-Slab Services - Hydraulic subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
09a073b7-597f-507f-a4c5-18c36fd14628 | checkpoint | In-Slab Services - Mechanical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
712acdc7-b4a7-52f0-a901-c68540c44cdc | checkpoint | In-Slab Services - Fire Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
236453d7-a578-5c50-93a0-18a68dbd4dc6 | checkpoint | In-Slab Services - Security Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
57f69192-958a-57f3-8f3c-a9e497f8f688 | checkpoint | Formwork Cast-ins - All timber fillets, drip grooves, Rebates, and proprietary shear connectors installed as required
c7e06a37-79f9-5353-8059-3f145d6d5f46 | checkpoint | Starter Bars - Confirm all starter bars for walls and columns installed as required per structural and architectural drawings and survey pins
d00e631c-e50c-574a-9aa3-68412fd9553a | checkpoint | Water Stops - Confirm installation of any proprietary water stops as required (ie; at CJ’s, etc…)
855ff8fa-6730-557a-8e52-d106ec75c5bb | checkpoint | Reinforcement Cover - Check top RLs for all reinforcement, ensuring adequate concrete cover. Confirm with Concreter. Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits.
dcb336a8-fd09-5bfa-873f-07af8cbbf30f | checkpoint | Concrete Falls - Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary
0c708f08-397b-5649-92f4-d4d6c37335ab | note | Cross-check the following drawings: See Hydraulic, Architectural Concrete Outlines and Structural drawings
37c28923-04ce-5966-8fbd-571b16e9c359 | checkpoint | Cleaning of Deck - Clean off decks and beams prior to pour and ensure all exposed off-form soffits are free of any dust, stains, and rust marks. Hose down if necessary.
2855ee05-1267-5a52-b798-36451d292a8f | section | During Concrete Pour
a996b133-8d9b-53cc-af5e-c4d995eba206 | checkpoint | Concrete Placement Checklist
7913c179-94c9-519d-a948-d0a9c94253c5 | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
79922c4d-a7b3-5475-9417-7a5ba8f297fa | tickbox | Confirm Delivery Docket References correct mix design
3c0e5aa6-2340-5e95-b8cf-be49dd705115 | tickbox | Plant and equipment checklist completed on concrete pump and lines
931fdd79-290f-5785-802c-dba7dfd82152 | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
248d7a4c-044f-5752-bebe-bb2ab35d27b9 | note | 1, 4, 7, 28 & 56 day compressive test results to be issued by batch plant
291a1c09-bd2e-50ce-899f-725b9e29c31d | note | Batch plant to issue monthly dry shrinkage test results
c2833c5a-a36d-5c23-89e2-ab93946ee01b | checkpoint | Record of Pour - Marked up drawing available to record location of each batch of concrete
f8f5594c-c38c-5d78-a8b6-38ab0fa98b6c | checkpoint | Concrete Finish - Ensure concrete contractor is aware of required concrete surface finish.
c1e85569-9cbf-50e3-9b95-e4470c2fbcbc | checkpoint | Slab Curing - Check cured when bleed water stops and able to access slab without marking and also amount used complies
14e178fb-fe69-52a0-91f6-30076e8b4f0a | checkpoint | Concrete Falls - Confirm concrete has falls to drainage points in slab.
a2dc03bb-a611-5d28-91e4-bf1fb10f9020 | checkpoint | Trade Representatives - Ensure a representative from each of the following is on site and witnessing the pour:
274596a9-8284-55c2-a562-3a463c31a7f4 | tickbox | Form Worker
6e693d5b-96b7-5efd-a753-91817e4b9749 | tickbox | Electrician
4d76e6fc-1f2c-55c3-a91d-791136188cdf | tickbox | Plumber
a671c5d5-4c08-5660-a9d1-8999d27af5cf | tickbox | Post Tensioner
2192aa73-f6ba-58af-8c61-4895a7d428fb | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry.
0c36bc32-cf0c-5072-977b-380ad8510aaa | section | After Concrete Pour
08728e08-995c-50af-a2ec-d7e14671870a | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan.
f886350e-a086-5135-9a70-b777886af386 | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
22ed6f70-72b8-5528-9059-0ffa3d38f35d | note | 6mm +/- from design RL
74023c59-165d-53fa-bcb2-6f6223d28ae6 | note | 6mm +/- from 3.0m straight edges
1495d922-a480-534f-b717-6368bad185b9 | checkpoint | Exposed Concrete Finish - Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610 (Class 1, 2 or 3)
73a62edd-f785-5a3d-9a66-3aa541d7b88b | checkpoint | Concrete Test Results - Note test results on ITP and attach:
a1ddf03f-e21d-552c-b850-a1e687cafdac | textbox | 1 Day
fe30e90a-5fb4-5064-a514-5f52dfe6511f | textbox | 4 Day
8becb43c-e7d2-5896-bc57-4c3a4c1c9126 | textbox | 7 Day
f9ca7c0a-9042-5d98-bf73-7ed0fad33737 | textbox | 28 Day
d3436848-b341-5571-8ded-d3c90f10030f | textbox | 56 Day
a376cbd5-1e22-5251-a5f8-f870a953ef4e | checkpoint | Initial Stressing - Concrete has achieved required strength MPa (10 MPa and confirmed by Concrete contractor)
c63b12e5-d21d-5ebd-a6d0-4bbcbc26a6ec | note | Concrete Contractor must issue Concrete test results, verbal not accepted
41f18e67-7d4a-5d5a-bb7e-80b7411ea4ea | checkpoint | Final Stressing - Concrete has achieved required strength Mpa (22 Mpa and confirmed by concrete contractor)
1188e90e-ee7d-54b8-b59d-1a0cd8f0a55d | note | Concrete Contractor must issue Concrete test results, verbal not accepted
14b415dd-206b-51ad-b6fb-ce3037f86b3e | checkpoint | Stressing Sign-off - Before stripping can commence final stress complete, Ducts grouted and PT supervisor issues verification records
fff3426b-83cc-50f5-8e4a-d67a41db9099 | note | Attach Post Tension Contractors ITP
77c98c2f-53b9-58f0-b5d3-8207838ca4b1 | checkpoint | Extension Records Approval - Engineer approval of extension records following final stress
2c04992a-3395-5768-9381-56b23470d61c | textbox | Record date when props were removed if not given approval by engineer
9d87b967-2d49-5717-80ce-42ebdedfe8b2 | checkpoint | All non-conformances closed out and accepted by Structural Engineer and Architect.
d36b933e-9fa1-5bbc-9958-546e8775e762 | signoff | Final ITP Review & Sign-off by Project Engineer
b6936572-b41d-4c59-9dbf-a184695232aa | checklist | Tiling - External Balcony Paver System |  | Tiling - External Balcony Paver System
da1beccd-60d2-4f6a-852a-f77bb1c280eb | section | Prior to Works
5fde8109-98ff-41fc-ba15-69f78d271c40 | checkpoint | Confirm Series and Scheme of finish for unit/work area
f771598d-a4a3-5761-a1fb-7cca111bc862 | textbox | Record Colour scheme of apartment/work area:
e56776c3-ecdc-4191-a707-6994e319d3f0 | checkpoint | Confirm site pavers/tiles match approved samples.
96f5a9a0-161b-57fa-8491-9029a73b7a6e | note | Review against Aconex Sample form, attach photos.
b5bf8277-c6c7-4daf-9f97-9ca72963fd6d | checkpoint | Confirm that all floor wastes & overflows are plugged during tiling works to prevent debris entering.
fd8e3ea7-4038-4881-993c-a1f28e3fe7b8 | checkpoint | Confirm that concrete has adequate falls to floor waste, and there are no puddles remaining after flood tests.
6609ba0a-f0eb-5d49-81f8-d404faab64bf | note | Ensure min. 1:100 Falls achieved on balconies.
623ed869-ef78-44bb-b382-b3199511e6a0 | checkpoint | Ensure Polypads are configured into correct shape and size for placement.
2905304a-d703-4c23-9f2c-521e22958493 | section | During Works
32af434c-afa3-43e6-bfb2-0d7e4c0047c7 | checkpoint | Confirm height of polypads is aligned to sliding door threshold (ie; flush transition).
8392364a-1380-49c2-81c7-db3b5b0f3951 | checkpoint | Ensure quality of tile installation is maintained, i.e. Alignment & Consistency of joints, Minimization of scratches & damage, no loose or ‘rocking’ pavers.
5c4c3083-deeb-4491-bfd5-ea7b274cc48f | section | After Works
9f42a66e-8093-4840-94ba-daff51b908f0 | checkpoint | Visually inspect all floor wastes and confirm each one is clean and clear.
73ab821b-4a30-42cb-bdb5-2774598475a0 | checkpoint | Attach Subcontractor ITP
b5c506e0-c287-4bd6-ad4c-a35fd7acd91a | section | Sign-off
3834a9ea-4d0d-4db3-96c6-e9dc890a357c | checkpoint | Subcontractor Sign-off
bc248a75-a1da-4b05-b517-3651101f07d5 | signoff | Subcontractor Sign-off
49171109-b860-4a7b-93a3-647df3bcddea | checkpoint | SDC Sign-off
1c8c3f6b-c501-48e1-a2e7-6f21f6fc6a56 | signoff | SDC Sign-off
7b773f7d-2729-4b67-b7f0-dd81dd1ecb6a | checklist | Tiling - Internal Areas |  | Tiling - Internal Areas
92da13aa-d6b7-49fb-9d40-821580aeb402 | section | Prior to Works
2cb68502-9050-4f4c-b797-39e01ee4c58b | checkpoint | Confirm Scheme of finish for apartment from Residential Finishes Schedule. Check tile being used matches’ schedule.
d4626207-ab20-5d82-a674-bb187a8d2f84 | textbox | Record Colour scheme of apartment/work area:
3fe3aa20-557c-40b0-9f54-6f9aa860c294 | checkpoint | Confirm Tile Set out with tiler prior to tiling from the architectural bathroom plans.
8688d241-ebd7-598d-8b09-555393846ef7 | textbox | Record plan showing set-out. Ensure tiler has the latest plans from ACONEX.
8d8a0aad-d5e9-4df9-9b16-a89782883eaf | checkpoint | Confirm tiles are from the same batch
9ff8676a-e6ca-5203-97aa-36176a129e12 | note | record photos of tile boxes where available
ec1e776a-3cc5-4dd3-9d8a-941ee9453720 | checkpoint | Confirm Tiles Floor Finish Level (FFL)
7485e19b-1944-5a81-bba8-06dc2b6ac8de | note | Record FFL being tiled (high point at door threshold).
748844d1-d49b-4a8e-93e3-76f336b0549e | checkpoint | Confirm all floor wastes are plugged during tiling works to prevent debris entering.
771ad1ce-ad7d-479a-8c7c-a881cad38e67 | checkpoint | Ensure Acoustic Matt installed where required per architectural insulation plans & acoustic report prior to works.
b247a64a-cb66-55c9-b96d-ab8b1c0a2db0 | note | Record photos of the matt installation
8a430abf-02fc-4209-96b5-3d257d154047 | checkpoint | Ensure associated works for under floor heating installed as required prior to completing tiling.
68d3d98c-a73e-5640-9f8a-13456242826f | note | Record photos of the under floor heating installation
0489cad5-a2e0-4a6c-9009-e0050a0de964 | section | During Works
a318215e-5438-4e72-8610-c72757a93414 | checkpoint | Confirm sand/cement screed ratio is as per AS.
d5a36bab-1faf-5e44-a7a4-0991f966e397 | note | Ratio - 1:4 (1 Cement / 4 Sand)
4f315f37-1543-4786-988f-c80ead475f8d | checkpoint | Confirm minimum 25mm tile bed at floor waste (can be less if engineered screed).
adfc2012-0d22-49ce-88da-804fa0a4227c | checkpoint | Confirm tile bed thickness at door threshold will allow finished tile to be aligned with FFL.
8006c743-3ade-49ab-9b94-d6adea844649 | checkpoint | Screed curing times – verify with tiler that screed has cured for suitable amount of time prior to tiling.
98d9d710-71db-4c45-8e33-67f0eeaa20b5 | signoff | Sign-off Hold Point – tiler to sign-off screed suitable to take tiling.
90bb1a27-89b5-4f7f-89e1-3e02a5be6403 | checkpoint | Moisture Barrier – confirm this has been applied over top of tile screed prior to tiling application.
26960503-e0a3-4681-9323-6a7fe8c10d92 | signoff | Record product being used and verify curing times adhered as well. Tiler to sign-off on curing prior to tiling.
a3b58126-fe49-4e79-ba1d-b5e6c59c74a6 | checkpoint | Confirm installation of floor wastes is flush with or 1mm below floor tile level.
63be1705-3ae6-4165-89c9-228d86c84017 | checkpoint | Stop wall and floor tiles 2-3mm short of edges and fill with resilient caulking compound.
fbebe1d7-1d9a-47a1-a0b5-6cbbc9cd8c15 | checkpoint | Confirm that floor waste (normal/smart) and strip drain is installed correctly per design drawings. Ensure grout line of tiles within floor waste line up with main floor.
9b34b42a-8735-490c-b22c-a2ef7de2a63d | checkpoint | Confirm tiles are set out per architectural design drawings. Check large format tile joints align with stone joints where detailed on bathroom plans.
19768309-d9e5-59d3-b72e-f9fada17a530 | note | Check against tile set-out points.
c3be98f8-9042-4922-b18b-c308191e4c1c | section | After Works
b7199d54-ad85-437e-ba8f-510b81630d6d | checkpoint | Visually inspect all floor wastes, and confirm each one is clean and clear
84e61e78-efdc-4670-8f46-cc2b509f8e08 | checkpoint | Floor tiles laid to falls – min 1:100 in main bathroom. Check min. 1:80 falls in shower.
4988c245-52ed-45db-8d9b-9e3e131a5aa0 | checkpoint | Confirm all joints are aligned and lipping of tiles does not exceed the requirements in the architectural specification.
021c363f-e08f-50af-a663-dee717c4bdc0 | note | Lipping requirements: - Unpolished Tiles 1.5mm - Polished Tiles (less than 300x300mm): 0.5mm - Polished Tiles (greater than 300x300mm): 1.5mm
8d0df113-19a4-416b-a59e-0c636c7199d4 | checkpoint | Confirm colour of grout is consistent and uniform.
dadffd34-d8eb-4b4b-a8f2-b70f3497fd71 | checkpoint | Confirm all tile edges line up and are plumb. Also check curved tile walls meet the required radius shown on bathroom layout plans.
22922851-02f8-4b9a-aed0-eb03415afce2 | checkpoint | Confirm all silicon jointing provided to all floor/wall tile junctions.
15ce663a-8ea7-56bb-87b2-3f16515a91a7 | note | Confirm all excess silicon is removed from tiles and adjoining surfaces.
23c38c8d-7417-4ffa-85b7-f431cf204ba6 | checkpoint | Review large format stone wall tiling to ensure vein matching per architectural bathroom elevation plans.
16f4b6fb-05b0-45fe-a9c9-c496334ac306 | checkpoint | Attach Subcontractor ITP
2d540328-a631-404a-8ebe-1175b1a1cc90 | section | Sign-off
63d17910-b389-458d-9d1d-dd7f46660fc3 | checkpoint | Subcontractor Sign-off
026fa2b0-d190-4ee5-b518-c236454406b4 | signoff | Subcontractor Sign-off
e06964fd-8182-45ee-81ca-dcd707652098 | checkpoint | SDC Sign-off
fd2ad924-c625-4018-8f28-8e9cf4294c8e | signoff | SDC Sign-off
63c071a4-8691-5d62-82c7-906aea997a3f/5 | checklist | Waterproofing - Balcony Areas |  | Waterproofing - Balcony Areas
6107e48c-eca3-5f07-91e4-be2679c46a44 | section | Prior to Works
8c97525e-9acd-5dec-9911-0defcb005f52 | checkpoint | Substrate - Review to ensure any voids or protrusions are filled and removed and ensure surface is prepared to take membrane (lightly sanded to promote adhesion)
19e171da-1973-52c2-824f-539b46134bbe | note | Also ensure substrate is clean and free of any water, dust and debris.
85a015df-86fe-594a-83bd-1d3a0a27ab2c | checkpoint | Verify with Plumber that their drainage works are completed prior to membrane commencement.
c38f5a78-fbaa-5942-bb3b-0098c6b8d89a | note | Attach Subcontractor ITP where relevant.
f435001a-afea-5481-ab9e-16cce2f58cf7 | checkpoint | Concrete Cracks - Review substrate for any cracking. Up to 2mm cracks fill with Polyurethane sealant. Above 2mm to be chased, cleaned and primed, then sealant applied.
91a5bec7-5fad-561e-88ef-d86803fc0a3e | checkpoint | Falls - Review concrete substrate to ensure min. 1:100 falls achieved and falling to floor wastes.
6eb4055d-0000-5a69-b942-472452654fb5 | checkpoint | Floor Wastes - Review puddle flange to ensure it is recessed and flush with floor substrate. The PVC flange should be lightly sanded to promote membrane adhersion.
37a01a3d-dff5-5797-ad34-a52868febae2 | note | Also check internal of floor wastes to ensure free from debris prior to waterproofing.
f5bb5cc7-bc10-4ca1-9b2a-d5eefc6ceaa5 | checkpoint | Wintergarden Façade - Waterstop angles are installed as per façade shop drawings:
2caf9876-c9f8-5371-9828-02576fca9049 | tickbox | Continuous angle around perimeter (not required in front of concrete columns)
3e18da12-ad54-566b-b6b7-e707812a5d7a | tickbox | No gaps and any joints spliced with a backing piece
91d55d14-e309-555e-aa14-884776117f5e | tickbox | Angles to butt into concrete columns
813e6008-ae05-58f4-a16a-15bb0b2864c5 | tickbox | Top of angles to be at consistent height, no sharp joints
5809d769-4733-4800-8967-09d7e59cd5ac | checkpoint | Wintergarden Façade - Anchors for waterstop angles installed using chemset
335b1ce1-4c3b-4e6d-961d-86bdb635296c | checkpoint | Wintergarden Façade - Subjambs installed flush to smoke seal, bedded in sealant and 5mm cut to allow differential movement between smoke seal and façade
2927c872-b826-586b-aa0e-f8f141406ca1 | checkpoint | Overflow Points - Review overflow points are installed correctly per plans (min. x2 per balcony) and pipework is proud of slab surface by min. 30mm.
99ac1ea6-a0b1-57ef-80a9-9aabbba87852 | note | Check overflow points are connected below to curtain wall façade and not blocked.
712524e4-2a53-5143-8558-d2fb6acfbed8 | checkpoint | Substrate Moisture Content - Verify that waterproofing contractor has tested moisture content of concrete substrate and is happy to proceed with works (ie; below 5%).
360a10fa-ca0b-580b-befd-bb7ec6e8057a | textbox | Record moisture meter reading.
7c376bae-53f2-533a-902f-862246d8d991 | signoff | Subcontractor to sign-off on substrate.
7efc1321-c66a-5c1b-b913-b8eb60633901 | checkpoint | Waterproofing Materials - Confirm approved waterproofing materials are being used for the works.
634c5298-97a0-541f-ac32-71b2c07ab2f7 | note | Waterproofing Primer: Sikalastic PU Primer. Waterproofing Membrane: Sikalastic 488
6c55705c-ab61-5cfc-b210-9de1a66112df | checkpoint | Record product batch/serial numbers for tracking of any future defects.
7dafab42-df09-5cb4-9548-4b0f4c395d76 | textbox | Batch/Serial Numbers:
aa4a7fb2-9caa-5f52-8999-e3e165f1eab8 | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect substrate to ensure prepared in accordance with design & specifications.
195177ea-ef02-513e-ba70-f0dc82125b2b | note | Attach record of inspection where applicable.
92080ba3-ff4e-5b82-a821-91dd29d1a5ca | section | During Works
7eab99ce-1783-482e-bb49-bb3c37678cbc | checkpoint | Ambient Conditions - Membrane Works
a1eedb97-a785-4e9b-8c82-72bbe2022fe9 | textbox | Record the ambient temperature information during membrane installation:
3de6f4cc-d289-5bac-9482-eadc45465338 | textbox | Record the Commencement date/time of the application:
4e32346e-2e5a-5914-bcc8-46830bb0b127 | textbox | Record the Finish date/time of the application:
1e9df0c4-7089-5c50-ace4-1efb121939a3 | checkpoint | Sealant/Bond Breakers - Confirm applied to all wall/floor and wall/wall junctions as well as around any services penetrations and wall fixings (ie; screw fixings, etc…). Surfaces should be primed prior to application of sealant/bond breakers.
54a0fd2f-1518-50bf-a8a4-0b9b238e0719 | note | Waterproofing Sealant: Nitroseal PU250 or PU400 (Check to ensure gaps not more than 20mm wide/deep for sealant application. Min. fillet of sealant should be 5mm). Bond Breaker: Nitroband Tape (ensure surface primed prior to install and overlapping at joints 150mm each side).
0fdd36de-056f-5765-8fe3-c9f513a54a84 | note | Check to ensure gaps not more than 20mm wide/deep for sealant application. Min. fillet of sealant should be 5mm. Record photos of the installation.
672a239f-90d1-4744-88bd-3a52e2de7be1 | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect priming and sealant/bond breakers to ensure they are installed in accordance with design & specifications.
53046c6e-e9ba-590f-a2d1-73bd81270820 | note | Attach record of inspection where applicable.
49aa3d9d-b632-50d7-9526-3ed84122bd37 | checkpoint | Floor Membrane - Confirm 1x coat of primer (Fosroc Nitroproof 510 - 6hr curing time prior to membrane application) & 2x coats of membrane (Fosroc Nitroproof 750 - requires 16hrs curing time between coats, final coat 36hrs curing time prior to Water Test).
b7856673-7c18-51e6-ba41-b57c6ed2557f | note | Attach progress photos of completed membrane works. Ensure no membrane on top of exposed elements (ie; curtain wall, etc…). Ensure balcony access is barricaded with signage to prevent damage from other trades.
027c4588-7b36-5e3b-af0c-0c9fa7d5975c | checkpoint | Membrane Skirting Upturn - ensure membrane applied 150mm up wall from structural floor level per standards.
88232dcb-f808-52e0-a447-d11f955bd1b1 | checkpoint | Wall Membrane - confirm membrane applied to wall substrate where taps installed (under finishes) and around curtain wall to slab junctions.
fb553774-6bab-5687-b702-c47629beec7c | note | Attach progress photos of completed membrane works.
688443b4-64a0-5344-b18a-a80a5ffc1b61 | section | After Works
d15dfc75-9a37-57bf-8301-5d54386b9db3 | checkpoint | Flood Testing: Block floor waste points & overflows and fill balcony to internal hob height and leave for 24hrs.
5ebf07ee-48f4-5ba4-bee5-89912732e6bb | note | Verify that final coat of membrane has had appropriate curing time (refer curring time notes in ITP above) prior to Flood testing.
d72ddf45-f8d7-5c08-9d18-6b6e2ac3f029 | note | Mark water level at start of flood testing to verify for any leaks/drops in water level. Attach before and after photos with time/date stamps.
317cf292-3992-5f46-a4ad-59882d64e301 | checkpoint | HOLD POINT - verification of Flood Testing Results - Any leaks Found?
d1c5791e-407f-51c0-b95a-0027665c89a0 | textbox | Note: if any leaks identified (if so re-membrane and test)?
a8b871d0-3dae-53c2-af55-7a4caff5a556 | signoff | Contractor to sign-off on flood testing results once passed.
8bd82640-dba8-5aff-b2ca-cf1adf578461 | checkpoint | Attach subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off
aa5dc2c2-0aab-5071-9617-547357f4ceb9 | checklist | Waterproofing - Internal Areas |  | Waterproofing - Internal Areas
6107e48c-eca3-5f07-91e4-be2679c46a44 | section | Prior to Works
11896af9-4810-485d-906b-25de1a547c62 | checkpoint | Product Summary Notes
4d63cdbc-890c-5ef4-8e18-ac56fa361dcf | note | Residential: - WPM 750 sheet membrane to bathroom floors (Primer is CA 750) - WPM 002 liquid membrane to bathroom walls, laundry floors and walls (Primer is WPM 265) Commercial bathrooms: - WPM 002 to floors and walls for retail and commercial amenities (Primer is WPM 265)
8c97525e-9acd-5dec-9911-0defcb005f52 | checkpoint | Substrate - Review to ensure any voids or protrusions are filled and removed and ensure surface is prepared to take membrane (lightly sanded to promote adhesion)
cdb190e7-0edd-5326-ae61-39d1b3113420 | note | Also ensure substrate is clean and free of any water, dust and debris.
85a015df-86fe-594a-83bd-1d3a0a27ab2c | checkpoint | Verify with Plumber that their drainage works are completed prior to membrane commencement.
99b4d606-7467-5edc-9eac-ba1baed4a7db | note | Attach Subcontractor ITP where relevant.
39d89f85-5772-46c5-b6fa-9e469cd88ebf | checkpoint | Confirm that the company/worker installing the membrane is an accredited applicator (ie; for Ardex Products).
7b7f6013-914d-5c31-8b97-11a69398d946 | note | Record Accredited Applicators Details.
f435001a-afea-5481-ab9e-16cce2f58cf7 | checkpoint | Concrete Cracks - Review substrate for any cracking. Up to 2mm cracks fill with Polyurethane sealant. Above 2mm to be chased, cleaned and primed, then sealant applied.
7e061a74-3c14-5ebe-8c19-2d9305e23947 | note | ARDEX WPM 750 Sheet Membrane - damaged concrete sections from 2mm - 30mm to be patched with ARDEX A 46 (curing takes roughly 2 days per 5mm thickness) ARDEX WPM 002 Liquid Membrane - cracks 2mm or less (seal and prime with ARDEX WPM 265 prior to applying membrane). Cracks greater than 2mm (apply bead of neutral cure silicone into the crack and extend 6mm either side, then ensure a piece of 190mm wide ARDEX Deckweb is installed between the WPM 002 membrane layers). This process can also be applied to movement and construction joints.
52027135-68db-5c84-aecc-f57d6fee27f1 | checkpoint | Falls - Review concrete substrate to ensure min. 1:100 falls achieved and falling to floor wastes (1:80 falls in shower area).
6eb4055d-0000-5a69-b942-472452654fb5 | checkpoint | Floor Wastes - Review puddle flange to ensure it is recessed and flush with floor substrate. The PVC flange should be lightly sanded to promote membrane adhersion.
2c14f164-90ff-5f49-bd68-5acad6e82ec1 | note | Also check internal of floor wastes to ensure free from debris prior to waterproofing.
712524e4-2a53-5143-8558-d2fb6acfbed8 | checkpoint | Substrate Moisture Content - Verify that waterproofing contractor has tested moisture content of concrete substrate and is happy to proceed with works (ie; below 5%).
7d0eae13-a207-5936-b0f1-eafcf320e87c | textbox | Record moisture meter reading.
7c376bae-53f2-533a-902f-862246d8d991 | signoff | Subcontractor to sign-off on substrate.
c06b9ba6-a458-504f-abf1-823bbed5f2a0 | checkpoint | Waterstop Angles - Check angles installed in correct position at wet area entry doors and showers.
5d404057-7fcf-5f52-9f72-74f34c532ea2 | note | Also check angles are installed at correct heights based of agreed 1m mark from FFL.
7efc1321-c66a-5c1b-b913-b8eb60633901 | checkpoint | Waterproofing Materials - Confirm approved waterproofing materials are being used for the works.
5c7024eb-7e4c-5fc8-91c3-2a03b7389564 | note | Refer product summary notes at start of ITP.
6c55705c-ab61-5cfc-b210-9de1a66112df | checkpoint | Record product batch/serial numbers for tracking of any future defects.
c99f006d-47b4-5186-9293-839d13199f80 | textbox | Batch/Serial Numbers:
aa4a7fb2-9caa-5f52-8999-e3e165f1eab8 | checkpoint | Membrane Supplier Inspection - Confirm membrane supplier inspection of substrate to ensure prepared in accordance with specification.
89540209-1fad-5648-9dda-381e843dbbd3 | note | Attach record of inspection where applicable.
92080ba3-ff4e-5b82-a821-91dd29d1a5ca | section | During Works
ed652c7a-249a-40f1-a610-bf394e0f1806 | checkpoint | Ambient Conditions - Membrane Works
7fa7c62c-944a-4593-a234-45d46fd916b0 | textbox | Record the ambient temperature information during membrane installation:
5b2166c6-db3d-52bb-a792-a39972e92cf1 | textbox | Record the Commencement date/time of the application:
1cd4fd38-6994-5907-bfe6-6707186d30d2 | textbox | Record the Finish date/time of the application:
21b406cf-265d-42fa-83dc-5dca2187efd6 | checkpoint | Priming Works - Confirm 1x coat of primer applied to approved substrate.
dd20848c-d9bb-5237-8f43-0939edac2661 | note | ARDEX CA 750 (for sheet membranes) - curring time 30min up to 4hrs prior to application of the sheet membrane pending ambient temperature conditions. ARDEX WPM 265 (for liquid membranes) - curring time 30min - 1hr prior to application of the membrane. Plastic PVC pipes should be primed with a solvent based plumbers pink primer.
d1daee1b-1022-5ce0-b4f6-c9525cb979f0 | note | Record Photos of primer installation once completed.
1e9df0c4-7089-5c50-ace4-1efb121939a3 | checkpoint | Sealant/Bond Breakers - Confirm applied to all wall/floor and wall/wall junctions as well as around any services penetrations and wall fixings (ie; screw fixings, etc…). Surfaces should be primed prior to application of sealant/bond breakers.
5608da12-5f95-5f02-88ad-ea553679e412 | note | Waterproofing Sealant: ARDEX ST neutral cure silicone sealant recommended (Where possible, the silicone should be at a 2:1 ratio (width:depth). Width and the depth of the joint should be minimum 5mm. Maximum joint width is 30mm and depth 15mm. For joints greater than 10mm deep a backing rod should be used). Waterproofing Bond Breakers: ARDEX STB/STA Tape (for sheet membranes WPM 750) or ARDEX Deckweb woven cloth reinforcement (for liquid membranes WPM 002) to be installed at floor to wall junctions. 190mm wide ARDEX Deckweb strip to be installed between first and second coats.
408a3379-65df-5bf1-9e54-ddc2248550ba | note | Record Photos of Sealant/Bond Breaker installation once completed.
d3baa309-8851-470c-989f-693faa36fe9f | checkpoint | HOLD POINT INSPECTION - Organise membrane consultants, regulated designer (FJC), membrane suppliers or PCA to inspect priming and sealant/bond breakers to ensure they are installed in accordance with design & specifications.
b43b5af4-b0d6-5410-bed0-fd2198876152 | note | Attach record of inspection where applicable.
cac60b72-5534-5c96-85ae-faf2f1d817bd | checkpoint | Floor Membrane Works (Sheet Membrane - WPM 750) - Ensure installed in accordance with manufacturers specifications:
ac9686cc-2586-5384-b331-dc5d7a675b3e | tickbox | Ensure sheets are overlapping on all ends min. 40mm
d1333f64-65d1-51d5-bca1-c544390fd3fd | tickbox | Ensure sheets are extended up walls min. 150mm above FFL (ie; overall approx. 200mm).
10740b6c-1820-50e3-81f9-4171fac103c0 | tickbox | Ensure there are no air pockets trapped below the membrane.
3e1aac82-a6b5-5a50-bad4-b090d7e81217 | tickbox | Ensure there is no membrane on top of exposed floor angles.
3dcc9f1d-29ad-5ed6-9454-30c3f1802e6c | tickbox | Ensure Membrane has cured for min. 1hr post installation before water testing/tiling.
a95c6670-e264-5499-9c1c-4cac62bf1d0f | note | Attach progress photos of completed membrane works. Ensure doorway is barricaded with signage to prevent damage from other trades.
eccda97a-14df-45b3-a49a-211db8924e1f | checkpoint | Floor Membrane Works (Liquid Membrane - WPM 002) - Ensure installed in accordance with manufacturers specifications:
9f6c1413-a37a-53fd-9e56-097618cf571f | tickbox | Ensure 2x coats of membrane applied to floors - 2hrs curring time between coats.
61303b9d-09c9-5367-8d66-2982f8fcc2af | tickbox | Ensure membrane extends up walls at least 100mm above FFL (ie; overall approx 150mm).
6113381c-9fc9-5e8d-a488-001f855d3913 | tickbox | Ensure there is no membrane on top of exposed floor angles.
5db33667-6583-5b97-b7f0-4c1fb4d136b8 | tickbox | Ensure 1st and 2nd coats of membrane are applied in opposite directions.
94827995-a86b-5070-b2c9-7bc5da1c9a70 | tickbox | Ensure membrane has cured for min. 48hrs post installation before water testing/tiling.
20f2e454-f35f-57ba-8fcf-dcc78c48a527 | note | Attach progress photos of completed membrane works. Ensure doorway is barricaded with signage to prevent damage from other trades.
d757db58-9b35-5be3-b59d-0a53aae43614 | checkpoint | Wall Membrane Works (Liquide Membrane - WPM 002) - Ensure installed in accordance with manufactures specifications:
768c4c63-1837-5ed7-880c-f005a6011367 | tickbox | Confirm wall membrane applied to whole shower area (at least 100mm above shower rose or full height of wall if ceiling mounted rose), around bath and basin areas.
09734480-a41a-5e62-a298-80c5be4edeb5 | tickbox | Confirm ARDEX STB/STA Tape installed at junction of sheet and liquid membrane if lapping these products.
57f15cc6-49da-5ed0-954c-5ff42cd743ea | tickbox | Ensure there is no membrane on hardware or fixtures.
b681cd9e-3ee3-5cc1-a1ee-9978ee5b0027 | tickbox | Ensure all gaps around wall penetrations are sealed and membraned appropriately.
9af588be-730b-582a-9973-9ff15451cd17 | note | Attach progress photos of completed membrane works.
688443b4-64a0-5344-b18a-a80a5ffc1b61 | section | After Works
2c3764a5-6602-57da-af17-349b6ac0a4fb | checkpoint | Flood Testing: Block floor waste points and fill room to door angle height and leave for 24hrs.
20016548-2d23-5440-93ba-4df48fab1113 | note | Verify that final coat of membrane has had appropriate curing time (refer curring time notes in ITP above) prior to Flood testing.
ab2fa52c-3e08-578f-a092-d87ec0e2b90e | note | Mark water level at start of flood testing to verify for any leaks/drops in water level. Attach before and after photos with time/date stamps.
317cf292-3992-5f46-a4ad-59882d64e301 | checkpoint | HOLD POINT - verification of Flood Testing Results - Any leaks Found?
b66d49bd-0563-5fc7-a413-f8ff393fdd19 | textbox | Note: if any leaks identified (if so re-membrane and test)?
a8b871d0-3dae-53c2-af55-7a4caff5a556 | signoff | Contractor to sign-off on flood testing results once passed.
8bd82640-dba8-5aff-b2ca-cf1adf578461 | checkpoint | Attach subcontractor ITP
09496d4b-7c1e-50f7-b5b3-7fe52f116dcb | section | Sign-off
ceec1c63-78e7-5b83-b841-d903548d7bea | checkpoint | Subcontractor Signoff
f5424f77-4a2a-59de-bc6a-11448aeb35d0 | signoff | Subcontractor Sign-off
ff3117c3-1ec6-5da4-84fc-07cee5c69768 | checkpoint | SDC Signoff
0bf5781f-1f36-5f62-afcd-715ce5ae2dda | signoff | SDC Sign-off