## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
311e7fae-cf06-444f-984e-307e1a5006e7 | checklist | Apartment Finishes ITP | itp | Apartment Finishes
cb835373-39b5-47a2-93b7-9bf739acede8 | section | Timber Floor
bd7e501b-6c2e-405a-9ce5-470884b35d86 | checkpoint | Measure Floor to Ceiling Height to ensure correct build up.
fb80a914-69e8-5ffc-be99-a69885031e36 | note | *Spot Check throughout apartment*
1c03eab3-da38-4353-9105-0f7a0e3ce520 | checkpoint | Ensure Acoustic Underlay has been installed.
e618ce75-f31f-4da8-912c-41ad7f29fd39 | checkpoint | Ensure Correct Setout
| note | *Refer to the architectural floor finishes plan*
1bf00e06-8d08-4ea7-a56a-6a3fa3d6dce1 | checkpoint | Ensure boards being installed are the correct colour scheme.
db75fdc7-b4a1-5e04-9435-b745d4694fa6 | textbox | List colour scheme and board colour:
e6218425-8a4c-4dc8-a23e-d97f2901a361 | checkpoint | Check any expantion joints have been installed in the correct location.
0664709d-8d04-46af-8756-ee658573400b | checkpoint | Check any purchaser upgrades have been installed
| note | *Refer to the room data sheet*
2d6915c5-3a54-488c-ba70-16f28d4bd219 | checkpoint | Ensure finished floor surface in within Mamimum deviation torerance.
1ea705f4-6536-5857-b164-d71ed3d219d1 | note | *3mm from a 3m staightedge laid in any direction*
5190ba9a-dcf0-442f-b3e4-bdd6cdadeb35 | checkpoint | Ensure threshold Setout is correct at all door ways.
29d37f5d-4d78-404b-a746-8aa8e3a6b73a | checkpoint | Ensure even distribution of board colour tones throughout apartment.
73e37ff7-4afb-4f6a-a545-344ec4c3e3f7 | checkpoint | Ensure Angles have been installed as per plans
f122ef0f-617c-47ac-91b6-db0ca4fd4f3c | checkpoint | Ensure correct caulking colour has been used, and confirm caulking has been installed in required locations.
876d53b6-3297-43cb-80fd-4b42d1171ca5 | checkpoint | Record product batch/serial number for tracking of any future defects
5501c17d-68bf-444c-a158-64b84fe06683 | checkpoint | Record photos of floor
59b40eec-8172-4e0c-a878-e2437fff145c | section | Carpet
d871dd14-3eb2-4280-b871-42268541091c | checkpoint | Ensure Acoustic Underlay has been installed.
97826c27-b86c-4b4f-9e2f-7f5f2f032768 | checkpoint | Confirm correct carpet colour has been installed
| checkpoint | Ensure any purchaser upgrades have been installed.
| note | *Refer to the room data sheet*
3e7dc61b-3d63-401f-8460-52c00515eebe | checkpoint | Ensure carpet seams have been installed neatly and in corrrect locations as per plans.
a749473f-277e-4056-b196-183bad590090 | checkpoint | Ensure Carpet levels at door thresholds.
d2d5ed96-8908-481c-8aef-04cb1e28f14c | checkpoint | Check for any imperfections in the carpet
103bd739-4a89-5868-9543-5516be88eb0a | note | *Including any ruff spots in the under the carpet*
| checkpoint | Attach contractor ITP
d2a6f37f-e385-4687-974a-a6329a1da32e | checkpoint | Record Photos of Carpet
ac4dede5-2298-4014-a528-682af129b0ca | section | Skirting
12b6307c-63fb-41eb-9391-eb317b46c989 | checkpoint | Confirm all Skirting is installed as per plans
| note | *Skirting should be installed on every plasterboard wall*
944f79b9-5a03-4fc2-8708-9f6750729e31 | checkpoint | Ensure all skirting intersection are neat
50a1a9ef-cb13-494d-a47d-af28e9b7e0e0 | checkpoint | Ensure there are not visible joints in skirting
68f6f00a-6167-487e-8b14-30f1b860224f | checkpoint | Ensure caulking under skirting is neat to the floor.
2a529e82-7f3c-48bf-9f39-b4980911efba | checkpoint | Ensure skirting rebate is cleanly installed
99d4fc36-1d83-4004-be4b-d496f34f4277 | checkpoint | Ensure there's no bowing in the skirting
25404baa-b8f6-451d-aa5a-258af258f069 | checkpoint | Confirm skirting is installed with correct gap for expanation joint (2-3mm)
| note | *Only if expanition joint is required*
| checkpoint | Attach contractor ITP
0ad09607-c096-49b4-9897-5a3b1b14c5a5 | checkpoint | Record photos of skirting
af164ea8-adee-46ab-82e4-28a25dacdd21 | section | Paint
7be47d7c-476a-4f55-b5b1-29ff34d9ff8f | checkpoint | Ensure wall substrate is set and sanded correctly
042faa81-e95b-409d-b702-b8a66caf1fce | checkpoint | Ensure paint colour is correct in each area
dde98014-2c58-41bc-8588-061e2aaeeea5 | checkpoint | Ensure paint is the correct finish
| note | *Refer to Achitectural Schedule and sample Sign offs"
f4a16ae4-89a7-4fbf-9740-572bf46b3689 | checkpoint | Check that black paint has been appied to required areas. i.e behind bulkhead grills
| note | *i.e. Behind bulkhead grills*
cb1e51fc-7e1d-4b4f-95d1-f9cf838aa8de | checkpoint | Check to ensure 5 class wall were installed to area's exposed to direct sunlight.
b327b49c-a6e2-478b-abed-00cc95f64c28 | checkpoint | Ensure top's and bottoms of doors in wet areas have been painted.
4f1ec874-8307-461d-8c6c-39c8137bfcda | checkpoint | Confirm there is no paint on other elements
| note | i.e. Windows, Door Frames, Lights, Switches, Joinery etc.
76a816c3-4fd5-4705-b2ab-896ef7b61639 | checkpoint | Ensure there are no divots in paint
1ba1f4bb-9b9f-4f6d-ad0c-e8d0450c9e46 | checkpoint | Ensure there are no visible brush strokes
04c14baa-3160-4514-8358-091c95597a26 | checkpoint | Confirm all required coats have been applied
| checkpoint | Attach Contractor ITP
ad31ab40-e273-4614-aa7e-c72c625a57f3 | checkpoint | Record Photos of Painted Walls
43a235d6-77c7-43d6-97fd-4ce2fde9fdf7 | section | Fixtures and Fittings
| checkpoint | Ensure all Fittings and Fixtures are installed as per architectural Plans
| note | * Refer to Architectural RCP, Bathroom/Kitchen Elevations.*
| radio | Laundry | Yes,No,N/A
| radio | Bathroom | Yes,No,N/A
| radio | Kitchen | Yes,No,N/A
| radio | Bedroom | Yes,No,N/A
| radio | Dining/Living | Yes,No,N/A
| checkpoint | Confirm any functional Fixtures/ Fittings are in working order
| radio | Laundry | Yes,No,N/A
| radio | Bathroom | Yes,No,N/A
| radio | Kitchen | Yes,No,N/A
| radio | Bedroom | Yes,No,N/A
| radio | Dining/Living | Yes,No,N/A
| checkpoint | Confirm correct quantities of all Fittings and Fixtures have been installed.
| note | *Reference Architectual RCP for Quanities*
| radio | Laundry | Yes,No,N/A
| radio | Bathroom | Yes,No,N/A
| radio | Kitchen | Yes,No,N/A
| radio | Bedroom | Yes,No,N/A
| radio | Dining/Living | Yes,No,N/A
| checkpoint | Confirm all fittings and Fixtures are the correct colour/ Finish.
| note | *Refer to Achitectual Schedule for each scheme, as well as any Purchaser Varitions*
| radio | Laundry | Yes,No,N/A
| radio | Bathroom | Yes,No,N/A
| radio | Kitchen | Yes,No,N/A
| radio | Bedroom | Yes,No,N/A
| radio | Dining/Living | Yes,No,N/A
| checkpoint | Record Photos of all Fitting and Fixtures
ff2ea0cc-e264-4242-a59a-b25d699fc8e4 | section | Sign-off
fd646ac6-dbc5-4836-8fea-56180f2158d1 | checkpoint | Subcontractor Signoff
45dd68cd-0c70-433c-8347-7b86ea54e951 | signoff | Subcontractor Sign-off
a210f335-9ce2-4431-bafb-004b8828aaac | checkpoint | SDC Signoff
7bb4578f-1506-485d-8fbb-bedcf462ddef | signoff | SDC Sign-off