## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Apartment Finishes | itp |  |  |  |  | Apartment Finishes ITP
section | Timber Floor
checkpoint | Measure Floor to Ceiling Height to ensure correct build up.
label | *Spot Check throughout apartment*
checkpoint | Ensure Acoustic Underlay has been installed.
checkpoint | Ensure Correct Setout
checkpoint | Ensure boards being installed are the correct colour scheme.
textbox | List colour scheme and board colour:
checkpoint | Check any expantion joints have been installed in the correct loction.
checkpoint | Check any purchaser upgrades have been installed
checkpoint | Ensure finished floor surface in within Mamimum deviation torerance.
label | *3mm from a 3m staightedge laid in any direction*
checkpoint | Ensure threshold Setout is correct at all door ways.
checkpoint | Ensure even distribution of board colour tones throughout apartment.
checkpoint | Ensure Angles have been installed as per plans
checkpoint | Ensure correct caulking colour has been used, and confirm caulking has been installed in required locations.
checkpoint | Record product batch/serial number for tracking of any future defects
textbox | Batch/Serial Numbers:
checkpoint | Record photos of floor
section | Carpet
checkpoint | Ensure Acoustic Underlay has been installed.
checkpoint | Confirm correct carpet colour has been installed
checkpoint | Ensure carpet seams have been installed neatly and in corrrect locations as per plans.
checkpoint | Ensure Carpet levels at door thresholds.
checkpoint | Check for any imperfections in the carpet
label | *Including any ruff spots in the under the carpet*
checkpoint | Record Photos of Carpet
section | Skirting
checkpoint | Confirm all Skirting is installed as per plans
checkpoint | Ensure all skirting intersection are neat
checkpoint | Ensure there are not visible joints in skirting
checkpoint | Ensure caulking under skirting is neat to the floor.
checkpoint | Ensure skirting rebate is cleanly installed
checkpoint | Ensure there's no bowing in the skirting
checkpoint | Confirm skirting is installed with correct gap for expanation joint (2-3mm) - Only if expanition joint is required.
checkpoint | Record photos of skirting
section | Paint
checkpoint | Ensure wall substrate is set and sanded correctly
checkpoint | Ensure paint colour is correct in each area
checkpoint | Ensure paint is the correct finish
checkpoint | Check that black paint has been appied to required areas. i.e behind bulkhead grills
checkpoint | Check to ensure 5 class wall were installed to area's exposed to direct sunlight.
checkpoint | Ensure top's and bottoms of doors in wet areas have been painted.
checkpoint | Confirm there is no paint on other elements
checkpoint | Ensure there are no divots in paint
checkpoint | Ensure there are no visible brush strokes
checkpoint | Confirm all required coats have been applied
checkpoint | Record Photos of Painted Walls
section | Fixtures and Fittings
checkpoint | Laundry, Bathroom, Kitchen
checkpoint | Ensure all Fittings and Fixtures are installed as per architectural Plans
label | * Refer to Architectural RCP, Bathroom/Kitchen Elevations.*
bool | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
checkpoint | Confirm any functional Fixtures/ Fittings are in working order
bool | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
checkpoint | Confirm correct quantities of all Fittings and Fixtures have been installed as per architectural RCP drawings
bool | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
checkpoint | Confirm all fittings and Fixtures are the correct colour/ Finish.
bool | Laundry, Bathroom, Kitchen, Bedrooms, Dining/Living Room
section | Sign-off
checkpoint | Subcontractor Signoff
holdpoint | Subcontractor Sign-off
checkpoint | SDC Signoff
holdpoint | SDC Sign-off
checklist | Joinery & Stone | itp |  |  |  |  | Joinery & Stone - ITP
section | Kitchen Butler’s Pantry
checkpoint | Shop Drawing (overarching)
label | Attach latest revision of approved shop drawings
checkpoint | Colour scheme
button | Correct colour scheme installed | Yes,No
checkpoint | Visual finish check
button | Free of damages, chips, or defects to veneers & panels | Yes,No
button | Even spacing observed in shadowlines | Yes,No,N/A
button | LED/reed switch installed in nominated locations on shop drawings | Yes,No,N/A
label | Ensure correct anxiliary fittings are installed
bool | Cutlery drawer
bool | Bins
button | Correct spec of handles are installed | Yes,No,N/A
checkpoint | Doors/drawers/compartments
button | Arrangement as per approved shop drawing | Yes,No
button | Dimensions of doors/drawers/compartments as per shop drawings | Yes,No
button | Internal colour as per approved shop drawing | Yes,No
button | Correctly aligned and square | Yes,No
label | Note: Tolerances from Architectural Spec
label | — Plumb and level 1:800
label | — Offsets in flush adjoining surfaces 0.5mm
label | — Alignment of adjoining doors 0.5mm
label | — Difference in scribe thickness for joinery items centred between walls 2mm
label | — Doors centred in openings 0
label | — Joints in finished surfaces 0
button | Doors/drawer hardware operating smoothly as intended | Yes,No
button | Check required access panels are incorporated | Yes,No,N/A
checkpoint | Appliance
label | Correct appliance models installed as per room data sheet
bool | Fridge
bool | Cooktop
bool | Microwave
bool | Wine fridge
bool | Dish washer
bool | Rangehood
bool | Oven
button | Appliance fitting correctly in designated compartment | Yes,No
button | Appliance free of defects, chips & scratches | Yes,No
checkpoint | Stone benchtop & splashback
button | Correct stone type installed | Yes,No
button | Stone level/square | Yes,No
button | Joints neatly caulked | Yes,No
button | Check exposed edges of all porcelin stone is polished | Yes,No
button | No cracks and chips | Yes,No
button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
checkpoint | Island bench stone
button | Correct stone type installed | Yes,No,N/A
button | Stone level/square | Yes,No,N/A
button | Joints neatly caulked | Yes,No,N/A
button | GPO cutout completed with even gap all around | Yes,No,N/A
button | Shadowline detail completed with even gaps all around | Yes,No,N/A
button | Sink & setdown dimensions as per approved shop drawings | Yes,No,N/A
button | No cracks and chips | Yes,No,N/A
button | Check top edge of joinery panels aligns with stone rebate | Yes,No,N/A
button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
button | For benches over 3m, check the joint is in the correct location as per approved shop drawings | Yes,No,N/A
checkpoint | PVR
button | Purchaser request implemented | Yes,No,N/A
checkpoint | Photos
label | Attach photos of completed joinery/stone at time of inspection
section | Wardrobe
checkpoint | Colour scheme
button | Correct colour scheme installed | Yes,No
checkpoint | Visual finish check
button | Free of damages, chips, or defects to veneers & panels | Yes,No
button | Even spacing observed in shadowlines | Yes,No,N/A
button | LED/reed switch installed in nominated locations | Yes,No,N/A
button | Glass shelves free of scratches/defects | Yes,No,N/A
button | Correct felt is installed in jewelery module | Yes,No,N/A
button | Correct spec of handles are installed | Yes,No,N/A
checkpoint | Doors/drawers/compartments
button | Arrangment as per approved shop drawing | Yes,No
button | Internal colour as per approved shop drawing | Yes,No
button | Correctly aligned and square | Yes,No
label | Note: Tolerances from Architectural Spec
label | — Plumb and level 1:800
label | — Offsets in flush adjoining surfaces 0.5mm
label | — Alignment of adjoining doors 0.5mm
label | — Difference in scribe thickness for joinery items centred between walls 2mm
label | — Doors centred in openings 0
label | — Joints in finished surfaces 0
button | Doors/drawer hardware operating smoothly as intended | Yes,No
button | Hanging rails securely installed with correct spacing | Yes,No
button | Check access panels are installed in correct location | Yes,No
checkpoint | PVR
button | Purchaser request implemented | Yes,No,N/A
checkpoint | Photos
label | Attach photos of completed joinery at time of inspection
section | Storage
checkpoint | Colour scheme
button | Correct colour scheme installed | Yes,No
checkpoint | Visual finish check
button | Free of damages, chips, or defects to veneers & panels | Yes,No
button | Even spacing observed in shadowlines | Yes,No,N/A
button | LED/reed switch installed in nominated locations | Yes,No,N/A
button | Correct spec of handles are installed | Yes,No,N/A
checkpoint | Doors/drawers/compartments
button | Arrangment as per approved shop drawing | Yes,No
button | Internal colour as per approved shop drawing | Yes,No
button | Correctly aligned and square | Yes,No
label | Note: Tolerances from Architectural Spec
label | — Plumb and level 1:800
label | — Offsets in flush adjoining surfaces 0.5mm
label | — Alignment of adjoining doors 0.5mm
label | — Difference in scribe thickness for joinery items centred between walls 2mm
label | — Doors centred in openings 0
label | — Joints in finished surfaces 0
button | Doors/drawer hardware operating smoothly as intended | Yes,No
button | Vent grille neatly installed | Yes,No
checkpoint | PVR
button | Purchaser request implemented | Yes,No,N/A
checkpoint | Photos
label | Attach photos of completed joinery at time of inspection
section | Bathroom
checkpoint | Colour scheme
button | Correct colour scheme installed | Yes,No
checkpoint | Visual finish check
button | Free of damages, chips, or defects to veneers/panels/mirror | Yes,No
button | Even spacing observed in shadowlines | Yes,No,N/A
button | No distortion in mirror | Yes,No,N/A
button | Check GPO/thermostat is installed in the correct location | Yes,No,N/A
checkpoint | Doors/drawers/compartments
button | Arrangment as per approved shop drawing | Yes,No
button | Internal colour as per approved shop drawing | Yes,No
button | Correctly aligned and square | Yes,No
label | Note: Tolerances from Architectural Spec
label | — Plumb and level 1:800
label | — Offsets in flush adjoining surfaces 0.5mm
label | — Alignment of adjoining doors 0.5mm
label | — Difference in scribe thickness for joinery items centred between walls 2mm
label | — Doors centred in openings 0
label | — Joints in finished surfaces 0
button | Doors/drawer hardware operating smoothly as intended | Yes,No
checkpoint | Stone Vanity Top
button | Correct stone type installed | Yes,No
button | Stone level/square | Yes,No
button | Joints neatly caulked | Yes,No
button | No cracks and chips | Yes,No
checkpoint | PVR
button | Purchaser request implemented | Yes,No,N/A
checkpoint | Photos
label | Attach photos of completed joinery at time of inspection
section | Laundry
checkpoint | Colour scheme
button | Correct colour scheme installed | Yes,No
checkpoint | Visual finish check
button | Free of damages, chips, or defects to veneers & panels | Yes,No
button | Even spacing observed in shadowlines | Yes,No,N/A
checkpoint | Doors/drawers/compartments
button | Arrangement as per approved shop drawing | Yes,No
button | Internal colour as per approved shop drawing | Yes,No
button | Correctly aligned and square | Yes,No
label | Note: Tolerances from Architectural Spec
label | — Plumb and level 1:800
label | — Offsets in flush adjoining surfaces 0.5mm
label | — Alignment of adjoining doors 0.5mm
label | — Difference in scribe thickness for joinery items centred between walls 2mm
label | — Doors centred in openings 0
label | — Joints in finished surfaces 0
button | Doors/drawer hardware operating smoothly as intended | Yes,No
button | Check 20mm undercut under the door | Yes,No,N/A
checkpoint | Appliance
label | Correct washer/dryer model installed
bool | Washer
bool | Dryer
checkpoint | Stone benchtop
button | Correct stone type installed | Yes,No
button | Stone level/square | Yes,No
button | Joints neatly caulked | Yes,No
button | Check exposed edges of all porcelin stone is polished | Yes,No
button | No cracks and chips | Yes,No
button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
checkpoint | PVR
button | Purchaser request implemented | Yes,No,N/A
checkpoint | Photos
label | Attach photos of completed joinery at time of inspection
section | PVR Joinery Items
checkpoint | PVR Joinery Items
button | Additional PVR joinery elements within this apartment? | Yes,No
textbox | If Y, expand to selection below:
checkpoint | Shop Drawing (overarching)
label | Attach latest revision of approved shop drawings
checkpoint | Colour scheme
button | Correct colour scheme installed | Yes,No
checkpoint | Visual finish check
button | Free of damages, chips, or defects to veneers & panels | Yes,No
button | Even spacing observed in shadowlines | Yes,No,N/A
button | LED/reed switch installed in nominated locations on shop drawings | Yes,No,N/A
button | Ensure correct anxiliary fittings are installed | Yes,No,N/A
checkpoint | Doors/drawers/compartments
button | Arrangement as per approved shop drawing | Yes,No
button | Dimensions of doors/drawers/compartments as per shop drawings | Yes,No
button | Internal colour as per approved shop drawing | Yes,No
button | Correctly aligned and square | Yes,No
label | Note: Tolerances from Architectural Spec
label | — Plumb and level 1:800
label | — Offsets in flush adjoining surfaces 0.5mm
label | — Alignment of adjoining doors 0.5mm
label | — Difference in scribe thickness for joinery items centred between walls 2mm
label | — Doors centred in openings 0
label | — Joints in finished surfaces 0
button | Doors/drawer hardware operating smoothly as intended | Yes,No,N/A
button | Check required access panels are incorporated | Yes,No,N/A
checkpoint | Appliance
button | Correct appliance models installed as per room data sheet | Yes,No,N/A
button | Appliance fitting correctly in designated compartment | Yes,No,N/A
button | Appliance free of defects, chips & scratches | Yes,No,N/A
checkpoint | Stone
button | Stone elements part of PVR joinery? | Yes,No
textbox | If Y, expand selection below:
checkpoint | Stone
button | Correct stone type installed | Yes,No,N/A
button | Stone level/square | Yes,No,N/A
button | Joints neatly caulked | Yes,No,N/A
button | Check exposed edges of all porcelin stone is polished | Yes,No,N/A
button | No cracks and chips | Yes,No,N/A
button | Check fixtures & fittings recessed or fixed to stone is installed in correct location | Yes,No,N/A
checkpoint | Photos
label | Attach photos of completed joinery/stone at time of inspection