## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Prestart Inspections
section | Details
checkpoint | Site has been cleaned in advance of our arrival on site
checkpoint | Walls are plumb and level
label | IMPORTANT
checkpoint | Tiling works running to programme - prior trades completed
checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
checkpoint | Data sheets, of products, are supplied on site with TA's
checkpoint | Inductions completed & Site Inspection checklist has been completed
checkpoint | All tools tagged and tested - (photo's required)
checkpoint | Tiler has current site safe - Input number and expiry
checkpoint | Tiler has correct PPE relevant to project.
checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
checklist | QA - Wall/Floor Preparation
section | Wall/Floor Preparation
checkpoint | Is the area clean, and cleared, ready for necessary preparation
checkpoint | Are flanges installed at correct depth in accordance with specified wastes
checkpoint | Has screeding been completed to shower at correct height and falls with correct product
checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
checkpoint | Floor levelling completed and applied as per requirements. (m2 rate) - if required
checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate) - If required
checkpoint | Supply & Fit Coraltread mat to the above area - if required
checklist | QA - Waterproofing
section | Waterproofing
checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
checkpoint | Gaskets have been installed to floor flange and wall plumbing fittings
checkpoint | Correct waterproofing is supplied as per project specification.
checkpoint | Waterproofing coat # 1 applied to floors and skirting (take photos) - Mapelastic Smart
checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
checkpoint | Flood tests, if required, undertaken and photos provided.
checklist | QA - Tiling Installation - WC
section | Tiling to floors and walls
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install tiles to floors as per drawings
checkpoint | Install skirting tiles as per drawings
checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
checkpoint | Install tiles to walls as per drawings
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | QA - Other Information
section | Other Information
checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
checkpoint | change of details and or instructions
checkpoint | Site specific details to be added
checkpoint | Material Details - Notes to be added of materials used on site
checkpoint | SSSP/TA forms attached
checklist | QA - Demo Works
section | Demo Works
checkpoint | Uplift and place in bin existing lobby tiles
checkpoint | Area left clean & tidy