## Sheet1
Id | Type | Name | Values | Prompting Name
| checklist | QA - Floor Vinyl |  | QA - Floor Vinyl
| section | PRIOR TO COMMENCEMENT
| checkpoint | Manufacturer's specifications on hand and consulted for substrate acceptance and installation instructions.
| checkpoint | Climate conditions and positioning of climate-altering services checked for compatibility as per manufacturer's specifications and NZS 1884:2013.
| checkpoint | Substrate is suitably clean and stable
| checkpoint | Curing/seasoning of substrate checked for compatibility as per manufacturer's specifications.
| checkpoint | Substrate is flat within a deviation of 6.0mm under a 3000mm straight edge laid in any direction.
| checkpoint | Substrate is smooth within a deviation of 1.0mm under a 150mm straight edge laid in any direction
| checkpoint | Relative humidity of subfloor measured as 75% or lower by hygrometer test.
| checkpoint | Setout planned prior to laying; per NZS 1884:2013, continuous lengths minimizing cross joins in the body of the area
| checkpoint | Walls plastered to a suitable standard to receive coved vinyl / wall vinyl / CBS
| checkpoint | Material prepared to be laid in a single floor, and of a single specified type, quality, colour and design, is from one manufacturing batch and dye lot.
| checkpoint | Confirm that permanent partitions have been installed before starting vinyl installation. Seek approval from the Main Contractor
| section | DURING WORKS
| checkpoint | Heated and rolled, seams welded and trimmed as per manufacturer's specifications.
| checkpoint | Primer shall be used where recommended by the adhesive manufacturer and shall be allowed to dry thoroughly before applying adhesive.
| checkpoint | Adhesive: Spread evenly, pressing down firmly and rolling (if recommended) to ensure full contact and a good bond overall. Remove surplus from exposed faces
| checkpoint | Adhesive systems protected from traffic for 24 hours after installation, if recommended by the manufacturer
| checkpoint | 30mm wide movement joints provided over structural joints and at junctions between different substrates.
| checkpoint | Edge cover strips provided at junctions with different finishes and to exposed edges.
| checkpoint | Where different floor covering abut at doorways where there is a fitted door, the junction is within the thickness of the closed door.
| checkpoint | Seams and cross-joins in homogenius vinyl should be thermo welded with matching weld rod.
| checkpoint | Fixing method as per manufacturer's specifications.
| checkpoint | Area examined for lumps, tightness and air pockets.
| checkpoint | Junctions scribed neatly up to returns, edges, fixtures and fittings.
| section | SIGNOFF
| checkpoint | Supervisor Signoff
| signoff | SIGN HERE / REQUEST SIGNOFF
| checkpoint | Main Contractor Signoff
| signoff | SIGN HERE / REQUEST SIGNOFF