## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QA - Floor Vinyl
section | PRIOR TO COMMENCEMENT
checkpoint | Manufacturer's specifications on hand and consulted for substrate acceptance and installation instructions.
checkpoint | Climate conditions and positioning of climate-altering services checked for compatibility as per manufacturer's specifications and NZS 1884:2013.
checkpoint | Substrate is suitably clean and stable
checkpoint | Curing/seasoning of substrate checked for compatibility as per manufacturer's specifications.
checkpoint | Substrate is flat within a deviation of 6.0mm under a 3000mm straight edge laid in any direction.
checkpoint | Substrate is smooth within a deviation of 1.0mm under a 150mm straight edge laid in any direction
checkpoint | Relative humidity of subfloor measured as 75% or lower by hygrometer test.
checkpoint | Setout planned prior to laying; per NZS 1884:2013, continuous lengths minimizing cross joins in the body of the area
checkpoint | Walls plastered to a suitable standard to receive coved vinyl / wall vinyl / CBS
checkpoint | Material prepared to be laid in a single floor, and of a single specified type, quality, colour and design, is from one manufacturing batch and dye lot.
checkpoint | Confirm that permanent partitions have been installed before starting vinyl installation. Seek approval from the Main Contractor
section | DURING WORKS
checkpoint | Heated and rolled, seams welded and trimmed as per manufacturer's specifications.
checkpoint | Primer shall be used where recommended by the adhesive manufacturer and shall be allowed to dry thoroughly before applying adhesive.
checkpoint | Adhesive: Spread evenly, pressing down firmly and rolling (if recommended) to ensure full contact and a good bond overall. Remove surplus from exposed faces
checkpoint | Adhesive systems protected from traffic for 24 hours after installation, if recommended by the manufacturer
checkpoint | 30mm wide movement joints provided over structural joints and at junctions between different substrates.
checkpoint | Edge cover strips provided at junctions with different finishes and to exposed edges.
checkpoint | Where different floor covering abut at doorways where there is a fitted door, the junction is within the thickness of the closed door.
checkpoint | Seams and cross-joins in homogenius vinyl should be thermo welded with matching weld rod.
checkpoint | Fixing method as per manufacturer's specifications.
checkpoint | Area examined for lumps, tightness and air pockets.
checkpoint | Junctions scribed neatly up to returns, edges, fixtures and fittings.
section | SIGNOFF
checkpoint | Supervisor Signoff
signoff | SIGN HERE / REQUEST SIGNOFF
checkpoint | Main Contractor Signoff
signoff | SIGN HERE / REQUEST SIGNOFF
checklist | QA - Wall Vinyl
section | PRIOR TO COMMENCEMENT
checkpoint | Manufacturer's specifications on hand and consulted for substrate acceptance and installation instructions.
checkpoint | Climate conditions and positioning of climate-altering services checked for compatibility as per manufacturer's specifications and NZS 1884:2013.
checkpoint | Substrate is suitably clean and stable
checkpoint | Curing/seasoning of substrate checked for compatibility as per manufacturer's specifications.
checkpoint | Substrate is flat within a deviation of 6.0mm under a 3000mm straight edge laid in any direction.
checkpoint | Substrate is smooth within a deviation of 1.0mm under a 150mm straight edge laid in any direction
checkpoint | Relative humidity of subfloor measured as 75% or lower by hygrometer test.
checkpoint | Setout planned prior to laying; per NZS 1884:2013, continuous lengths minimizing cross joins in the body of the area
checkpoint | Walls plastered to a suitable standard to receive coved vinyl / wall vinyl / CBS
checkpoint | Material prepared to be laid in a single floor, and of a single specified type, quality, colour and design, is from one manufacturing batch and dye lot.
checkpoint | Confirm that permanent partitions have been installed before starting vinyl installation. Seek approval from the Main Contractor
section | DURING WORKS
checkpoint | Heated and rolled, seams welded and trimmed as per manufacturer's specifications.
checkpoint | Primer shall be used where recommended by the adhesive manufacturer and shall be allowed to dry thoroughly before applying adhesive.
checkpoint | Adhesive: Spread evenly, pressing down firmly and rolling (if recommended) to ensure full contact and a good bond overall. Remove surplus from exposed faces
checkpoint | Adhesive systems protected from traffic for 24 hours after installation, if recommended by the manufacturer
checkpoint | 30mm wide movement joints provided over structural joints and at junctions between different substrates.
checkpoint | Edge cover strips provided at junctions with different finishes and to exposed edges.
checkpoint | Seams and cross-joins in homogenius vinyl should be thermo welded with matching weld rod.
checkpoint | Fixing method as per manufacturer's specifications.
checkpoint | Area examined for lumps, tightness and air pockets.
checkpoint | Junctions scribed neatly up to returns, edges, fixtures and fittings.
section | SIGNOFF
checkpoint | Supervisor Signoff
signoff | SIGN HERE / REQUEST SIGNOFF
checkpoint | Main Contractor Signoff
signoff | SIGN HERE / REQUEST SIGNOFF