## CCTV Bases
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
CCTV Tower Bases |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
CCTV Bases
Design |  | PS1 design for CCTV bases | UCCL/MEL | Prior to construction | PS1 design approval by Meridian | S | R
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing hardfill/site concrete | Scala achieves minimum 3 blows per 100mm | W | W
Formwork |  | Visual inspection | UCCL | Prior to placing concrete | Dimensional check completed and within tolerances. Formwork installed inspected as being suitable for pouring concrete. | H | W
Steel Reinforcing |  | Visual inspection | UCCL | Prior to placing concrete | Steel installed as per IFC drawings. Grade of steel as specified. Number, size and spacing of bars as per IFC drawings. | H | W
Post Pour Inspection |  | Visual inspection | UCCL | Following placement of concrete | Post pour inspection sheet to be completed Concrete Docket Photos | W | W

## Lightning Bases
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
Lightning Tower Bases |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
Tank Slab
Design |  | PS1 design for lightning bases | UCCL/MEL | Prior to construction | PS1 design approval by Meridian | S | R
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing hardfill/site concrete | Scala achieves minimum 3 blows per 100mm | W | W
Formwork |  | Visual inspection | UCCL/RSV Consulting | Prior to placing concrete | Dimensional check completed and within tolerances. Formwork installed inspected as being suitable for pouring concrete. | H | W
Steel Reinforcing |  | Visual inspection | UCCL/RSV Consulting | Prior to placing concrete | Steel installed as per IFC drawings. Grade of steel as specified. Number, size and spacing of bars as per IFC drawings. | H | W
Post Pour Inspection |  | Visual inspection | UCCL | Following placement of concrete | Post pour inspection sheet to be completed Concrete Docket Photos | W | W

## Tranformer Foundations
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
Transformer Foundations and HV Ducts |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
Transformer Foundations (Installation)
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing hardfill | Scala achieves minimum 3 blows per 100mm | W | W
Hardfill Layer |  | Visual inspection | UCCL | Following placement of hardfill layer | Hardfill levels to line and level and within tolerances | W | W
Installation |  | Visual inspection As-Built Positions | UCCL | On completion of installation | Foundations installed to correct line and level and within tolerances. As-built drawings. | S | R
High Voltage Ducts
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing thermal bedding | Scala achieves minimum 3 blows per 100mm | W | W
Hardfill Layer |  | Visual inspection | UCCL | Following placement of hardfill layer | Hardfill levels to line and level and within tolerances | W | W
Ducting QA |  | Duct Inspection Record | UCCL | Per trench | Duct Inspection Checklist completed per trench | S | W
Thermal Backfill | Plateau test accepted in place of MDD | Visual inspection | UCCL | Following installation of ducts, where specified | 10 pasess with plate compactor, per MELNZ-RFI-000310 | W | W
Sand Backfill | Plateau test accepted in place of MDD | Visual inspection | UCCL | Following installation of ducts, where specified | Self compaction of sand, as per MELNZ-RFI-000310 | W | W
As-Built Survey Drawings |  | Surveying | UCCL | On completion of installation | As-built drawings provided to Meridian | S | R

## Fire Water Tank
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
Fire Water Tank |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
Tank Slab
Design |  | PS1 design for tank slab | UCCL/MEL | Prior to construction | PS1 design approval by Meridian | S | R
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing hardfill/site concrete | Scala achieves minimum 3 blows per 100mm | W | W
Hardfill Layer |  | Visual inspection | UCCL | Following placement of hardfill layer | Hardfill levels to line and level and within tolerances | W | W
Concrete Mix Design |  | Mix design to be approved prio to use | UCCL/RSV Consulting | Prior to use on site | Mix design as per PS1 design and approved by RSV Consulting | S | A
Formwork |  | Visual inspection | UCCL/RSV Consulting | Prior to placing concrete | Dimensional check completed and within tolerances. Formwork installed inspected as being suitable for pouring concrete. | H | W
Steel Reinforcing |  | Visual inspection | UCCL/RSV Consulting | Prior to placing concrete | Steel installed as per IFC drawings. Grade of steel as specified. Number, size and spacing of bars as per IFC drawings. | H | W
Foundation Earth |  | Visual Inspection | UCCL, MEL | Prior to placing concrete | Earth bars and cables installed as per instruction by MEL. | H | H
Post Pour Inspection |  | Visual inspection | UCCL | Following placement of concrete | Post pour inspection sheet ot be completed. PS4 sign off. | W | W
Pump Slab
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing hardfill/site concrete | Scala achieves minimum 3 blows per 100mm | W | W
Hardfill Layer |  | Visual inspection | UCCL | Following placement of hardfill layer | Hardfill levels to line and level and within tolerances | W | W
Formwork |  | Visual inspection | UCCL | Prior to placing concrete | Dimensional check completed and within tolerances. Formwork installed inspected as being suitable for pouring concrete. | H | W
Steel Reinforcing |  | Visual inspection | UCCL | Prior to placing concrete | Steel installed as per IFC drawings. Grade of steel as specified. Number, size and spacing of bars as per IFC drawings. | H | W
Foundation Earth |  | Visual Inspection | UCCL, MEL | Prior to placing concrete | Earth bars and cables installed as per instruction by MEL. | H | H
Post Pour Inspection |  | Visual inspection | UCCL | Following placement of concrete | Post pour inspection sheet ot be completed. | W | W
Fire Water Tank
Design |  | PS1 design for tank | UCCL | Prior to construction | PS1 design approval by Meridian | S | R
Tank Installation |  | Visual inspection | UCCL | On completion of tank installation | Record of installation QA report by Tasman Tanks installer | W | W
Tank Completion |  | PS4 for tank installation | UCCL | On completion of tank installation | Signed PS4 | W | R

## Stormwater (incl. Fire Water)
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
Stormwater (incl. Fire Water Pond) |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
Stormwater
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing hardfill | Scala achieves minimum 3 blows per 100mm | W | W
Backfill |  | Visual inspection | UCCL | Following placement of backfill layers | Backfill compacted and to line and level within tolerances | W | W
Hush Pit Installation |  | Visual inspection As-Built Positions | UCCL | On completion of installation | Installed to correct line and level and within tolerances. | W | W
Manhole Installation |  | Visual inspection As-Built Positions | UCCL | On completion of installation | Installed to correct line and level and within tolerances. | W | W
As-Built Survey Drawings |  | Surveying | UCCL | On completion of installation | As-built drawings provided to Meridian | S | R
Firewater Pond
Pond Liner |  | Supplier/Installer Documentation | UCCL | On completion of installation | Supplier/installer documentation provided to Meridian on Completion | W | W
Backfill on Liner |  | Visual inspection | UCCL | On completion of installation | Material specifications Photos | W | W
As-Built Survey Drawings |  | Surveying | UCCL | On completion of installation | As-built drawings provided to Meridian | S | R

## Streetlights
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
Streetlights |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
Streetlights
Design |  | PS1 design for streetlight installation | UCCL | Prior to construction | PS1 design approval by Meridian | S | R
Subgrade |  | Scala test of subgrade | UCCL | After excavation, prior to placing hardfill/site concrete | Scala achieves minimum 3 blows per 100mm | W | W
Backfill |  | Visual inspection | UCCL | On installation of street light bases | Backfill material meets specifications | W | W
Electrical Installation |  | Installer documentation (COC) | UCCL/ NorthPower | On completion of installation | Installer documentation (COC) provided to Meridian | W | W
As-Built Survey Drawings |  | Surveying | UCCL | On completion of installation | As-built drawings provided to Meridian | S | R

## Watermain
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
Watermain |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
Watermain
Material Supply |  | Material dockets | UCCL | On receiving materials | Materials meet specification | S | W
Butt Welding |  | Weld Records | UCCL | On completion of installation | Test weld tensile report Welds meet specification. | W | W
EF Welding |  | Weld Records | UCCL | On completion of installation | Welds meet specification. | W | W
Pressure Testing |  | Pressure test records | UCCL | On completion of installation, prior to charging the system | Pressure test passes | H | W
As-Built Survey Drawings |  | Surveying | UCCL | On completion of installation | As-built drawings provided to Meridian | S | R

## Wastewater
INSPECTION & TEST PLAN
|  | Contract Name: | [5 empty] | Rev: | Date | Approved | Date
|  | 7020 Civil Works |  |  | Hold Point (H) | Verify (V)
Wastewater |  |  |  |  | Submit (S) | Review (R)
[5 empty] | Approve(A) | Witness (W)
[5 empty] | Witness (W) | Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Client | DATE | COMMENTS
Wastewater
Material Supply |  | Material dockets | UCCL | On receiving materials | Materials meet specification | S | W
Mini-Manholes |  | Installation
EF Welding |  | Weld Records | UCCL | On completion of installation | Welds meet specification. | W | W
Connection |  | Council Inspection/Approval | WDC | On completion of installation, prior to backfilling | Council approval | H | H
Backfill and Reinstatement |  | Backfill records | UCCL | On completion of reinstatement | Backfill and resintatement meets specification | W | W
As-Built Survey Drawings |  | Surveying | UCCL | On completion of installation | As-built drawings provided to Meridian | S | R