## Sheet1
1.1.1 | Bedding material GAP 20 for Concrete Pipes PAP 7 for PE pipes | Per Batch | CIV Spec - S9.3.11 AS/NZS 3725 | Accept/ Reject | N/A | Dockets / Material Data Sheets | R | SUB | R | Hold Point |  | 1.1.1 - Bedding material GAP 20 for Concrete Pipes PAP 7 for PE pipes | Frequency - Per Batch | Spec/standard - CIV Spec - S9.3.11 AS/NZS 3725 | Acceptance Criteria - Accept/ Reject | Measuring Devices - N/A | Reporting Format - Dockets / Material Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - | 1.1.1 - Bedding material GAP 20 for Concrete Pipes PAP 7 for PE pipes
1.1.1 | Backfill Material GAP65 or GAP40 or AP40 | Per Batch | CIV Spec - S9.3.12 CIV Spec - S4.4.5 | Accept / Reject | N/A | Dockets / Material Data Sheets | R | SUB | R | Hold Point |  | 1.1.1 - Backfill Material GAP65 or GAP40 or AP40 | Frequency - Per Batch | Spec/standard - CIV Spec - S9.3.12 CIV Spec - S4.4.5 | Acceptance Criteria - Accept / Reject | Measuring Devices - N/A | Reporting Format - Dockets / Material Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - | Frequency - Per Batch
1.2.1 | Pre-Cast Manholes | Each Unit | CIV Spec - S9.3.7 | Dockets/ Visual Checks | N/A | Dockets / Material Data | R | SUB | R | Hold Point |  | 1.2.1 - Pre-Cast Manholes | Frequency - Each Unit | Spec/standard - CIV Spec - S9.3.7 | Acceptance Criteria - Dockets/ Visual Checks | Measuring Devices - N/A | Reporting Format - Dockets / Material Data | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - | Spec/standard - CIV Spec - S9.3.11 AS/NZS 3725
1.2.2 | Concrete Pipes: 375Ø RCRRJ Class 4 300Ø RCRRJ Class 4 225Ø RCRRJ Class 4 | Each Pipe | CIV Spec - S9.3.1 DP001-MMD-DRW-SW-D- Z-3100 to 3110 | Dockets/ Visual Checks | N/A | Dockets / Technical Data Sheets | R | SUB | R | Hold Point |  | 1.2.2 - Concrete Pipes: 375Ø RCRRJ Class 4 300Ø RCRRJ Class 4 225Ø RCRRJ Class 4 | Frequency - Each Pipe | Spec/standard - CIV Spec - S9.3.1 DP001-MMD-DRW-SW-D- Z-3100 to 3110 | Acceptance Criteria - Dockets/ Visual Checks | Measuring Devices - N/A | Reporting Format - Dockets / Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - | Acceptance Criteria - Accept/ Reject
1.2.3 | PE Pipes 280Ø ODPE 100 PN16 | Each Pipe | CIV Spec - 10.3.2 DP001-MMD-DRW-SW-B- Z-3051 to 3052 | Dockets/ Visual Checks | N/A | Dockets / Technical Data Sheets | R | SUB | R | Hold Point | Pipe colour tbc | 1.2.3 - PE Pipes 280Ø ODPE 100 PN16 | Frequency - Each Pipe | Spec/standard - CIV Spec - 10.3.2 DP001-MMD-DRW-SW-B- Z-3051 to 3052 | Acceptance Criteria - Dockets/ Visual Checks | Measuring Devices - N/A | Reporting Format - Dockets / Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - Pipe colour tbc | Measuring Devices - N/A
1.2.4 | Access covers and frames Landside: 240 kN Class D Airside: 900 kN Class G | Each unit | CIV Spec - S9.3.8 | Shop drawings, Dockets/ Visual Checks | N/A | Dockets / Technical Data Sheets | R | SUB | R | Hold Point |  | 1.2.4 - Access covers and frames Landside: 240 kN Class D Airside: 900 kN Class G | Frequency - Each unit | Spec/standard - CIV Spec - S9.3.8 | Acceptance Criteria - Shop drawings, Dockets/ Visual Checks | Measuring Devices - N/A | Reporting Format - Dockets / Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold Point | Remarks - | Reporting Format - Dockets / Material Data Sheets
1.3.1 | Insitu Concrete Mix Design | Each structure | CIV Spec - S13.3.1.2 | Accept / Reject | N/A | Design Mix | R | SUB | R | Hold point |  | 1.3.1 - Insitu Concrete Mix Design | Frequency - Each structure | Spec/standard - CIV Spec - S13.3.1.2 | Acceptance Criteria - Accept / Reject | Measuring Devices - N/A | Reporting Format - Design Mix | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Hold point | Remarks - | HCL - R
1.4.1 | In-situ Reinforcement | Each Structure | CIV Spec - S14.3.1 | Accept/Reject | N/A | Dockets/ Technical Data Sheets | R | SUB | R |  |  | 1.4.1 - In-situ Reinforcement | Frequency - Each Structure | Spec/standard - CIV Spec - S14.3.1 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Dockets/ Technical Data Sheets | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - | Remarks - | SC - SUB
1.5.1 | Pipe CHAR(AMP) Pit Waterproofing – Hydrotite CJ 0725 or Similar | Each Pipe and Structure | DP001-MMD-DRW-SW-F-Z- 3211 Rev 1 | Accept/Reject | N/A | Dockets/ Technical Data Sheets | [5 empty] | 1.5.1 - Pipe CHAR(AMP) Pit Waterproofing – Hydrotite CJ 0725 or Similar | Frequency - Each Pipe and Structure | Spec/standard - DP001-MMD-DRW-SW-F-Z- 3211 Rev 1 | Acceptance Criteria - Accept/Reject | Measuring Devices - N/A | Reporting Format - Dockets/ Technical Data Sheets | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - | Consult - R
2.1.1 | Existing pipes / manholes to be removed or retained | Each pipe | CIV Spec - S9.4.1 | Removed and disposed OR sealed and capped off | N/A | Photos / Asbuilts | I | SUB | R | RFI if any found that are not expected | Survey on site/ asbuilts review capped off any found | 2.1.1 - Existing pipes / manholes to be removed or retained | Frequency - Each pipe | Spec/standard - CIV Spec - S9.4.1 | Acceptance Criteria - Removed and disposed OR sealed and capped off | Measuring Devices - N/A | Reporting Format - Photos / Asbuilts | HCL - I | SC - SUB | Consult - R | Hold Points Sign off - RFI if any found that are not expected | Remarks - Survey on site/ asbuilts review capped off any found | Hold Points Sign off - Hold Point
2.1.2 | Survey Setout Pipe alignments, Position, Manholes Position and Heights | Each Manhole | N/A | Survey Setout records and Setout pegs | GPS, Total Station | Setout CSV file, Photos/Visual | [5 empty] | 2.1.2 - Survey Setout Pipe alignments, Position, Manholes Position and Heights | Frequency - Each Manhole | Spec/standard - N/A | Acceptance Criteria - Survey Setout records and Setout pegs | Measuring Devices - GPS, Total Station | Reporting Format - Setout CSV file, Photos/Visual | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - | Remarks -
2.2.1 | Excavation Extents | Each element installed | CIV Spec - S9.4.2 CIV Spec - S4.5.9 (earthworks section) | -20mm to +0mm o | Rotating level and GPS | N/A | M |  |  |  | Watercare Civil Construction Standard C2 referenced | 2.2.1 - Excavation Extents | Frequency - Each element installed | Spec/standard - CIV Spec - S9.4.2 CIV Spec - S4.5.9 (earthworks section) | Acceptance Criteria - -20mm to +0mm o | Measuring Devices - Rotating level and GPS | Reporting Format - N/A | HCL - M | SC - | Consult - | Hold Points Sign off - | Remarks - Watercare Civil Construction Standard C2 referenced | 1.1.1 - Backfill Material GAP65 or GAP40 or AP40
2.2.2 | Drainage manholes/ pits subgrade testing | Drainage manholes and pits: 2 tests at the base of excavation | CIV Spec - S4.6.2.2 (earthworks section) | Bearing Capacity 100kpa Shear Vane tests at 0.5m below the base and 1.0m below the base or Scala Penetrometer tests to 1.0m below the base | Shear Vane Test or Scala Test | Photos, Excel CHAR(AMP) pdf | M | SUB | W |  | If ground failing, Undercut 400mm and fill with 5Mpa flowable fill | 2.2.2 - Drainage manholes/ pits subgrade testing | Frequency - Drainage manholes and pits: 2 tests at the base of excavation | Spec/standard - CIV Spec - S4.6.2.2 (earthworks section) | Acceptance Criteria - Bearing Capacity 100kpa Shear Vane tests at 0.5m below the base and 1.0m below the base or Scala Penetrometer tests to 1.0m below the base | Measuring Devices - Shear Vane Test or Scala Test | Reporting Format - Photos, Excel CHAR(AMP) pdf | HCL - M | SC - SUB | Consult - W | Hold Points Sign off - | Remarks - If ground failing, Undercut 400mm and fill with 5Mpa flowable fill | Frequency - Per Batch
2.2.3 | Pipe Trench subgrade testing | Each trench at every 5m | CIV Spec – S9.5.2.1 | Minimum CBR 3% | Scala Test | Excel CHAR(AMP) pdf | M | SUB | R | Witness point | If failing Undercutting required. Engineer to confirm the Undercut details | 2.2.3 - Pipe Trench subgrade testing | Frequency - Each trench at every 5m | Spec/standard - CIV Spec – S9.5.2.1 | Acceptance Criteria - Minimum CBR 3% | Measuring Devices - Scala Test | Reporting Format - Excel CHAR(AMP) pdf | HCL - M | SC - SUB | Consult - R | Hold Points Sign off - Witness point | Remarks - If failing Undercutting required. Engineer to confirm the Undercut details | Spec/standard - CIV Spec - S9.3.12 CIV Spec - S4.4.5
2.2.4 | Bedding, surround | Per installation | As per drwgs min/ max fill CIV Spec - S9.4.3 DP001-MMD-DRW-SW-F-Z- 3270 Rev 2 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1 | 0mm / +3mm | Rotating level / tape / staff | Photos, QVC | M | * |  |  | PAP7 for PE CHAR(AMP) PVC GAP 20 For Concrete Pipes | 2.2.4 - Bedding, surround | Frequency - Per installation | Spec/standard - As per drwgs min/ max fill CIV Spec - S9.4.3 DP001-MMD-DRW-SW-F-Z- 3270 Rev 2 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1 | Acceptance Criteria - 0mm / +3mm | Measuring Devices - Rotating level / tape / staff | Reporting Format - Photos, QVC | HCL - M | SC - * | Consult - | Hold Points Sign off - | Remarks - PAP7 for PE CHAR(AMP) PVC GAP 20 For Concrete Pipes | Acceptance Criteria - Accept / Reject
2.2.5 | Pipe installation, Connection and jointing | Each pipe | CIV Spec - S9.4.4 CIV Spec - S9.4.9 Watercare General Construction Standards Section 9-C3 DP001-MMD-DRW-SW-F-Z- 3270 Rev 2 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1 | Position tolerance +/- 10mm Level Tolerance +/-5mm Pipe grade as per design | Observation | QVC, Long section Check sheets, As-Builts | I |  |  | Witness Point | Caps to be used if lines not complete, Chases dug out for belled socket joints Rubber seals | 2.2.5 - Pipe installation, Connection and jointing | Frequency - Each pipe | Spec/standard - CIV Spec - S9.4.4 CIV Spec - S9.4.9 Watercare General Construction Standards Section 9-C3 DP001-MMD-DRW-SW-F-Z- 3270 Rev 2 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1 | Acceptance Criteria - Position tolerance +/- 10mm Level Tolerance +/-5mm Pipe grade as per design | Measuring Devices - Observation | Reporting Format - QVC, Long section Check sheets, As-Builts | HCL - I | SC - | Consult - | Hold Points Sign off - Witness Point | Remarks - Caps to be used if lines not complete, Chases dug out for belled socket joints Rubber seals | Measuring Devices - N/A
2.2.6 | Backfilling | Each Pipe | CIV Spec - S4.4.4 Table 4.3 (Earthworks Section) DP001-MMD-DRW-SW-F-Z- 3270 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1 | CIV > 25 Clegg Test corelated to an NDM | Clegg Hammer | Photos, QVC, Clegg Sheets | M | SUB |  | Witness Point | Engineer to inspect before backfilling | 2.2.6 - Backfilling | Frequency - Each Pipe | Spec/standard - CIV Spec - S4.4.4 Table 4.3 (Earthworks Section) DP001-MMD-DRW-SW-F-Z- 3270 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1 | Acceptance Criteria - CIV > 25 Clegg Test corelated to an NDM | Measuring Devices - Clegg Hammer | Reporting Format - Photos, QVC, Clegg Sheets | HCL - M | SC - SUB | Consult - | Hold Points Sign off - Witness Point | Remarks - Engineer to inspect before backfilling | Reporting Format - Dockets / Material Data Sheets
2.3.1 | Pre- Cast Manholes | Each Unit | CIV Spec - S9.4.6 Watercare General Civil Construction Standard 9C.4 | Position tolerances +/- 10mm Level Tolerance -0mm to + 3mm. Manufacturers installation guidelines | As-Builts | Photos | [5 empty] | 2.3.1 - Pre- Cast Manholes | Frequency - Each Unit | Spec/standard - CIV Spec - S9.4.6 Watercare General Civil Construction Standard 9C.4 | Acceptance Criteria - Position tolerances +/- 10mm Level Tolerance -0mm to + 3mm. Manufacturers installation guidelines | Measuring Devices - As-Builts | Reporting Format - Photos | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - | HCL - R
2.3.2 | Mass Concrete Stormwater Manholes (Thickening) | Each Unit | CIV Spec - S13.4.3.2 DP001-MMD-DRW-SW-F-Z- 3211 | 20MPa concrete | As-Builts | Photos |  |  |  |  | Refer to Table 2 for dimensions in DP001- MMD-DRW-SW-F-Z- 321 Rev 3 | 2.3.2 - Mass Concrete Stormwater Manholes (Thickening) | Frequency - Each Unit | Spec/standard - CIV Spec - S13.4.3.2 DP001-MMD-DRW-SW-F-Z- 3211 | Acceptance Criteria - 20MPa concrete | Measuring Devices - As-Builts | Reporting Format - Photos | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - Refer to Table 2 for dimensions in DP001- MMD-DRW-SW-F-Z- 321 Rev 3 | SC - SUB
2.3.3 | Insitu Manholes | Each Unit | CIV Spec - S13.3.1.2 Watercare Standard Section C4. Concrete | Position tolerances +/- 10mm Level Tolerance -0mm to + 3mm | As-Builts | Photos, QA check sheets | [5 empty] | 2.3.3 - Insitu Manholes | Frequency - Each Unit | Spec/standard - CIV Spec - S13.3.1.2 Watercare Standard Section C4. Concrete | Acceptance Criteria - Position tolerances +/- 10mm Level Tolerance -0mm to + 3mm | Measuring Devices - As-Builts | Reporting Format - Photos, QA check sheets | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - | Consult - R
2.3.4 | Trench Excavation | Each Unit | CIV Spec - S13.4.1 | Scala test Min 3% CBR or Min Bearing capacity 100kPa | Shear Vane/Scala test | Photos, test Results PDF | R | SUB | R | Witness point |  | 2.3.4 - Trench Excavation | Frequency - Each Unit | Spec/standard - CIV Spec - S13.4.1 | Acceptance Criteria - Scala test Min 3% CBR or Min Bearing capacity 100kPa | Measuring Devices - Shear Vane/Scala test | Reporting Format - Photos, test Results PDF | HCL - R | SC - SUB | Consult - R | Hold Points Sign off - Witness point | Remarks - | Hold Points Sign off - Hold Point
2.3.5 | Formwork | Each unit | CIV Spec - S13.4.2 | Shop drawings, | N/A | Photos, QC check Sheet, Engineer Inspection | M | SUB | I | Witness point |  | 2.3.5 - Formwork | Frequency - Each unit | Spec/standard - CIV Spec - S13.4.2 | Acceptance Criteria - Shop drawings, | Measuring Devices - N/A | Reporting Format - Photos, QC check Sheet, Engineer Inspection | HCL - M | SC - SUB | Consult - I | Hold Points Sign off - Witness point | Remarks - | Remarks -
2.3.6 | Reinforcing Steel | Each Unit | CIV Spec - S14.4.2 CIV Spec - S14.4.8 CIV Spec - S14.4.11 CIV Spec - S13.5.1 DP001-MMD-DRW-SW-F-Z- 3210 | Plans and Shop drawings | N/A | Photos, QC check Sheet, Engineer Inspection |  |  |  | Hold Point | Engineer to inspect before concreting | 2.3.6 - Reinforcing Steel | Frequency - Each Unit | Spec/standard - CIV Spec - S14.4.2 CIV Spec - S14.4.8 CIV Spec - S14.4.11 CIV Spec - S13.5.1 DP001-MMD-DRW-SW-F-Z- 3210 | Acceptance Criteria - Plans and Shop drawings | Measuring Devices - N/A | Reporting Format - Photos, QC check Sheet, Engineer Inspection | HCL - | SC - | Consult - | Hold Points Sign off - Hold Point | Remarks - Engineer to inspect before concreting | 1.2.1 - Pre-Cast Manholes
2.3.7 | Pipe Connection to Manholes | Each Unit | CIV Spec - S10.4.5 DP001-MMD-DRW-WW-F- Z-3203 Rev 2 DP001-MMD-DRW-SW-F-Z- 5034 Watercare Standards WW11 | Plans and Shop drawings | N/A | Photos, QVC |  |  |  |  | For HDPE pipe connection refer to WW11 drawing | 2.3.7 - Pipe Connection to Manholes | Frequency - Each Unit | Spec/standard - CIV Spec - S10.4.5 DP001-MMD-DRW-WW-F- Z-3203 Rev 2 DP001-MMD-DRW-SW-F-Z- 5034 Watercare Standards WW11 | Acceptance Criteria - Plans and Shop drawings | Measuring Devices - N/A | Reporting Format - Photos, QVC | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - For HDPE pipe connection refer to WW11 drawing | Frequency - Each Unit
2.3.8 | Backfilling | Each Unit | CIV Spec - S13.4.4 Table 4.3 (Earthworks Section) | CIV > 25 Clegg Test corelated to an NDM | Clegg Hammer | Photos, QVC, Clegg Sheets | M | M |  | Witness Point | Engineer to inspect before backfilling | 2.3.8 - Backfilling | Frequency - Each Unit | Spec/standard - CIV Spec - S13.4.4 Table 4.3 (Earthworks Section) | Acceptance Criteria - CIV > 25 Clegg Test corelated to an NDM | Measuring Devices - Clegg Hammer | Reporting Format - Photos, QVC, Clegg Sheets | HCL - M | SC - M | Consult - | Hold Points Sign off - Witness Point | Remarks - Engineer to inspect before backfilling | Spec/standard - CIV Spec - S9.3.7
2.3.9 | Benching | Each Unit | DP001-MMD-DRW-F-Z- 3200 | Material Dockets | N/A | Drainage QVC. Photos |  |  |  |  | Benching Rendered to Min 1 in 12 grade | 2.3.9 - Benching | Frequency - Each Unit | Spec/standard - DP001-MMD-DRW-F-Z- 3200 | Acceptance Criteria - Material Dockets | Measuring Devices - N/A | Reporting Format - Drainage QVC. Photos | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - Benching Rendered to Min 1 in 12 grade | Acceptance Criteria - Dockets/ Visual Checks
2.3.10 | Manhole Throat, Lid | Each Unit | WaterCare Standard WW6 and WW 7 DP001-MMD-DRW-SW-F-Z- 3210 DP001-MMD-DRW-SW-F-Z- 3211 | Materials Dockets, Shop Drawings | N/A | QVC, Photos |  |  |  |  | Reference to Watercare General Construction drawings | 2.3.10 - Manhole Throat, Lid | Frequency - Each Unit | Spec/standard - WaterCare Standard WW6 and WW 7 DP001-MMD-DRW-SW-F-Z- 3210 DP001-MMD-DRW-SW-F-Z- 3211 | Acceptance Criteria - Materials Dockets, Shop Drawings | Measuring Devices - N/A | Reporting Format - QVC, Photos | HCL - | SC - | Consult - | Hold Points Sign off - | Remarks - Reference to Watercare General Construction drawings | Measuring Devices - N/A
3.1.1 | As built Works | Each pipe | CIV Spec - S9.4.10 | Position tolerance +/- 10mm Level Tolerance +/- 5m | Surveyor Equipment, Total Station | Certified As-built PDF and DWG file | R | Sub | R |  |  | 3.1.1 - As built Works | Frequency - Each pipe | Spec/standard - CIV Spec - S9.4.10 | Acceptance Criteria - Position tolerance +/- 10mm Level Tolerance +/- 5m | Measuring Devices - Surveyor Equipment, Total Station | Reporting Format - Certified As-built PDF and DWG file | HCL - R | SC - Sub | Consult - R | Hold Points Sign off - | Remarks - | Reporting Format - Dockets / Material Data
3.2.1 | CCTV Survey | Each new pipe and Manholes | CIV Spec - S9.5.2.4 | Accept / Reject | CCTV | Video and Report | R | Sub | R | Hold point | Shall be carried out prior to final pavement surfacing for new and remaining pipes | 3.2.1 - CCTV Survey | Frequency - Each new pipe and Manholes | Spec/standard - CIV Spec - S9.5.2.4 | Acceptance Criteria - Accept / Reject | Measuring Devices - CCTV | Reporting Format - Video and Report | HCL - R | SC - Sub | Consult - R | Hold Points Sign off - Hold point | Remarks - Shall be carried out prior to final pavement surfacing for new and remaining pipes | HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold Point
Remarks -
1.2.2 - Concrete Pipes: 375Ø RCRRJ Class 4 300Ø RCRRJ Class 4 225Ø RCRRJ Class 4
Frequency - Each Pipe
Spec/standard - CIV Spec - S9.3.1 DP001-MMD-DRW-SW-D- Z-3100 to 3110
Acceptance Criteria - Dockets/ Visual Checks
Measuring Devices - N/A
Reporting Format - Dockets / Technical Data Sheets
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold Point
Remarks -
1.2.3 - PE Pipes 280Ø ODPE 100 PN16
Frequency - Each Pipe
Spec/standard - CIV Spec - 10.3.2 DP001-MMD-DRW-SW-B- Z-3051 to 3052
Acceptance Criteria - Dockets/ Visual Checks
Measuring Devices - N/A
Reporting Format - Dockets / Technical Data Sheets
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold Point
Remarks - Pipe colour tbc
1.2.4 - Access covers and frames Landside: 240 kN Class D Airside: 900 kN Class G
Frequency - Each unit
Spec/standard - CIV Spec - S9.3.8
Acceptance Criteria - Shop drawings, Dockets/ Visual Checks
Measuring Devices - N/A
Reporting Format - Dockets / Technical Data Sheets
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold Point
Remarks -
1.3.1 - Insitu Concrete Mix Design
Frequency - Each structure
Spec/standard - CIV Spec - S13.3.1.2
Acceptance Criteria - Accept / Reject
Measuring Devices - N/A
Reporting Format - Design Mix
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Hold point
Remarks -
1.4.1 - In-situ Reinforcement
Frequency - Each Structure
Spec/standard - CIV Spec - S14.3.1
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - Dockets/ Technical Data Sheets
HCL - R
SC - SUB
Consult - R
Hold Points Sign off -
Remarks -
1.5.1 - Pipe CHAR(AMP) Pit Waterproofing – Hydrotite CJ 0725 or Similar
Frequency - Each Pipe and Structure
Spec/standard - DP001-MMD-DRW-SW-F-Z- 3211 Rev 1
Acceptance Criteria - Accept/Reject
Measuring Devices - N/A
Reporting Format - Dockets/ Technical Data Sheets
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks -
2.1.1 - Existing pipes / manholes to be removed or retained
Frequency - Each pipe
Spec/standard - CIV Spec - S9.4.1
Acceptance Criteria - Removed and disposed OR sealed and capped off
Measuring Devices - N/A
Reporting Format - Photos / Asbuilts
HCL - I
SC - SUB
Consult - R
Hold Points Sign off - RFI if any found that are not expected
Remarks - Survey on site/ asbuilts review capped off any found
2.1.2 - Survey Setout Pipe alignments, Position, Manholes Position and Heights
Frequency - Each Manhole
Spec/standard - N/A
Acceptance Criteria - Survey Setout records and Setout pegs
Measuring Devices - GPS, Total Station
Reporting Format - Setout CSV file, Photos/Visual
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks -
2.2.1 - Excavation Extents
Frequency - Each element installed
Spec/standard - CIV Spec - S9.4.2 CIV Spec - S4.5.9 (earthworks section)
Acceptance Criteria - -20mm to +0mm o
Measuring Devices - Rotating level and GPS
Reporting Format - N/A
HCL - M
SC -
Consult -
Hold Points Sign off -
Remarks - Watercare Civil Construction Standard C2 referenced
2.2.2 - Drainage manholes/ pits subgrade testing
Frequency - Drainage manholes and pits: 2 tests at the base of excavation
Spec/standard - CIV Spec - S4.6.2.2 (earthworks section)
Acceptance Criteria - Bearing Capacity 100kpa Shear Vane tests at 0.5m below the base and 1.0m below the base or Scala Penetrometer tests to 1.0m below the base
Measuring Devices - Shear Vane Test or Scala Test
Reporting Format - Photos, Excel CHAR(AMP) pdf
HCL - M
SC - SUB
Consult - W
Hold Points Sign off -
Remarks - If ground failing, Undercut 400mm and fill with 5Mpa flowable fill
2.2.3 - Pipe Trench subgrade testing
Frequency - Each trench at every 5m
Spec/standard - CIV Spec – S9.5.2.1
Acceptance Criteria - Minimum CBR 3%
Measuring Devices - Scala Test
Reporting Format - Excel CHAR(AMP) pdf
HCL - M
SC - SUB
Consult - R
Hold Points Sign off - Witness point
Remarks - If failing Undercutting required. Engineer to confirm the Undercut details
2.2.4 - Bedding, surround
Frequency - Per installation
Spec/standard - As per drwgs min/ max fill CIV Spec - S9.4.3 DP001-MMD-DRW-SW-F-Z- 3270 Rev 2 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1
Acceptance Criteria - 0mm / +3mm
Measuring Devices - Rotating level / tape / staff
Reporting Format - Photos, QVC
HCL - M
SC - *
Consult -
Hold Points Sign off -
Remarks - PAP7 for PE CHAR(AMP) PVC GAP 20 For Concrete Pipes
2.2.5 - Pipe installation, Connection and jointing
Frequency - Each pipe
Spec/standard - CIV Spec - S9.4.4 CIV Spec - S9.4.9 Watercare General Construction Standards Section 9-C3 DP001-MMD-DRW-SW-F-Z- 3270 Rev 2 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1
Acceptance Criteria - Position tolerance +/- 10mm Level Tolerance +/-5mm Pipe grade as per design
Measuring Devices - Observation
Reporting Format - QVC, Long section Check sheets, As-Builts
HCL - I
SC -
Consult -
Hold Points Sign off - Witness Point
Remarks - Caps to be used if lines not complete, Chases dug out for belled socket joints Rubber seals
2.2.6 - Backfilling
Frequency - Each Pipe
Spec/standard - CIV Spec - S4.4.4 Table 4.3 (Earthworks Section) DP001-MMD-DRW-SW-F-Z- 3270 DP001-MMD-DRW-SW-F-Z- 5031 Rev 1
Acceptance Criteria - CIV > 25 Clegg Test corelated to an NDM
Measuring Devices - Clegg Hammer
Reporting Format - Photos, QVC, Clegg Sheets
HCL - M
SC - SUB
Consult -
Hold Points Sign off - Witness Point
Remarks - Engineer to inspect before backfilling
2.3.1 - Pre- Cast Manholes
Frequency - Each Unit
Spec/standard - CIV Spec - S9.4.6 Watercare General Civil Construction Standard 9C.4
Acceptance Criteria - Position tolerances +/- 10mm Level Tolerance -0mm to + 3mm. Manufacturers installation guidelines
Measuring Devices - As-Builts
Reporting Format - Photos
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks -
2.3.2 - Mass Concrete Stormwater Manholes (Thickening)
Frequency - Each Unit
Spec/standard - CIV Spec - S13.4.3.2 DP001-MMD-DRW-SW-F-Z- 3211
Acceptance Criteria - 20MPa concrete
Measuring Devices - As-Builts
Reporting Format - Photos
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks - Refer to Table 2 for dimensions in DP001- MMD-DRW-SW-F-Z- 321 Rev 3
2.3.3 - Insitu Manholes
Frequency - Each Unit
Spec/standard - CIV Spec - S13.3.1.2 Watercare Standard Section C4. Concrete
Acceptance Criteria - Position tolerances +/- 10mm Level Tolerance -0mm to + 3mm
Measuring Devices - As-Builts
Reporting Format - Photos, QA check sheets
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks -
2.3.4 - Trench Excavation
Frequency - Each Unit
Spec/standard - CIV Spec - S13.4.1
Acceptance Criteria - Scala test Min 3% CBR or Min Bearing capacity 100kPa
Measuring Devices - Shear Vane/Scala test
Reporting Format - Photos, test Results PDF
HCL - R
SC - SUB
Consult - R
Hold Points Sign off - Witness point
Remarks -
2.3.5 - Formwork
Frequency - Each unit
Spec/standard - CIV Spec - S13.4.2
Acceptance Criteria - Shop drawings,
Measuring Devices - N/A
Reporting Format - Photos, QC check Sheet, Engineer Inspection
HCL - M
SC - SUB
Consult - I
Hold Points Sign off - Witness point
Remarks -
2.3.6 - Reinforcing Steel
Frequency - Each Unit
Spec/standard - CIV Spec - S14.4.2 CIV Spec - S14.4.8 CIV Spec - S14.4.11 CIV Spec - S13.5.1 DP001-MMD-DRW-SW-F-Z- 3210
Acceptance Criteria - Plans and Shop drawings
Measuring Devices - N/A
Reporting Format - Photos, QC check Sheet, Engineer Inspection
HCL -
SC -
Consult -
Hold Points Sign off - Hold Point
Remarks - Engineer to inspect before concreting
2.3.7 - Pipe Connection to Manholes
Frequency - Each Unit
Spec/standard - CIV Spec - S10.4.5 DP001-MMD-DRW-WW-F- Z-3203 Rev 2 DP001-MMD-DRW-SW-F-Z- 5034 Watercare Standards WW11
Acceptance Criteria - Plans and Shop drawings
Measuring Devices - N/A
Reporting Format - Photos, QVC
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks - For HDPE pipe connection refer to WW11 drawing
2.3.8 - Backfilling
Frequency - Each Unit
Spec/standard - CIV Spec - S13.4.4 Table 4.3 (Earthworks Section)
Acceptance Criteria - CIV > 25 Clegg Test corelated to an NDM
Measuring Devices - Clegg Hammer
Reporting Format - Photos, QVC, Clegg Sheets
HCL - M
SC - M
Consult -
Hold Points Sign off - Witness Point
Remarks - Engineer to inspect before backfilling
2.3.9 - Benching
Frequency - Each Unit
Spec/standard - DP001-MMD-DRW-F-Z- 3200
Acceptance Criteria - Material Dockets
Measuring Devices - N/A
Reporting Format - Drainage QVC. Photos
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks - Benching Rendered to Min 1 in 12 grade
2.3.10 - Manhole Throat, Lid
Frequency - Each Unit
Spec/standard - WaterCare Standard WW6 and WW 7 DP001-MMD-DRW-SW-F-Z- 3210 DP001-MMD-DRW-SW-F-Z- 3211
Acceptance Criteria - Materials Dockets, Shop Drawings
Measuring Devices - N/A
Reporting Format - QVC, Photos
HCL -
SC -
Consult -
Hold Points Sign off -
Remarks - Reference to Watercare General Construction drawings
3.1.1 - As built Works
Frequency - Each pipe
Spec/standard - CIV Spec - S9.4.10
Acceptance Criteria - Position tolerance +/- 10mm Level Tolerance +/- 5m
Measuring Devices - Surveyor Equipment, Total Station
Reporting Format - Certified As-built PDF and DWG file
HCL - R
SC - Sub
Consult - R
Hold Points Sign off -
Remarks -
3.2.1 - CCTV Survey
Frequency - Each new pipe and Manholes
Spec/standard - CIV Spec - S9.5.2.4
Acceptance Criteria - Accept / Reject
Measuring Devices - CCTV
Reporting Format - Video and Report
HCL - R
SC - Sub
Consult - R
Hold Points Sign off - Hold point
Remarks - Shall be carried out prior to final pavement surfacing for new and remaining pipes