## Sheet1
Material Supply | Material dockets | UCCL | On receiving materials | Materials meet specification | S | W | Material Supply | SPECIFICATION REFERENCE - | TEST REQUIRED - Material dockets | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - On receiving materials | ACCEPTANCE CRITERIA - Materials meet specification | UCCL - S | CLIENT - W | Material Supply
Mini-Manholes | Installation | [5 empty] | Mini-Manholes | SPECIFICATION REFERENCE - | TEST REQUIRED - Installation | INSPECTION BY - | TASK TIMING OR TASK FREQUENCY - | ACCEPTANCE CRITERIA - | UCCL - | CLIENT - | SPECIFICATION REFERENCE -
EF Welding | Weld Records | UCCL | On completion of installation | Welds meet specification. | W | W | EF Welding | SPECIFICATION REFERENCE - | TEST REQUIRED - Weld Records | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - On completion of installation | ACCEPTANCE CRITERIA - Welds meet specification. | UCCL - W | CLIENT - W | TEST REQUIRED - Material dockets
Connection | Council Inspection/Approval | WDC | On completion of installation, prior to backfilling | Council approval | H | H | Connection | SPECIFICATION REFERENCE - | TEST REQUIRED - Council Inspection/Approval | INSPECTION BY - WDC | TASK TIMING OR TASK FREQUENCY - On completion of installation, prior to backfilling | ACCEPTANCE CRITERIA - Council approval | UCCL - H | CLIENT - H | INSPECTION BY - UCCL
Backfill and Reinstatement | Backfill records | UCCL | On completion of reinstatement | Backfill and resintatement meets specification | W | W | Backfill and Reinstatement | SPECIFICATION REFERENCE - | TEST REQUIRED - Backfill records | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - On completion of reinstatement | ACCEPTANCE CRITERIA - Backfill and resintatement meets specification | UCCL - W | CLIENT - W | TASK TIMING OR TASK FREQUENCY - On receiving materials
As-Built Survey Drawings | Surveying | UCCL | On completion of installation | As-built drawings provided to Meridian | S | R | As-Built Survey Drawings | SPECIFICATION REFERENCE - | TEST REQUIRED - Surveying | INSPECTION BY - UCCL | TASK TIMING OR TASK FREQUENCY - On completion of installation | ACCEPTANCE CRITERIA - As-built drawings provided to Meridian | UCCL - S | CLIENT - R | ACCEPTANCE CRITERIA - Materials meet specification
UCCL - S
CLIENT - W
Mini-Manholes
SPECIFICATION REFERENCE -
TEST REQUIRED - Installation
INSPECTION BY -
TASK TIMING OR TASK FREQUENCY -
ACCEPTANCE CRITERIA -
UCCL -
CLIENT -
EF Welding
SPECIFICATION REFERENCE -
TEST REQUIRED - Weld Records
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - On completion of installation
ACCEPTANCE CRITERIA - Welds meet specification.
UCCL - W
CLIENT - W
Connection
SPECIFICATION REFERENCE -
TEST REQUIRED - Council Inspection/Approval
INSPECTION BY - WDC
TASK TIMING OR TASK FREQUENCY - On completion of installation, prior to backfilling
ACCEPTANCE CRITERIA - Council approval
UCCL - H
CLIENT - H
Backfill and Reinstatement
SPECIFICATION REFERENCE -
TEST REQUIRED - Backfill records
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - On completion of reinstatement
ACCEPTANCE CRITERIA - Backfill and resintatement meets specification
UCCL - W
CLIENT - W
As-Built Survey Drawings
SPECIFICATION REFERENCE -
TEST REQUIRED - Surveying
INSPECTION BY - UCCL
TASK TIMING OR TASK FREQUENCY - On completion of installation
ACCEPTANCE CRITERIA - As-built drawings provided to Meridian
UCCL - S
CLIENT - R