## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
6c1c3c63-cf34-418a-834d-4265a8c15da9 | checklist | ITP-001 - Clearing & Grubbing | itp | ITP-001 - Clearing & Grubbing
1005a90e-a77c-4b19-9e59-a1ce01ab5ebb | section | 1 - Preliminary Works
832f0955-0019-496d-8ebf-929b982c7ecc | checkpoint | 1.1 - Check current drawings are used on site for works
1a0a8b35-6a7e-5ffa-b6dd-1342cced3f4f | note | FREQUENCY: Prior to commencing any activity
d914ec62-3886-586a-b6d1-3f5529db56bf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
344f7770-f608-5ff5-87a0-34a1aab21243 | note | – using the correct and complete set of drawings
59048460-0680-5b18-a9d1-7f749578b6dc | note | – all drawings are the latest revision
d174c247-f1de-5187-972b-8faab23ef5fd | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3be40858-1d13-5f71-a009-ff70bd14704e | note | INSPECTION/TEST METHOD: Visual inspection
99b29e75-c8c8-54bf-8b92-cc90d5044559 | note | RECORD OF CONFORMITY: This ITP signed
1ceac7ad-a578-5007-9ec7-18d7ca0d90ac | note | HP*
2233bf48-7620-552b-ac7d-d314b36dd2b8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f4417d7a-64a1-5a2d-afe0-ad7890093beb | date | Date Completed:
51695790-e4f2-4401-8916-11e18b41b521 | checkpoint | 1.2 - Implementation of all measures and controls
88b4a47f-8063-5641-92e1-0bf526c4234c | note | FREQUENCY: Prior to commencing any activity
4489bcc7-7a0b-5644-9e81-c49de22b5dfe | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
6622fd5c-11c8-5946-96ae-0963eda62b5d | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
80e26f54-e10f-5ff1-8a3e-2f053338d685 | note | INSPECTION/TEST METHOD: Visual Inspection
19079a04-ca28-5a66-8451-62cfc17cfd34 | note | RECORD OF CONFORMITY: This ITP signed
0bd463cd-9692-5d37-b6ce-ab3eb175bcf3 | note | HP*
923fee71-dd99-54bb-b873-1891b727fe6c | note | RESPONSIBILITY: Site Engineer / Site Foreman
8bb89998-e676-57cb-b17b-8653c59d0f28 | date | Date Completed:
9c8df558-8ce4-4057-b9ba-99121162018c | checkpoint | 1.3 - Excavation Permit issued
b1165102-22c8-5cc4-b6b5-aaee9aa2c470 | note | FREQUENCY: Prior to Commencing
2e451377-d9eb-54df-9d21-7b447deaf87e | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
52a52af9-f3a1-5227-8244-c94181a66df2 | note | REFERENCE DOCUMENTS: Excavation Permit
8c59f3d0-1a68-55f8-bd91-40ca2d3a48d9 | note | INSPECTION/TEST METHOD: Document review
5732c33d-ac17-53e0-a09f-1363d66e6c71 | note | RECORD OF CONFORMITY: Excavation Permit #
26e35c12-0220-5692-8084-e98b20981922 | note | IP
70d26eaf-2820-5971-9582-6a7653d8a02e | note | RESPONSIBILITY: Site Engineer
9d23e3b7-f9e0-5fda-803c-00544eda3d33 | date | Date Completed:
138f6177-c36f-4a64-85ff-c8c8e56bc91b | checkpoint | 1.4 - Flora & Fauna
3e047bf7-ebfb-5fed-859a-df60bef71e5c | note | FREQUENCY: Prior to commencing clearing
9ae9e017-4c55-5f19-9972-6bbd5e7382c4 | note | ACCEPTANCE CRITERIA: A qualified Ecologist is or trained wildlife handler to be present during removal of native vegetation; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
7e4d52f1-5c14-56f6-a5fc-dd7cf609910b | note | REFERENCE DOCUMENTS: Construction Environmental Management Plan Appendix 2
9cd8a393-78d7-57e3-bd4a-177fc8b51dd1 | note | INSPECTION/TEST METHOD: Visual Inspection
6f17f7ec-84c4-554d-a417-bb095620361e | note | RECORD OF CONFORMITY: This ITP Signed off
0fd0d655-d9ba-5a4a-8b32-c48f556765a2 | note | IP
8b05920c-f3ea-5085-9df4-3772230b9b77 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b34c80f4-7e22-5a67-9845-95894aa9f540 | date | Date Completed:
0d02ab1f-08de-4290-a6b7-fe0236fd6465 | checkpoint | 1.5 - Permit to distrurb flora & fauna
2ee67278-ae8d-57ae-ae4b-9a85b7599a19 | note | FREQUENCY: Prior to commencing clearing
e871f00e-6994-5be3-a1ab-04bd186b95a0 | note | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
72928fd6-575e-5715-ab5d-4987f83bac45 | note | REFERENCE DOCUMENTS: Condition Plans endorsement
7c950460-bd43-572b-a64d-df3f906e625f | note | INSPECTION/TEST METHOD: Visual Inspection
52a558d4-bf9f-5379-825d-43a0bd645084 | note | RECORD OF CONFORMITY: This ITP Signed off
985078b6-0183-576c-9178-e30aed3eddc6 | note | IP
10d07fd3-9e88-53d5-89f3-a66ca9f117b6 | note | RESPONSIBILITY: Project Engineer
ef59b5bd-fc0f-5168-8178-c5e2b17a0351 | date | Date Completed:
9c5a01d1-4a56-4940-9cd7-3e0cb6867e94 | section | 2 - Clear & Grub
30472483-fc8d-442e-8b41-5af77c023bb3 | checkpoint | 2.1 - Define work area
bedaacc9-8786-5f48-88bc-18adbf598bd1 | note | FREQUENCY: Prior to commencing clearing
72bb045f-fd41-5e5b-8fbd-a0d2a9e684e1 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
828db756-e2eb-589e-b3b3-8ac7236c6d85 | note | REFERENCE DOCUMENTS: 201.1
c06aa22d-2292-53db-abd2-8a28abd1a66c | note | INSPECTION/TEST METHOD: Inspect
ff89a70b-f481-53e4-8c7c-b9778ae13464 | note | RECORD OF CONFORMITY: This ITP Signed off
f16e315e-22d6-5e6d-a673-ea68a0bee5e2 | note | HP
d28fbe0f-440e-5021-b5c9-59f85efd7bb1 | note | RESPONSIBILITY: Project Engineer/ Superintendent
938f203e-6e22-56c6-9eb2-4df10a5e4c18 | date | Date Completed:
ab0f20a4-c86e-424e-950b-90d92cb20e71 | signoff | AUTHORITY HOLDPOINT
0515cb32-4596-4536-ae6d-167fdd2e1d87 | checkpoint | 2.2 - Cultural Heritage and Areas of Significance
fbea0059-e351-5d53-9e9d-53ccca188f33 | note | FREQUENCY: Prior to commencing clearing
82b77fe7-c3a0-5363-be22-f2685bbac3a4 | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
e44f7731-f1cd-5571-92cc-a6e7a20dd922 | note | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
47528cbe-802b-5737-871a-ed6d570fb607 | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
1556e9db-6b2e-5492-b54c-6f51ef92615b | note | REFERENCE DOCUMENTS: CHMP
39b5fb45-551c-544f-bd76-6d607e2c2bdb | note | INSPECTION/TEST METHOD: Inspect
771b9844-f659-57a4-9929-1511dbbef854 | note | RECORD OF CONFORMITY: This ITP Signed off
3918bd8f-d00b-59f0-bebf-24b96bf48c04 | note | HP
c9b7736d-9e1f-5427-a031-3a6c3a9db488 | note | RESPONSIBILITY: Project Engineer/ Superintendent
7f3a27c0-8ea4-5252-a794-82d8ecc30d63 | date | Date Completed:
7cfc2607-9188-452e-a440-313679acd92c | signoff | AUTHORITY HOLDPOINT
29fe4e93-9cbb-4e07-b344-1f0497762297 | checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
29a27bea-66f5-542f-a139-4aaae8312f90 | note | FREQUENCY: Prior to commencing clearing
fd91649c-01af-5809-b257-7cd455a7df88 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
665ed0b2-05d6-59b7-9ded-abb4621833bd | note | REFERENCE DOCUMENTS: Drawings CEMP, Tree Management Plan 176.I1
f009f0c2-2c69-5c35-9201-027878b221fb | note | INSPECTION/TEST METHOD: Visual Inspection
cf49e99f-d259-5f82-90f6-fa0dfd8be54b | note | RECORD OF CONFORMITY: This ITP Signed off
a5fc5d22-3fd6-5f39-a1f4-f629ce058e06 | note | HP
dcfb3425-bf3d-59d5-be09-101a2fffa8f3 | note | RESPONSIBILITY: Project Engineer/ Superintendent
6814b6fd-d675-5fcf-abb0-a79f0704cd96 | date | Date Completed:
c1242f46-106e-4cf1-aa61-0ffa1816cb8b | signoff | AUTHORITY HOLDPOINT
080ffc59-1e14-41cc-a38e-b9132bf96ff9 | checkpoint | 2.4 - Felling of Trees
742fb401-3e0b-5a97-bf8c-4704f8280bc0 | note | FREQUENCY: Prior to commencing clearing
f1ceeb3e-44a9-5cf5-99e5-c65e34d39a12 | note | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
902647ba-58f5-5b6d-98fa-f32b972fedc8 | note | REFERENCE DOCUMENTS: 201.04
98d89b79-2b08-5080-b23b-2643df53949a | note | INSPECTION/TEST METHOD: Visual Inspection
458fba15-3183-5cb9-ac36-24f6cb2d3c37 | note | RECORD OF CONFORMITY: This ITP Signed off
c856be9c-423c-558a-a60b-cd42eaabd507 | note | IP
3e9d6c25-ee45-5191-ae58-8b3c55951117 | note | RESPONSIBILITY: Site Engineer / Site Foreman
00e2286c-2c42-53ca-97a7-a98eb4c0e330 | date | Date Completed:
480ce50f-4d73-4a85-800d-79db72742909 | checkpoint | 2.5 - Backfill holes
15166199-aff0-560d-8e79-9eee6f88866f | note | FREQUENCY: After clearing
76e8f827-2010-5c30-a0c7-7a182a5bc9b6 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
bc29b51c-2ed1-5bb5-b41c-a2c3c3f1b3f3 | note | REFERENCE DOCUMENTS: 201.05
55b44258-7896-56e6-9c65-424fd8a95fa2 | note | INSPECTION/TEST METHOD: Visual Inspection
1b9bef76-5a40-5e97-8932-dc364d3dbf42 | note | RECORD OF CONFORMITY: This ITP Signed off
ff3c3338-4881-5a4b-b5bb-cc3cd5fa2394 | note | IP
52aa6ef0-4fa1-57ca-9257-2237aef7cba7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
df201209-97e9-55f3-9fe8-88ce1641f7ef | date | Date Completed:
3ba6ab36-99df-4d98-81da-4a2b697ba536 | checkpoint | 2.6 - Dispose of Trees and vegetation
038a8a79-8aa8-5801-8d0a-815969cf0aeb | note | FREQUENCY: After clearing
17c59396-b290-53e9-9bd7-78863191e3a0 | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
70e218be-37d9-57ca-a907-50ed71a80cdf | note | ○ Noxious weeds shall not be mulched.
bd1ae649-5d88-5c69-944c-246f518d9bd6 | note | REFERENCE DOCUMENTS: 201.07
bab4b9d7-b25c-5d0c-acac-ff2964705d0c | note | INSPECTION/TEST METHOD: Visual Inspection
5cb96eda-dd6d-54ac-989e-b522cedeae52 | note | RECORD OF CONFORMITY: This ITP Signed off
6b7a1c96-8457-5fed-a5f9-21d935bfe31c | note | IP
4851a7e3-ee3a-5ee1-b657-3c55821f9ce5 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0c3ace34-3bd2-5626-94fe-ab041913d1f4 | date | Date Completed:
b851bb0e-5586-4852-b229-00f0561c1fac | checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
e480c1a9-af78-5680-b7b1-35a311ee4fae | note | FREQUENCY: After clearing
84ca8272-de48-5f69-ab60-2d849cf2dffd | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
9f4a46f0-93a7-5664-848a-04a718fce315 | note | REFERENCE DOCUMENTS: 201.07
de352218-3af9-5611-9708-6b57bf6408fa | note | INSPECTION/TEST METHOD: Visual Inspection
d02946a5-39f3-5d13-ae52-26811412da22 | note | RECORD OF CONFORMITY: This ITP Signed off
999e4989-1834-5916-901c-fcb8ebbb3ec7 | note | IP
df3a005b-8886-5e81-8be4-b7776117c05c | note | RESPONSIBILITY: Site Engineer / Site Foreman
b3639bfc-7e08-52da-b684-ce4ee031b356 | date | Date Completed:
8350c8b3-0694-419b-b51a-34e3494e8ed6 | checkpoint | 2.8 - Stripping of topsoil
514bd428-7dbc-50aa-ab31-5018a6a2560c | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
04fed428-b0ba-5732-90aa-85325a0cef1f | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation. Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
3ac0ce46-a356-5440-ac33-58ec738de23f | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
4ba2c4fa-3ef0-5a5c-99cc-7b71a7e9f2f8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
d0f874ea-4e1a-5021-9b30-b77da59a21fc | note | INSPECTION/TEST METHOD: Visual Inspection
ba9a1c71-5232-5cf8-a179-178f958723fc | note | RECORD OF CONFORMITY: This ITP Signed off
0b13fb7d-e308-567a-a97a-fa775bfbab78 | note | IP
340e797c-62f8-581b-bfb9-3e07bd910788 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1eb7cc78-bcb5-59fd-b821-28f7a41545ad | date | Date Completed:
eca9ee7a-d662-43ed-b77d-c68b1034e563 | checkpoint | 2.9 - Removal of abandoned services
f1c9ba6a-d6b1-55ca-a6ab-48ed4b1810e0 | note | FREQUENCY: Prior to commencing works
a8b50227-067c-5c14-af51-a1f2384606d6 | note | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade.
6a5e5606-9c51-5c6c-a94d-e9af78bd5583 | note | ○ Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
ec5520b5-142a-5fe9-b63e-8905807c072f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
50f247c9-45c5-5c58-b399-8a2e8b0b8c2b | note | INSPECTION/TEST METHOD: Visual Inspection
bcc3a253-b63b-506c-af95-55dd714cc7c0 | note | RECORD OF CONFORMITY: This ITP Signed off
3f1f3898-9192-5ac6-bc0b-5e4b5f0f55cb | note | IP
1656360b-ba07-5c0a-9765-ba4ea670c50f | note | RESPONSIBILITY: Site Engineer / Site Foreman
65c23c22-de1b-5499-933b-635a73f37c49 | date | Date Completed:
af6f3ccd-6765-4cf8-bd96-231f92884b46 | checkpoint | 2.10 - Clearing of Trees and Vegetation
51a853da-5c87-550c-8a76-9e1cdd5d5fc3 | note | FREQUENCY: During clearin works
52bbf621-74cb-5006-9de0-2a9cad8ce7da | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
3511720d-1182-54ac-9a6a-99d5cd5e207c | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
b2d17109-f03b-522e-849c-f2f3cf2fe449 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
89ca1216-be14-5d28-87e0-1b1a405d973b | note | INSPECTION/TEST METHOD: Visual Inspection
9fedefc6-4405-5a66-8938-c7947bf34e28 | note | RECORD OF CONFORMITY: This ITP Signed off
05c9a840-642e-5519-963e-a481cac4df4e | note | IP
3586951a-210e-5694-ab9d-65068316ec47 | note | RESPONSIBILITY: Site Engineer / Site Foreman
7b1f395c-df89-5d8e-874c-47ea49789b87 | date | Date Completed:
fce9b691-15ad-4577-b79d-7529720396cf | checkpoint | 2.11 - Grubbing of vegetation
8449d8e1-2c70-5de4-833b-20f3f8cf878e | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
3d7d4035-ef1b-53ed-afa7-d82b63db70cb | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
b299fe99-b3b3-5043-93e7-4d44d919b5f3 | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
c63e74d7-2883-54aa-9c2d-b24312aa4efb | note | REFERENCE DOCUMENTS: CEMP, VicRoads Spec. Cl.201.05
56376ce6-9093-571f-8245-190f89644a5e | note | INSPECTION/TEST METHOD: Visual Inspection
a1e84fa6-12bf-50b3-84bd-4421c5bd397d | note | RECORD OF CONFORMITY: This ITP Signed off
96701840-c5e9-5b65-b8f3-53f74011bbbf | note | IP
64d8571b-5470-5ac4-9bf3-e72bd0c46775 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d4e5c4b1-bc3b-5683-a8eb-e1edcba3d56f | date | Date Completed:
475e1aa9-1c06-417c-8817-c76b35490a6c | checkpoint | Final Inspection
8d1bb3c2-1350-5fff-a085-a1285c5f1ced | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7e7b300d-e2b4-55b7-87b5-ef70f7b64bf6 | textbox | Print Name:
92ce5e5c-8454-5ff2-924e-4a827fb4041d | textbox | Position:
1d116141-4883-5be4-987e-82e16ae5ce10 | date | Date:
1c3019c0-3472-49f2-8bdf-7bf7ef180b96 | checklist | ITP-003 - Earthworks Foundation | itp | ITP-003 - Earthworks Foundation
a20e87dc-4a1d-47d5-b27e-ef6fa9a10edf | section | 1 - Preliminary Works
b2048020-c08c-4d99-85c5-a3e8db08814a | checkpoint | 1.1 - Induction
4a48cccf-1011-5c45-bd9d-f2bae24bcc78 | note | FREQUENCY: Prior to Commencing Work
8b70780d-a3ed-569a-951f-8c24afe79070 | note | ACCEPTANCE CRITERIA: All personnel on site have completed site specific induction
e6052155-b360-53d2-bcd9-9bc61a8a4cb7 | note | REFERENCE DOCUMENTS: Induction Register
bba14646-0050-5c28-b54a-b01d4ca07e5b | note | INSPECTION/TEST METHOD: Document Review
ac7ecd91-11b8-50a9-af39-d14630e4cfde | note | RECORD OF CONFORMITY: This ITP signed
46f1add8-e152-5cc4-b735-7903fbcda0b9 | note | HP*
808be6ff-b7a0-5976-b80b-8e4576d6eb7c | note | RESPONSIBILITY: Site Engineer / Site Foreman
7a7f282c-b569-54b1-a7cf-06f2b041ddcd | date | Date Completed:
ef5b6000-9a52-4d19-a2fb-1ade41a4c9fe | checkpoint | 1.2 - Implementation of all measures and controls
c34c8f6b-706f-5fa5-a292-c6e42231b57a | note | FREQUENCY: Prior to commencing any activity
5a5b9c0a-ef41-53d8-ad6c-94f88cd3ef6d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
64b8adfe-c920-540f-a634-3d60ecb481e0 | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
d22532e1-20b6-57e4-8089-d3659bd2edc9 | note | INSPECTION/TEST METHOD: Document Review
9925e8d3-9ec1-58b5-9891-935268dccc9f | note | RECORD OF CONFORMITY: This ITP signed
d529e988-a189-5ffe-8549-8a2f6471b09d | note | HP*
9e043c63-4c40-56b1-9946-68856ae42eba | note | RESPONSIBILITY: Site Engineer / Site Foreman
c984115d-e0cb-5c99-86a0-2db194f00c31 | date | Date Completed:
39ff253e-f152-4838-8155-c03c0bee97a3 | checkpoint | 1.3 - Excavation Permit issued
cda5dad5-8d94-5ea5-9777-996441d2b54b | note | FREQUENCY: Prior to commencing
6fe2d3c6-3f8b-5e29-8157-4e45ac803e75 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
3f1b1d9a-02c0-5ada-9784-16a602397fe6 | note | REFERENCE DOCUMENTS: Excavation Permit
98eea0c5-3644-5c24-a660-11238a0b1f15 | note | INSPECTION/TEST METHOD: Document Review
a2a07710-a3de-5e77-bfab-9418a7e7985a | note | RECORD OF CONFORMITY: Excavation Permit No.
99b3ab66-68b3-5668-9a79-0095074a7bee | note | IP
55050026-d47d-504d-ad78-17da3f6536b1 | note | RESPONSIBILITY: Site Engineer & Superintendent
e424e54f-fda9-593e-8dce-3b292f8a19a4 | date | Date Completed:
b5d33fd7-c934-4f90-8a9c-ef23bf4c229c | checkpoint | 1.4 - Check that current revision drawings are being used
11d9ff91-7756-5f16-8488-4b52f682fec7 | note | FREQUENCY: Prior to Commencing Work
742799df-fd0f-5403-9a73-0934f9f3a262 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
fb72ac8c-2419-58ff-a9a7-5005117a82a0 | note | REFERENCE DOCUMENTS: IFC Drawings
de6661c4-f040-5055-a3b5-bb7f745ab73e | note | INSPECTION/TEST METHOD: Document Review
c8205007-4826-5299-8877-f7d9c520fb5a | note | RECORD OF CONFORMITY: This ITP Signed off
e948e34a-8635-5f50-9edd-c2be278a9b88 | note | IP
a975be8a-e075-542e-81d2-50de8a859b24 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a17150c6-6e84-5ceb-89c7-d31f1cf24ff2 | date | Date Completed:
fcb14b5b-eb15-4e18-b1d9-50df2b0f8c07 | checkpoint | 1.5 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
097291b4-4f48-55c6-85c5-cd2e44392fd5 | note | FREQUENCY: Prior to Commencing Work
bb9fc4ff-595c-50f6-9526-eb820fcde285 | note | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
2d70d6d6-6862-5a01-ba87-b3383c6a1c4a | note | REFERENCE DOCUMENTS: IFC Drawings CEMP CHMP
4ba7f549-10c3-5112-b233-0c42b3937cc3 | note | INSPECTION/TEST METHOD: Document Review
4aae62a3-d98c-5646-89ce-d2e1714bd087 | note | RECORD OF CONFORMITY: This ITP Signed off
b4116a8d-c85a-5c14-bb08-1fb597c9641e | note | IP
9d01e0ec-bfa2-5c42-97de-5091f47c7c08 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6aa7adec-1d48-596a-8717-5e21ee1fbe7f | date | Date Completed:
e6548fc4-f789-49a0-9f6e-f0a89ce584a3 | checkpoint | 1.6 - Verification of Site Clearing
e66387b5-cb6f-5cac-a2c9-c148007f5a2e | note | FREQUENCY: Prior to Commencing
baf50e7d-bfb9-5a2b-bc94-90ff50ec2fe4 | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
90e6a850-822e-56b5-b454-dd69d1e9c9ea | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05 ITP-001
1065338e-0f70-5e58-8130-8ff40bb18dba | note | INSPECTION/TEST METHOD: Visual Inspection
3dd47db4-5828-5c47-94e0-2843330eeff2 | note | RECORD OF CONFORMITY: This ITP Signed off
0cd66baa-bb20-5bd2-9553-e01f96bc07a5 | note | IP
09a3dbd1-f3ff-520b-9ccd-37db4d70024a | note | RESPONSIBILITY: Project Engineer
fcb87a40-f0a1-5050-86dc-636393868a18 | date | Date Completed:
86beeadd-514b-421b-8af2-e87b3e198dbe | checkpoint | 1.7 - Placing Fill
9c7e7967-cece-55cb-a7f0-8f69df430a94 | note | FREQUENCY: Prior to Commencing Fill
cdedda1c-c7a0-5e19-879e-d537b75db2a7 | note | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
92fb30c7-e3c1-5090-a507-38ee24455d98 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
4ed405a6-600e-5ad2-b63d-056123c964b5 | note | INSPECTION/TEST METHOD: Visual Inspection
613c17dc-760c-51c5-99ab-3758c2722a67 | note | RECORD OF CONFORMITY: This ITP Signed off
cfe8d95e-ce9d-51f4-97f1-40aeffc06603 | note | IP
5ef6d2b2-5563-562a-8f60-0d33a06ba8a5 | note | RESPONSIBILITY: Project Engineer
2de34540-72d9-577c-ac4e-953c955ff54e | date | Date Completed:
9f9e49cf-4e04-4edc-a3be-5979235eb145 | checkpoint | 1.8 - Rock Subgrade
e728c4f7-bf7d-542f-9773-d6a523b439dc | note | FREQUENCY: During Excavation
be30472c-55d6-56cd-8a98-86da267a54fa | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
0b9f0e6b-0343-5433-8118-3012d1f75cf3 | note | ○ Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review.
21766ee5-c1d7-5e63-a6b1-307d819fd1e4 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
d5527800-9adc-5c71-abe3-d3e1de79bc26 | note | INSPECTION/TEST METHOD: Visual Inspection
a3a880e5-1d18-5371-bbaf-6668f67a784a | note | RECORD OF CONFORMITY: This ITP Signed off
c1c366d0-6ed3-5a6e-b8bb-5719b59fb980 | note | IP
d5dbd7e8-ecde-5a87-b39f-db9fbdb015c0 | note | RESPONSIBILITY: Project Engineer
db19c722-08a6-5e44-9b3e-aae74be910eb | date | Date Completed:
96fcc52d-8c84-49e8-813e-96b86515ac42 | checkpoint | 1.9 - Ground Water
2357ebec-9f3b-5c4b-b5b9-945ce24ad699 | note | FREQUENCY: During Excavation
a2b3cffa-dd75-55c8-aef5-89afdf64be6c | note | ACCEPTANCE CRITERIA: The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted .
421ef586-b8e0-5d09-8a84-364866784764 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(h)
aff910dd-4337-5dc4-8175-18d2eca68f38 | note | INSPECTION/TEST METHOD: Visual Inspection
066d6bb1-4328-514e-8834-84c21e1428aa | note | RECORD OF CONFORMITY: This ITP Signed off
469790f1-3ae3-539c-890e-6cc4ee5f7a9d | note | IP
89362532-44ed-5224-a04a-bf5d91e0497b | note | RESPONSIBILITY: Project Engineer
6a42f5af-2fc6-5be0-8355-a6a501a32275 | date | Date Completed:
ecaf0746-f8a6-4fde-9f67-9db5805e7782 | checkpoint | 1.10 - Unsuitable Material
c46c9589-759b-5d3b-bbf6-2a62fc96c007 | note | FREQUENCY: During Excavation
e68ce4c3-986e-58ca-972e-111f6dde360b | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
d888037f-63f0-587d-8c6f-09fbbaaf9d24 | note | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
62b40282-a34e-5437-84bf-ee1a8d83fac3 | note | REFERENCE DOCUMENTS: IFC Drawings
942baa82-fbbe-5e87-aa26-3f8fc2a04066 | note | INSPECTION/TEST METHOD: Visual Inspection
f4c24c70-f259-5e17-b294-2ab22eea27dc | note | RECORD OF CONFORMITY: This ITP Signed off
9411307a-ec17-5704-a63e-d29471739c77 | note | IP
5d8beac0-0b78-5ea2-b703-7b3f397ceb64 | note | RESPONSIBILITY: Project Engineer
adb921f5-3f89-5c85-b5f3-02656a6d806d | date | Date Completed:
18b28947-96f7-43c9-a02b-a56d7d3c0acd | section | 2 - Construction Works
94344248-ab56-4494-bb74-c51ffc3cebc8 | checkpoint | 2.1 - Survey set-out
caa8d552-301b-58cf-8996-27e985f4bb21 | note | FREQUENCY: Prior to Commencing
5830680a-3504-51eb-bd72-f8b7d6c8c477 | note | ACCEPTANCE CRITERIA: The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings.
415ccdb0-4028-50ab-bc44-7232ffa711ee | note | REFERENCE DOCUMENTS: IFC Drawings
2bf815bf-44fa-59ac-a3a7-691f81196757 | note | INSPECTION/TEST METHOD: Site Inspection
94b82532-f5de-58df-a0de-068c38dc6ed3 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
d2967244-01ee-500e-b30b-0a34fdd1b983 | note | SCP
cb3c4066-7e0f-5896-b56d-4b0a27ace84c | note | RESPONSIBILITY: Project Engineer/ Superintendent
32d778ff-b772-5791-bb06-ea5aac292987 | date | Date Completed:
52fcb841-7f3f-44fe-8c98-fa7e0c827b0b | checkpoint | 2.2 - Placement of Geotextiles
cfaa963b-4998-5c0a-9f48-24e261abebee | note | FREQUENCY: On cut surfaces
21872a6e-8218-590b-b8d7-f159eec9e590 | note | ACCEPTANCE CRITERIA: Geotextiles / fabrics placed as per manufacturers specification
14b613aa-562e-5d32-9fde-ed60a78c646b | note | REFERENCE DOCUMENTS: Drawings, Manufactuer specification
8403a711-375b-5387-9a42-bf4838c894ca | note | INSPECTION/TEST METHOD: Verify
7f1ef894-251b-510b-9c80-fd36eba7dbf3 | note | RECORD OF CONFORMITY: This ITP Signed off
350ce06a-61e9-5982-8a2b-39b78936520e | note | IP
9768806b-f7fb-5e3d-afc0-c7cee2e2a2e9 | note | RESPONSIBILITY: This ITP Signed off
6fcb5ac0-b26e-5eba-b6ad-16b2373af9c2 | date | Date Completed:
d9ddd41a-a938-4954-871e-0ba93f644d75 | checkpoint | Final Inspection
ac525b02-781c-5660-a333-738d9466dedf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
01cdf37a-9a3f-5be9-88dd-4ef13c033780 | textbox | Print Name:
0117e0e4-2ecf-51b6-aaf6-97ee474f05fc | textbox | Position:
41e3aadb-07e9-554b-900b-69821b5fc20b | date | Date:
eca99399-cb73-4b3c-b320-a95045161e9d | checklist | ITP-004 - Fill with Class 3 Material | itp | ITP-004 - Fill with Class 3 Material
baac0d4d-3ad9-403d-8bac-0b9c762c4ea5 | section | 1 - Preliminary Works
ee243d46-447f-417b-a9e0-cd1d57bc5e6c | checkpoint | 1.1 - Induction
b911cf72-d271-598b-881a-2fd143131eea | note | FREQUENCY: Prior to Commencing
ff5c431d-4dc0-5124-a8f4-333b8c93b4db | note | ACCEPTANCE CRITERIA: All personnel on site have completed the site specific induction
a9d0b68c-e7ed-546b-b771-ded4f6097bfb | note | REFERENCE DOCUMENTS: Inductions Register
c22d22a8-b39b-57f2-9ce6-cb9dda1cbe5c | note | INSPECTION/TEST METHOD: Document review
9a7511dc-e496-5e7f-96c3-6cfa3aa2b659 | note | RECORD OF CONFORMITY: Site induction signed.
df25fb7e-9089-5323-bd28-079f5d21f2ce | note | AP
82d6eb27-06b5-5ea2-8d88-8cab77019e99 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0f5e4adc-7caa-5b12-9734-b044f5b77f04 | date | Date Completed:
b207e901-5cd7-48fa-a53f-5d9e7efe7f85 | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
5af599a6-e5d1-5bd5-8068-5079498a1c77 | note | FREQUENCY: Prior to commencing
d34d7a19-7dce-57df-b309-7313ad50880d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
5b08119a-142b-531a-b608-f88d6ae04bf5 | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
208ad874-7518-5faa-aa4e-e7839488d29a | note | INSPECTION/TEST METHOD: Document Review
d074bc46-cf6d-5f92-88d8-61bf0d9afcbd | note | RECORD OF CONFORMITY: SWMS(s) signed
b1aabeeb-1f78-5d98-839e-9c7e6b1fe1cd | note | HP
88e8e284-ab2c-521f-8a77-05a9dac7273a | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
1e560225-0c98-5313-b3f4-09ce837513a1 | date | Date Completed:
2e5b0dbd-2671-40d5-946f-a1d41600ed90 | signoff | AUTHORITY HOLDPOINT
8b182f22-3e8a-42b9-b56d-3213e469be3e | checkpoint | 1.3 - Check that current revision drawings are being used
aabde27c-a6b4-52f0-b917-13dadd33d092 | note | FREQUENCY: Prior to Commencing
e77cfcbd-707d-5543-8430-dfb1749df6d1 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
64f79ba0-d6db-5d76-af92-576a859d952c | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
7eb5a20c-700b-513a-ac49-33fc403708ff | note | INSPECTION/TEST METHOD: Document review
430ee2ce-17cc-599d-a73e-b9c13ba7a649 | note | RECORD OF CONFORMITY: Latest Revision Drawings
cc771646-e5fe-5b0d-8751-b102ae55ca7e | note | AP
cb8a055f-fc9c-5eef-92d5-4ab628e8e489 | note | RESPONSIBILITY: Site Engineer / Site Foreman
814195ba-1f37-5746-aedc-c286de9d8fd9 | date | Date Completed:
88d9ccd0-c2bd-424e-95f8-35be40bf86a6 | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
ab911df3-27b8-50e8-bb4f-dd8f504b526b | note | FREQUENCY: Prior to Commencing
44718a79-ebc4-5322-bd89-b641e4ecd18c | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
f7c644a4-a4da-57e7-821c-16f2aa603373 | note | REFERENCE DOCUMENTS: IFC Drawings CEMP CHMP
dea13e07-58c7-59f6-b872-e8573e31834a | note | INSPECTION/TEST METHOD: Document review & Site inspection
18e599e5-8124-5746-8745-8109af7d819a | note | RECORD OF CONFORMITY: Signed ITP
16404b2b-0155-5f95-b993-bfdaf2effcef | note | IP
f1dabd95-530f-5e4f-87a7-1e2a7d4be9f8 | note | RESPONSIBILITY: Site Engineer
244489f6-823f-5d83-8054-d41280822e6f | date | Date Completed:
bc7cae5b-d11a-431d-8fed-3cbebe2959c0 | checkpoint | 1.5 - Excavation Permit issued
a12365b0-0b6c-5d5f-98b9-921cc3e3c6f7 | note | FREQUENCY: Prior to Commencing
0ec30f04-de99-5d7b-a04a-0cd509d9e990 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
2b1ece96-6581-5437-8130-8b653aebf8e2 | note | REFERENCE DOCUMENTS: Excavation Permit
9fab6b01-1e87-5c7b-8d28-38b1207284c4 | note | INSPECTION/TEST METHOD: Document review
27a21b70-8379-51f6-bfa5-c0f8f106ff59 | note | RECORD OF CONFORMITY: Excavation Permit #
c67631d7-d426-5f61-a113-383ffb7d12d4 | note | IP
6fb1383f-9275-58cf-8b12-f375d085a75c | note | RESPONSIBILITY: Site Engineer
966e1c81-95c1-574b-98f0-f120ffb9a325 | date | Date Completed:
c5b0bc94-90bf-4937-ac7a-b75ce04638a4 | section | 2 - Placing Class 3 Material
9a02e54a-8b4b-44ff-9f57-4630c5c48d56 | checkpoint | 2.1 - Survey set-out
3e71196b-5f12-58c7-be43-97afc791e63e | note | FREQUENCY: Prior to Commencing Excavation
ae601d75-8d38-5f7a-9a95-a65dae91145f | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
5b141481-e5a3-58c8-a0b6-f7ff52ac21c4 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
74f13fba-ed96-5ab3-b00b-3e2ab16c81dd | note | INSPECTION/TEST METHOD: Site Inspection
991c980f-3d99-5fc0-9a0d-f622313377e7 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
99761c2e-cb2c-5dad-99bb-7bb8142e8833 | note | SCP
e8a70784-6b26-5b7a-9009-0b299f54a5c6 | note | RESPONSIBILITY: Site Engineer & Surveyor
6bbe27b3-c4e0-52a5-b618-8516cbe08d93 | date | Date Completed:
526dff09-a8da-4aa4-9045-804c70f276dd | checkpoint | 2.2 - Fill Construction
6961165d-eecf-5775-8893-3c0c85094de3 | note | FREQUENCY: Prior to Commencing Excavation
65b1b0ad-9538-51a5-aefc-38dec76b20f8 | note | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
a5b571e9-b6f8-5544-aa76-748701079cff | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
5e00eea5-a078-5132-9931-cb07b2d4f6c6 | note | INSPECTION/TEST METHOD: Site Inspection
e62170e9-ef7f-5be5-a4f7-65b9c7074e4b | note | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
2e318f7d-e251-5198-9386-c7086ae74edb | note | HP
a99b67a0-a921-5e15-9e98-9db170e66595 | note | RESPONSIBILITY: Site Engineer & Superintendent
893ee8ed-a8f8-5d56-9dcf-974f2f7e4437 | date | Date Completed:
64e6b477-dfca-475d-bc87-bc6a4bbdaa3c | signoff | AUTHORITY HOLDPOINT
488f94e8-ea45-4cfe-bd81-5f4880f8d61a | checkpoint | 2.3 - Keyed fill layers
908c958c-29ed-5b60-97d8-3b386f75e680 | note | FREQUENCY: During Excavation
73be8505-be0f-5b30-8de5-c9390e9091dd | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
590a93d9-3454-5b71-ac8b-044982aeb00c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
c53668f8-6f81-5bd4-924e-3b39fa507c8d | note | INSPECTION/TEST METHOD: Site Inspection
3e882a81-67e7-5b26-8817-311c301fc3c7 | note | RECORD OF CONFORMITY: Signed ITP
0bc797ad-07ba-52da-a016-e10124b8ecdc | note | IP
4b7cb857-d604-566c-b2f3-5c3e3655e16a | note | RESPONSIBILITY: Site Engineer
b0f23cbc-1175-54ec-9ba1-21c9fb6f95df | date | Date Completed:
89a860b9-a9b6-445c-aab5-3a129e78738b | checkpoint | 2.4 - Layer thickness
862c4a6d-7a19-58d7-abde-a4663bfd8f8a | note | FREQUENCY: During Excavation
b06fa636-b2a1-5f77-bff3-0030cd7cafbf | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
8f0a19f4-31e4-5d44-bcf1-48c43231020d | note | ○ A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
0b15f7c8-a643-5381-aa11-04537e36672e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
0cd43ee0-3940-508d-9297-a6f5de809e73 | note | INSPECTION/TEST METHOD: Site Inspection
2c125760-59ea-5c99-9441-ec3639f67b98 | note | RECORD OF CONFORMITY: Signed ITP
4bfa9280-be61-5c95-beb8-804942f771c4 | note | IP
01fd660d-0d30-5b63-9cdb-b31cc6b79ecb | note | RESPONSIBILITY: Site Engineer
70d5cb99-0a94-5596-9dc7-ea983cfff4b2 | date | Date Completed:
6d9bf5b8-7eef-4a3d-b737-c124128ec663 | checkpoint | 2.5 - Proof Roll
3bd0b88a-45e5-57de-91e3-37180d105710 | note | FREQUENCY: Each Fill Layer
a77ece5e-4fc1-5164-bc18-7571004ec6c3 | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173.
f3e645b3-6c43-5173-be57-57572cd83fbd | note | ○ Superintendent to be present during all test rolling.
7332b8a7-33ec-5bcf-859c-1b03889198db | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12 Cl.173.03
c4663a50-388a-544a-9b50-dc4b239b9f30 | note | INSPECTION/TEST METHOD: Site Inspection
01c1b810-8655-554e-b1bd-8c6e26e5ffe6 | note | RECORD OF CONFORMITY: Proof Roll Form completed & signed.
fa252fb8-eaf4-5c02-bd25-213a3bd37f89 | note | WP
51171dd6-ad71-5b76-b814-131f8227f20e | note | RESPONSIBILITY: Site Engineer & Superintendent
7c2bdcfb-e503-5661-b154-e19c04677e92 | date | Date Completed:
34d220d9-2bd7-4e40-ac3c-ff1d2b159704 | checkpoint | 2.6 - Preparation of final surface
61e34580-6eb5-535c-9516-04a0f11d59df | note | FREQUENCY: Prior to construction of subgrade layer
1f36af1d-e5c8-522e-9469-0b4d8d643f02 | note | ACCEPTANCE CRITERIA: The top of the Class 3 material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
2a1e64a9-e446-587a-803d-51b7d301d43d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15 Cl. 204.03(g)
646f14de-9f40-50b4-ac9e-bd53fcfd956b | note | INSPECTION/TEST METHOD: Site Inspection
309700b9-62b8-53ff-9573-16b02ee0d483 | note | RECORD OF CONFORMITY: Signed ITP
bd84ab0b-07c0-51e6-88e0-6d9cfe2f29e6 | note | IP
27585962-6480-503f-9db7-0a05257d489f | note | RESPONSIBILITY: Site Engineer
de59e658-d88d-5587-847d-f1d1ad629a85 | date | Date Completed:
b492867a-e5f4-46ac-b836-dcaba2cee80e | checkpoint | 2.7 - Conformity with Drawings
0a63ab2e-ca06-528e-b649-7d53d11ddb98 | note | FREQUENCY: Prior to construction of subgrade layer
d01fe5cb-0a67-5d33-9818-0cad130ece59 | note | ACCEPTANCE CRITERIA: Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
1b22968b-7e09-55e0-bde2-deb062aecf5e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.03(f)
24ca62a1-cb94-51b1-930f-1150cd63193c | note | INSPECTION/TEST METHOD: Site Inspection
d9ce7b60-f660-5fb5-b944-e4d2178dfc5d | note | RECORD OF CONFORMITY: Signed ITP
c99fe65a-aa6b-5069-91c9-aca10904db56 | note | IP
f4b94784-e584-5438-8c85-c8c45d97578e | note | RESPONSIBILITY: Site Engineer
d16808da-24a3-594c-96eb-5cc5824f361c | date | Date Completed:
0888932d-66b0-46f9-81a0-abdf0f41f23f | section | 3 - Testing
670b06cd-fdfc-47e2-b201-4a6ff6bf4a38 | checkpoint | 3.1 - Compaction Testing
7a99cbe2-ad1f-52f9-95aa-0010795f22fe | note | FREQUENCY: 3 x tests every layer
38a89a40-abd0-56e6-8cfa-de0062c6c702 | note | ACCEPTANCE CRITERIA: Compaction testing to ensure 100% Standard Compaction Density Ratio
7061dc9f-d98f-5ca1-a5c2-4b22bcb70557 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.13(a), Cl.204.13(b) Table 204.131, Table 204.142
adddb2af-6388-5da9-b5c8-318844a7f4d8 | note | INSPECTION/TEST METHOD: Site Inspection
3186ba91-83d5-5d9a-96c0-393a30cfbc60 | note | RECORD OF CONFORMITY: Compaction Test Records
b8f44f31-4de0-584f-bdd4-32933b60ac7a | note | TP
817a61bf-4584-575a-8801-48cfb0aef254 | note | RESPONSIBILITY: Site Engineer
a4c0e7d2-0682-557b-a831-210d1ae7f748 | date | Date Completed:
b904e229-71ec-4557-9b6f-9d45a7a961b6 | checkpoint | Final Inspection
a9a9b286-2aef-591f-8fb9-a0f49b4ab440 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
abc05ee8-5230-5b1e-adce-c1873b4413a3 | textbox | Print Name:
0ae32779-a049-5a8e-a063-fa5c71c8473a | textbox | Position:
adf077d5-72d2-5e70-804b-bfdbf45b75e5 | date | Date:
c43bfef6-02de-4131-ab56-1ba0011bcb14 | checklist | ITP-011 - Bored Piling | itp | ITP-011 - Bored Piling
a90d4beb-9454-473a-b5b3-563dd28e56e7 | section | 1.0 - Design and Submissions
5a040340-656b-4973-8b30-801c5873d2fc | checkpoint | 1.1 - Check for correct documetation
d63321c5-4d69-593f-bdb2-9d692c72a603 | note | FREQUENCY: Before commencement of activity
f7a4cd27-67b7-5d3c-90e4-9ecbcbb73395 | note | ACCEPTANCE CRITERIA: Check correct documentation is being utilized (latest drawing revision) and IFC/ Proof Engineering
3d815ed6-6dcf-5586-ae60-7c410af103cc | note | REFERENCE DOCUMENTS: Drawings
2a5f5272-c1f5-5f1f-a9df-eb698cf5bd16 | note | INSPECTION/TEST METHOD: Current revision of drawing
facf6555-a5b6-593e-bd39-47212295c10c | note | RECORD OF CONFORMITY: Current revision of drawing
ec29992b-d1af-588a-a499-cfca482e7119 | note | HP*
809efd9b-8b66-5776-9d6d-bc8a042cb9af | note | RESPONSIBILITY: Project Engineer, Site Engineer
31b582af-86d2-5c48-a13f-3ad1cb1ffe07 | date | Date Completed:
cd90fd0d-31e5-4f4f-b67b-e45a6c66e4d1 | checkpoint | 1.2 - Approval of Mix Design
b306dc76-ce48-558a-a5e3-202f0df2a0e0 | note | FREQUENCY: No less than 4 weeks prior to commencement of activity
b035d2d7-b32f-528d-94a8-00b6a2739dab | note | ACCEPTANCE CRITERIA: Mix design reviewed and approved by superintendent.
a0b20829-c4f4-55cc-9ce7-c3d3cd6bddb9 | note | REFERENCE DOCUMENTS: Cl 610.07(b
bdef042c-092b-5c57-8223-a2adced35d67 | note | INSPECTION/TEST METHOD: Approval
dcc42e45-eb80-57a4-96a8-071fc32a1368 | note | RECORD OF CONFORMITY: VicRoads letter of approval
b31d6547-123d-54fb-8cc7-fb5ce3d49bbe | note | AP
beb407d2-1f9f-57af-8789-292d64772fec | note | RESPONSIBILITY: Superintendent
482d2d35-e53d-5af1-893f-70ce71253c70 | date | Date Completed:
d7657aef-ce70-45cf-a9e2-90ab8b106c58 | checkpoint | 1.3 - Approval of Quality Procedure
f6a08c4b-f5b1-5e57-bcd9-783e933ef83c | note | FREQUENCY: No less than 4 weeks prior to commencement of activity
9864e383-7780-5fe9-bfa7-c502bcd8ed8f | note | ACCEPTANCE CRITERIA: Proposed materials and pile construction procedures reviewed by the superintendent
67ac1f90-59af-50a1-8742-130435ed286b | note | REFERENCE DOCUMENTS: Cl 606.03(a)
4b76e40c-7527-5319-b6ec-71ded238d9e5 | note | INSPECTION/TEST METHOD: Approval
37895923-583a-5795-9b3b-0b3b49303e3b | note | RECORD OF CONFORMITY: VicRoads letter of approval
a2f96719-16c0-52d3-b461-48008b33f131 | note | HP
c9977b64-572a-5fb2-9447-c8402c96892a | note | RESPONSIBILITY: Superintendent
333a6150-ac6e-560d-a8bb-01d3c1730241 | date | Date Completed:
1e55d836-2044-473f-ad5d-88a8c950a9f3 | signoff | AUTHORITY HOLDPOINT
cde0a8a4-73c3-467c-b78f-809000512afc | checkpoint | 1.4 - Ensure Traffic, Safety, Quality and Environmental management measures are in place
f4354265-2eef-52ac-a2b2-fee69b8ba2e8 | note | FREQUENCY: Prior to commencement of activity. EMP at least 2 weeks prior
1fb79ca7-a36e-5631-91e7-8c90618d2ed5 | note | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
39a1d2a6-fa0d-5037-8673-1c3a45dd20ef | note | REFERENCE DOCUMENTS: PSP, TMP & EMP
22279dcb-074e-541d-b8f0-adc367fe452d | note | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
3a8dd8ea-3ada-5c42-b75f-26d5e77d1b76 | note | RECORD OF CONFORMITY: Inspection
5642b2ed-a5f0-57d0-9bf3-afb174a208b3 | note | HP
f3001e14-704f-5030-bf5e-dfd7210b8c6a | note | RESPONSIBILITY: Site Engineer, Superintendent
63326553-66e4-54b7-97fc-f1ecf09c151e | date | Date Completed:
ea67bf6f-a234-4e69-9b6a-b90eef90aeb4 | signoff | AUTHORITY HOLDPOINT
4cda175b-35fb-41a5-9875-69972f43bdfe | checkpoint | 1.5 - Certification of approved Hot Dip Galvanising
e2884133-65c2-5a70-8868-529f07f31b9d | note | FREQUENCY: Prior to Epoxy coating
daecd7e2-4ae8-57e9-ab9d-5eb699152da5 | note | ACCEPTANCE CRITERIA: Galvanising treatment in accordance with appropriate Standard documents and Design specification 200 microns
4bef1f66-72e5-5ac2-a56a-6c688cb55db8 | note | REFERENCE DOCUMENTS: Drawings AS/NZ4680
c9c3a20f-f0a4-52ad-8620-0afe22b28ad9 | note | INSPECTION/TEST METHOD: Verify
371035fb-eb22-5b0c-96f1-311cb9a64649 | note | RECORD OF CONFORMITY: Manufacturers certificate
64b6a5e2-5c16-50b7-9f9d-fdfcfb2ea535 | note | HP*
0ae5e9a0-f1aa-521c-9253-2086d5691577 | note | RESPONSIBILITY: Project Manager, Site Engineer
9813d24f-00b0-5339-8db9-cd670c50cfc4 | date | Date Completed:
9a8dacee-762d-4ac0-943f-6e6cd4d308ba | checkpoint | 1.6 - Certification of approved Epoxy coating
19677d82-677d-5aee-ae1d-d89a56ae44b9 | note | FREQUENCY: Prior to arrival on site
291cc0db-d5c8-5679-b7dc-be937c6fed0e | note | ACCEPTANCE CRITERIA: Epoxy treatment in accordance with appropriate Standard documents and Design specification
3ef2e216-c2ff-5842-be59-5d716f888496 | note | ○ 2 x Base Coat GFX @ 250 microns
3e27602e-518c-5d64-be42-7e50872f59cb | note | ○ 1 x Top Coat Polyurethane, 100 microns
3bf821ae-37dc-5713-9315-f074ef28223d | note | REFERENCE DOCUMENTS: Drawings AS2312
5244c57a-c939-502f-968a-f73c8e0e7a0e | note | INSPECTION/TEST METHOD: Verify
c9fbe3b0-f713-5057-965b-81a78ecebe20 | note | RECORD OF CONFORMITY: Manufacturers certificate
57c9b860-3ea4-58f9-a89d-0379d46f5ddd | note | HP*
223109eb-143b-5f62-bb7e-553d6b8ecb4f | note | RESPONSIBILITY: Project Manager, Site Engineer
6249c0ab-fd1c-5413-93f2-d218a38b8ec9 | date | Date Completed:
8ee76dbf-d00a-4cf1-86f0-172699b0bdf4 | section | 2.0 - Bored Piling
f47e2d30-2f09-4a17-956d-b302d9cd2846 | checkpoint | 2.1 - Survey and setout
29f823c1-63f2-57cd-94b7-47b706f402dc | note | FREQUENCY: Each Pile
1a97c657-fba4-5f8d-95d3-ebd6be4bcdd0 | note | ACCEPTANCE CRITERIA: Survey and confirm position and depth as per drawing
df15eb49-8ba3-581f-ba4c-3447e58e269d | note | REFERENCE DOCUMENTS: Drawings
d15e649a-9d30-5b56-91c5-cb7c2c3e24cc | note | INSPECTION/TEST METHOD: Survey
59d7ea00-7b1b-5bf4-b99e-e2f00b32a77d | note | RECORD OF CONFORMITY: This ITP Signed off
56bf9591-00a6-5fe0-88d3-e3f5f1ffad7a | note | IP
3e987908-e8eb-5cf4-ac0e-9db2507db128 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
a148e2e4-0031-5e77-8664-1c6afaebcf4b | date | Date Completed:
c03d537f-5024-4549-a48d-d42537a9bbf3 | checkpoint | 2.2 - Excavation Levels
e8a06ed8-98b9-5a06-bf77-bbf9b70dca7a | note | FREQUENCY: Each Pile
548b5116-6615-5185-8308-c9e6eadbef4b | note | ACCEPTANCE CRITERIA: Check the excavation levels and base are acceptable and conform to the drawing prior to commencement of piling works.
ed5bb94d-43d1-5db3-ab29-e24da5ce4ce7 | note | REFERENCE DOCUMENTS: Drawings
260b6e45-5f04-5919-9393-a57b2d887bde | note | INSPECTION/TEST METHOD: Verify
2e70e51f-19b6-59f5-a43f-7cf0f07e8ddb | note | RECORD OF CONFORMITY: Drilling check sheet
a25419cc-eb1f-5ca9-831f-2731efd46f30 | note | HP
7df556ef-b3e7-5597-b0c9-ff5c872330f4 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
6e4eeabf-f437-58d0-bcd9-bf1db5159aad | date | Date Completed:
64ce988f-833d-4eda-8166-72f68b403512 | signoff | AUTHORITY HOLDPOINT
416d2367-020f-4f68-b520-73164f7c7011 | checkpoint | 2.3 - Inspection of Pile Excavation
3c3f8acc-6888-51ad-b289-d7dfe31ca35d | note | FREQUENCY: Each Pile
ef2fda15-c42d-550c-bebb-84b7fd8a06ae | note | ACCEPTANCE CRITERIA: First 3 piles to be inspected by Geotechnical Engineer to check dimensions and toe level are correct and within tolerance. Correct Toe level.
6aeaf34d-aa9f-5afa-aab2-eab4d80bd3ee | note | ○ Material encountered consistent with design.
9cf04c52-72af-5777-a006-70d653ab0abc | note | REFERENCE DOCUMENTS: Drawings Cl 606.06
dec819e6-ea0a-5b46-88fa-5a0c624e44a5 | note | INSPECTION/TEST METHOD: Inspection / Test Method
782ebc2b-da8c-5d8b-b9f4-3716ca94fe43 | note | RECORD OF CONFORMITY: This ITP Signed off
e795a154-06f9-52ad-90a4-94efdde9c09d | note | HP
1747ae37-5abe-50e3-8b69-a0351ffc28e7 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
964afbe3-f90a-5638-882b-f76fac519ee3 | date | Date Completed:
9cbbe4f7-e57a-4c1f-a692-62f32459d118 | signoff | AUTHORITY HOLDPOINT
ab1c1c19-8b7c-4fa5-afeb-b5936da2730f | checkpoint | 2.4 - Bore Logs
514b6cba-6678-5ddf-aa4a-5212a68945bd | note | FREQUENCY: Each Pile
fccc8526-11a1-56e2-b0af-0aaebc5ec27c | note | ACCEPTANCE CRITERIA: All bore logs and pile installation records to be sent to and reviewed by designer
4d5cb7a2-129c-567e-8970-c9366935c586 | note | REFERENCE DOCUMENTS: Bore logs
6de753fb-eaea-5dbb-ab20-164f2f486356 | note | INSPECTION/TEST METHOD: Verify
df999e31-f6f3-5ad7-b964-ed3979c6a4ba | note | RECORD OF CONFORMITY: Drilling check sheet
d0c77dee-cab4-505e-ac41-65ca375fe7cb | note | HP
da833372-1ad8-547e-97aa-360930002e78 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
805cfd12-14d7-5531-a9c9-d3fe408bd741 | date | Date Completed:
7f55db87-aa8d-43b4-9757-5e565a792264 | signoff | AUTHORITY HOLDPOINT
4f5507a9-38dc-4ca0-93bc-40ae19e4f6d5 | checkpoint | 2.5 - Spacers installed on Reinforcement Cage
ff46ed86-c6c9-568b-bde3-a77bdf39ba3a | note | FREQUENCY: Each Pile
d26785de-d71e-5bfe-b69f-4b59172d2550 | note | ACCEPTANCE CRITERIA: Spacers/supports to be placed along steel reinforcement at a maximum 2m intervals
05fc34dd-6894-503e-a425-3046d50f345a | note | REFERENCE DOCUMENTS: Cl 611.10
1b74c588-b091-57d5-af68-8a747f817279 | note | INSPECTION/TEST METHOD: Inspection
d572c3a7-6823-50d0-95c9-bbd3822d388a | note | RECORD OF CONFORMITY: This ITP Signed off
6b828064-f8d2-5d1e-a028-f7d57f5dfb31 | note | HP*
be1170d2-387d-5877-9802-11d81f612af3 | note | RESPONSIBILITY: Site Engineer, Superintendent
318f130c-8e62-5881-9e89-73779e52308a | date | Date Completed:
fc19ec2c-e9b9-4da5-9b4a-32178fe31ee4 | checkpoint | 2.6 - Inspection of column and cage height and centre
b4a0b526-9e71-5787-a41c-cb6cab16d4ae | note | FREQUENCY: Each Pile
0ef47a0e-ed1f-5806-850b-bbd5c175a5d9 | note | ACCEPTANCE CRITERIA: Ensure heights, centre and spacing of reinforcement cage and column are in accordance with drawings and within tolerance
37950c27-440e-54e1-9166-3a69d7c7a2e5 | note | REFERENCE DOCUMENTS: Drawings Cl 606.08
5591bdbb-ee2b-5a3c-a613-08acdabe5ab8 | note | INSPECTION/TEST METHOD: Inspection
95f463d0-208f-5210-a77d-13f0708a3292 | note | RECORD OF CONFORMITY: This ITP Signed off
099657fb-cd1c-506f-9b51-a2d607180b9b | note | IP
46a54964-2924-5dfd-9dd7-3e6201a09898 | note | RESPONSIBILITY: Site Engineer, Superintendent
5a2a34fb-de2d-5d92-b723-c600cfa55cef | date | Date Completed:
a1543083-0a18-4aad-8394-08d419e8ab68 | section | 3.0 - Placing and Finishing Concrete
73fcbde1-b40e-4a6f-ade2-ca9b051a851f | checkpoint | 3.1 - Quality Checks
f0915946-3961-5203-9cb4-3435ab261ac2 | note | FREQUENCY: Prior to each concrete pour
4b937bd6-93a5-57fe-b219-f4b0c0c9a86d | note | ACCEPTANCE CRITERIA: Relevant ITPs and Quality Control checklists completed and reviewed
c3b425e2-3199-5a9c-90a8-913e361cbd08 | note | REFERENCE DOCUMENTS: Cl 610.18
95709998-dbc1-5b8a-8d33-d4d2dcf583e4 | note | INSPECTION/TEST METHOD: Inspection
f8b4c1c2-3a62-57e7-9123-b60dfaa6747f | note | RECORD OF CONFORMITY: This ITP Signed off
68bacbc5-5840-5a33-aeed-dad626d8642a | note | HP
ef002c4c-93c4-51d4-875e-7b47a5602635 | note | RESPONSIBILITY: Site Engineer, Superintendent
1e184b8f-fdb8-5487-9ac5-0d4cee6e1821 | date | Date Completed:
7cbeebd9-2daf-4230-95a0-b16a51093972 | signoff | AUTHORITY HOLDPOINT
4feaa42b-0344-4c10-94e9-bcfc6ae6a224 | checkpoint | 3.2 - Carry out sampling of concrete
a12f9063-de4d-5af8-ab1d-7ba01d85dff1 | note | FREQUENCY: Each concrete pour
d338db26-ed0f-59bd-aaa5-8996473bb02f | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16 Slump: As per VR450/50 mix 675mm (+/- 125mm) (550mm - 800mm)
027cae97-0672-5b31-b70d-d24d4e5e84a0 | note | REFERENCE DOCUMENTS: Cl 610.16, Table 610.161
76405fdf-1a69-5d9c-9e12-f8050e5b619f | note | INSPECTION/TEST METHOD: Verify
0f9cb192-0594-512a-9156-1a3baba12547 | note | RECORD OF CONFORMITY: Checklist
0a859ea6-5d2e-5cb2-9351-b5836250a28b | note | IP
0417cefd-2606-5029-b0a3-48e875842ab6 | note | RESPONSIBILITY: Site Engineer
cbbd6909-caeb-5225-81e9-7738740488ee | date | Date Completed:
4e118a8c-3233-45ad-a7af-0997f46b103a | checkpoint | 3.3 - Record location of each batch
5d4c1287-dec0-53f7-a475-589adcabea8c | note | FREQUENCY: Each concrete pour
ed8e6e69-207e-57f2-bffc-4a0b5ce8a633 | note | ACCEPTANCE CRITERIA: Batch location recorded
53506938-02d8-54ad-ae87-f4dee67e36bd | note | REFERENCE DOCUMENTS: Cl 610.15
c82f7e3f-2b9a-52b1-99a3-2c1cdee80e8b | note | INSPECTION/TEST METHOD: Verify
2c6efe0f-7071-5c4c-9967-a578faf54c7a | note | RECORD OF CONFORMITY: Checklist
84eb6968-4aa6-50b8-a4e1-d96f002e61be | note | IP
7375cffc-e8e2-5963-a705-6d74ce79c5a0 | note | RESPONSIBILITY: Tester
5718e651-f19e-5d13-a202-b828646d3c6e | date | Date Completed:
57310678-c54a-47a0-86de-7330357c11e4 | checkpoint | 3.4 - 7 Day concrete test result
dea2738b-c46f-5a8e-a1a2-9bf462972047 | note | FREQUENCY: Each sample
d6b60fb6-d535-5250-9996-5fe30d24abf2 | note | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 35MPa
72f99441-d349-5a26-a27c-70b1f84806e3 | note | REFERENCE DOCUMENTS: Cl 610.05
5af6aafb-a4a4-51e8-92d9-3a265884e105 | note | INSPECTION/TEST METHOD: Test Report
04d46e37-2c6d-576b-a54d-3f6681e0d0a1 | note | RECORD OF CONFORMITY: This ITP Signed off
44606ca7-c11e-548e-9fa6-0d330e34c2bc | note | TP
d254d9bd-5406-5210-8f82-9c1cca3572fc | note | RESPONSIBILITY: Site Engineer
a97098d8-001f-5a04-b9ec-502c571b316e | date | Date Completed:
89413466-6dff-4c80-a41b-7b17ae3ffbb1 | checkpoint | 3.5 - 28 Day concrete test result
bae31b42-c0e7-565e-b2ac-24d57f299439 | note | FREQUENCY: Each sample
798a053d-99b9-5fac-a59e-85a4e697e2ee | note | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 50MPa
072ce635-0120-5cdc-a298-c5317bda058d | note | REFERENCE DOCUMENTS: Cl 610.05
9091a287-a183-5e5f-9032-cc5b38649baa | note | INSPECTION/TEST METHOD: Test Report
defdbea4-c6f8-5763-83f5-e01a371f1669 | note | RECORD OF CONFORMITY: This ITP Signed off
f9f338cb-6609-5d02-8453-e71af014efa1 | note | TP
ad5af7af-2ddb-5986-99fd-58de7775431b | note | RESPONSIBILITY: Site Engineer
8cc8677c-6396-57ec-b6e7-960b79ad9761 | date | Date Completed:
1cefac56-a975-4df6-ab32-f9e63b591fd3 | checkpoint | 3.6 - Tolerance Check and As Built Survey
be2a8d3b-769c-5198-a0c2-56749bbf0ed8 | note | FREQUENCY: Each Pile
a1f0472a-ec72-5905-8cd8-30b08f0e8459 | note | ACCEPTANCE CRITERIA: Check tolerances and survey pile positions. Mark all details correctly on as-builts. Pile head position and verticality
3be3a761-0533-5e3d-a1c9-91bec2983219 | note | REFERENCE DOCUMENTS: Cl 605
0c62f368-ffbd-5b81-bf63-ecd3dcac9f47 | note | INSPECTION/TEST METHOD: Survey
6564b67b-32cb-50e0-93c4-7730d9ca138f | note | RECORD OF CONFORMITY: Survey report
09cdbcd9-abce-5482-85cb-b5dd78583bce | note | WP
2cdfd5d7-ec98-5322-a592-57cf5f292999 | note | RESPONSIBILITY: Site Engineer
fd54e042-ea08-5bba-8ae8-a65f0a284b6c | date | Date Completed:
3ff818c4-57eb-4612-ba47-fed5caded742 | checkpoint | Final Inspection
763cd206-1106-5a53-bde5-97d3fee5148c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
392aaaec-debf-5d31-bceb-2e51e46d52d8 | textbox | Print Name:
5be9057a-ea15-5411-b2ab-783170a47e84 | textbox | Position:
8465c7cd-25d0-5b84-9dfa-d0807a3a7f93 | date | Date: