## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - EPS and Sleepers | itp |  |  |  |  | ITP - EPS and Sleepers
section | 1 - Design and Submissions
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Check correct documentation is being utilized (latest drawing revision) and IFC/ Proof Engineering
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Current revision of drawing
label | CONFORMANCE RECORD: Current revision of drawing
label | *HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.3 - Approval of construction material
label | FREQUENCY: No less than 4 weeks prior to commencement of activity
label | ACCEPTANCE CRITERIA: Proposed materials and specifications approved by DPT
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Approval
label | CONFORMANCE RECORD: VicRoads letter of approval
label | *HP
label | RESPONSIBILITY: Fulton Hogan / VicRoads Superintendent
date | Date Completed:
checkpoint | 1.4 - Ensure Safety, Traffic, Quality & Environmental management measures are in place
label | FREQUENCY: Prior to commencement of activity.
label | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
label | REFERENCE DOCUMENTS: PSP, TMP
label | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
label | CONFORMANCE RECORD: Inspection
label | HP*
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 1.5 - Working Pad Assessment
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Constructed as per Design
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Witness
label | CONFORMANCE RECORD: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan / PSM Geotechnical
date | Date Completed:
section | 2 - Sleeper Install
checkpoint | 2.1 - Survey & Set out
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Survey and confirm the position of the Sleeper wall to be constructed
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Survey
label | CONFORMANCE RECORD: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.2 - Construct Pile
label | FREQUENCY: Prior to installing sleepers
label | ACCEPTANCE CRITERIA: Ensure the pile is built to manufactures specification for Sleepers
label | ○ Ensure the pile is level and smooth to allow proper placement of sleepers
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | CONFORMANCE RECORD: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Drainage
label | FREQUENCY: Prior to installing blocks
label | ACCEPTANCE CRITERIA: Install the agricultural pipe on the footing as per manufacture specification
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.4 - DTP Inspection of Sleeper and EPS installation
label | FREQUENCY: First layer of Sleeper install
label | ACCEPTANCE CRITERIA: Inspected onsite by DTP geotechnical
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: This ITP signed off
label | IP
label | RESPONSIBILITY: VicRoads / Fulton Hogan
date | Date Completed:
checkpoint | 2.5 - Placing Sleepers
label | FREQUENCY: Each layer of Sleeper
label | ACCEPTANCE CRITERIA: Place the first course of Sleepers. Ensure each block unit is in full contact with the footing and adjacent blocks and the remainder of the sleepers to the design specification
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 2.6 - Installation of Coredrain
label | FREQUENCY: Prior to EPS backfill
label | ACCEPTANCE CRITERIA: Ensure the Coredrain is installed to the manufacturers specification and the design specification
label | REFERENCE DOCUMENTS: Installation guide, Drawings
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | 3.2 - Installing EPS backfill
label | FREQUENCY: Each Layer of EPS
label | ACCEPTANCE CRITERIA: Ensure EPS is installed as per manufacturer guidelines
label | ○ Each block is fitted without gaps and are laid in a brick pattern
label | ○ Ensure Geofabric is installed in accordance with drawings
label | REFERENCE DOCUMENTS: Installation guide, Drawings
label | INSPECTION/TEST METHOD: Inspection
label | CONFORMANCE RECORD: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | Final Inspection
label | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Print Name:
textbox | Position:
date | Date: