## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Resource to use
Site QA
Tier 2: level 34; Tier 3: North | template builder
Tier 3: east | template builder
Tier 3: west | template builder
Tier 2: level 33; Tier 3: soffit | template builder
Tier 3: North | template builder
Tier 3: east | template builder
Tier 3: south | template builder
Tier 3: west | template builder
Tier 2: level 32; Tier 3: soffit | template builder
Tier 3: North | template builder
Tier 3: east | template builder
Tier 3: south | template builder
Tier 3: west | template builder
Tier 2: level 31; Tier 3: soffit | template builder
Tier 3: east | template builder
Tier 2: level 30; Tier 3: east | template builder

## Checklist Template Builder
Component | Name | Values
checklist | Precinct Cladding Checklist
checkpoint | Structure suitable, with correct stud layout for panel installation
checkpoint | Gib installed and fixed as per gib manual, fixing spacings and location correct
checkpoint | Proclima wrapping applied as per manual, no bubbles. Extora tape to penetrations and extoseal to openings.
signoff | approval by MC
checkpoint | Panel primary fixing spacings below maximum design allowance, with correct gauge and embedment depth. Naideck tape installed.
checkpoint | Secondary fixing spacings below maximum design allowance, of correct gauge
signoff | approval by MC
checkpoint | Sealant installed and tidy
checkpoint | Panels correctly coloured, cleaned without defects
signoff | APPROVAL MC

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty