## HDPE Liner
Project: SH1/29 Intersection Upgrade
Viking HDPE ITP
Item No. | Inspection and Test Point | Inspection/Tested by | Method of Inspection/Test | Frequency | Records | Downer Conformance of Compliance Signoff
[6 empty] | Downer Signature | Date | Comments / Closeout Details
1 | Viking's HDPE Liner ITP
1.00.01 | Safety Induction | Safety Supervisor | Site Induction | Prior to starting works | Induction Records
1.00.02 | Site Safety Inspection | Safety Supervisor | Visual | Prior to starting works | QA1
1.00.03 | Pre start site Inspection | Liner Supervisor | Visual | Prior to starting works
1.00.04 | Subgrade Surface Inspection | Liner Supervisor | As per RFI-R-0144.01 | Each new area to be lined | QA2
1.00.05 | Subgrade Acceptance Certificate | Liner Supervisor | Visual | Each new area to be lined | QA3
1.00.06 | Material Delivery Report | Liner supervisor Quality Inspector | Visual | Each delivery | QA4 QA5
1.00.07 | Daily Progress Report | Liner supervisor Quality Inspector | Measure | Daily | QA6
1.00.08 | Daily Qualification Weld Destructive test as per project spec | Liner supervisor Quality Inspector | Tensiometer | Trial Weld prior to start daily | QA7
1.00.09 | Anchor trench locations and depth before backfilling | Liner Supervisor | Visual & Measure | Prior to lining | QA7.5
1.00.10 | Panel Placement | Liner Supervisor | Measure & record | Daily | QA8
1.00.11 | Panel Seaming Record | Liner Supervisor | Measure & record | All Seams | QA9
1.00.12 | Seam Testing - Non destructive | Liner supervisor Quality Inspector | Manometer Vaccum Chamber Spark | All | QA10
1.00.13 | Rip Rap Placement | Liner supervisor Quality Inspector | As per RFI-R-0144.01 | As placing | Site Record
1.00.14 | Topsoil Placement | Liner supervisor Quality Inspector | As per RFI-R-0144.01 | As placing | Site Record
1.00.15 | Repair Report | Liner supervisor Quality Inspector | Vaccum Chamber Spark Test | All repairs, test method to be confirmed by supervisor | QA12
1.00.16 | As-Built Panel Layout Drawing (sketch) | Liner supervisor | Measure | On completion | QA13
1.00.17 | Practical Completion Certificate | Liner Supervisor |  | On completion | QA14
4.37 | Pavement Marking Materials
| High performance markings | All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. The Contractor shall nominate the brand, type and proposed application methods for materials to be used. This information shall be provided for approval prior to application. | Datasheets | Prior to Installation | HP
| Glass beads | All glass beads added to the paint for reflectorised line application shall be in accordance with AS/NZS 2009 Glass Beads for Road-Marking Materials and the current NZTA Policy and Testing Regime for Heavy Metals (T17). | Datasheets | Prior to Installation | R
| Raised Pavement Markers | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. | Datasheets | Prior to Installation | R
| Edge Marker Posts: | Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval. | Datasheets | Prior to Installation | R