## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - HDPE Liner | itp |  |  |  |  | ITP - HDPE Liner
section | 1.00 - Viking's HDPE Liner ITP
checkpoint | 1.00.01 - Safety Induction
label | Inspection/Tested by - Safety Supervisor
label | Method of Inspection/Test - Site Induction
label | Frequency - Prior to starting works
label | Records - Induction Records
checkpoint | 1.00.02 - Site Safety Inspection
label | Inspection/Tested by - Safety Supervisor
label | Method of Inspection/Test - Visual
label | Frequency - Prior to starting works
label | Records - QA1
checkpoint | 1.00.03 - Pre start site Inspection
label | Inspection/Tested by - Liner Supervisor
label | Method of Inspection/Test - Visual
label | Frequency - Prior to starting works
checkpoint | 1.00.04 - Subgrade Surface Inspection
label | Inspection/Tested by - Liner Supervisor
label | Method of Inspection/Test - As per RFI-R-0144.01
label | Frequency - Each new area to be lined
label | Records - QA2
checkpoint | 1.00.05 - Subgrade Acceptance Certificate
label | Inspection/Tested by - Liner Supervisor
label | Method of Inspection/Test - Visual
label | Frequency - Each new area to be lined
label | Records - QA3
checkpoint | 1.00.06 - Material Delivery Report
label | Inspection/Tested by - Liner supervisor, Quality Inspector
label | Method of Inspection/Test - Visual
label | Frequency - Each delivery
label | Records - QA4, QA5
checkpoint | 1.00.07 - Daily Progress Report
label | Inspection/Tested by - Liner supervisor, Quality Inspector
label | Method of Inspection/Test - Measure
label | Frequency - Daily
label | Records - QA6
checkpoint | 1.00.08 - Daily Qualification Weld Destructive test as per project spec
label | Inspection/Tested by - Liner supervisor, Quality Inspector
label | Method of Inspection/Test - Tensiometer
label | Frequency - Trial Weld prior to start daily
label | Records - QA7
checkpoint | 1.00.09 - Anchor trench locations and depth before backfilling
label | Inspection/Tested by - Liner Supervisor
label | Method of Inspection/Test - Visual & Measure
label | Frequency - Prior to lining
label | Records - QA7.5
checkpoint | 1.00.10 - Panel Placement
label | Inspection/Tested by - Liner Supervisor
label | Method of Inspection/Test - Measure & record
label | Frequency - Daily
label | Records - QA8
checkpoint | 1.00.11 - Panel Seaming Record
label | Inspection/Tested by - Liner Supervisor
label | Method of Inspection/Test - Measure & record
label | Frequency - All Seams
label | Records - QA9
checkpoint | 1.00.12 - Seam Testing - Non destructive
label | Inspection/Tested by - Liner supervisor, Quality Inspector
label | Method of Inspection/Test - Manometer, Vaccum Chamber, Spark
label | Frequency - All
label | Records - QA10
checkpoint | 1.00.13 - Rip Rap Placement
label | Inspection/Tested by - Liner supervisor, Quality Inspector
label | Method of Inspection/Test - As per RFI-R-0144.01
label | Frequency - As placing
label | Records - Site Record
checkpoint | 1.00.14 - Topsoil Placement
label | Inspection/Tested by - Liner supervisor, Quality Inspector
label | Method of Inspection/Test - As per RFI-R-0144.01
label | Frequency - As placing
label | Records - Site Record
checkpoint | 1.00.15 - Repair Report
label | Inspection/Tested by - Liner supervisor, Quality Inspector
label | Method of Inspection/Test - Vaccum Chamber, Spark Test
label | Frequency - All repairs, test method to be confirmed by supervisor
label | Records - QA12
checkpoint | 1.00.16 - As-Built Panel Layout Drawing (sketch)
label | Inspection/Tested by - Liner supervisor
label | Method of Inspection/Test - Measure
label | Frequency - On completion
label | Records - QA13
checkpoint | 1.00.17 - Practical Completion Certificate
label | Inspection/Tested by - Liner Supervisor
label | Method of Inspection/Test -
label | Frequency - On completion
label | Records - QA14
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature