## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement (Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design)
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
section | Transport 01
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 03
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | Other
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
bool | Set out
bool | Core Holes
bool | Install dowels
checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove back propping when instructed by consulting Engineers.
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
section | Details
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Eliment
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation
checkpoint | Embeded Item - Fillet / Chamfer instasllation
checkpoint | Concrete cover check minimum 50mm
checkpoint | Panel Thickness check,allignment check (150Mm)
checkpoint | Panel length check, allignment check
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Double Check the measurments - Diaganal
checkpoint | Reinforcement (Reo) placed, cleaned, tightned
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist
section | Job Aproval Documents/Constrction Documents
checkpoint-no-status | Complete Material "Bucket List"
checkpoint-no-status | Top Edge Lifter
textbox | Lifter:
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould,Supports,Ties
checkpoint | Reinforcment Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check
checkpoint | Concrete cover Check - minimum 50mm
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments (diaganal)
checkpoint | QA - Concrete N32 Mix - Special Adjustments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged
dropdown | Finish | Fine finish,Broom finish
checkpoint | Curing Procedure arranged