## ITP-026
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-021
[11 empty] | Revision : 0 | Date : 08/04/2025
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Wests Road |  | Construction of Track in Ballast Sections |  | Name: | Leo Watson | Name: | Rocky Sam |  | Name: | Shaun Kent
Contract No: |  | 8B6000 |  | Specifications: Yarra Trams Infrastructure - Tram Track Construction Standard, Yarra Trams Technical Specification, Design Drawings
|  |  |  | Structure / Component: Tram Tracks |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : | 2025-04-08 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Works | • Ensure that all employees and contractors are using the most current and complete set of drawings | Design Drawings and Register | Visual Inspection | This ITP Signed Off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Check Materials |  | Prior to Commencing Works | • Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used • Check condition of rail sleepers • Ensure rail jewellery is of sound condition • Ensure ballast is clean, free from clay, dirt and other deleterious matter or weathered pieces of rock and free of dust. • Ensure ballast has been tested for conformity by a NATA certified laboratory and the results have been documented and recorded. On-site testing shall be completed for the particle size and shape of the ballast used. | AS 1085 & CE-019-ST-0033 cl 4.8.1 | Visual Inspection | This ITP Signed Off | HP* | Client, Fulton Hogan Engineer |  |  | N/A
1.3 | Check Base Course |  | Prior to Commencing Works | • Ballast track construction shall not be carried out over any length of formation until the formation has been checked and approved by the superintendent. | CE-019-ST-0033 cl 4.8.1 | Visual Inspection | This ITP Signed Off | HP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check Special Works Components |  | Prior to Commencing Works | Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending. Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails. | CE-019-ST-0033 cl 4.6.2 | Verify | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Check Curved rail |  | Prior to Commencing Works | Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent. Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting. | CE-019-ST-0033 cl 4.6.3 | Verify | This ITP Signed Off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.5 | Welders Qualifications |  | Prior to Commencing Works | Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails TLIW3015 Weld Rails using Aluminothermic welding process TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry | CE-019-ST-0033 Appendix C | Verify | This ITP Signed Off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.6 | Ultrasonic Testers Qualifications |  | Prior to Commencing Works | Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing. | CE-019-ST-0033 Appendix C | Verify | This ITP Signed Off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Placement and Compaction of Ballast |  | Each Lot | • Prior to laying sleepers, 50mm Ballast shall be placed, graded and compacted in one or more layers to a total minimum depth of 150mm. • Compaction shall be by a smooth wheeled vibrating roller as specified for earthworks. • The superintendent shall inspect completed work prior to placement of sleepers. | CE-019-ST-0033 cl 4.8.1 | Visual Inspection | This ITP Signed Off | HP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Installation of Sleeper |  | Each Lot | • Concrete tramway sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement • Concrete tramway sleepers shall also comply with the design offsets at each chainage. | CE-019-ST-0033 cl 4.8.2 | Visual Inspection | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Placement of Rail |  | Each Lot | • Ensure rail strings conform to rail plan • All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts • Bottom of rail and bearing surface shall be clean of foreign materials before laying • Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device • Geometry tolerances as follows: - Centreline location: +/- 3mm - Level: +/- 3mm - Line measured (>10m chord): +/- 3mm - Twist (3.5m chord): +/- 2mm - Cant: +/- 3mm - Gauge (open track): +3mm, -0mm -Gauge,Turnouts (opposite crossings):+2, -0mm -Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Cant shall be applied uniformly over transitions | CE-019-ST-0033 cl 4.9 | Visual Inspection | Completion of track charts | HP | Fulton Hogan Engineer |  |  | N/A
2.4 | Fastening of Rail |  | Each Lot | • Each sleeper shall be fastened to rail with approved jewellery and rail clips. • Clips shall be installed with panpuller or equivalent. • All fasteners shall be sealed as per agreed method with Yarra Trams. | CE-019-ST-0033 cl 4.8.3 | Visual Inspection | This ITP Signed Off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Tampering of Ballast & Sleepers |  | Each Lot | • After track construction and prior to tamping, cribs and shoulers are to be filled to top of sleeper with extra ballast. • All sleepers shall be lifted, lined and tamped after installation and fastening of rails. • The depth of ballast following tamping shall be 200mm from top of sub ballast to bottom of sleepers. | CE-019-ST-0033 cl 4.8 | Visual Inspection | This ITP Signed Off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.6 | Rail End Preparation |  | Each Lot | • Rails shall be saw cut or flame cut • Minimum closure length from proximity of welds shall be 3m • Rail end conditions shall match (i.e flame cut - flame cut) | CE-019-ST-0033 cl 4.9 | Visual Inspection | This ITP Signed Off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.7 | Welding of Rail |  | Each Weld | • Joints shall be square across the track • Maximum skew at square joints shall be 65mm • Portions shall match rail type (i.e HHR, Ordinary) •Welds shall not be within: - 3m of another weld - 3m of a rail end - 1.5m of a glued insulation joint assembly • Field welds shall be +/- 50mm from centre of bay between sleepers • Weld Return forms shall be completed by qualified welder • Welds shall be grinded after 1 hour • Welds shall be free of water • Post grinding, welds shall be cleaned for visual inspection | CE-019-ST-0033 cl 4.9 | Visual Inspection | This ITP Signed Off | TP | Fulton Hogan Engineer | N/A |  | N/A
2.8 | Grinding & Cleaning Welds |  | Each Weld | The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld. Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection. | CE-019-ST-0033 Appendix C | Visual Inspection | This ITP Signed Off | IP | Fulton Hogan Engineer YT |  |  | N/A
2.9 | Installation of Check Plate |  | When required | • Where Tee Head Rails are used at special works, crossovers, or on curves up to 325m, check plates shall be fitted in accordance with Table 2 of the Yarra Trams Infrastructure Tram Track Construction Standard. | CE-019-ST-0033 cl 4.6.7 | Verify | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.1 | Track Adjustment |  | When required | Allowance must be made for expansion and contraction of rail to control stress.In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep. Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008. | CE-019-ST-0033 cl 4.9 | Visual Inspection | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.11 | Track Bonds |  | Each Lot | • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications • Ensure bonds are sealed as per agreed method with Yarra Trams | CE-019-ST-0033 cl 4.5 Design Drawings | Inspection / Test Method | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
3 | Testing
3.1 | Track Testing |  | Each Weld | • All welds shall be tested by qualified NDT operator • Failed welds shall be cut out and replaced • Testing documentation shall be recorded and supplied to the superintendent | CE-019-ST-0033 Appendix C | Inspection / Test Method | This ITP Signed Off | TP | Fulton Hogan Engineer/NDT |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K18: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on M18: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on I26: KAMEL, Mustafa: Is track QA actually a hold point?
Note on E30: BROMWICH, Damon: Include weld tolerance requirement