## Master List Templates
Id | Type | Name | Values | Prompting Name
fab90c11-a510-5a00-9cd8-8b3b9620cbf2 | checklist | ITP-005 - Flexible Pavement Construction | itp | ITP-005 - Flexible Pavement Construction
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
e0e726e1-03f5-5bd5-8794-646fdea2f249 | checkpoint | 1.1 - SET OUT OF WORKS
21a438d3-f799-5869-9ca0-65c3b2e95d5d | note | FREQUENCY: Each lot as required
1d06acbf-a00b-5e03-9db8-c71bc225cc9b | note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
e7ec4598-5998-59f4-a6da-3f7c62b4d1c4 | note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
472ba5b7-b2fb-5b14-afce-13d6e376b05d | note | ○ Refence checking to be conducted with string lines
56cd3848-d046-5659-9cff-3b5220170d1e | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
3c2d0e5c-ad3e-51fb-98da-f6b89fada6e6 | note | METHOD: Survey set-out
46d63712-60bf-5ace-98dd-1bb84e6dab98 | note | RECORD: Signed ITP
21f50034-22b9-5a3f-a7a2-09ceb5f4bd7e | note | SCP
703fbd8e-ae1f-50f0-8dd9-fd0f1075f13b | note | RESPONSIBILITY: FH Project Manager
2c71cf9a-452c-5dba-96a4-f047f6c8fbae | date | Date Completed:
264a16ad-2e71-5132-a15f-6a71ca088ced | checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
e0c1e4c3-01ae-5a28-a97c-457c30e6c254 | note | FREQUENCY: Prior to commencing any activity
83cee339-0a84-599d-96a0-5475fb179165 | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
77b93b7c-0603-5666-8f86-2d17e5e3bf3e | note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
bb1ab119-fea3-5851-ae1a-f1ed4b3d8e0d | note | METHOD: Survey Report
f870a3d7-5a52-5e57-a3ad-fb8808c4ba5c | note | RECORD: Signed ITP
9a11a0fc-62d5-5c21-baed-7d41c3cfb678 | note | IHP
d54a04d6-e5f9-5007-a6a1-5f5743055cd1 | note | RESPONSIBILITY: FH Project Manager
103858ec-6146-5004-8f4e-cc047cefe7fe | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
dbd9ce85-0c7a-550c-99ee-48caf50d3562 | checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
4f049f58-666a-5046-a5a3-8c374b9a2092 | note | FREQUENCY: Each lot as required
890cc7f0-2c5e-5912-a0df-e7880170454d | note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
33ba4406-6891-5a3e-be9b-aeb2dd202059 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
45aafbde-c218-53c8-ba9f-ec8067913673 | note | METHOD: Visual & Laboratory Report
21091960-9352-507b-9d8e-8277980a5e20 | note | RECORD: Signed ITP
6b7d5eae-9cf2-575f-ad7d-b90f11fad58e | note | IHP/AP
80f3b5fd-1d3f-5c4a-af15-dbc902752ec9 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
5b1c301b-eca4-5af8-918b-90a5383de1df | date | Date Completed:
c31cd46c-71a6-5377-9562-3f8dc0f6ef52 | checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
f0d761e5-1cf1-5154-9067-05b632345722 | note | FREQUENCY: Each Lot
73f4bc54-68aa-56d1-8e9f-b58949ad10f5 | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
58ca41af-e55f-53c8-ac78-0969bd212cab | note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
7298ed6a-a8d2-5300-ad8c-a877189c71ff | note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
673b97e8-f973-55cc-a012-7eff9d3dd982 | note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
2d522158-75e2-5ada-b75c-c6d64e3633b6 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
5a2a1a0f-8eb3-5562-985f-a06d6a3bd2ca | note | METHOD: Laboratory Test Report
38b38ded-4382-55a9-8321-91cce0bafc89 | note | RECORD: Signed ITP
fc050c64-6bbd-5fcc-a1d3-60db57ebc55a | note | IHP/IP/AP
aa41352b-a014-580f-a92f-f3367cc11c4d | note | RESPONSIBILITY: FH Project Manager/FH Site supervisor/RRV Superintendent
091e976c-11b3-5010-bec3-26cdfc39bcbf | date | Date Completed:
0ab143a2-e650-5576-bff5-9a365a7ead39 | checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
cf26d6d1-0a57-51a5-8998-6140e6be89af | note | FREQUENCY: Each Lot
7021f6a6-d397-5d7a-891b-d587e34330a3 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
b77690bb-91cb-57fc-89d4-7c8858b0d4ec | note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
ddebae22-3f6e-5344-8a8a-847524cc851a | note | METHOD: Proof roll
5502962f-5656-5b8c-b4cc-be0affcca612 | note | RECORD: Signed ITP & Test Report
1d60d458-0615-5369-8e39-1fa82e4810bb | note | HP/AP
fb4f3192-b1fb-5ea8-99b9-42ab1d8acccb | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
35502628-900b-5e3a-81f1-cd8fab79ff54 | date | Date Completed:
dfb368da-a096-5427-ab0d-4219cac63f72 | signoff | AUTHORITY HOLDPOINT
30dd4d76-cf89-5bbf-94c3-44642a49aa5b | checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
dd9451ef-7628-5777-b511-8406baf71479 | note | FREQUENCY: Each Lot
b5517203-2972-5415-a154-7513e172b6f0 | note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
93744061-4d1c-5633-81ff-e0fcad3646da | note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
7ca6e396-4048-5fbb-a817-d7b9b6aec8eb | note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
8e8eaa68-3058-5d05-bab8-40a44dbc94ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
1bb3836a-8681-55de-961b-4ea84c3730ab | note | METHOD: Survey report
c9b54e4d-138a-5902-a65d-40167a8a0199 | note | RECORD: Signed ITP
17e955f5-a405-5b78-9b63-88db0449b409 | note | IHP/WP
0ee07f49-db61-5573-aa0e-f85d91236efa | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
0e76f698-81d7-554d-acc6-0a5da44178f2 | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
7ac89bf9-222c-5771-bff6-eadc91bf12d7 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
726d8fff-32d0-5a53-897e-89e54955aa0a | textbox | Print Name:
9fd2b4b9-a3d2-5ac2-ae5f-5981ed4b8a07 | textbox | Position:
2b92b7c0-85c8-53f5-8ecf-7a7cc9248cd9 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP