## Master List Templates
Id | Type | Name | Values | Prompting Name
850ee71d-d2df-5dad-a93c-b836182b2248 | checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
26d5d62f-8773-5d6d-81f7-d3753ca4498e | checkpoint | 1.1 - Site Inspection and Base Conditions
d688b9be-5b87-57c4-9401-8e4ee3044ced | note | FREQUENCY: Prior to commencing paving.
77fe2bc8-1442-5be1-96e4-22b2b5e30898 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
5db3395a-5a33-563d-af34-17c90380b207 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
9f664117-1f46-5641-8a55-271a2941339d | note | METHOD: Visual Inspection
f6b9ce53-7b0e-55f5-bf58-2190378470f2 | note | RECORD: Signed ITP
3149520a-eadf-5e65-84c7-25d8c44897df | note | WP
62204960-fdca-5390-8706-6d46b6c16a02 | note | RESPONSIBILITY: Site supervisor
7a542c34-35be-501d-bef9-f7c96b21f6bf | date | Date Completed:
4977d416-cdc2-5db9-a0a9-9fa87c56ca6a | checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0a2ecb52-16f0-520a-a241-548c9b5501b7 | note | FREQUENCY: Prior to commencing paving.
58b668e8-a984-5f99-847e-f7f7849aa2ec | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
21a4db70-16bd-5874-b125-c5d207382d63 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
e74390b4-ae7a-5952-85e9-f515b4722f5a | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
c975c47b-f504-5bc5-af6d-5fc2f3139d57 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
b5ace85e-d10c-5e83-8616-5240a88f8e00 | note | METHOD: Calibrated thermometer
05794ef6-1210-5f5e-988c-9e216f5d1c6e | note | RECORD: Signed ITP
1fa6e8b4-45b7-5c03-9bd0-ad631acac909 | note | IP
b320e086-223b-5c4d-a615-12e62920d7f4 | note | RESPONSIBILITY: Project Engineer/Site supervisor
cc06b2f3-d3c5-5b1b-8572-83b09a446a34 | date | Date Completed:
258a39b8-19ff-5418-829d-82c7f06ce5e9 | checkpoint | 1.3 - Surface Preparation
4e54f265-bace-5007-9924-59ff70e7ba9d | note | FREQUENCY: Prior to commencing paving.
3ca451bd-60bc-5aa8-82ff-2fb8f95d4ae6 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
d7bca43d-b98f-5a72-b645-801e4af922e9 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
b7150c70-7401-5f10-a71c-de2898c7e3a7 | note | METHOD: Sweep Clean and Inspect
6deba588-d573-5826-8f7d-5cf57d2a7308 | note | RECORD: Signed ITP
4f8547f4-8f39-585e-846f-eb93a72dee5f | note | WP
97ac1dbb-d171-51cc-b773-9def1a760570 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
05dbeb64-1a43-5b0f-ab97-a2a9299cfea7 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
3d8767f9-be0b-5aac-8f8d-8d8d30576afc | checkpoint | 2.1 - Application of Tack Coat
2bc89cc0-05fd-5d39-8173-cf3ac73aea87 | note | FREQUENCY: Prior to commencing paving
984a04d0-36e7-50cd-8190-d10f5be69ef0 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
b126fdc9-f32a-5128-a548-41a431071e21 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
a513f9de-8a20-5afb-8cdb-fe7b7bf868e4 | note | METHOD: Visual Inspection & photo evidence
819b6f4c-677c-5939-bf3e-385c4c9c3ddf | note | RECORD: Signed ITP/Spray Record
085a77d8-e12c-5d16-97d2-38661c7775e2 | note | WP
db648bc6-04a9-5f5c-ac17-0872310e84da | note | RESPONSIBILITY: Project Engineer/Site Supervisor
9524c87e-3988-520f-8b62-836e7879ac95 | date | Date Completed:
d22d01c7-b271-511d-bf41-2fff8ae5a522 | checkpoint | 2.2 - Planned Joints
ba46facf-a072-5cc6-93b1-8ddeca9a627d | note | FREQUENCY: Prior to commencing paving
22cc8efb-d9e3-5cfa-9255-9ae523d70f8a | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
ab9a16a0-8110-5e82-9f33-bbb12b923d13 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
95996cce-9371-5937-9658-016a41201d7a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
3d58eaf1-61e9-5cc6-b381-2f3448a26604 | note | RECORD: Signed ITP/Job Sheet
00d39b2f-424d-567f-bfa5-6a0decd08391 | note | WP
9ec50226-d017-515d-846c-a3e479e4b999 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
dbb35a21-e66d-5201-a4d2-1dff79c94fad | date | Date Completed:
6661068e-fea7-5cf6-8f24-87de51d674b3 | checkpoint | 2.3 - Commencement of Placing
cca105be-6bd6-5600-ac6f-65bcc11a3079 | note | FREQUENCY: Prior to commencing Paving
683db6f9-07e7-55cd-8bb3-bdaa06b97f49 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
068e27e3-051d-572c-8924-d5b1ea8f3f4a | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
b511a1d6-2391-58b3-a195-d66345ed525d | note | METHOD: Visual Inspection
53a5f474-6809-567f-bcda-a795f9214c82 | note | RECORD: Signed ITP
63aeb9c7-da48-5ccd-8879-363cd0e982d5 | note | HP
a51be06b-60e3-5c7c-91e1-0b8ed01b9320 | note | RESPONSIBILITY: Fulton Hogan Project Engineer
2feae5b8-a61c-5937-9a35-e1a01f92a36d | date | Date Completed:
34e18449-c3fd-51e1-b56f-ccf521a5d073 | signoff | AUTHORITY HOLDPOINT
6011a022-02be-59a2-94b2-a549f045b1b4 | checkpoint | 2.4 - Delivery of Mix
35c6435e-3596-510a-ab77-9fe4f8e7b182 | note | FREQUENCY: Each Load
8dac07ce-4df2-5efe-83be-bf1ba1081dc2 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9ef15b20-6680-5bdb-9cfb-9fa375011ac0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
ed145bdc-d3cd-59b4-a60d-32e90a0175ef | note | METHOD: Visual Inspection & Delivery Docket
31350090-570c-5cb2-8a93-d05f68c8ecf7 | note | RECORD: Signed ITP & Production Dockets
01d78e9e-b9b9-5b71-bbd4-212c346d7d27 | note | WP
bec095f5-a796-55ca-b444-42f5b4d59bea | note | RESPONSIBILITY: Project Engineer/Site Supervisor
19cc829a-5c9e-5a21-8524-84978ad9bf59 | date | Date Completed:
df52cdfd-6140-55da-9bdb-919ccff3ef0e | checkpoint | 2.5 - Traceability
82c1addb-3683-5b4c-93c1-01ea48344802 | note | FREQUENCY: Each Load
e1f1bbfe-0d5f-5c7f-83bc-c2f11703b555 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
7b7f2e40-84a3-555e-8ae0-489a7049337d | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ee9c3476-6420-55a6-9993-a2d1de3442f4 | note | METHOD: Project Engineer/Site Supervisor
23c11b58-21bc-500e-a1c6-850486660080 | note | RECORD: Signed ITP & Traceability
e70ee5c4-d130-52b6-a5d5-7af94576eccc | note | IP
9adf5571-8d0c-5fdf-b3ae-6535c2707fa5 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
44a30b4e-f09a-5f2b-bfae-62dff848ba35 | date | Date Completed:
c2ae29b9-5806-569e-9a2b-c426503dac7f | checkpoint | 2.6 - Layer Thickness and Level Control
ff96ea57-e6b4-5e2f-b266-c33d5fc970c0 | note | FREQUENCY: Regularly during paving
b8b4c9e2-2100-5327-a3a9-c2ab0e694095 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
5a70b30b-e11f-5018-bb87-4345416cb836 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
08d03c8b-a82b-5ccf-8737-a66353e78fcb | note | METHOD: Dips, string line, measurements oﬀ kerb
ad93486a-b761-59b7-8a32-3da121a65202 | note | RECORD: Signed ITP & Traceability
73b78505-8b06-529d-b7e6-0c4856c4aca5 | note | WP
34ac231a-8cb8-5f66-a3c2-d0bf25788dad | note | RESPONSIBILITY: Project Engineer/Site Supervisor
33018af0-6960-5889-8c7c-7c828282672d | date | Date Completed:
36fd9b7a-b6e8-5247-b9fc-beb7b3b74a89 | checkpoint | 2.7 - Paver Stoppages
002feb29-adaf-5658-ae69-f5df46cafaf1 | note | FREQUENCY: If paver stops
3e721a1b-0f43-56cf-805a-523cb54c3fba | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
942ba5fa-42f6-5275-9f04-0f4ea0d094da | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
a00ce693-9716-5d75-b53b-2000b9676a84 | note | ○ 40km/h – 20-1
d42553af-6974-50c2-90d8-9801971de2bf | note | ○ 60km/h – 30-1
cac18e2c-74bf-5902-8668-cfd79548b07f | note | ○ 80km/h – 40-1
b5595fd4-381d-5048-8c44-8b281365a04f | note | ○ >80km/h – 50-1
81117fe2-cc8b-5f28-91ac-5bc494815aca | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
b2bc6f2f-ff8b-514c-8300-32611bfa4ad0 | note | METHOD: Thermometer
e73f5314-0277-5e7e-b7d9-f0cf640711b4 | note | RECORD: Signed ITP & Traceability
8a42da44-1238-560a-ad9a-d42ac4ae2cb9 | note | WP
1e0101a2-201b-53fd-bb91-8a1a1ca37140 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8ccf48ab-72e6-5fba-bf7d-c5a8ec70a402 | date | Date Completed:
7b5f6175-7f46-5e8e-9ee6-408a701b92a1 | checkpoint | 2.8 - Surface Finish of Wearing Course
4dfcca4d-6cd9-5059-96c5-7f49ee738a46 | note | FREQUENCY: During paving and after ﬁnal roll
69febd5b-5b7e-5aaa-8709-463fd2426c24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
150e0736-0b04-54a4-8e7a-7931c1c79df7 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
df87ffeb-c1aa-56b5-83c7-41217ac9ccdf | note | METHOD: Visual Inspection
9fea420f-2c0a-5f15-ba5e-3302a9a34645 | note | RECORD: Signed ITP & Traceability
984f1f0d-073b-5547-9c56-1bad2e6177d0 | note | WP
29c20c6b-d274-509f-bafb-d926f20bdb16 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
ad523783-fc01-5bf0-a6ee-655ee901c821 | date | Date Completed:
10f33595-9d77-50f4-8495-2fa4d6875210 | checkpoint | 2.9 - Kerb and Channel
07ca60f3-ee52-57e6-b0dd-5cb66e9cc014 | note | FREQUENCY: During paving and after ﬁnal roll
8645ebc8-f881-5f69-8a08-46d7a3097f08 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
8dd06cfd-fb12-53a9-8ad4-f0e267ff66ff | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
767fd6b1-2d01-5b59-84fe-65c38d519d41 | note | METHOD: Visual Inspection & Measurement
ccbd261d-642c-5fbb-887f-4c9d8bd42bbb | note | RECORD: Signed ITP & Traceability
d7fce216-ea7a-573d-b611-c9e33c6889d4 | note | WP
accfc560-ed8b-54d2-a681-96c53a9c120b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8429c875-5a5e-5cce-ae99-b0f6f2a50ad8 | date | Date Completed:
d4973271-760f-5b31-af74-2ebb3b7ab3b1 | checkpoint | 2.10 - Alignment of layers not placed against concrete edge
627dfba2-fac7-556e-9e93-8665eddfa9ab | note | FREQUENCY: During paving and at completion of work
9f42c967-3d8b-50e2-b03a-b701b4fbb12b | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
cb25d7fe-dae1-5e4a-946c-f9075c8adc68 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
93f531db-bdf6-5972-91cb-a8bcc1019e4c | note | METHOD: Alignment as marked by Surveyor and measured
263cd0dd-a3b4-55bc-b476-0f0d7811254b | note | RECORD: Survey Report
7ad599ca-07d1-5ee5-9751-8cf7ecdc9b38 | note | SCP
7db19754-8f98-5056-befa-eb8448c94030 | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
be21af9a-dbbb-5d73-923b-ce2e4ed1d78b | date | Date Completed:
26d72225-2718-546d-bfad-44cc023633ba | checkpoint | 2.11 - Width of layers not placed against concrete edge
4a9a14be-2086-57b2-9593-b9bf91e5b5b0 | note | FREQUENCY: During paving and at completion of work
b081645d-0eff-5ff6-94da-c8c81aba66a7 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5682dcc8-6286-5be5-9903-fe928cd88306 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
e182e220-7601-562e-bf1d-b783541a2e5a | note | METHOD: Measurement
576e1c36-cb82-5e07-add9-c30db9da78dd | note | RECORD: Survey Report
7e12bf87-ce19-57c7-a3cd-c48f136371db | note | IP
701fd94e-b617-5779-a62e-9088f361468c | note | RESPONSIBILITY: Project Engineer/Site Supervisor
e05f32b5-a38f-5191-b348-2b4e005ae60a | date | Date Completed:
d7d138dc-b209-5f3f-9e52-54a34e093893 | checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
297135e5-ed13-5bf2-b6b3-60822e7847e5 | note | FREQUENCY: During paving and at completion of work
8d32ab87-f6d9-51a3-8e39-5ddb6e23cb82 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
d9f9b24e-9138-5594-8bf9-8d9afacda926 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
08f0e70b-8783-508a-a289-8e3212659fc3 | note | METHOD: Measurement or suﬃcient time has lapsed
68f2edb5-423d-58f6-880b-ffe22f7d8951 | note | RECORD: This ITP
1a9d1188-0fef-5f2d-b2ce-39a176b42ce6 | note | IP
7f4e2eb8-984e-5863-aa73-35bf680251cf | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c0ea7700-500e-5ee0-81ff-63d8cd2a82fc | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
6a8c7900-a2b5-5b4c-a9f2-c7a3c37ec233 | checkpoint | 3.1 - Compaction
3ea01a93-90b8-5aad-ab52-1f0ad5c4630d | note | FREQUENCY: Per Lot (6 shot test)
f36c22c2-771b-518e-9f9f-2e96e8204641 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
df530418-75cf-5498-a9e5-98a12f1077d2 | note | ○ 95.0% or greater Accept lot
a885aa2a-d150-5ded-be97-e54e3a8180ee | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
8722fdb1-40ee-5b6c-abb6-5c54ceeb6058 | note | ○ 92.9% or less Remove and replace asphalt
7b0a66d6-9185-5c93-ad10-be01dcf44c4b | note | For layers ≥50mm, if characteristic thickness is:
4c3f1e16-ed84-5603-936e-2256cef26004 | note | ○ 96.0% or greater Accept lot
960a15fd-97c4-5533-bd6b-de6cc1e8d086 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
1ba6fd39-3ae3-5145-8d5c-44343953e3dd | note | ○ 93.9% or less Remove and replace asphalt
e43ae737-0256-515e-8077-48ee79a67f65 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
85937a4b-7422-55a2-b459-567d8e37a27f | note | METHOD: Compaction Testing
48296b9b-c05b-522a-8bdf-b1b3e3e1d468 | note | RECORD: Asphalt Field Compaction Report
c9314ccd-99a3-56e3-99d9-ad7ee2ee0c09 | note | TP
2f032d04-b346-521b-a1d8-8762ffc48592 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
ed7eab13-91ea-5ca6-93e8-5c612059edcf | date | Date Completed:
cbc56fa7-00d7-56ad-8ff1-adc73e4f310b | checkpoint | 3.2 - Surface Levels
a3b57793-0945-5ea8-9026-0401d2e010c9 | note | FREQUENCY: Each lot as required
c97caed1-4c69-5de5-813f-f2b9636177e1 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
56a92c5a-65bf-53fe-9336-974dfc6b8971 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
d96e15c5-222a-5ebb-9cfc-9599336885ad | note | METHOD: Survey
b93cd5ab-2182-52e5-9651-43d28c3e9ba9 | note | RECORD: Signed ITP & Survey Reports
14cf22b7-2397-5b6a-903e-3f50db452276 | note | SCP
fa364c43-4d29-58d2-9f4a-d9e17cc7dac5 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
d05db9ed-8783-5625-8556-9a307514c7ca | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
17776558-95c5-52a4-b43c-e734ad34c2d6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
12075917-4f55-5e71-a2da-d7268412a15a | textbox | Print Name:
59b83e06-98fd-57f0-a0b3-0202a69fc95c | textbox | Position:
58008f9d-4619-5f03-a977-6d42d33a406f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP