## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
| Scope |  |  | Site QA
Rows
|  | Site QA | dynamic | Site QA
Columns
|  | All Subbie Rough-in Progression |  | All Subbie Rough-in Progression
|  | All Subbie Fit off & Testing Progression |  | All Subbie Fit off & Testing Progression
|  | As Builts |  | As Builts
|  | Ductwork |  | Ductwork
|  | Grille Fit-Off |  | Grille Fit-Off
Detailed Progress
| Scope |  |  | Site QA
Rows
|  | Stage 1 | dynamic | Stage 1 | Site QA
|  | Stage 2 | dynamic | Stage 2 | Site QA
|  | Stage 3 | dynamic | Stage 3 | Site QA
|  | Stage 4 | dynamic | Stage 4 | Site QA
Columns
|  | All work in zone completed & appear compliant |  | All work in zone completed and appear compliant
|  | Update As-Built's of any known changes |  | Update As-Built's of any known changes
|  | Pops & flex installed as per latest drawing |  | Pops & flex installed as per latest drawing
|  | Correct hanger spacing/supports installed for flex |  | Correct hanger spacing / supports installed for flex
|  | Free from support off other services |  | Free from support off other services
|  | Flexible duct connections completed |  | Flexible duct connections completed correctly
|  | Blade dampers installed as documented & left in the open position |  | Blade dampers installed as documented and left in the open position
|  | BD pop access panel coordinated & marked |  | BD pop access panel coordinated and marked
|  | Cushion boxes installed as per latest drawing |  | Cushion boxes installed as per latest drawing
|  | Balancing dampers installed as documented & left in the open position |  | Balancing dampers installed as documented and left in the open position
|  | Location of register coordinted with other services & marked on plan or floor |  | Location of register coordinted with other services and marked on plan or floor
|  | Grilles installed in correct location as per latest duct layout/RCP |  | Grilles installed in correct location as per latest duct layout / RCP
|  | Correct grille type installed |  | Correct grille type installed
|  | Grille installed flush & square |  | Grille installed flush and square
|  | Are all grilles installed correctly? Air leaks, vibration or failure |  | Are all grilles installed correctly? Air leaks, vibration or failure
|  | Grille color as per schedule |  | Grille color as per schedule
|  | Grille left clean of fingerprints & caps installed where required |  | Grille left clean of fingerprints and caps installed where required
|  | Grille fit-Off completed to drawings/specification & Area left clean/tidy |  | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)