## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
a097cb40-5552-4755-af59-b706995af1f3 |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 001 - "A" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
5ae40588-29c0-4d4e-8a48-ba73f538a4f5 |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 002 - "B" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
03960d9f-7cb7-4c96-84de-671bc9b8699b |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 003 - "C" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
ed00401e-7d69-4e3f-ae56-a34c448f39d7 |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 004 - "D" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
7dc7299a-d46e-4455-a093-4014d4cf5153 |  | work-in-progress | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 005 - "E" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation -
7c4b260f-66c0-4af3-b55e-3d82c84cb197 |  | work-in-progress | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 006 - "F" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation -
cf823d27-c169-4c8b-8bc0-b02d3390972a |  | work-in-progress | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 007 - "G" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation -
cc93290d-57df-40c2-97c6-bfbce25cd9ad |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 008 - "H" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
dfb1a078-3e01-482d-8bcf-1858189901a0 |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 009 - "I" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
81547592-13cd-4244-9b1c-879e27d5ed28 |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 010 - "J" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
9208d2ea-deb8-40f7-876e-88ed701c769c |  | not-started | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Lot 011 - "K" Drainage line; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation
841a8d6d-e6cc-4f36-9474-25a0e3744e1f |  | work-in-progress | RR-SEPD-BESS-FIC-005-01 - Drainage installation | checklist | FALSE | FALSE | Tier 1: Drainage; Tier 2: Western RW - Weep holes drainage; Tier 3: RR-SEPD-BESS-FIC-005-01 - Drainage installation