## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 1cf9bf3c-5b76-49f4-aefe-ec4432480c18 |  | checklist | Site Diary |  |  |  |  | Yes | Site Diary | 127de568-4a5f-4b33-8796-df1a567534d4
checkpoint-status | 9b11b4a6-e613-4480-b926-17fffe310f22 |  | checkpoint | Areas of work accessible for the day
select | 1f89da42-3e8a-5fd6-b920-eacde811f7f4 |  | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | f2a9ec5b-73b8-536e-abd7-9ea79d6ef749 |  | textbox | Date
text | a33c00d2-deba-5661-b14a-0538f9e927d2 |  | textbox | Year
text | bbc5d704-7b68-57f3-b450-dfbda064b0dc |  | textbox | Number of workers on site
text | 75b26b99-1f15-5d0e-8e45-51934571691c |  | textbox | HSR on site today enter name
text | b882ee4f-26b5-545e-a0a1-9f5da0751d6d |  | textbox | First Aider on site today enter name
text | 12912011-cf4c-5312-b008-94381a8b4798 |  | textbox | Injury on site today enter name
checkpoint-no-status | 0027670d-9fa6-4f14-84da-7980fb699ee5 |  | checkpoint | Work area 1 details entered
text | e8843fc5-8a36-5a89-9ce9-77723430790b |  | textbox | Area
select | 7c019750-bd41-550e-880b-435ada54d7bc |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 58e22317-41d8-566a-9ac5-50073db900b7 |  | textbox | Comments
checkpoint-no-status | 334e12a2-beff-4ab3-b648-308551001281 |  | checkpoint | Work area 2 details entered
text | f067eb10-7646-59a2-8bfb-f73506df5055 |  | textbox | Area
select | 444d58be-9773-53be-9621-97244f8a1f7f |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 44f6f688-c0e4-59e5-b147-a7a3561db636 |  | textbox | Comments
checkpoint-no-status | 0c20e5af-7a4a-41c0-95e6-b90c0f2f530d |  | checkpoint | Work area 3 details entered
text | ad6dd27d-bb97-5c85-86d7-616347993177 |  | textbox | Area
select | ba9c74fc-af64-5d52-b8fc-9e56b16fe6c7 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | d7aea682-2661-534b-8673-9964dec07686 |  | textbox | Comments
checkpoint-no-status | c5fdef3f-4435-410c-bbf2-3bd5c00486a4 |  | checkpoint | Work area 4 details entered
text | 9c110cdd-a116-5e18-b073-0fd2b1c67603 |  | textbox | Area
select | 2b752774-ee64-5f87-bdb3-dd56da10cb01 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 4744a55a-503b-53ed-b59c-8535e2d702c7 |  | textbox | Comments
checkpoint-no-status | 35ed3add-e0fc-4e22-a991-571840a84b46 |  | checkpoint | Work area 5 details entered
text | 8f116bfa-ead9-5f0a-839b-027f109c58e3 |  | textbox | Area
select | 80f97641-c039-511e-8ac9-b1c00b0d52dd |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | d9dff6f5-6528-5f28-99c5-91cabb5d4f74 |  | textbox | Comments
checkpoint-no-status | 606eea05-6422-407d-8900-d54cd49fe716 |  | checkpoint | Work area 6 details entered
text | f82e6215-ce3b-515f-9272-5df4b2e13ab9 |  | textbox | Area
select | 5d0cb0f4-bc0f-5c76-bf5e-08b7bd85ca50 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | eaf71137-beb2-52c0-a0b5-fbcbdb1acde2 |  | textbox | Comments
checkpoint-no-status | 64632d6e-0f23-42e0-aa98-4dbe4410d1fc |  | checkpoint | Work area 7 details entered
text | 70f6d5e3-eb4d-5346-a70a-aabebf2f47fc |  | textbox | Area
select | 1147d62e-63c6-5190-ac24-56a4a0dd3292 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 3b83bee4-80e4-5e57-955c-b83a9c52bbbd |  | textbox | Other
checkpoint-no-status | 57d81170-b55a-46c5-8fb3-d241492cb292 |  | checkpoint | Work area 8 details entered
text | 4062dca0-24a2-5517-ba32-4cca7ccaaadd |  | textbox | Area
select | 57650e9b-a0d3-5421-993d-0deaf8ca53e6 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 34beb10c-8b78-5b29-bb6e-4c6e31cbab28 |  | textbox | Comments
checkpoint-no-status | 2d9a900d-caae-43ac-8a84-e9731da06df4 |  | checkpoint | Weather conditions entered
select | b312da9b-9b76-5ee1-bad7-470466b1f0b1 |  | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | 8fe2180b-ac38-5e42-97ee-38627bf6af22 |  | textbox | Min temp predicted
text | 3fb8097c-ab3a-5ddd-85c5-3aae327bff5c |  | textbox | Max temp predicted
checkpoint-no-status | 108aa9b2-b50c-41dc-9562-342b1afda366 |  | checkpoint | Delays from inclemency
text | 973ef57c-9f96-579c-9e5b-ad034e014539 |  | textbox | Total Hours of delay
select | 02797a8b-c26a-57a8-a9a9-7eb7154003c5 |  | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | ea7a8c19-f405-446f-8819-9a8b118da3bd |  | checkpoint | Delays from Builders or Others
text | 05a6ec7e-eeef-52a4-87af-0dd78cb6c4c5 |  | textbox | Total Hours of delay
select | 194ff355-5bfa-5f4f-a61a-ac7ec42fb179 |  | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist-flat | b3a8a134-249d-4cc5-bbae-a0f6a411987d |  | checklist | SWMS Task Observation |  |  |  |  | Yes | SWMS Task Observation | 1c56360b-f3c0-46f6-996d-ee3ee78693c5
checkpoint-status | 4a5bf7ac-68e1-4789-94d5-34f73fe60e6f |  | checkpoint | Please attach any relevant documents or photos
text | e6009f58-753d-5483-a0d5-5e994cd316c7 |  | textbox | Observer:
text | 363793ea-c38f-5042-ac4b-ed2b090eeece |  | textbox | Task being Observed:
text | 56829dd0-bb4a-5784-9734-168b291d43b3 |  | textbox | Name/Number of SWMS:
text | 15c4925a-a410-53d5-9ca9-b57e4d3a6002 |  | textbox | Workers Observed Undertaking the Task ( add names and positions / roles)
checkpoint-status | 8423d9b5-2506-4269-b218-61d65e905e7b |  | checkpoint | Have the workers been inducted into and signed onto the SWMS?
checkpoint-status | a30908c2-79ff-4672-9f71-cd8cfb347447 |  | checkpoint | Does the SWMS adequately describe the sequence of basic job steps?
checkpoint-status | ae04960c-73fa-4e43-874e-ef44997480f1 |  | checkpoint | Does the SWMS identify the relevant hazards?
checkpoint-status | c25a2ce7-6b73-4c67-9d9e-93338b0b39ec |  | checkpoint | Are the controls being implemented?
checkpoint-status | f8d2b676-a081-4b3d-bfa7-e9f7b46e0a20 |  | checkpoint | Any additional hazards identified?
text | ae1770c5-d31e-5078-bd34-bbe6c9116e26 |  | textbox | General Comments
text | cc0a38f4-64ae-5d1e-b312-de39d30bde43 |  | textbox | Action / Recommendation
checkpoint-status | ac287b7b-cf7a-4f6d-9f13-5faf41c36fca |  | checkpoint | Sign off required ( Person Conducting Observation & Bosfrom representative)
holdpoint | 924fd4af-8c0f-4ba6-8622-56ddf884c1db |  | signoff | Attach signatures
checkpoint-status | e878d306-48ef-4b34-8e40-ebfe5ac4d2c0 |  | checkpoint | Values Added (Office Use Only)
text | f845ac34-3f4a-5f90-8d8f-793b5f849ed5 |  | textbox | Labour Hours Total
text | c55fb6ef-1263-53be-8a41-d317153da340 |  | textbox | Labour Value
text | e744ae32-d6a6-584b-af28-1d54f6014225 |  | textbox | Total Variation Value
checklist-flat | 579b169e-f8ee-469f-9865-61857b7b0e49 |  | checklist | Deck Handover |  |  |  |  | Yes | Deck Handover | 2ab943c6-91c7-4112-b398-5b92cd03a930
checkpoint-status | 4adc6dbf-2b79-406b-b3c4-7b5236c7fdbf |  | checkpoint | Communication between all trades
checkpoint-status | 2c9f5820-e214-4d3d-83d8-dcd6f42b93e7 |  | checkpoint | Signage and barricades in place
checkpoint-status | be19a538-478b-4557-a7c4-8d6752db26fb |  | checkpoint | Deck clean and clear of materials
checkpoint-status | fae71dab-bf8d-4114-a176-ad6827f525e9 |  | checkpoint | Loose materials are stacked and secure
checkpoint-status | 7ac43b2c-7c5a-46fb-856f-e05fc9f476ee |  | checkpoint | Any backpropping required to handle loads of reo and other equipment
checkpoint-status | a80ddd71-07ae-4e4f-a74b-d713140a39eb |  | checkpoint | Designated walkways established
checkpoint-status | 26e6ebf6-cc5c-4654-a607-54076b5dde5a |  | checkpoint | All loose materials removed from edge
checkpoint-status | e09319cf-9b30-43ee-ac42-99946261a05e |  | checkpoint | Are all penetrations covered and secured
checkpoint-status | dc1c6043-a20b-4918-8f7c-48eb243e7854 |  | checkpoint | Rubbish bin on Deck
checkpoint-status | 7bfc9be2-1190-482c-8074-ebc402261b3c |  | checkpoint | Perimeter Screens / Edge protection installed
checkpoint-status | 05c4ff48-72df-409b-88d1-14a2e9757f59 |  | checkpoint | Correct spacing of frames, props and timbers
checkpoint-status | 28f00302-ce08-4392-809e-907b9e74e1ae |  | checkpoint | Correct joist and bearer sizes
checkpoint-status | a44cb486-c9a7-44b7-b386-5d10d2ea62d7 |  | checkpoint | Acceptable jack extensions
checkpoint-status | 76390012-2f4f-48ca-aaff-454316e74a21 |  | checkpoint | Quality of materials
checkpoint-status | 0de3c493-6aa0-44dc-9415-6762fb623a92 |  | checkpoint | Adequate bracing to ensure stability
holdpoint | 7f26dac9-a30b-4b3c-ad73-3ad1fb6018bc |  | signoff | Deck Handover signed off
checklist-sectioned | ee759c27-0e5d-4e65-b5ab-f6ae80aeb1f9 |  | checklist | Stairs (in-situ) Checklist |  |  |  |  | Yes | Stairs (in-situ) Checklist | 34aacfa5-cc1e-44a3-b498-8cff1dbed2ec
checkpoint-group | 70b5389c-6221-4465-a081-eba667df6164 |  | section | Phase 1
checkpoint-status | 44ef3490-0244-4770-8e58-031b74256b2a |  | checkpoint | Area accessible & ready
checkpoint-status | c7f1ba03-83c3-4d18-b561-05ec329486aa |  | checkpoint | Drawing references entered
text | d0074658-014a-5836-8a4f-93b1712325eb |  | textbox | Architectural
text | e582ecf6-d1b6-5e22-b227-afd7a9788b7f |  | textbox | Structural
text | b5f4e876-701d-543e-86a6-cfc04ab33de9 |  | textbox | Other
checkpoint-status | a871093f-da4d-4142-9f45-f0d989a13468 |  | checkpoint | Current plans in use
checkpoint-status | 6ed02d4f-e64e-4179-9caf-9b40b1772c29 |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | cb55bea0-93ed-4fa8-953c-118ceaa76410 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 967feb5f-3ddb-4afe-a846-e03a7e4c7e7a |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 5205f449-71db-4790-b25a-2d9bcd132141 |  | checkpoint | Base of stairs cleaned
checkpoint-status | ee7199f4-bfbf-414b-9670-6c05e5a4465a |  | checkpoint | Riser heights confirmed
checkpoint-status | ae8b49c5-a9b8-4272-9aba-89c147b1ce43 |  | checkpoint | Going lengths confirmed
checkpoint-status | 9e7a3f5f-e4bb-4886-bc7a-d0eca476efb7 |  | checkpoint | Correct Class of Finish
holdpoint | 16645d18-693f-449b-ba9a-dd644c04afc0 |  | signoff | Inspection by site engineer
checkpoint-group | 8ce3de8a-2bdc-4ad6-bf4c-3fb248cb91b2 |  | section | Phase 2
checkpoint-status | 6fc82be8-9667-4804-a7e6-326e46e0896f |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | eeb881aa-3003-4caa-a826-a930abcc79d7 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 34603252-a524-43a3-9e25-4f7414c82691 |  | checkpoint | Base of stairs cleaned
checkpoint-status | b2761e07-0be2-440e-be39-ec797bd0256b |  | checkpoint | Riser heights confirmed
checkpoint-status | 30176ca4-6ca7-44a2-ac34-64192272239d |  | checkpoint | Going lengths confirmed
checkpoint-status | 5b8a0368-e41e-4305-bc9a-bf14fe22be5d |  | checkpoint | Correct Class of Finish
holdpoint | e57458f0-150c-4028-a869-9166f5946751 |  | signoff | Inspection by site engineer
checklist-sectioned | 0b0a45c1-77e2-430b-9e52-b03c45cfc891 |  | checklist | General Incident Notification |  |  |  |  | Yes | General Incident Notification | 44f7bcb8-4d6b-4350-8007-c340942aaa6f
checkpoint-group | 6a0ae64f-800c-4a6e-9fdf-8df93901d185 |  | section | Details of the person completing this form
checkpoint-status | 320b5bde-1230-4244-9cf3-8bbe8c4bd373 |  | checkpoint | Attach any relevant photos or documents
text | 1f173d14-761a-5dd6-a039-32f7c2b66981 |  | textbox | Name
select | a1fa773a-1a7b-5ba6-936c-00f9be770b75 |  | dropdown | Position | Site Manager, Project Manager, Construction Manager, EHS Advisor, Other
text | 692fc316-9ce7-57ca-be4c-69c6a25f6c41 |  | textbox | Contact number:
text | e51b1b1f-b1c0-54b6-b161-ac5c15bfe9f5 |  | textbox | Completion date
holdpoint | e93581e2-f90d-45ce-a5b8-622b3d4f814a |  | signoff | Signature Required
checkpoint-status | b0e206da-78a9-4388-901f-6ca9cd9db34a |  | checkpoint | Report reviewed by (mark if applicable)
boolean | 73466984-e38c-528d-8720-8672de39e5c1 |  | tickbox | Site Manager
boolean | 9726aeea-0b03-521a-b88a-220ab01cd0f5 |  | tickbox | Construction Manager
checkpoint-status | dd0879f7-f978-40fa-ab47-ebfcde49e8dc |  | checkpoint | EHS ADVISER ONLY – Head Office
text | e2ef83f2-a969-516c-b03a-ce46c9321fe8 |  | textbox | Date received
text | 20a53823-719c-5b57-9740-7e03cc2ae995 |  | textbox | Date closed (Final)
text | 40b249f3-4b81-5c96-9552-48a401eb952e |  | textbox | Date submitted to EHS Administration
checkpoint-status | f0c0b5c4-0c8b-4390-93c7-602dbd2b8d69 |  | checkpoint | EHS ADMINISTRATION ONLY Head Office
text | 74fdb73f-7e0c-574f-841a-0e2c49956b8f |  | textbox | Date received
text | 1f93c8e5-0b03-5b21-9e2b-948239c2d02e |  | textbox | Date processed
checkpoint-status | a871c884-6c4e-4611-81f3-9410489e2e05 |  | checkpoint | EHS REVIEW ( EHS Manager)
boolean | 2a98b050-d6c4-5233-b6e3-17afd755bd38 |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 9149302b-6240-54f7-88c4-28a29bbe1356 |  | tickbox | No
checkpoint-status | 16dc866a-aa35-4658-b0e7-d00a08706f62 |  | checkpoint | EHS System / SWMS amendment required?
boolean | 76742ff5-cea2-578b-a5f0-c758c057ac2a |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 4c2f1a69-fcbc-5c0d-aa62-f304b56f8bed |  | tickbox | No
text | d3023cc8-e541-5432-94eb-b7f96b5df8a5 |  | textbox | Head Office EHS Manager sign off date
checkpoint-group | a328f8e3-b247-4c43-9af4-e603350e9ac0 |  | section | Incident Type
checkpoint-status | 28fdd3f6-edc2-464b-8d07-9fc4832170e2 |  | checkpoint | Was a person injured as a result of the incident? - If PASS Only complete an Accident/Incident Notification Report (Form No. 01a) - If FAIL complete this form
checkpoint-status | 5af5b293-9f58-458c-81b4-c2af4f8d6f71 |  | checkpoint | Has an environmental issue arisen from this event? If PASS Only complete an Environmental Incident Notification and Investigation Report (Form No 01b) - If FAIL Complete this Form.
checkpoint-group | 8d96d325-09ce-4aa4-85d1-7d88d9ea119a |  | section | Project Details
checkpoint-status | bfeb095c-0f69-4993-9c4d-160ecf0b5eb9 |  | checkpoint | Report Status and Date:
boolean | fbd9e4f8-d51b-5df3-8101-27b43b04799c |  | tickbox | Initial
text | 8e0c4516-2e76-556c-bd44-fc4d0ddc15c0 |  | textbox | Date
boolean | c12a2c66-d3ab-51c3-a36c-ed1f97e0eb39 |  | tickbox | Interim
text | f8af5f0a-8e47-528b-95f8-3454fc2fdd31 |  | textbox | Date
boolean | 416e175e-b13a-51f7-a009-dc6850e29c4a |  | tickbox | Final
text | b554466e-2ef3-5540-8a95-c2ae0b9a1249 |  | textbox | Date
checkpoint-group | b3c3aa25-9d00-4e86-a124-4db706f5e0b0 |  | section | Incident Details
checkpoint-status | 1e121682-e127-4b8f-bad0-fe9d6f5bb7b0 |  | checkpoint | Date/Time of the Incident
text | f46ef44d-b9f4-55ff-976b-0004965b03b2 |  | textbox | Date
text | 246b6ae9-c3fe-56f6-885b-936678424d27 |  | textbox | Time
text | bd600ca9-ed94-5561-9999-440666c45dc7 |  | textbox | Site location of the Incident
text | cdcdc3d6-8fa5-56d1-88e0-9a1d3d4b436b |  | textbox | Detail how the Incident happened
checkpoint-status | 39e4b49c-065a-4443-bf63-b53e36c452fe |  | checkpoint | Services affected by the event
boolean | 7d980aa4-b3a8-5d85-9f43-b194b5953b5a |  | tickbox | Electricity
boolean | cf726a90-938a-5f52-afa6-ed3b4ae9527a |  | tickbox | Potable Water
boolean | a5fa5c81-6f01-5084-8a83-2905ec78be8e |  | tickbox | Storm Water
boolean | d07250ff-495b-5d7c-b117-41218c7c5ffd |  | tickbox | Sewer
boolean | 4dade4c8-eae5-5619-8d52-207f0ade09d6 |  | tickbox | Fire Mgt Services
boolean | 3b90e5a0-8b6d-52f5-8f03-eaef194e53d9 |  | tickbox | Fire/Smoke Alarms
boolean | 9bfc3bae-4ce7-556a-8c67-352258245590 |  | tickbox | Air-conditioning
boolean | 5909a147-546f-5cb9-9f6e-b1c22e2e7fba |  | tickbox | Security/Access
boolean | bb601bb6-1a58-5b76-bd3b-5a736ba1fe2c |  | tickbox | Communications
boolean | 61d3ca19-7765-5e58-8ced-bf456c7a0638 |  | tickbox | Gas
boolean | 22f5d8b9-ca0e-5688-82b8-bd84f76ad828 |  | tickbox | Other
boolean | 4747c30c-a336-533c-ba56-e99cbc797495 |  | tickbox | N/a
checkpoint-status | 97f77a60-1762-4941-ab17-5e169d847ac1 |  | checkpoint | Detail the factors that contributed to the Incident
boolean | 578168bf-82a9-5aa7-ac75-6d907cf4c8cf |  | tickbox | Design/Layout
boolean | 175fc2ed-2780-53fa-afbc-927c6bb28550 |  | tickbox | Equipment
boolean | 0b926953-8615-5a80-9eba-54692df8bfc8 |  | tickbox | Operator error
boolean | 86ea1fdc-06f1-56b3-b6c8-47601a95ec75 |  | tickbox | PPE
boolean | 3b9679b6-f8d7-52ae-a0be-0bf454d18717 |  | tickbox | Training
boolean | dc389518-6d64-552d-be50-98466d011191 |  | tickbox | Supervision
boolean | 6cdae7fe-e917-5e93-aa54-69f291bd770f |  | tickbox | Unknown location
boolean | 86e46b41-ef97-574a-838a-226d87555f0c |  | tickbox | Other unspecified
boolean | 371eb0eb-d603-5a04-8a6d-2fc77fe396da |  | tickbox | Housekeeping
boolean | 7fd8972b-f371-5d6c-b8e6-05db1417ff4f |  | tickbox | Procedure (WMS)
boolean | 53e3f072-42a3-58fb-be38-fe9110c5e442 |  | tickbox | Weather conditions
checkpoint-status | f4c09ece-9b2f-4da6-98fe-369f9eaac348 |  | checkpoint | Was a WMS supplied for this type of work?
checkpoint-status | 13e33866-d6c9-4f4c-b0ff-21ef11083c4c |  | checkpoint | Was the WMS approved by Principle Contractor
checkpoint-status | a7670202-af4f-450b-b04f-55c90e686ec1 |  | checkpoint | Was the WMS signed by all personnel involved in the activity?
checkpoint-status | 9ae1ebb3-c0fb-425a-bb92-47e22941170f |  | checkpoint | EHS Improvement Notice
checkpoint-status | 3cfa8035-5f3e-4e92-8ecc-adb5a3a9791c |  | checkpoint | Was the work activity being performed in accordance with the WMS?
checkpoint-status | 856489e0-4f76-4b35-86d3-0cbdffa5a7d0 |  | checkpoint | Was a Tool Box Talk held relating to this work activity?
checkpoint-status | b74bd8ca-fe80-4859-923a-7508bdf52a60 |  | checkpoint | Was any external certification required for this work?
boolean | 0def7d08-7cce-5ad6-adfe-f2729bba49b4 |  | tickbox | If Yes, was it obtained prior to works commencing?
checkpoint-status | a3403062-02c5-4410-8a70-4250e7381237 |  | checkpoint | Was any monitoring required for this type of work?
boolean | cba5379c-223f-5aa6-be4d-9abd9054d7b0 |  | tickbox | If Yes, was it in place?
checkpoint-status | ac726257-719a-4fe0-8cec-42d525b1d9bc |  | checkpoint | Was an Authority to Work Permit required?
boolean | d9c2fd29-3e33-5f21-a934-62911a889846 |  | tickbox | If Yes, was a Permit issued?
checkpoint-status | 35b34b89-0d44-4f2d-9985-e51c750b0709 |  | checkpoint | Were any Regulatory Permits required for this work?
boolean | 417b026b-8a0d-55cf-9606-f7617a682c78 |  | tickbox | If Yes, was a Permit obtained?
checkpoint-status | ac38a827-8e04-4301-8827-99a61071607e |  | checkpoint | Was a Notice of Impacting Activity required?
boolean | e63e2c0a-92eb-51ae-87cb-65e3ffdd6983 |  | tickbox | If Yes, was it issued?
checkpoint-status | 7200c515-9414-4b78-a8c9-23fc68fbb701 |  | checkpoint | Estimated time impact of the event
boolean | 092a9f21-97c2-5d5c-b901-f8e49396b17e |  | tickbox | No impact. No loss of production.
boolean | 9601c0e7-54c3-58e3-ba61-cdcf34534c0e |  | tickbox | Limited impact. Production loss in localised area.
boolean | 6d652116-e53b-505a-88a7-2929404049e1 |  | tickbox | Major impact. Production loss across project site.
checkpoint-status | 7c056e9d-d864-4311-b78c-791ba6e31dfa |  | checkpoint | Details of any persons involved in the Incident - Attach Statement forms to this report
text | d823e307-a69c-599c-a028-1cf29f81922e |  | textbox | Full Name
text | 70a15afb-1dac-5dbd-b628-7fa58844ed7c |  | textbox | Company
text | c0feaf97-77ac-5c09-9d31-0b7e533e7c39 |  | textbox | Contact No.
button | c0b6759c-b022-5708-9262-18245cf7d826 |  | button | Statement | Yes, No
text | e8158626-5d4a-59bb-bf38-94cfab3ec29a |  | textbox | Full Name
text | 1c4d535f-963d-518b-9ef0-0cbf7e495f5d |  | textbox | Company
text | 9f05824c-1aac-5bde-9094-2e76f6ce0681 |  | textbox | Contact No.
button | b69d4de4-de78-5522-a45e-7c37d74cb4c2 |  | button | Statement | Yes, No
checkpoint-status | 30c61c0d-64cd-4710-87fe-546eece47b7a |  | checkpoint | Details of any witnesses to the Incident - Attach Statement forms to this report
text | 237e5ee2-27df-54bf-8944-9529e8efaf2b |  | textbox | Full Name
text | 6d286b15-b5c0-5e92-8989-9334d2aab099 |  | textbox | Company
text | e5ccd465-ccc4-5f7d-ae1a-ba3b48e18050 |  | textbox | Contact No.
button | 754eaac0-f137-5b9b-b36c-e2d0a8519199 |  | button | Statement | Yes, No
text | 9fad4f2d-83f0-52dc-9b68-1f67c191e329 |  | textbox | Full Name
text | 3fef7105-56e9-5ef6-91ed-0f074df25147 |  | textbox | Company
text | a8045c48-a6f4-5f74-a43c-94099b36f6e8 |  | textbox | Contact No.
button | 02ebe7e3-8d9e-51d2-8486-ba3838230cdd |  | button | Statement | Yes, No
checkpoint-status | cec4f58a-2b25-4f7e-8493-1fc79ce4296a |  | checkpoint | What actions have been implemented to prevent similar Incident
boolean | 3c55f730-c55b-5444-889e-b3ad0f9ab42a |  | tickbox | Equipment change
boolean | 0b81303e-4e8f-5ca7-9359-29124c281f01 |  | tickbox | Certification obtained
boolean | 3425f727-8965-5ab7-8346-9f27ccc12d08 |  | tickbox | WMS change
boolean | 0f2049d5-cddf-5b04-909a-6e672b295cec |  | tickbox | PPE change
boolean | 2192028f-440f-55ee-b79c-2d6fff65c5a2 |  | tickbox | Site Meeting
boolean | 845bcd55-a1c1-5bdd-bc1d-2f00abc59096 |  | tickbox | Toolbox Talk
boolean | 931b3ec6-b6be-5932-95d8-f6975b09b7cb |  | tickbox | Housekeeping
boolean | c0063800-044e-5b5a-bb04-32f98fd44e38 |  | tickbox | Training
boolean | f4cd21d2-28f3-57fd-9e28-66cddc1e2f9b |  | tickbox | Other
checkpoint-status | eaad49c1-19f0-4165-a764-fa344e809f0c |  | checkpoint | Has an EHS Instruction been issued to the P/C company or Bosform?
checkpoint-status | 5ac7018f-1f2d-4e13-ac30-e0e1c836b4f0 |  | checkpoint | Has an EHS Improvement Notice been issued to the Bosform?
checkpoint-status | cfc5dae3-0470-4cfb-b8de-b7a0f5bdbaa8 |  | checkpoint | Has a Risk/Hazard Assessment been completed?
checkpoint-status | 340b4f2c-2367-4c34-9025-9f73420fa9ec |  | checkpoint | What Hierarchy of Control measures were considered in the corrective action
boolean | d186c924-a5c9-5d76-b014-284581bf0808 |  | tickbox | Elimination
boolean | b5b4256c-6976-5711-88a8-54b18d354bdd |  | tickbox | Substitution
boolean | 24a32e0c-61ce-5c34-8ff4-939039e3c12c |  | tickbox | Engineering
boolean | dc1ec8b4-3dfb-5b88-83c0-584faa948346 |  | tickbox | Administration
boolean | 402f9a4f-1930-556f-a8d9-e95253bc6fe2 |  | tickbox | PPE
text | 426a8773-df17-545e-9ac9-b03b1a05edc5 |  | textbox | Date of action
text | 40cc0596-28bf-5245-aaaa-0f0ffbd8d165 |  | textbox | Responsible company/s
text | b617f0a8-523d-5eb2-99f2-606d5c09aa9e |  | textbox | Review date
checkpoint-status | c09696c5-3855-4ae6-9a64-77fc66935b15 |  | checkpoint | Statement/s
checkpoint-status | bd8ee7cc-e463-41ce-bcbd-fabe0cf3c5d8 |  | checkpoint | Monitoring certificates
checkpoint-status | d3107443-caa7-48cd-ae2f-331cee03a23f |  | checkpoint | Site Induction forms
checkpoint-status | a6eb1e58-998b-440f-803f-2c37e48f0310 |  | checkpoint | WMS relevant to the activity
checkpoint-status | f0cadc2d-79dc-4880-b1fb-3e002896ea38 |  | checkpoint | Tool Box Talk or Meeting form/s
checkpoint-status | 92b9b42a-705e-48f9-81c7-f1e149922118 |  | checkpoint | Engineer certification
checkpoint-status | 71b94b65-3ef6-46cc-b83e-a6c4ed147b34 |  | checkpoint | Photos
checkpoint-status | f7844a6b-f9a6-45a2-8daa-dc35aa1adccf |  | checkpoint | EHS Instruction
checklist-flat | 2935656a-e2b5-4ea7-88e2-cf801e7087b0 |  | checklist | Columns Checklist |  |  |  |  | Yes | Columns Checklist | 4bbffd5c-21e5-4d23-a407-3f06b6cf2aa6
checkpoint-status | edb915fc-6f3e-4fa4-8328-f81205fef49f |  | checkpoint | Area accessible & ready
checkpoint-status | 47a89d76-c81f-4332-86bb-3e00666af67d |  | checkpoint | Drawing references entered
text | fbec3f52-0e9d-5cbb-85df-092019fa301f |  | textbox | Architectural
text | 6a8eca08-6dfd-5699-b5b6-8d3b07899a21 |  | textbox | Structural
text | 87dc16db-d355-5779-b89a-95844ddc5011 |  | textbox | Other
text | 5c7ee2ca-d3f8-5933-bd43-1138cf693c0e |  | textbox | Column No
checkpoint-status | f10c0f70-0e53-4c1c-8624-a6b3055b62a7 |  | checkpoint | Current plans in use / Latest drawings checked and referenced
checkpoint-status | 6b10ce08-9d6b-4702-8470-e0245827d04b |  | checkpoint | Survey points given for 2 points
checkpoint-status | 0a0dba8f-9fdc-40cb-a9cd-67448924aaee |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status | b1f4238a-d116-4cf6-8f20-7d1152c95365 |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint | 7bc92e6c-d165-4b4f-9d48-8f001e455458 |  | signoff | Inspection from site engineer
checkpoint-status | 9bb5ba36-4d62-4f8b-b822-d6d5f31cbc31 |  | checkpoint | Column box cleaned & oiled
checkpoint-status | 8fad520f-8677-4699-9781-8317292927b5 |  | checkpoint | Placement of column box over cage
checkpoint-status | abbca84b-82c2-4798-8de5-a6d7ef251d7e |  | checkpoint | Bracing props secured
checkpoint-status | 4ee78f44-2225-41a8-90bc-3e5647cd879c |  | checkpoint | Column plumbed
checkpoint-status | 7bd0779a-029e-4f60-9321-a5c9a17eb3e8 |  | checkpoint | Correct class of finish
checklist-flat | 1a91e2a5-a030-4c2d-aea5-525feb84aa62 |  | checklist | Injury Form |  |  |  |  | Yes | Injury Form | 6a2da01d-e683-433d-ae29-46e381707308
checkpoint-status | 6e21b5eb-b7ef-46a7-b22d-f5d0baeea3a3 |  | checkpoint | Injury form completed
text | fafb7c4a-e670-5d1e-a653-6a62e8967839 |  | textbox | Date of incident
text | b9e8c1e6-0017-57bc-9142-65d903d98553 |  | textbox | Time
text | 4aac2ad4-3267-5828-a16d-48776ea97e0e |  | textbox | Site location of the accident / incident
text | 3f5b7fb4-920d-5620-bff5-26dcfc228420 |  | textbox | Detail of how the accident / incident happened
label | 3ee3d7d8-572d-5028-a73b-f71eb93494af |  | note | Details of injured person
text | 5d80093d-5e7d-5a67-8ae5-d27f19501d6c |  | textbox | First name
text | 376795fa-d3ca-50ce-9599-4eb1d40a9b03 |  | textbox | Last name
text | 1ef785b8-20b2-5007-bfd5-90ee70b0105f |  | textbox | DOB
text | 499d0722-3e90-526f-9d44-0e2977214f58 |  | textbox | Contact No
text | d13ccfa2-bce2-5d7a-97e4-35c8c7112060 |  | textbox | Address
text | eef46ef3-fad9-55d4-aaa2-8567fc606071 |  | textbox | Company
text | 457c1ff3-eb94-547b-8fc7-dba4836c417b |  | textbox | Trade
text | 5e805f20-8d72-5b8a-a64d-c725579f74b4 |  | textbox | Date Inducted
select | ad46207c-36ca-5418-99d9-4b42d06912b5 |  | dropdown | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
select | e6b8813b-0d59-5d64-928f-4ab7dde851b9 |  | dropdown | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
select | 8e127b5a-11b8-54c5-83dc-b9f5b490f438 |  | dropdown | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
text | 18386197-c406-5543-af2c-e29742b4860f |  | textbox | Initial treatment given
text | 4a7fe413-2474-5fab-8f54-191dcbf01177 |  | textbox | Was follow up treatment provided
text | bde6dc55-b2f9-582d-8595-3a268d191082 |  | textbox | Medical centre / Doctor / Hospital attended
text | 11612d7b-d5bb-5bb1-93b9-6eafa72f3dc5 |  | textbox | Date / time attended
button | a5b2e2c8-d8ec-535b-9c55-b8009d3251f7 |  | button | Regulator notified | Yes, No
label | 2377a798-3adb-5f9c-8816-2abec3bd6a59 |  | note | Witness details
text | 4284be98-0f0b-5bed-b8ab-456c74f50a2f |  | textbox | Witness name & contact details
text | 3317dcc6-98d8-5796-8a29-91bd29dd86d4 |  | textbox | Witness name & contact details
select | da9f647b-e24b-55e8-9b70-b6808efd7ff0 |  | dropdown | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
text | 1da88f8f-11b4-5a7a-8f7f-6dfe4cfac242 |  | textbox | Other
label | f1ecbbb8-4ea6-5c8c-8bc3-1012db25291c |  | note | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
checkpoint-status | f03ca5be-d06a-4ce6-ac69-9bd3592e2533 |  | checkpoint | Signature of injured worker
checkpoint-status | 0ef480d1-4ce1-454e-b545-d2f50fe70cf7 |  | checkpoint | Person completing this form
checklist-flat | 0c8742e8-ea5d-4612-9c13-94e2ffe52fc8 |  | checklist | Walls Checklist |  |  |  |  | Yes | Walls Checklist | 6e6be716-9add-4360-8e57-dac13a94640a
checkpoint-status | b659b013-5679-49fe-8a05-2efa9714f78f |  | checkpoint | Area accessible & ready
checkpoint-status | 6192288c-ebe6-4c0e-980e-ff6a15e98323 |  | checkpoint | Drawing references entered
text | e8928ff8-aa26-588f-aecb-10747ee3ef91 |  | textbox | Architectural
text | c3c0c55f-878e-58cb-9e13-c4505318d307 |  | textbox | Structural
text | 43002f5e-f2cd-5674-9b0e-821c90ada4a8 |  | textbox | Other
checkpoint-status | 831e355b-1c61-4643-98db-1747bd30ff30 |  | checkpoint | Current plans in use
checkpoint-status | 252148d4-239d-4d4b-8eec-ef597b99269e |  | checkpoint | Survey points given for 2 points
checkpoint-status | 9206f2b2-cc79-4845-ba64-d88f266f80cc |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status | 10479613-5b48-45ea-9256-db0a3b56db3f |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | fed0c838-fdfd-484b-ba4c-343f32e91738 |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status | 1687a292-ae50-40f4-a91f-06092b6fe679 |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status | fa35dc11-c62d-4850-9c33-970cd473ed9d |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | d8260235-7fed-44a8-a395-e889d0de076a |  | checkpoint | Base of walls cleaned
holdpoint | 16303d2d-f277-4f3a-8639-bd5a9893a2d0 |  | signoff | Inspection by site engineer
checkpoint-status | 67c1c435-42fd-4505-8c92-570d6a88c14e |  | checkpoint | Closing shutter installed
checkpoint-status | 1118ad99-1000-4dd3-8317-1c1ffad78cac |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status | c5fd4140-f349-472b-aa93-68acaef00e85 |  | checkpoint | Correct Class of Finish
checklist-flat | 67c679ea-0fee-4188-a485-6c6b9ccd3dfe |  | checklist | Suspended Slab Checklist |  |  |  |  | Yes | Suspended Slab Checklist | 877e1ef9-5f81-4243-bdd7-f9729aa54c9c
checkpoint-status | e8fe9920-e73e-482f-ba05-91244a091ec0 |  | checkpoint | Area accessible & ready
checkpoint-status | 1fc08894-8127-4061-91e4-7b659e9aace2 |  | checkpoint | Drawing references entered
checkpoint-status | aff4d3bf-ef89-454b-99e6-12361fce8857 |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 8d24b493-1c7b-465b-bf8f-b3cd196f7f71 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | a5c5eb87-4697-49f9-bb43-4933eaf0019c |  | checkpoint | Grids marked by builder
checkpoint-status | db6a3cc1-500f-419d-ac21-7586f5fb2a21 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | b4301763-8455-4209-b55b-47eed54323fb |  | checkpoint | Fillet & drip mould installed
checkpoint-status | f46af747-2a0a-44ac-aa52-a1ae1fe26cc0 |  | checkpoint | Check set down position & RL
checkpoint-status | b96d5a1e-89f1-4671-ae0c-53096540ddde |  | checkpoint | Check penetrations installed
checkpoint-status | cfb6640a-b162-4abf-99fa-ea9e9f22a678 |  | checkpoint | Prop drop head wedges are secure
checkpoint-status | 2050fb74-4275-4dd1-8810-88fe5d327db3 |  | checkpoint | Column blockouts installed
holdpoint | 8cebb797-13ae-4861-b371-03149ddb273e |  | signoff | Inspection by site engineer
checkpoint-status | b77a99ae-9cc6-43d8-91af-e3457b328894 |  | checkpoint | check back propping as per design
checkpoint-status | 9d24cbd2-9b98-4cf2-b9cf-6d7b06ae8725 |  | checkpoint | Blow off deck
holdpoint | 7b766f55-4c70-4410-acbf-9604e1ed8b81 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | a9ef3739-75d9-48f8-ad62-6e715c192dd6 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | cfbca866-0a47-4bf3-a99e-0e7442a18b6c |  | checkpoint | Correct Class of Finish
checkpoint-status | 0a305487-8de2-44a7-b833-9ff608f4e204 |  | checkpoint | Stripping, cleaning & materials removed
checklist-sectioned | 9cb7e785-726e-45fa-9146-cfd02119c254 |  | checklist | Stairs Checklist |  |  |  |  | Yes | Stairs Checklist | 9eca252a-0b71-4acc-822b-2e916010bcfe
checkpoint-group | ffb0c201-8c24-47f3-95e1-4ab265c37406 |  | section | Phase 1
checkpoint-status | 7c12cf20-1ff3-4cf3-96bc-f3859481333f |  | checkpoint | Area accessible & ready
checkpoint-status | ae205a49-2cfd-43d3-8672-ae28d8e919d4 |  | checkpoint | Drawing references entered
text | 31f907cb-c90d-5583-9683-a7fb5e5791ed |  | textbox | Architectural
text | 820fe366-9158-5231-8247-d8ce4e645785 |  | textbox | Structural
text | 45084d4d-19b4-5bab-b6c6-a1cd6270bfe1 |  | textbox | Other
checkpoint-status | 1405f53a-94e6-4ef6-a113-03bd80471652 |  | checkpoint | Current plans in use
checkpoint-status | f1b3872f-a6d5-4f74-8f3f-6be77b45369b |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | cd6ae7c8-1164-4f66-9894-6acd9fb4e2db |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 081438fa-b875-4731-ac29-09b24b7d74fc |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 47649c80-ac92-4cc3-a5fc-7c10c988ea02 |  | checkpoint | Base of stairs cleaned
checkpoint-status | e64db8b6-e46b-4b45-bc07-46e5768b7b7b |  | checkpoint | Riser heights confirmed
checkpoint-status | 0e6bd656-5177-43ba-8ed3-0ca02427e0ba |  | checkpoint | Going lengths confirmed
checkpoint-status | 7837d0f6-1ecf-4d5e-85bb-cf660b044624 |  | checkpoint | Correct Class of Finish
holdpoint | 22ff1126-28ed-4379-bb0e-fdee7acd1c08 |  | signoff | Inspection by site engineer
checkpoint-group | 79e7bf5a-4338-4a63-a742-55ef98587426 |  | section | Phase 2
checkpoint-status | 03fa6a3f-5315-48a5-92ea-adfec2c81e99 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 79dd2097-ac85-49eb-8fae-6d5c51189348 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | c038dc50-98e6-41b6-9c03-48807c5bbe22 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 8963c1d2-16c7-4129-a17e-973c4f9c304e |  | checkpoint | Riser heights confirmed
checkpoint-status | 45f7c7c9-5c54-4b96-b362-3a7402e087a2 |  | checkpoint | Going lengths confirmed
checkpoint-status | 646095ac-c485-4a89-949d-0e88194e6c50 |  | checkpoint | Correct Class of Finish
holdpoint | 6e6cd75c-babd-4f48-87df-2be6b137f322 |  | signoff | Inspection by site engineer
checklist-flat | e4b6d836-3417-4718-b423-2567f62d0839 |  | checklist | SOG Checklist |  |  |  |  | Yes | SOG Checklist | b52221ca-278c-4f2b-8ba4-9ce637b2bf65
checkpoint-status | 4a151275-2f41-4692-8f02-adf435413c18 |  | checkpoint | Area accessible & ready
checkpoint-status | 07142055-e516-46c2-b718-c30aba26088d |  | checkpoint | Drawing references entered
checkpoint-status | 92235a8e-48ed-41f7-8a06-14a0d1193e2f |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 9b3b714b-4bb4-4b2d-b4bd-deb26a9aa257 |  | checkpoint | Grids marked by builder
checkpoint-status | 372cfba1-9a49-4736-8b79-a61476d80d9f |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | dc012141-a0a6-4e53-a088-f1023b1c5bee |  | checkpoint | Edge Boards Secure & Placed in correct position.
holdpoint | b6b0a38c-66d1-4637-bca7-fc01b284c724 |  | signoff | Do not commence concrete till all works agreed
checklist-flat | 6b6ea132-3339-418f-b8a4-fee91093201c |  | checklist | Daily Pre Start |  |  |  |  | Yes | Daily Pre Start | be7cc5cc-1ad4-417d-a668-41dcd1a692b9
checkpoint-status | e0c70a85-e8fb-4b44-b8f5-ac1cad2cdb8b |  | checkpoint | Daily pre start meeting completed
text | 1467d3e6-99bc-55b0-883e-ad087b263a3b |  | textbox | Date
text | 46c88c4e-1e31-5641-917d-1d2af0a8555f |  | textbox | Time
text | 16190550-6161-5778-af14-d5cb04c64c61 |  | textbox | Location
text | 2c603086-ce36-5413-97f2-c7a6496fe011 |  | textbox | Supervisor / meeting leader
text | 10d4de6b-fe8a-595a-b37d-d686c361465b |  | textbox | Project Manager & Construction Supervisor attending
select | 222f2ab4-e902-5506-872e-c66346ec1fe1 |  | dropdown | Current weather | Rain, Wind
text | cdced135-989e-5001-b087-34ec773b0f92 |  | textbox | Temp
select | 1b4a6bba-15b0-52fe-97b9-e69219613421 |  | dropdown | Forecast | Rain, Wind
text | 0e01ace5-9aaa-5457-a159-7ff7234f62f7 |  | textbox | Temp
button | a4bdeff9-b80d-5055-bf78-ccb1602bafc8 |  | button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
button | ef0ae1f3-62f6-5205-974d-07f4032daa0e |  | button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
text | b4876fe4-bd9e-5d20-83fa-b5126a030327 |  | textbox | Any issues from the previous day
button | c93c6834-3b82-53bd-bb62-e49433cf2286 |  | button | Do you need to change SWMS | Yes, No
text | f160ed73-ee87-5ada-8864-ed5a3d652739 |  | textbox | First aiders on site today
text | 68bb3cc9-fc2d-561c-89b7-57dbe18171f2 |  | textbox | Apprentice & who are they assigned to
text | 94f7cd14-1359-5fac-850f-a4c9b7be88e7 |  | textbox | Apprentice & who are they assigned to
text | d37117ed-ddee-5dd3-a7cc-5f3470d4a6ba |  | textbox | Apprentice & who are they assigned to
text | 55768db0-f3dc-5414-bfdf-efa063d715bd |  | textbox | Todays tasks / jobs
select | 14bb7af3-fdae-50f9-aa04-6a460e359f63 |  | dropdown | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
button | 1dda8434-30c9-5ea9-b78b-0258acf98cbc |  | button | SWMS in place for all activities | Yes, No
button | d273b09f-4e56-5132-aaa2-8c80b94f8c34 |  | button | Hot works | Yes, No
button | 55a0afcf-5034-5e47-a893-8d2c21aa5e8d |  | button | Excavation | Yes, No
button | f0a31025-a6bf-5b0e-9c38-fb8c985d58c9 |  | button | Ladder | Yes, No
button | 917d4535-fc21-50d1-8624-06976c84e822 |  | button | Core | Yes, No
button | db741a2f-afd8-5328-95b3-7f6dfc5fb5c6 |  | button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
checklist-sectioned | 6a698e78-ea57-4992-9a97-33f68dc5079d |  | checklist | Core Lids Checklist |  |  |  |  | Yes | Core Lids Checklist | c7ab8eb2-4a98-444e-819c-517c6866ea74
checkpoint-group | 6267a8d9-8375-411a-aedf-cef566e4aa45 |  | section | Phase 1
checkpoint-status | 4902f2fb-348b-46bd-ae03-fc54f269bf08 |  | checkpoint | Area accessible & ready
checkpoint-status | d74ebd9a-4db8-4260-aa21-63ef0b1916fa |  | checkpoint | Drawing references entered
text | 80b80cfe-6938-5de8-8fdd-d45f9366daad |  | textbox | Architectural
text | f5778c90-e274-56b3-868d-766d9f7852aa |  | textbox | Structural
text | 61d0b488-e7f8-530a-902e-277a6a6940d7 |  | textbox | Other
checkpoint-status | 5b6923b2-3e5f-4a97-af25-ac2d401ebd8c |  | checkpoint | Materials used complies with design documentation
checkpoint-status | ec339729-9d3e-458d-a731-b23a672467cc |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | d46ad51f-91d2-4e67-9216-07f2d3c20d10 |  | checkpoint | Grids marked by builder
checkpoint-status | 1eba3dae-343d-41b4-aafc-84110ccba009 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 6a3052a4-68d9-435e-8ac9-f5461fc27414 |  | checkpoint | Fillet & drip mould installed
checkpoint-status | 0f06d0a9-ccbf-4a1e-87df-2c3a5129c747 |  | checkpoint | Check set down position & RL
checkpoint-status | 07072ef9-bf3e-4b48-8744-f8b2605c858a |  | checkpoint | Check penetrations installed
checkpoint-status | feaa87b0-09b6-464d-9c05-e329c8001072 |  | checkpoint | Column blockouts installed
holdpoint | ea4ea66d-fb4b-408b-af29-31970a35ff94 |  | signoff | Inspection by site engineer
checkpoint-group | ff93a211-4d18-4d0a-9c55-2c84449e088e |  | section | Phase 2
checkpoint-status | 6ef045b0-3c8c-4a56-9001-de3036a57bb2 |  | checkpoint | Check back propping as per design
checkpoint-status | 91f14a51-a7e0-433c-a5f2-081eff5d301f |  | checkpoint | Blow off deck
holdpoint | 1c3120ed-5afc-4da7-af07-662f29a0b590 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 96a8bf8f-87a7-493d-83c5-65e655f4d6db |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | 89f75fd8-0d7c-47db-89d9-085ade59c91c |  | checkpoint | Correct Class of Finish
checkpoint-status | 1ead3952-5f6e-41ed-85bc-9e7ae582e9f6 |  | checkpoint | Stripping, cleaning & materials removed
label | f9d9b65a-7f82-56c4-b8b3-18ccf1a7e29c |  | note | Take photos
checklist-sectioned | a1a3bb74-3843-4aaf-b75b-7e22572fa9c6 |  | checklist | Core System Checklist |  |  |  |  | Yes | Core System Checklist | c8f258c8-6be6-4aee-9948-d840947c1da3
checkpoint-group | 3dcb209c-3d4c-4f3a-9b09-c27e9851737d |  | section | Pre Lift
checkpoint-status | e4f61ff1-be50-4d7d-b26c-43bd32da2e94 |  | checkpoint | Confirm concrete strength MPA 15 has been reached at connection points (Builder to supply)
checkpoint-status | 51a2c413-c522-42ea-9ba9-ec46fda8504c |  | checkpoint | Signage in place (Stripping in progress/Jumping in progress/ No access)
checkpoint-status | 57229120-870c-4907-b887-c3879c18d5c5 |  | checkpoint | Exclusion Zone in place
checkpoint-status | c8372313-b175-4a88-b439-40cd98323a6a |  | checkpoint | Spotters in place on slab below jump (outside exclusion zone)
checkpoint-status | e888edd6-fc3b-46c7-a6a5-b6c093b95734 |  | checkpoint | All Platforms cleaned and clear from rubbish
checkpoint-status | f57f4ded-e9e9-41be-8529-4786930e8b3a |  | checkpoint | All loose materials removed from edge
checkpoint-status | e95d4d37-4cb5-427f-9b31-05aec32eb3e8 |  | checkpoint | Clear communication between team leaders and Crane crew (toolbox talk)
checkpoint-status | 88c96a4f-3fd1-4b17-a203-93d705a66b14 |  | checkpoint | Ladders available and secured
checkpoint-status | 436b2620-5618-4a7d-a7f1-d980866ec4a9 |  | checkpoint | Flipper systems lubricated
checkpoint-status | 894c5a68-4464-48c5-bedb-0b025d400a49 |  | checkpoint | Trailing Decks clean of debris
checkpoint-status | 6019d2b3-e6e6-4f8f-8a97-cccd15bfca14 |  | checkpoint | Trailing decks clear of protruding ferrals in walls above
checkpoint-status | dac11318-a2bb-442a-b00f-be45109797b5 |  | checkpoint | Check exclusion zones in pit below are in place
checkpoint-status | 0b0d2bca-3a78-47c4-a47d-bf2bc5b780c3 |  | checkpoint | Plumber to check pipes to water cooler
checkpoint-status | 08eca5a8-fd95-4e3e-b9e5-12e7e571a3a9 |  | checkpoint | Transfer RL heights
checkpoint-group | 55126183-1592-4aef-bf58-a013550f9574 |  | section | Post Lift
checkpoint-status | c84a8335-5882-4d7f-b080-b2daa56a5c6a |  | checkpoint | Confirm connection points are secure and all engaged
checkpoint-status | b3432e55-b451-4033-98e4-1cd687387e64 |  | checkpoint | Confirm mesh secured to doors and penetrations
checkpoint-status | 854e57e4-bc28-4cd9-906f-ab64de1931be |  | checkpoint | Signage in place
checkpoint-status | 052d4aa2-af40-4f5d-a34d-0de920d2e4b3 |  | checkpoint | Screens and mesh infills are in place and secure
checkpoint-status | 6d75f2a2-2774-4b21-95e2-fed6a229aa3f |  | checkpoint | Loose materials are stacked and secure each day
checkpoint-status | c2a01628-1fe3-4f48-a127-90d7a530fc82 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 1aa89d10-b9e6-4e8e-9734-c348c4ad40b4 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 8bacfc60-f6d1-47e9-9431-987c6ed11d20 |  | checkpoint | Loads on platforms not exceeded
checkpoint-status | 90eacb76-cea5-4465-9af0-d4fc13c7b6ce |  | checkpoint | Ladders available and secured
checkpoint-status | 9472d115-265d-4293-a34c-26803371ae25 |  | checkpoint | Access is clear and marked
checkpoint-status | 5e54500d-892e-47e9-84b4-bd97bc41d9cf |  | checkpoint | Power Board connected
checkpoint-status | b33aa7c4-faaa-491f-8687-ec03d941947f |  | checkpoint | Confirm ready for lift with all involved - Team Leaders
checklist-flat | 5dc95afc-1f0c-4da3-9bb9-0a110eb8066b |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Toolbox Meeting | cdbaabc3-c5a0-4273-93d6-4c83b5d98d2c
checkpoint-status | 2c872313-fdb8-4ba6-b873-283526970737 |  | checkpoint | Toolbox signed off - Attach an forms
text | bb94000b-dad3-593a-8172-77d858135ca7 |  | textbox | Work area
text | 1a65525a-6e41-5fca-8b64-d17fc1361084 |  | textbox | Supervisor
text | 489485ab-bbe4-5588-b1f5-82b343414a32 |  | textbox | Date
text | 64ba0b51-625a-54f9-ab4b-6511e16777ca |  | textbox | Time am / pm
text | 691881a6-b28a-549b-9fcb-10984ec45553 |  | textbox | Actions from last meeting
text | 8ae2e291-a46d-595a-9f94-be4772ba9e53 |  | textbox | Injuries last week
text | 3ac40917-5a37-5c7d-9416-0b1056132bdd |  | textbox | Near misses last week
text | c7a50c82-b2e0-5bb6-ad59-23e6e4bfc3e9 |  | textbox | Safety Items discussed
text | 4eb7e8ea-e9af-586f-b2c1-80a677457fb9 |  | textbox | Comments from the floor
text | 0a1a3981-3b04-5e55-a75d-37c4774706fd |  | textbox | New business
text | 904c83fd-54cf-51b3-948a-79afb9eacb15 |  | textbox | Attendees
checkpoint-status | 7a2db00b-28ba-46ec-b3c0-62a24838c23f |  | checkpoint | Attendance verified
checklist-sectioned | ea6d3737-76c6-4136-a8ca-7b8de0d46e81 |  | checklist | Screens |  |  |  |  | Yes | Screens Checklist | d0464fdb-3bf7-40a2-8777-f3847dccca8f
checkpoint-group | 9a40f96f-c5a0-4b07-8110-3ad6f8c71f56 |  | section | Pre Lift
checkpoint-status | 12bcc522-5aaa-473a-8622-180095c53216 |  | checkpoint | Area accessible & ready
text | d660b218-e9d8-5a42-9eb5-1c3b10061087 |  | textbox | Screen number
checkpoint-status | 5e50d441-b612-4f09-824f-8df744e64846 |  | checkpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 7aff5a55-f998-497e-97a7-0d9a4462dde8 |  | checkpoint | Signage in place
checkpoint-status | a77b0660-4585-4fba-8398-a59809f050de |  | checkpoint | Exclusion Zone with name and number of supervisor– Ground level and Slab level
checkpoint-status | afd47c3b-1182-42de-96cc-7b9c154af3cd |  | checkpoint | Spotters in place
checkpoint-status | ce7d2603-2d14-48c4-bd7c-7fd607b31a98 |  | checkpoint | WMS ready and signed on to
checkpoint-status | 2b64d107-dc24-4118-8526-077b7ee64221 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | f6d1a403-3db6-44e1-8a6a-c7e400b484bb |  | checkpoint | All loose materials removed from edge
checkpoint-status | 8ca15f1c-9d35-459b-9557-d185d7869ea9 |  | checkpoint | Edge protection installed on Level/s to be exposed once lifted
checkpoint-status | 0f17eff2-0a61-48ec-b7da-ece85933e651 |  | checkpoint | Deflector shields removed
checkpoint-status | e1e3f0d0-c296-4a42-a083-d2d90811c79f |  | checkpoint | Radio communication woking between screen crew
checkpoint-status | 9e534d2d-4294-429d-8193-e07d522b0955 |  | checkpoint | Hydraulic lifting Apparatus installed correctly if using lifter
checkpoint-status | a69f58dd-97a4-4982-b637-d79fddbcabfa |  | checkpoint | Screen Free from Debris
checkpoint-status | b92bb22e-0d22-4a7f-ab03-6ce7737293de |  | checkpoint | All wire infills detached
checkpoint-status | bb74cbaa-90dd-42c5-b40c-70dceac5813e |  | checkpoint | Confirm ready for lift with all involved - Team Leader
checkpoint-status | 41bd3ae6-22be-4a7d-b88e-49079f491a99 |  | checkpoint | Work at heights permit completed - attach or take photo of permit
checkpoint-group | f2d52a56-bbb3-4a30-a62c-2877c33c2ea2 |  | section | Post Lift
checkpoint-status | 91b83003-a746-4788-85ce-8c94ff20ef61 |  | checkpoint | Ensure all gaps are closed
checkpoint-status | 836bf909-c300-4daf-b7d9-38208648c4ce |  | checkpoint | Mesh to be install where required
checkpoint-status | 41fb5fed-1169-4152-9c51-e032283eaba5 |  | checkpoint | Double check all needles are secure and double nuts in place
checkpoint-status | ce2192ba-3d10-4ff6-b149-3db2e1eec8a4 |  | checkpoint | Clean and clear area
checkpoint-status | d98690d3-330b-4d0e-a699-3acb4609f9da |  | checkpoint | Remove exclusion zones and barricades
checkpoint-status | f6dacae3-c12a-4a1a-9595-112b67813b92 |  | checkpoint | Bar caps for protruding z bars
checklist-flat | 5a19ac95-0df1-4ae2-a1e0-91444eb71b91 |  | checklist | Progress Claim Checklists |  |  |  |  | Yes | Progress Claim Checklists | e629cb7b-856f-4bac-bb59-6a6fed9ec48c
checkpoint-status | d02ec8f7-3873-4ff5-a601-6d87fc627d86 |  | checkpoint | Please add Comments / Photos
select | 833cfaf1-a19a-5b3b-a1c3-dfdeeebe9290 |  | dropdown | General | Site Establishment / Prefab, SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | bb5afac7-4fad-536c-87a4-c34cc4234d1e |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 48bee97d-ab87-5b79-a2a7-8a9b557483b1 |  | textbox | General Notes
checkpoint-status | a2810aab-90c2-40a2-b498-16660c659aa2 |  | checkpoint | Please add Comments / Photos
select | 3d8e7057-4114-544a-8865-5f36caf8e5d8 |  | dropdown | Level | SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | 67c90014-8e88-5c52-8347-cd895aa9ffa8 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Design Pre-fab Establishment of Lift Core System, Install on Site of System, Removal of System, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Screens, Install Jumping & Removal of Screens
select | 58bafc9e-2b9a-5c85-91b8-9ebc2bad6a14 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 2cad6e78-fefd-5a49-993d-56c2942d41ae |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 3b633027-98c7-57a5-b6a7-97f383e42d55 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | f2a92896-502e-5b4f-9f7f-8a4a1c13537e |  | textbox | General Notes
checkpoint-status | ca060e60-8a67-4a44-8b76-7ee6a0069a98 |  | checkpoint | Please add Comments / Photos
select | 3966e910-fd12-5257-8b77-75181f0e0a38 |  | dropdown | Level | SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | 7bd29cfb-469e-57fb-9657-b3bae663f48d |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Design Pre-fab Establishment of Lift Core System, Install on Site of System, Removal of System, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Screens, Install Jumping & Removal of Screens
select | 4fa09961-1d61-5fbe-bf04-fbcfdd5f2daf |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | a8dbc08a-2979-5736-97c7-135d27795634 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 633e6c99-0b00-58dc-9b72-b153ab2145b8 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | a66c8690-e55d-59b5-ae82-834f0ffcfb94 |  | textbox | General Notes
checkpoint-status | 39896221-d1fb-497b-8009-ae33cbf75260 |  | checkpoint | Please add Comments / Photos
select | c17b8cf9-6a26-5a80-a9df-e3fc46cdeab8 |  | dropdown | Level | SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | efd00004-567c-510f-a46a-f2a7210d81b0 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Design Pre-fab Establishment of Lift Core System, Install on Site of System, Removal of System, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Screens, Install Jumping & Removal of Screens
select | c85d95ea-bfab-5a9d-b3cf-1f98361c42c9 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | e1818f8c-da8d-50b3-abad-ff3d6a603ef5 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 0642ec39-5a5d-5469-b557-5fa7b7fda6b5 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 39f1f70a-dddb-5352-b71d-535df522a62e |  | textbox | General Notes
checkpoint-status | 3634a185-f6cd-49fb-824e-42ef9504601e |  | checkpoint | Please add Comments / Photos
select | 0fbcce7c-fc91-5037-9499-39afc81d7b14 |  | dropdown | Level | SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | 853813ca-4c92-5ce5-a243-0a61f4d7f051 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Design Pre-fab Establishment of Lift Core System, Install on Site of System, Removal of System, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Screens, Install Jumping & Removal of Screens
select | b378dd83-8ac6-591f-9ba1-d3e8fb2b7a86 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 8a5d1893-f508-5414-93e9-adaf0daaf4c1 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 705316db-cadb-5c91-905d-ca180be9305e |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | e4937211-909f-518f-9508-a5936654c0c6 |  | textbox | General Notes
checkpoint-status | 2900a2e9-bc35-463b-b4e0-7b10f8f0f18f |  | checkpoint | Please add Comments / Photos
select | 2e631abf-8947-580a-9e6f-832c7b2dbf40 |  | dropdown | Level | SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | 98e31574-cc1e-5852-9505-0042a0bf6c34 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Design Pre-fab Establishment of Lift Core System, Install on Site of System, Removal of System, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Screens, Install Jumping & Removal of Screens
select | ebbb715a-b6c4-53a0-83fd-a7ecf12484d0 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 5676fe85-db42-5d1e-a2a5-f843ab48bb64 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | a3b5958c-6810-55e9-91b7-3af82400b7a3 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 4cd6b16d-dfee-5079-90b2-e3606ba824cd |  | textbox | General Notes
checkpoint-status | ff614680-4d1b-4b41-8562-2629d4dc5c85 |  | checkpoint | Please add Comments / Photos
select | e5042ae2-10b2-5317-aa4d-40db808a1290 |  | dropdown | Level | SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | 26e8e4fc-6909-50f2-bfed-6975916b7661 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Design Pre-fab Establishment of Lift Core System, Install on Site of System, Removal of System, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Screens, Install Jumping & Removal of Screens
select | bae9035a-8aea-5e48-b5fa-fb2164970898 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | f6ef9285-1e87-5eee-952a-e293c9ec8e08 |  | textbox | General Notes
checkpoint-status | 29415bea-5149-4513-b1a1-d31d394f4bdb |  | checkpoint | Please add Comments / Photos
select | 666c3f92-4ceb-5479-a079-7ea1dab4b1e4 |  | dropdown | Level | SOG B3, Basement 3, Basement 2, Basement 1,G, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25 Plant Deck
select | 89c685bf-c35c-5f1a-8951-33867e52f361 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Design Pre-fab Establishment of Lift Core System, Install on Site of System, Removal of System, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Screens, Install Jumping & Removal of Screens
select | 575ae2d7-a909-5b89-ab05-d44405438c07 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | a16908ea-cf84-5a27-a5bb-a9e5da47a3ff |  | textbox | General Notes
checklist-sectioned | 43e69888-9558-4733-b7fe-adf0049f149d |  | checklist | Hoist |  |  |  |  | Yes | Hoist Checklist | ff996700-9d7e-499f-8ea2-96f5c7a05982
checkpoint-group | edde7785-9723-4a4d-a7c6-b7fef7e0874d |  | section | Install
checkpoint-status | a02ec0e9-f739-4c7b-ba81-9c2cd3298697 |  | checkpoint | Area accessible & ready to recive hoist
text | 1c097330-25b7-5328-9dd0-0ce5ffd172a9 |  | textbox | Hoist ID. Number
checkpoint-status | f67b8ca2-f4d8-45d2-8458-caf05891417b |  | checkpoint | Adequate Crane or Franna to install (heaviest lift required 4.5 tonne)
button | a044cbe7-f1d7-590d-828e-0ee9a0fe57d8 |  | button | Copy the Certificate of service and sevice history onsite | Yes, No
text | 1679ff22-315f-57bd-be6f-4d40bdae2320 |  | textbox | Name and Number of Rigger
checkpoint-status | 6e0c8c78-8472-498d-9997-fbfe3ba572de |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
holdpoint | 3b07f52a-38a3-42f0-908e-9413dd43da26 |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | a3f48812-d4b5-4663-b6ef-c23de70b5e6a |  | checkpoint | Scaffolder on site to assist in edge protection if required
checkpoint-status | 241e01d1-ce88-480e-9494-91dbaf7c569a |  | checkpoint | Signage in place
button | 39433f82-d071-5a1c-9104-5c2e3de2a426 |  | button | 3 Phase power acessable and adequate circuit breaker 75 start Amps at power sorce | Yes, No
checkpoint-status | bbcc2bab-1c12-4561-bb53-081a296ff3f2 |  | checkpoint | Exclusion Zone around required area
checkpoint-status | 98ee34d6-81db-4cce-a350-95f52bf1887e |  | checkpoint | WMS ready and signed on to
checkpoint-status | de641a00-beb8-47ae-bbc4-8aa8857ae361 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 6b52fecc-1254-418f-acd2-a37178e86077 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 30588a80-0d62-4c0f-b19c-d7d1ca019a99 |  | checkpoint | Gates installed
holdpoint | 20c37520-f2d4-4ec5-8449-5d9d05ce6812 |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | 41a5a208-79b2-499e-83a8-8a30bf2eb8b1 |  | checkpoint | Log book for hoist is onste and in good condition
button | 2378b05c-98cf-54e4-8cb9-61197a18117d |  | button | Copy of Bosform comissioning sheet on site and completed | Yes, No
checkpoint-group | 4c85d351-5ce8-4c6c-8762-567ac7763f5b |  | section | Hoist Jump and Dismantle
checkpoint-status | 1d100597-197e-427d-8d30-cc5ad06c9c85 |  | checkpoint | Ensure exclusion zones are in place
checkpoint-status | 35362c2b-4150-4e21-93ee-472427af34a4 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | f69b5c7c-30f0-458b-8d79-ee31876f45d2 |  | checkpoint | All loose materials removed from edge
text | d893af32-88be-5a7d-bfde-4a1c90d68360 |  | textbox | Name and Number of Rigger
checkpoint-status | 7ca3b021-ba2a-4233-8ef2-92fb35600db4 |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
checkpoint-status | 78bb7103-22f7-4a41-b4c4-2353b12f49e3 |  | checkpoint | Scaffolder on site to assist in edge protection if required
text | d89878b0-72db-506b-b75d-f9781b55e6f7 |  | textbox | Level Number to be Jumped to
checkpoint-status | 3484ee0a-6662-453e-8e03-c2461ac686a7 |  | checkpoint | Gates installed on Level/s to be exposed once lifted
holdpoint | 8b9415cc-6d14-4f73-8090-75be60aeaa86 |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 16ba1af5-a531-4911-897b-f23a4d3c44ce |  | checkpoint | Signage in place
button | cfa76af3-6bd2-5286-a7e5-cb4eefe4fd78 |  | button | Hoist Screen installed if required | Yes, No
holdpoint | a1072d7e-c9cc-4d4c-9e99-ee6b512d54cd |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | 3218ec5c-b32a-4c32-8bb3-b755eb200026 |  | checkpoint | Remove exclusion zones and barricades