## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 7aeda628-06ea-4c17-8748-73f9b8a54110 |  | checklist | Site Diary |  |  |  |  | Yes | Site Diary | 0917ce1b-581b-494a-9a77-fc5666e8b45b
checkpoint-status | 04d5d149-c6f0-41f9-a7d0-02000ebb218e |  | checkpoint | Areas of work accessible for the day
select | cab7be56-665e-5bed-83db-de8512406a79 |  | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | a17c479c-25fa-577f-8eb2-4ff10020cd08 |  | textbox | Date
text | d5ab0d1a-cfa5-5339-ac2b-3b8aada40cc6 |  | textbox | Year
text | 23bad33e-022c-5e23-89da-c6e391587686 |  | textbox | Number of workers on site
text | 6115013f-3e13-556e-af1d-6cc370f4b515 |  | textbox | HSR on site today enter name
text | 1eb486c8-431e-57d1-a56f-489599da2bf4 |  | textbox | First Aider on site today enter name
text | 38f07661-900e-5f76-a722-21e579da51cf |  | textbox | Injury on site today enter name
checkpoint-no-status | d0ff982f-4e42-417d-877d-f66b2532500c |  | checkpoint | Work area 1 details entered
text | 79dc2e9d-e7ce-51bb-b4d4-c5133ad8b989 |  | textbox | Area
select | dc0bc86d-7d21-5b24-bbf6-0e3f3c301236 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | f3eb93bb-55cb-5ac2-bc97-79404d506b4d |  | textbox | Comments
checkpoint-no-status | 14caa1e8-2f3f-444d-89da-d97e8ce3e971 |  | checkpoint | Work area 2 details entered
text | 0c96c02e-a4db-5b97-872f-030080077b88 |  | textbox | Area
select | 1099148a-c3ad-58f2-b0f2-3ac0459916a8 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 27097205-f8c5-5750-96d3-3ce107da53fd |  | textbox | Comments
checkpoint-no-status | bd3526d8-8182-4375-99b8-e84f460b55ff |  | checkpoint | Work area 3 details entered
text | 2dc4ddda-5817-520a-ab27-d20cf8db4c29 |  | textbox | Area
select | 9357914e-b62c-5a06-b452-004b073bd039 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | f4a81c05-31cf-5538-aea8-2aa2533b480f |  | textbox | Comments
checkpoint-no-status | 27b4502b-f356-455e-8aeb-4999d229d004 |  | checkpoint | Work area 4 details entered
text | 29681781-36e1-5e21-ab52-e07e2b22e612 |  | textbox | Area
select | 922546de-45c7-5bf5-b4ab-699dfaa2350f |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 3be80a2e-3cbe-5345-a461-aada0df45476 |  | textbox | Comments
checkpoint-no-status | da3c87a3-be8c-4fa2-ab87-90cbc8c5f87c |  | checkpoint | Work area 5 details entered
text | 32157c2b-0a8f-586c-a61a-9795512a461a |  | textbox | Area
select | fa99fa71-9a9c-50f7-b424-178907bfe2bc |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | bdb39e11-edb1-5673-bb8e-7a91734982b0 |  | textbox | Comments
checkpoint-no-status | aaefc80e-9c86-462d-b99f-988ddedfe00f |  | checkpoint | Work area 6 details entered
text | 07ff5f89-2119-5d23-b56a-d4ee54131aba |  | textbox | Area
select | 22d207a8-9957-55e0-94aa-8c5a8f0968f7 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | c2ff1300-e14a-52b0-a425-e2882ed92404 |  | textbox | Comments
checkpoint-no-status | 646d516c-4275-4f89-a913-965641e06dd0 |  | checkpoint | Work area 7 details entered
text | fe65d55b-bbc9-5632-9456-646edd5f212a |  | textbox | Area
select | 9125c8c5-5588-54dd-8638-d8a210a10aa5 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 7805f2a0-4ae6-5a35-9c7a-8cd7691ed61a |  | textbox | Other
checkpoint-no-status | fed9a3a0-36ba-4edb-a06b-6e2183ae9559 |  | checkpoint | Work area 8 details entered
text | 6c7adae5-d64b-5862-a782-94113b6b5560 |  | textbox | Area
select | 50500748-dc8b-5778-8394-8d44b3fff8a2 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 246d717f-d706-5cc5-a757-1d95ecdc3d0b |  | textbox | Comments
checkpoint-no-status | ffb8a5e6-5b44-48d8-a7d7-b34888c93f87 |  | checkpoint | Weather conditions entered
select | 353d0fdf-6546-5fed-936b-6c9621a1a751 |  | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | 320de7e0-c757-509e-a57e-f7a1789b2441 |  | textbox | Min temp predicted
text | 1c0c27c0-d5e4-504c-acc6-350ab46cc810 |  | textbox | Max temp predicted
checkpoint-no-status | 12d0f7c5-1c5d-45c3-ae31-79ce5714da72 |  | checkpoint | Delays from inclemency
text | 2c54634e-226e-5563-bd87-a473a8e79113 |  | textbox | Total Hours of delay
select | adde69c6-4290-56b0-a5da-481b014cb947 |  | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | ca1a687b-4a39-4af5-a612-60bdca268e93 |  | checkpoint | Delays from Builders or Others
text | 5bfc5be0-c65d-5de4-8007-cb9af307752e |  | textbox | Total Hours of delay
select | f2f0f869-8bac-59c7-82b6-c76fd2aa8459 |  | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist-flat | 73ea65ab-886b-486d-9bc9-5c523ba3fc24 |  | checklist | EOT Record |  |  |  |  | Yes | EOT Record | 17452856-ff2f-4174-b97c-15d15707a10b
checkpoint-status | fa277522-0d85-469e-89c4-7274671ebe92 |  | checkpoint | Areas of work accessible for the day
select | e53d1d04-9313-55fe-966e-893ed0010e0b |  | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | 0f2f1f6f-f738-5666-93cd-e0e25c4e6f49 |  | textbox | Date
text | 13932a85-5996-5269-894a-d9b03eb3582c |  | textbox | Year
text | 303a1d33-f872-594a-b703-e8f1f4bfc093 |  | textbox | Number of workers on site
checkpoint-no-status | a7e62468-8b29-4b8d-bd08-c9fb62ba01a0 |  | checkpoint | Weather conditions entered
select | 2df02538-60c9-534a-9970-04b9c2a36e7f |  | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | 4296eade-5f12-5419-b9e9-3cd8060538c5 |  | textbox | Weather predicted
checkpoint-no-status | de9534c0-465f-4c73-bffa-d5df30dfdc0c |  | checkpoint | Delays from inclemency
text | c9d8e9b5-cb02-5a73-b614-73451169718c |  | textbox | Total Hours of delay
select | d8c1ca93-658e-54b1-b500-605022f2a7ce |  | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | 1f1ddf9c-fcc3-4b2d-9c03-cbaf7af4e676 |  | checkpoint | Delays from Builders or Others
text | ae28ceb0-f84b-5913-b8a7-9e931ea295af |  | textbox | Total Hours of delay
select | 0f51b20a-9aa0-5c41-80c9-6ae2433b5bc1 |  | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist-flat | f22f2c42-b238-462f-a7bf-01607b0755fd |  | checklist | Walls Checklist |  |  |  |  | Yes | Walls Checklist | 221f21d6-2e01-49d5-ba3f-77a6dcb0dfea
checkpoint-status | 78131fe2-2b97-46d9-915f-e37b1da512ad |  | checkpoint | Area accessible & ready
checkpoint-status | e6b6d8a4-bbed-4824-b10b-83f87b2d7f28 |  | checkpoint | Drawing references entered
text | 24e9ec24-cbf4-57f6-887f-461829204184 |  | textbox | Architectural
text | 36a34719-d605-58bc-afb8-76bf0e45cd83 |  | textbox | Structural
text | 2f543bc4-ae85-5bae-acdb-dc60f941fffc |  | textbox | Other
checkpoint-status | 550695a2-1ede-43d8-85b5-169274397307 |  | checkpoint | Current plans in use
checkpoint-status | 07039950-e00f-4e79-81c5-eb8fa9e11dad |  | checkpoint | Survey points given for 2 points
checkpoint-status | 028fea5c-8eb5-4ccd-bf31-4a88ce4c6aae |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status | aa33182a-7078-48cb-b63f-e7e5311a8d7f |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | d7db0e2c-3614-41ed-921e-7c0606fcc825 |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status | fc5d0184-b28c-4082-9b0f-c5129b66318c |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status | 25f0c4f9-a625-48cc-8d9c-93dfa744405a |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 0952c43b-b8a8-426e-8dc9-398cd8535295 |  | checkpoint | Base of walls cleaned
holdpoint | 042a71ed-db9a-4203-91a6-bdeed5dd118b |  | signoff | Inspection by site engineer
checkpoint-status | 7ef25c9a-be0a-4243-9d3c-6562699db527 |  | checkpoint | Closing shutter installed
checkpoint-status | 9bd1d30e-0d03-4495-a235-6b5c2bcf3c54 |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status | 2300e014-4246-4377-8c31-1aa40217cd37 |  | checkpoint | Correct Class of Finish
checklist-sectioned | f3022b6e-07a0-486e-ad8a-917a2559b470 |  | checklist | Core Lids Checklist |  |  |  |  | Yes | Core Lids Checklist | 26d8e915-f710-4077-9951-7d6c2c8ae59f
checkpoint-group | d6dc7419-298c-4730-ad13-0ed6c25f9b12 |  | section | Phase 1
checkpoint-status | 15fc610c-37ac-407e-8ba2-6d4029a978bf |  | checkpoint | Area accessible & ready
checkpoint-status | 974facaa-d441-4d31-912b-77eba11f6502 |  | checkpoint | Drawing references entered
text | 2eb0126d-7e8d-522a-a942-7f6277cc162f |  | textbox | Architectural
text | 24435fca-3c35-5755-bda4-a8d10e8bbf73 |  | textbox | Structural
text | 673edcc0-ad98-58d7-8e78-e62fd86740c6 |  | textbox | Other
checkpoint-status | ee26946b-52f6-4f56-bb85-55398eb1c824 |  | checkpoint | Materials used complies with design documentation
checkpoint-status | fcbf248c-1713-435e-8795-8e60cb785786 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | b6852b55-b1f1-4445-b7c4-24c58a84e720 |  | checkpoint | Grids marked by builder
checkpoint-status | 73e79cd4-90f4-4b50-99ad-f1ac325ac7dc |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 8ff7130d-593e-42cc-a476-58d14d960547 |  | checkpoint | Fillet & drip mould installed
checkpoint-status | e93581a4-94d5-416f-a5e6-7a7a308f066f |  | checkpoint | Check set down position & RL
checkpoint-status | b5608063-63e9-4f01-86fc-0a7918bf9331 |  | checkpoint | Check penetrations installed
checkpoint-status | 1d1676c1-877d-406e-be97-4c0142efe993 |  | checkpoint | Column blockouts installed
checkpoint-group | 66df1325-0950-4308-836c-ddeb271e9824 |  | section | Phase 2
checkpoint-status | efc856c8-9846-4e68-9a64-cafa6dbcbbcc |  | checkpoint | Check back propping as per design
checkpoint-status | fe7d1eb9-afcc-4cac-a2cd-dde43e568c56 |  | checkpoint | Blow off deck
holdpoint | ba354e07-38f6-48a0-b8ca-0fd3b6f05de3 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 8dda1602-7e8a-4211-9e43-82169ea87e82 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | d00f84ff-bdc5-4cdd-8ea9-4c4cafd7b417 |  | checkpoint | Correct Class of Finish
checkpoint-status | 3f11638d-c8e9-4086-ac3c-501a73573e41 |  | checkpoint | Stripping, cleaning & materials removed
checklist-flat | bba71637-d1e1-4331-942d-c8e4b0325083 |  | checklist | Injury Form |  |  |  |  | Yes | Injury Form | 2d5e4ff3-da54-48a3-9b06-cd149dbaf9b2
checkpoint-status | eca3e913-54e4-4a64-beac-fcc83bec4e05 |  | checkpoint | Injury form completed
text | 2be82cbb-663f-59cb-8d69-c215d938f651 |  | textbox | Date of incident
text | 975d79fd-d658-5cf9-a8d7-f55ae211a6e5 |  | textbox | Time
text | 7d24092d-b16c-51c0-8d54-aee12d1d06bb |  | textbox | Site location of the accident / incident
text | db1286b1-d99c-5b0e-9c4d-444a81cfa4cb |  | textbox | Detail of how the accident / incident happened
label | 6fb24fb1-6db2-5c7a-9d65-03aa43a71cde |  | note | Details of injured person
text | 9ef9e4e6-7157-50d0-973b-5b68650f9a81 |  | textbox | First name
text | 6613947e-cebb-554c-a85b-5767b935e9b5 |  | textbox | Last name
text | 93d99c92-4e43-539b-a12f-95fa91f2a78d |  | textbox | DOB
text | 5b39ed2a-2bcd-5fba-8c58-a9115c82e0c0 |  | textbox | Contact No
text | 06d0e416-49fa-549d-b3d5-7cf55ea4bbbc |  | textbox | Address
text | 9c951591-1c6d-5a99-a2e1-1c9964edbabd |  | textbox | Company
text | a3ccf9da-6c65-51b2-aeba-fd03080355e6 |  | textbox | Trade
text | 9792581c-75ad-5cc0-9242-87cb846917d6 |  | textbox | Date Inducted
select | 2cda6a64-fbe9-5609-bcb0-ac2d1b8e6b76 |  | dropdown | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
select | e5f74553-c7a4-5662-90ce-83beed86df03 |  | dropdown | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
select | 30750425-5b39-5d2c-a29c-24937495af48 |  | dropdown | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
text | 07f5f742-bffa-5c83-a8db-4309903ea8c5 |  | textbox | Initial treatment given
text | f9eaf09c-7576-5c3a-a8c4-e5b793b78fe6 |  | textbox | Was follow up treatment provided
text | fe2fd09a-217d-53ca-80f8-87f1e4724617 |  | textbox | Medical centre / Doctor / Hospital attended
text | 0b697389-de86-5382-bc6e-116897d55d5d |  | textbox | Date / time attended
button | 87e0fffb-916b-5bbb-bb51-c2f74f9d9fbc |  | button | Regulator notified | Yes, No
label | c656bd4d-521f-57ff-b95d-c46e005870ae |  | note | Witness details
text | 3f2a7c6a-35dd-5dbf-a216-4cc8b8639ed2 |  | textbox | Witness name & contact details
text | 18d23cc2-e9b2-5d67-97c3-42fd04055fa3 |  | textbox | Witness name & contact details
select | 286d9099-7db9-5e59-a238-d4ce924c941c |  | dropdown | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
text | 8613f25c-d433-50f9-80f3-05765404df3c |  | textbox | Other
label | 60c53001-b528-5d16-9a5b-d31b36f52f22 |  | note | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
checkpoint-status | 5b0ddf35-0218-4afb-bea1-8d96b275f40b |  | checkpoint | Signature of injured worker
checkpoint-status | 1d23fe28-e1e9-4865-b196-fdb4d8eaeaef |  | checkpoint | Person completing this form
checklist-sectioned | 6ba4eccf-4048-44e3-9760-e18b6f09be5d |  | checklist | General Incident Notification |  |  |  |  | Yes | General Incident Notification | 44f7bcb8-4d6b-4350-8007-c340942aaa6f
checkpoint-group | 657adafc-fb07-432a-a863-cdf6e4ea8297 |  | section | Details of the person completing this form
checkpoint-status | 28e04031-350b-4ae1-b868-2dcfd60fb16e |  | checkpoint | Attach any relevant photos or documents
text | 1f173d14-761a-5dd6-a039-32f7c2b66981 |  | textbox | Name
select | a1fa773a-1a7b-5ba6-936c-00f9be770b75 |  | dropdown | Position | Site Manager, Project Manager, Construction Manager, EHS Advisor, Other
text | 692fc316-9ce7-57ca-be4c-69c6a25f6c41 |  | textbox | Contact number:
text | e51b1b1f-b1c0-54b6-b161-ac5c15bfe9f5 |  | textbox | Completion date
holdpoint | acef0cd2-f9ff-487d-b981-3b6f5b7ec4eb |  | signoff | Signature Required
checkpoint-status | 835b0a17-8ead-48a3-9594-a20f598dc18e |  | checkpoint | Report reviewed by (mark if applicable)
boolean | 73466984-e38c-528d-8720-8672de39e5c1 |  | tickbox | Site Manager
boolean | 9726aeea-0b03-521a-b88a-220ab01cd0f5 |  | tickbox | Construction Manager
checkpoint-status | 5ab9c5cc-1412-4ee9-ba4e-41092543f00d |  | checkpoint | EHS ADVISER ONLY – Head Office
text | e2ef83f2-a969-516c-b03a-ce46c9321fe8 |  | textbox | Date received
text | 20a53823-719c-5b57-9740-7e03cc2ae995 |  | textbox | Date closed (Final)
text | 40b249f3-4b81-5c96-9552-48a401eb952e |  | textbox | Date submitted to EHS Administration
checkpoint-status | f0592677-46ee-46af-98a5-35eaee843509 |  | checkpoint | EHS ADMINISTRATION ONLY Head Office
text | 74fdb73f-7e0c-574f-841a-0e2c49956b8f |  | textbox | Date received
text | 1f93c8e5-0b03-5b21-9e2b-948239c2d02e |  | textbox | Date processed
checkpoint-status | 224429d1-c728-4534-b421-22ec949a03b7 |  | checkpoint | EHS REVIEW ( EHS Manager)
boolean | 2a98b050-d6c4-5233-b6e3-17afd755bd38 |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 9149302b-6240-54f7-88c4-28a29bbe1356 |  | tickbox | No
checkpoint-status | 4c2455ba-2124-4b4b-9d9e-4d94d0679415 |  | checkpoint | EHS System / SWMS amendment required?
boolean | 76742ff5-cea2-578b-a5f0-c758c057ac2a |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 4c2f1a69-fcbc-5c0d-aa62-f304b56f8bed |  | tickbox | No
text | d3023cc8-e541-5432-94eb-b7f96b5df8a5 |  | textbox | Head Office EHS Manager sign off date
checkpoint-group | 829af6d4-f03a-49ef-8b72-677ea3b00401 |  | section | Incident Type
checkpoint-status | 41fbf33b-06f1-46ab-9a3c-c6cb7a4f0bba |  | checkpoint | Was a person injured as a result of the incident? - If PASS Only complete an Accident/Incident Notification Report (Form No. 01a) - If FAIL complete this form
checkpoint-status | 2850555c-93a2-4b69-af19-edc76ad1935b |  | checkpoint | Has an environmental issue arisen from this event? If PASS Only complete an Environmental Incident Notification and Investigation Report (Form No 01b) - If FAIL Complete this Form.
checkpoint-group | 93c1701e-eb4c-4bfa-a490-ba914cf18ca3 |  | section | Project Details
checkpoint-status | b15e7b82-f1bc-4ec7-9b70-2c785b5f391d |  | checkpoint | Report Status and Date:
boolean | fbd9e4f8-d51b-5df3-8101-27b43b04799c |  | tickbox | Initial
text | 8e0c4516-2e76-556c-bd44-fc4d0ddc15c0 |  | textbox | Date
boolean | c12a2c66-d3ab-51c3-a36c-ed1f97e0eb39 |  | tickbox | Interim
text | f8af5f0a-8e47-528b-95f8-3454fc2fdd31 |  | textbox | Date
boolean | 416e175e-b13a-51f7-a009-dc6850e29c4a |  | tickbox | Final
text | b554466e-2ef3-5540-8a95-c2ae0b9a1249 |  | textbox | Date
checkpoint-group | 1ab007a1-ac9b-4a14-99bb-b70752aaf330 |  | section | Incident Details
checkpoint-status | 2488bb48-26bf-41de-8600-0c85d64dc96a |  | checkpoint | Date/Time of the Incident
text | f46ef44d-b9f4-55ff-976b-0004965b03b2 |  | textbox | Date
text | 246b6ae9-c3fe-56f6-885b-936678424d27 |  | textbox | Time
text | bd600ca9-ed94-5561-9999-440666c45dc7 |  | textbox | Site location of the Incident
text | cdcdc3d6-8fa5-56d1-88e0-9a1d3d4b436b |  | textbox | Detail how the Incident happened
checkpoint-status | ccf4b9ed-6aaa-4f0d-8b67-3fa7a4b94915 |  | checkpoint | Services affected by the event
boolean | 7d980aa4-b3a8-5d85-9f43-b194b5953b5a |  | tickbox | Electricity
boolean | cf726a90-938a-5f52-afa6-ed3b4ae9527a |  | tickbox | Potable Water
boolean | a5fa5c81-6f01-5084-8a83-2905ec78be8e |  | tickbox | Storm Water
boolean | d07250ff-495b-5d7c-b117-41218c7c5ffd |  | tickbox | Sewer
boolean | 4dade4c8-eae5-5619-8d52-207f0ade09d6 |  | tickbox | Fire Mgt Services
boolean | 3b90e5a0-8b6d-52f5-8f03-eaef194e53d9 |  | tickbox | Fire/Smoke Alarms
boolean | 9bfc3bae-4ce7-556a-8c67-352258245590 |  | tickbox | Air-conditioning
boolean | 5909a147-546f-5cb9-9f6e-b1c22e2e7fba |  | tickbox | Security/Access
boolean | bb601bb6-1a58-5b76-bd3b-5a736ba1fe2c |  | tickbox | Communications
boolean | 61d3ca19-7765-5e58-8ced-bf456c7a0638 |  | tickbox | Gas
boolean | 22f5d8b9-ca0e-5688-82b8-bd84f76ad828 |  | tickbox | Other
boolean | 4747c30c-a336-533c-ba56-e99cbc797495 |  | tickbox | N/a
checkpoint-status | c069b2b5-f2d3-4653-ad00-3b309e350431 |  | checkpoint | Detail the factors that contributed to the Incident
boolean | 578168bf-82a9-5aa7-ac75-6d907cf4c8cf |  | tickbox | Design/Layout
boolean | 175fc2ed-2780-53fa-afbc-927c6bb28550 |  | tickbox | Equipment
boolean | 0b926953-8615-5a80-9eba-54692df8bfc8 |  | tickbox | Operator error
boolean | 86ea1fdc-06f1-56b3-b6c8-47601a95ec75 |  | tickbox | PPE
boolean | 3b9679b6-f8d7-52ae-a0be-0bf454d18717 |  | tickbox | Training
boolean | dc389518-6d64-552d-be50-98466d011191 |  | tickbox | Supervision
boolean | 6cdae7fe-e917-5e93-aa54-69f291bd770f |  | tickbox | Unknown location
boolean | 86e46b41-ef97-574a-838a-226d87555f0c |  | tickbox | Other unspecified
boolean | 371eb0eb-d603-5a04-8a6d-2fc77fe396da |  | tickbox | Housekeeping
boolean | 7fd8972b-f371-5d6c-b8e6-05db1417ff4f |  | tickbox | Procedure (WMS)
boolean | 53e3f072-42a3-58fb-be38-fe9110c5e442 |  | tickbox | Weather conditions
checkpoint-status | 19e335af-cb03-4649-99b3-9f9bf4bd3e2b |  | checkpoint | Was a WMS supplied for this type of work?
checkpoint-status | 5be61213-7149-461c-9f37-9a0817785d40 |  | checkpoint | Was the WMS approved by Principle Contractor
checkpoint-status | e3495a46-404e-44e5-b454-f6f652702f51 |  | checkpoint | Was the WMS signed by all personnel involved in the activity?
checkpoint-status | 7da51230-93cc-4d8f-a42c-b3b570edeee8 |  | checkpoint | EHS Improvement Notice
checkpoint-status | 11c67c5d-a308-418d-a715-b4d5dc35f644 |  | checkpoint | Was the work activity being performed in accordance with the WMS?
checkpoint-status | d8a3277a-7c0b-41a3-bffd-d96bc5ab66ce |  | checkpoint | Was a Tool Box Talk held relating to this work activity?
checkpoint-status | eac4d128-e427-4ad0-bafc-f8a3f0287089 |  | checkpoint | Was any external certification required for this work?
boolean | 0def7d08-7cce-5ad6-adfe-f2729bba49b4 |  | tickbox | If Yes, was it obtained prior to works commencing?
checkpoint-status | eb5e1e73-8dd5-4df2-b502-eabf7886ed9a |  | checkpoint | Was any monitoring required for this type of work?
boolean | cba5379c-223f-5aa6-be4d-9abd9054d7b0 |  | tickbox | If Yes, was it in place?
checkpoint-status | 85369082-9852-41c2-9adf-6160367ada6c |  | checkpoint | Was an Authority to Work Permit required?
boolean | d9c2fd29-3e33-5f21-a934-62911a889846 |  | tickbox | If Yes, was a Permit issued?
checkpoint-status | fb8ab9d9-7b2a-4b29-a331-6487fdafc564 |  | checkpoint | Were any Regulatory Permits required for this work?
boolean | 417b026b-8a0d-55cf-9606-f7617a682c78 |  | tickbox | If Yes, was a Permit obtained?
checkpoint-status | 59c4c8c1-d22b-4861-b771-0f7e65efb80f |  | checkpoint | Was a Notice of Impacting Activity required?
boolean | e63e2c0a-92eb-51ae-87cb-65e3ffdd6983 |  | tickbox | If Yes, was it issued?
checkpoint-status | a1a41917-598b-4517-8592-4b2b60a59211 |  | checkpoint | Estimated time impact of the event
boolean | 092a9f21-97c2-5d5c-b901-f8e49396b17e |  | tickbox | No impact. No loss of production.
boolean | 9601c0e7-54c3-58e3-ba61-cdcf34534c0e |  | tickbox | Limited impact. Production loss in localised area.
boolean | 6d652116-e53b-505a-88a7-2929404049e1 |  | tickbox | Major impact. Production loss across project site.
checkpoint-status | ae8fe690-afbe-4a6a-b16b-4fecd0b9f6ef |  | checkpoint | Details of any persons involved in the Incident - Attach Statement forms to this report
text | d823e307-a69c-599c-a028-1cf29f81922e |  | textbox | Full Name
text | 70a15afb-1dac-5dbd-b628-7fa58844ed7c |  | textbox | Company
text | c0feaf97-77ac-5c09-9d31-0b7e533e7c39 |  | textbox | Contact No.
button | c0b6759c-b022-5708-9262-18245cf7d826 |  | button | Statement | Yes, No
text | e8158626-5d4a-59bb-bf38-94cfab3ec29a |  | textbox | Full Name
text | 1c4d535f-963d-518b-9ef0-0cbf7e495f5d |  | textbox | Company
text | 9f05824c-1aac-5bde-9094-2e76f6ce0681 |  | textbox | Contact No.
button | b69d4de4-de78-5522-a45e-7c37d74cb4c2 |  | button | Statement | Yes, No
checkpoint-status | 85044df1-424d-44d1-b72e-34179221054f |  | checkpoint | Details of any witnesses to the Incident - Attach Statement forms to this report
text | 237e5ee2-27df-54bf-8944-9529e8efaf2b |  | textbox | Full Name
text | 6d286b15-b5c0-5e92-8989-9334d2aab099 |  | textbox | Company
text | e5ccd465-ccc4-5f7d-ae1a-ba3b48e18050 |  | textbox | Contact No.
button | 754eaac0-f137-5b9b-b36c-e2d0a8519199 |  | button | Statement | Yes, No
text | 9fad4f2d-83f0-52dc-9b68-1f67c191e329 |  | textbox | Full Name
text | 3fef7105-56e9-5ef6-91ed-0f074df25147 |  | textbox | Company
text | a8045c48-a6f4-5f74-a43c-94099b36f6e8 |  | textbox | Contact No.
button | 02ebe7e3-8d9e-51d2-8486-ba3838230cdd |  | button | Statement | Yes, No
checkpoint-status | 1bae05b1-1445-4b33-9730-fc4ef7315b79 |  | checkpoint | What actions have been implemented to prevent similar Incident
boolean | 3c55f730-c55b-5444-889e-b3ad0f9ab42a |  | tickbox | Equipment change
boolean | 0b81303e-4e8f-5ca7-9359-29124c281f01 |  | tickbox | Certification obtained
boolean | 3425f727-8965-5ab7-8346-9f27ccc12d08 |  | tickbox | WMS change
boolean | 0f2049d5-cddf-5b04-909a-6e672b295cec |  | tickbox | PPE change
boolean | 2192028f-440f-55ee-b79c-2d6fff65c5a2 |  | tickbox | Site Meeting
boolean | 845bcd55-a1c1-5bdd-bc1d-2f00abc59096 |  | tickbox | Toolbox Talk
boolean | 931b3ec6-b6be-5932-95d8-f6975b09b7cb |  | tickbox | Housekeeping
boolean | c0063800-044e-5b5a-bb04-32f98fd44e38 |  | tickbox | Training
boolean | f4cd21d2-28f3-57fd-9e28-66cddc1e2f9b |  | tickbox | Other
checkpoint-status | acdfe77d-1628-4cd9-aac2-72bd05eef0d1 |  | checkpoint | Has an EHS Instruction been issued to the P/C company or Bosform?
checkpoint-status | 657ff3cb-fb63-415b-a537-19e77d33e138 |  | checkpoint | Has an EHS Improvement Notice been issued to the Bosform?
checkpoint-status | b2200c72-086b-439e-96b7-ac6d3f03c442 |  | checkpoint | Has a Risk/Hazard Assessment been completed?
checkpoint-status | 6f2198fd-01f7-4b3a-8682-d58f81812250 |  | checkpoint | What Hierarchy of Control measures were considered in the corrective action
boolean | d186c924-a5c9-5d76-b014-284581bf0808 |  | tickbox | Elimination
boolean | b5b4256c-6976-5711-88a8-54b18d354bdd |  | tickbox | Substitution
boolean | 24a32e0c-61ce-5c34-8ff4-939039e3c12c |  | tickbox | Engineering
boolean | dc1ec8b4-3dfb-5b88-83c0-584faa948346 |  | tickbox | Administration
boolean | 402f9a4f-1930-556f-a8d9-e95253bc6fe2 |  | tickbox | PPE
text | 426a8773-df17-545e-9ac9-b03b1a05edc5 |  | textbox | Date of action
text | 40cc0596-28bf-5245-aaaa-0f0ffbd8d165 |  | textbox | Responsible company/s
text | b617f0a8-523d-5eb2-99f2-606d5c09aa9e |  | textbox | Review date
checkpoint-status | 150b41d5-a2e8-4fb5-918f-10118e7701e2 |  | checkpoint | Statement/s
checkpoint-status | 9e2ae524-e67b-4dda-b9c1-9c0fb7764048 |  | checkpoint | Monitoring certificates
checkpoint-status | 55bf8a88-9b49-45ee-9dde-1563b22b4dcb |  | checkpoint | Site Induction forms
checkpoint-status | 42354ffc-f521-41c1-894a-2869349617d3 |  | checkpoint | WMS relevant to the activity
checkpoint-status | c94f273a-44d3-441d-a51a-d0e0ebd90462 |  | checkpoint | Tool Box Talk or Meeting form/s
checkpoint-status | 0ab91379-9251-4df2-95b9-46e87e822aec |  | checkpoint | Engineer certification
checkpoint-status | 4549c18d-f522-4c4e-b41d-91cc54c0fc89 |  | checkpoint | Photos
checkpoint-status | 02b572a3-8c5e-4523-944a-70a58c43c84e |  | checkpoint | EHS Instruction
checklist-sectioned | 80aa35da-5845-43cc-bb05-b980b3d312ed |  | checklist | Screens |  |  |  |  | Yes | Screens | 53fddb50-74ff-4016-9931-b5c3eb644b05
checkpoint-group | 1d08f772-882e-4cd5-b2b6-e8748eade6b2 |  | section | Pre Lift
checkpoint-status | 957694cf-5cf9-4c91-87c9-11bd553c06c7 |  | checkpoint | Area accessible & ready
text | 5e1e555e-90da-52cd-a4c2-a8f6030180bd |  | textbox | Screen number
checkpoint-status | 18b7d5af-2132-4638-9d1a-9db1960ba165 |  | checkpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 70e431a7-d91c-4b8c-9efa-387d5f89be3d |  | checkpoint | Signage in place
checkpoint-status | 3f63c160-1442-4e85-8f3a-aee9f26a72c2 |  | checkpoint | Exclusion Zone with name and number of supervisor– Ground level and Slab level
checkpoint-status | 4a04abbb-094d-4301-84b6-5962fa714ba8 |  | checkpoint | Spotters in place
checkpoint-status | b239fdb0-a6be-48ef-89a4-68c985a8d821 |  | checkpoint | WMS ready and signed on to
checkpoint-status | 7a997787-2919-41ac-88ee-4b361db34b73 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | d81c8252-7b1e-4f65-ba0d-fd811075eb37 |  | checkpoint | All loose materials removed from edge
checkpoint-status | fa5c70e2-e24e-4887-8deb-b63549c767ca |  | checkpoint | Edge protection installed on Level/s to be exposed once lifted
checkpoint-status | 0514a9ef-be77-43f2-a151-924723761602 |  | checkpoint | Deflector shields removed
checkpoint-status | 81c11f02-5b9f-4916-af87-b09a002a8d58 |  | checkpoint | Radio communication woking between screen crew
checkpoint-status | 21684875-c964-4199-b793-86bfd2e5b2f2 |  | checkpoint | Hydraulic lifting Apparatus installed correctly if using lifter
checkpoint-status | d53dfee2-049b-4770-8279-ce91f62485a6 |  | checkpoint | Screen Free from Debris
checkpoint-status | 89d437ed-4330-4556-9dd8-f1072473b162 |  | checkpoint | All wire infills detached
checkpoint-status | 85579602-6264-4be8-a7a4-729e1b98876c |  | checkpoint | Confirm ready for lift with all involved - Team Leader
checkpoint-status | 2b50dc81-4f8e-47e7-b307-2d28f98c543c |  | checkpoint | Work at heights permit completed - attach or take photo of permit
checkpoint-group | 16c8c29e-1e78-4309-8336-933a8c4dcd15 |  | section | Post Lift
checkpoint-status | bae07bb9-053b-42cc-94b1-59bc2ef954f7 |  | checkpoint | Ensure all gaps are closed
checkpoint-status | 0d7ae425-aaf1-442e-bb9b-e19ee3e01955 |  | checkpoint | Mesh to be install where required
checkpoint-status | a820ce4e-b2cf-4e2b-8bff-373e09a02786 |  | checkpoint | Double check all needles are secure and double nuts in place
checkpoint-status | 12aeeddc-8dbd-4ab9-a691-110f72352663 |  | checkpoint | Clean and clear area
checkpoint-status | e1fb3c55-d492-4241-b35a-7ba17e94d5e4 |  | checkpoint | Remove exclusion zones and barricades
checkpoint-status | 501de006-e09e-4641-ba8f-b29991b3daa9 |  | checkpoint | Bar caps for protruding z bars
checklist-flat | 3c152796-a342-4541-8e56-f4c3cdd419e9 |  | checklist | S.O.G Checklist |  |  |  |  | Yes | S.O.G Checklist | 56932f1a-65c1-4dbc-ade2-9ba3650cf0e3
checkpoint-status | 42107b9c-b7ca-4f09-8333-89234c882a7b |  | checkpoint | Area accessible & ready
checkpoint-status | 760b3666-9404-42ad-91f5-6eafc9d4306c |  | checkpoint | Drawing references entered
text | 0037f79b-e5cf-5d41-9225-2840b705e3f5 |  | textbox | Architectural
text | 3445eb7e-a9f4-5abb-8b8a-67aebc3f012b |  | textbox | Structural
text | 359d8629-e7ae-572e-952c-f2363024baa9 |  | textbox | Other
checkpoint-status | 23e3cd68-557d-401e-9d22-155831a0e1c7 |  | checkpoint | Current plans in use
checkpoint-status | 9c569c35-b5cb-499b-b8a3-ef57e7700236 |  | checkpoint | Survey points give for grids
checkpoint-status | 1b785d89-1f06-4c6f-9c06-38ca2498d3c0 |  | checkpoint | Surveyors points given for edge boards
checkpoint-status | b7da188e-73f7-408c-896c-a065bb230e81 |  | checkpoint | Datum RL supplied by surveyor
checkpoint-status | aa20a49d-0a32-46d5-90b9-60697bf3697f |  | checkpoint | Edge boards plumb & straight
checkpoint-status | c8662e2b-a8f2-4149-a39a-130b259d4fa6 |  | checkpoint | Step downs secure & correct RL
checkpoint-status | b3d31735-fa47-4e15-bb3f-fee36cac2d98 |  | checkpoint | Dowels installed on pour joins
checkpoint-status | 314343ef-cd64-4e5b-b971-a9d8878e564e |  | checkpoint | Column blockouts installed
checkpoint-status | b01e3919-25c9-4ccf-bb2c-2ea0835c798b |  | checkpoint | Correct Class of Finish
checklist-flat | 65fa4192-5cef-4ff2-8405-df292b2ab6b2 |  | checklist | Columns Checklist |  |  |  |  | Yes | Columns Checklist | 56edaf64-7baf-43a2-be27-c22e622f96ff
checkpoint-status | 239469ff-c518-4355-b7c2-7506350fb025 |  | checkpoint | Area accessible & ready
checkpoint-status | 3aa9f14a-bd65-4869-9e5e-5a978dbaa97a |  | checkpoint | Drawing references entered
text | 9b7dd4a4-334b-5fb9-8eea-2ed93f3be379 |  | textbox | Architectural
text | 899acfe4-8361-538e-9487-591b4ced3f46 |  | textbox | Structural
text | dd3d2382-b46f-5e1a-aeef-0eab2d71f96d |  | textbox | Other
text | e62545ba-9f17-5530-b7b1-a1ba2bd2c6ec |  | textbox | Column No
checkpoint-status | 52ca97d8-15c5-4d01-bbd5-e914f46a6c09 |  | checkpoint | Current plans in use / Latest drawings checked and referenced
checkpoint-status | e6dd8ecb-3a1a-45fb-a8be-7d0e80af47af |  | checkpoint | Survey points given for 2 points
checkpoint-status | bf0437e7-c586-43fd-a89d-8b5e256b7fce |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status | 4fc3f7c7-3666-4b52-a926-5263331b482c |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint | 642ea67b-6550-4c77-94e1-64222610c218 |  | signoff | Inspection from site engineer
checkpoint-status | 31b304cb-1d9a-4582-9d27-26ca6e645039 |  | checkpoint | Column box cleaned & oiled
checkpoint-status | 26d8c61f-5f15-4466-8faa-57c3bb5f8270 |  | checkpoint | Placement of column box over cage
checkpoint-status | 003bc37d-4e55-494a-9c5b-6bf91a7c5325 |  | checkpoint | Bracing props secured
checkpoint-status | a36f045e-7df0-4942-ac46-1f35db848a07 |  | checkpoint | Column plumbed
checkpoint-status | aa0a806e-b4ac-4f53-8b42-33597934d0f5 |  | checkpoint | Correct class of finish
checklist-flat | 8a777d17-17a7-4690-8dd8-ed3ef34fd305 |  | checklist | Weekly Labour Hire Control |  |  |  |  | Yes | Weekly Labour Hire Control | 70c39af4-22f3-4190-8b50-fad0da2e9975
checkpoint-status | 3dc1ed76-4d62-4dc8-822a-f861db57a149 |  | checkpoint | Tuesday
text | 1ddbeaf5-97d5-5176-9bf4-77d0a738142c |  | textbox | Date
text | ab31d2af-3000-5514-b021-9e02c87d8f3b |  | textbox | General Comments
checkpoint-status | a5b27f9f-5514-44b3-9abb-68f04d642cb4 |  | checkpoint | Wednesday
text | e97dda53-1f6d-594f-922e-cb8219831c8a |  | textbox | Date
text | f5fd8ffb-03be-5473-a21b-279cf6672d59 |  | textbox | General Comments
checkpoint-status | 7d5d2cfb-449a-4d73-9d73-001046ff28ae |  | checkpoint | Thursday
text | df861d31-7c22-5c6c-b4f7-a1d60857110f |  | textbox | Date
text | e12f5879-b291-58d6-95a1-55be55487a27 |  | textbox | General Comments
checkpoint-status | b827c049-4dad-4ade-b0e1-63631aca723b |  | checkpoint | Friday
text | 4649272c-38d9-5705-af1b-19929efbe71b |  | textbox | Date
text | e1180701-daeb-55fb-a36d-009a0b90f7ee |  | textbox | General Comments
checkpoint-status | f4d5307d-b5b8-450e-b34c-219c77d0f8e4 |  | checkpoint | Saturday
text | 44bf41f2-5ec5-51e1-b0b4-917d35fa8367 |  | textbox | Date
text | fc287732-a47b-5e14-9027-7a8eb1f1b382 |  | textbox | General Comments
checkpoint-status | 4df8f01b-2bb4-4dce-af77-87c47c0c41f2 |  | checkpoint | Monday
text | 06bd6fa4-3761-5b9c-9693-818daaa74724 |  | textbox | Date
text | ccc0fbeb-6086-5c82-8aea-fb29441ed11c |  | textbox | General Comments
checkpoint-status | 47cb20f4-b01c-41cb-a26a-c0db0b49301b |  | checkpoint | Tuesday
text | 313c57c4-9627-5162-b430-176d8393c999 |  | textbox | Date
text | 2f82d666-e790-53fe-b847-469a0c8bdc4c |  | textbox | General Comments
checkpoint-status | 159d6c7b-8bb3-42ac-bf19-53815672eba5 |  | checkpoint | Please Attach Timesheet
holdpoint | c2f59475-27fe-4ba4-a029-a44fbf7e99a8 |  | signoff | Client Confirmation Signature
checklist-flat | c4a471a7-e2a2-413c-9933-e09c1b1aeefe |  | checklist | Suspended Slab Checklist |  |  |  |  | Yes | Suspended Slab Checklist | 8e54d63c-a1d3-4fd2-9530-81471cbc5495
checkpoint-status | 9232df77-dbe7-44af-8bca-ccc6fd0ea4a7 |  | checkpoint | Area accessible & ready
checkpoint-status | a3394871-0acf-47b5-b6b0-df554f70b0b5 |  | checkpoint | Drawing references entered
checkpoint-status | ef484d16-e146-48f7-90d2-552bdeb8be38 |  | checkpoint | Materials used complies with design documentation
checkpoint-status | fbcfbbbb-be8b-4a01-8f95-c79baca988ee |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | fa43413e-835d-43c2-8ae5-a4af2137a372 |  | checkpoint | Grids marked by builder
checkpoint-status | 15012f7a-5f08-491f-904c-8f47c106f7d2 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 0b2c8c65-1561-41a7-beaa-0539dd5077e8 |  | checkpoint | Fillet & drip mould installed
checkpoint-status | bae171a0-b1e6-4c03-816d-7f2cdfc5459b |  | checkpoint | Check set down position & RL
checkpoint-status | d2a79ff7-faea-4349-87b9-55a1d630d820 |  | checkpoint | Check penetrations installed
checkpoint-status | 25b20e89-3b79-4dd4-966c-a1501dc99417 |  | checkpoint | Prop drop head wedges are secure
checkpoint-status | 94b20a5d-23ef-4b1d-bab9-06b1c2d8487f |  | checkpoint | Column blockouts installed
holdpoint | 3ac5122a-0563-4b68-bd9b-8b2a534c6bfc |  | signoff | Inspection by site engineer
checkpoint-status | 094662bd-b8de-4d96-a5e2-d253ad6ffd34 |  | checkpoint | check back propping as per design
checkpoint-status | c2a7ecdb-6298-42f7-bb26-8f26edc1a63a |  | checkpoint | Blow off deck
holdpoint | 29e7fdda-16da-4f80-bed3-71dc844d84a2 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 0806a04a-cd32-4253-bf39-e721f6201ca9 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | 364143ac-4416-47b3-8518-53a697e75f6b |  | checkpoint | Correct Class of Finish
checkpoint-status | de1b2310-55af-47a8-8ce0-18eb23cb2368 |  | checkpoint | Stripping, cleaning & materials removed
checklist-sectioned | db42dfdf-b127-41b5-992c-eb3ea9c10306 |  | checklist | Jump System / Climb Track Checklist |  |  |  |  | Yes | Jump System / Climb Track Checklist | 922b7689-c02a-4974-8853-c26376e576f9
checkpoint-group | 9076bda7-2d71-4f2e-b1f3-c57e4c254108 |  | section | Pre Lift
checkpoint-status | d0e292b3-30b2-49f8-ba34-31bb86071c33 |  | checkpoint | Confirm concrete strength MPA 15 has been reached at connection points (Builder to supply)
checkpoint-status | d2300e14-106a-406f-a21d-a53dbb2c7bd2 |  | checkpoint | Signage in place (Stripping in progress/Jumping in progress/ No access)
checkpoint-status | 050e5403-905f-4db7-b5c6-9d7cbc528092 |  | checkpoint | Exclusion Zone in place
checkpoint-status | 8de8ce94-8d7c-4023-958d-c5db9bcfdcb4 |  | checkpoint | Spotters in place on slab below jump (outside exclusion zone)
checkpoint-status | 3758668d-32f3-4533-a605-da57ce4f9158 |  | checkpoint | All Platforms cleaned and clear from rubbish
checkpoint-status | 2d620310-2f49-45c2-985e-6c9d73a39a2b |  | checkpoint | All loose materials removed from edge
checkpoint-status | aaae7152-77cd-453b-bce6-ee11fba3bc5b |  | checkpoint | Clear communication between team leaders and Crane crew (toolbox talk)
checkpoint-status | a07f380c-f069-4660-87f1-4be8209d0b85 |  | checkpoint | Ladders available and secured
checkpoint-status | 8949ae9c-4d9f-4338-bacb-297359c97727 |  | checkpoint | Flipper systems lubricated
checkpoint-status | 2e8c8f75-2e1d-44cc-bca4-69d146b66078 |  | checkpoint | Trailing Decks clean of debris
checkpoint-status | e7faa047-485b-4658-b39f-6270829e2199 |  | checkpoint | Trailing decks clear of protruding ferrals in walls above
checkpoint-status | 3f4ab5fa-f3d6-4fc0-8947-8e2b556319ab |  | checkpoint | Check exclusion zones in pit below are in place
checkpoint-status | eb02bd6c-a283-459d-9c26-a770c77eefdd |  | checkpoint | Plumber to check pipes to water cooler
checkpoint-status | 086115a5-cf22-4733-9fb3-7830bf14f741 |  | checkpoint | Transfer RL heights
checkpoint-group | a744ef5c-3724-4bbe-8039-00f17082a8c1 |  | section | Post Lift
checkpoint-status | 00417cb6-db7d-4f17-83bc-c297e67852bf |  | checkpoint | Confirm connection points are secure and all engaged
checkpoint-status | c6d8d622-946a-48fc-a47c-068fd5787dc5 |  | checkpoint | Confirm mesh secured to doors and penetrations
checkpoint-status | d77ec5a3-20c7-4c62-b937-3232a29391fe |  | checkpoint | Signage in place
checkpoint-status | a3bcd24c-d57e-4f61-bba5-8cdbd0eaf6f3 |  | checkpoint | Screens and mesh infills are in place and secure
checkpoint-status | d060ba2e-c02e-47eb-8dc5-d363130d2d63 |  | checkpoint | Loose materials are stacked and secure each day
checkpoint-status | ee6030ae-e75e-4303-96c5-11ce1c66901f |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 15971bfe-1ce4-4911-bbe9-0bc57b173fac |  | checkpoint | All loose materials removed from edge
checkpoint-status | 92ab1440-1633-4ec4-82d8-54ae4b55d3b3 |  | checkpoint | Loads on platforms not exceeded
checkpoint-status | 5587c544-43cf-451b-9af3-dc7418261c1a |  | checkpoint | Ladders available and secured
checkpoint-status | b308933e-c2b1-4959-8bf6-9fcb379714a3 |  | checkpoint | Access is clear and marked
checkpoint-status | 2ab213ce-9082-467c-b611-6f486392c874 |  | checkpoint | Power Board connected
checkpoint-status | e3bd20fb-a27b-40e2-a84b-e094ce3de560 |  | checkpoint | Confirm ready for lift with all involved - Team Leaders
checklist-flat | 592faedb-3c08-4233-9c05-e7cd406f159c |  | checklist | Progress Claim Checklists |  |  |  |  | Yes | Progress Claim Checklists | 95e067ed-7b1f-4111-9ba4-96a0a92d4dd2
checkpoint-status | be63b777-01d2-414c-bd49-f44266f208db |  | checkpoint | Please add Comments / Photos
select | 709fe0c3-f903-5d3e-a8aa-fddf783bd24f |  | dropdown | General | Site Establishment / Prefab, SOG , Ground, 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | b3e37527-f96d-5a75-8ca4-38ac1c9139ae |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 24061cbd-bab6-5e0c-a9d5-2dd9d92a1229 |  | textbox | General Notes
checkpoint-status | a18f00f8-985c-466e-9f0d-a68e58f8156e |  | checkpoint | Please add Comments / Photos
select | cf8a0aa6-1de2-5a33-86cc-e89dab8c5998 |  | dropdown | Level | SOG , Water Tank / Energex Room, 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | edc22e2c-dd27-5752-8ea7-d5cd05b5fea0 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Columns, Formwork to Vertical RC Walls, Formwork to Vertical Core Walls, Formwork to Suspended Slab, Quick Stair System including Handrails and wreathing (Fire Stairs Only),
select | 1d77eb61-2857-5f74-a693-1de812e71158 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 0990739e-76ad-5168-a18c-666e3d8f7c58 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | b8e66338-7dac-57d0-850f-c1121093e3c1 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | fc5b2b61-9a98-5bab-8454-9ea31839b490 |  | textbox | General Notes
checkpoint-status | eb55e2d8-9333-4055-b6c3-ce7b98b62d18 |  | checkpoint | Please add Comments / Photos
select | 37867675-40e3-5d7e-8844-d14056d89106 |  | dropdown | Level | SOG , 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | 2dd3aca0-21be-51fe-b9d6-2e431f3f25ee |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Columns, Formwork to Vertical RC Walls, Formwork to Vertical Core Walls, Formwork to Suspended Slab, Quick Stair System including Handrails and wreathing (Fire Stairs Only),
select | 9ec9234d-4c5b-56c9-b42f-7eff4631add8 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 7f007025-8745-541a-91c9-8959b4a2fbe8 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | c486166c-283a-5ec9-ae48-86d9142cc592 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 8022a649-e2f8-5695-87bd-f554dfc90710 |  | textbox | General Notes
checkpoint-status | 5ba7c499-89c8-4ba6-a19c-990e1d480ea7 |  | checkpoint | Please add Comments / Photos
select | ff18b834-f309-5983-affe-fa62f6b69d4b |  | dropdown | Level | SOG , 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | 576b4564-03fc-5f11-a929-9dbaa06cd2c5 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Columns, Formwork to Vertical RC Walls, Formwork to Vertical Core Walls, Formwork to Suspended Slab, Quick Stair System including Handrails and wreathing (Fire Stairs Only),
select | b4e1c47b-f986-5e13-8146-f025aedbab6c |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 8f6f6fb4-19f4-57b6-8e6f-55d0e2a1e7fc |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | ed98b19e-d3a4-5fda-92ab-d5024b58b12f |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 77fa102f-e41f-5da1-887f-83e228b0c771 |  | textbox | General Notes
checkpoint-status | 3050d35a-c973-423a-b3fc-f698e9eef012 |  | checkpoint | Please add Comments / Photos
select | 2f0a9ff1-30a7-572f-90cc-679f54525702 |  | dropdown | Level | SOG , 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | e56dc134-68c2-5fa3-aef1-2bf89e955831 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Columns, Formwork to Vertical RC Walls, Formwork to Vertical Core Walls, Formwork to Suspended Slab, Quick Stair System including Handrails and wreathing (Fire Stairs Only),
select | 6772bf0e-b592-5ed4-9bcc-4b9b2f74625e |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 60ca6109-677e-5ec5-a977-29fa1092086c |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | bb2f3ef4-bdda-5ab1-85f9-d290faf820c4 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | f6f799ac-f77d-5ac0-99df-d371ac85a723 |  | textbox | General Notes
checkpoint-status | 9f8a5a25-aeaf-4e62-9010-600926579813 |  | checkpoint | Please add Comments / Photos
select | ee40f0cf-07a7-5b30-9b8b-67d0295a0357 |  | dropdown | Level | SOG , 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | 5070f74c-ffd2-524a-b5b4-2bee552050ce |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Columns, Formwork to Vertical RC Walls, Formwork to Vertical Core Walls, Formwork to Suspended Slab, Quick Stair System including Handrails and wreathing (Fire Stairs Only),
select | be9b0c39-9caa-5f63-8859-0e8477884a57 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | d4b8a463-1a14-52fe-ab6f-dc4ebffc6339 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 883150bb-6d86-5559-b7bd-d0ae9a748f54 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 0eb154f0-567e-584b-83f5-0c24a175528b |  | textbox | General Notes
checkpoint-status | d6d4d317-60b5-41fe-8335-096d39ba4a0e |  | checkpoint | Please add Comments / Photos
select | 6225b1c8-8e48-5b2f-8a30-b3423a3f6bfd |  | dropdown | Level | SOG , 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | 63b9e0b7-3ee0-5490-9ba3-a8334c36b044 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Columns, Formwork to Vertical RC Walls, Formwork to Vertical Core Walls, Formwork to Suspended Slab, Quick Stair System including Handrails and wreathing (Fire Stairs Only),
select | 3ae63fcb-6d9d-5079-9194-433a8ca4c3e6 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | e806c16f-1cdf-5f4c-90e1-5dbc5c25c5c8 |  | textbox | General Notes
checkpoint-status | 89ba7e13-7f76-4323-8a7c-550a0c1b642b |  | checkpoint | Please add Comments / Photos
select | b06d9b29-7bf9-5046-b384-eb53ac7dea71 |  | dropdown | Level | SOG , 1, 2, 3, 4, 5, 6, 7, Plant Deck
select | 36c11a44-2ec2-505f-929d-52d2194136ae |  | dropdown | Description of Works | Quick Stair System including Handrails and wreathing (Fire Stairs Only),
select | 805b11d5-8bbf-54fd-a7f7-4f2f564481b1 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 3bba7e2d-2aa4-5715-a561-88ec2fe65837 |  | textbox | General Notes
checklist-sectioned | a6697bcc-bd5d-492c-a872-dbcd856a5c02 |  | checklist | Stairs (in-situ) Checklist |  |  |  |  | Yes | Stairs (in-situ) Checklist | a356506f-6e9c-4a28-8735-6fd592ffe767
checkpoint-group | f6c87606-709d-4ecd-b322-201670e54592 |  | section | Phase 1
checkpoint-status | 9576126b-4f60-4ca1-8bf4-fc4ea0b84c2d |  | checkpoint | Area accessible & ready
checkpoint-status | e9f2bbf5-9331-4109-b4b4-5990212a3fdc |  | checkpoint | Drawing references entered
text | ae27f434-43ea-5397-8300-0aba4e27a842 |  | textbox | Architectural
text | 951df585-0541-541e-95e7-08cd7327ec4c |  | textbox | Structural
text | 5e837e65-be0e-5834-9cbd-2cc5a0fb2444 |  | textbox | Other
checkpoint-status | fd36d794-93d4-4c76-b0ac-7b946e0c3f33 |  | checkpoint | Current plans in use
checkpoint-status | 53776326-f415-420b-9945-f340b532ba86 |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | 7fbc5cdd-97c8-40ee-a727-546cd9f22a9d |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | f2bc57dc-dac2-4a3e-a0d8-e696dc492fe0 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | c3c720a2-db7e-4fc9-ac2f-a2a5e486e000 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 5792873c-16fb-404d-b2c2-41cada74b29d |  | checkpoint | Riser heights confirmed
checkpoint-status | e6d79964-3eb3-4bb4-a7d7-551417c7573b |  | checkpoint | Going lengths confirmed
checkpoint-status | eabbd33f-7b00-4ffd-a6b0-5095b0077ff0 |  | checkpoint | Correct Class of Finish
checkpoint-group | 58e4d4f1-714e-4781-a2e2-ac268db51a10 |  | section | Phase 2
checkpoint-status | c51f5de2-4bb9-41c2-aa9d-1e87efa06644 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | d9a55606-56bd-4ae5-8e59-ffe25917c9b8 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 3b6b7b13-d68f-45b5-88b6-76b5fece6b0d |  | checkpoint | Base of stairs cleaned
checkpoint-status | e809580f-3dce-4390-a57e-789c44da5540 |  | checkpoint | Riser heights confirmed
checkpoint-status | 83b5e84b-2289-4631-86f0-d31413b4d490 |  | checkpoint | Going lengths confirmed
checkpoint-status | 166de175-ca07-4719-9a9f-54e82a409323 |  | checkpoint | Correct Class of Finish
checklist-flat | a86ce582-57ad-4050-a2af-7c143577cfd7 |  | checklist | Deck Handover |  |  |  |  | Yes | Deck Handover | a512a7b5-655c-4afb-8ae4-f1b7fd25344c
checkpoint-status | ec72f3cd-014e-4c69-ac28-80ee06144be7 |  | checkpoint | Communication between all trades
checkpoint-status | 8cd64569-ab68-4a09-975a-1eb3d9187f07 |  | checkpoint | Signage and barricades in place
checkpoint-status | 363bc440-50ac-4cdf-8a65-b3609351b181 |  | checkpoint | Deck clean and clear of materials
checkpoint-status | 15d6119c-38a7-4236-96e8-2e14cc9e68c5 |  | checkpoint | Loose materials are stacked and secure
checkpoint-status | a21cf5ff-535e-48ae-a5f9-edc0310c6ec7 |  | checkpoint | Any backpropping required to handle loads of reo and other equipment
checkpoint-status | 5e582567-27ac-48d4-a48b-20ba02a5fce9 |  | checkpoint | Designated walkways established
checkpoint-status | 925c6122-0c10-45a7-8051-1e538eaa039e |  | checkpoint | All loose materials removed from edge
checkpoint-status | 264cee3b-0b7f-4fbb-ad89-4b37f4024b66 |  | checkpoint | Are all penetrations covered and secured
checkpoint-status | 2fdf73a8-7074-4002-ad59-57b67fcf1093 |  | checkpoint | Rubbish bin on Deck
checkpoint-status | d1e0f5d6-7562-4915-8049-29a745977d17 |  | checkpoint | Perimeter Screens / Edge protection installed
checkpoint-status | f8915bfe-3af9-4573-a6e7-1d4213e3a09d |  | checkpoint | Correct spacing of frames, props and timbers
checkpoint-status | 85a8784b-ea83-4f44-8b83-2281336d9348 |  | checkpoint | Correct joist and bearer sizes
checkpoint-status | 2b467cb6-47a2-48a2-a33a-d76605aa4c15 |  | checkpoint | Acceptable jack extensions
checkpoint-status | d333eb62-462a-49be-9161-7fcfc03a4edc |  | checkpoint | Quality of materials
checkpoint-status | 22d729f5-9fd9-4a47-85fe-5a74e2836557 |  | checkpoint | Adequate bracing to ensure stability
holdpoint | f88bdf98-82dd-450f-8852-fc01bcdc3b80 |  | signoff | Deck Handover signed off
checklist-flat | c6800d22-4dbc-49bd-adbf-95915ff7213c |  | checklist | Daily Pre Start |  |  |  |  | Yes | Daily Pre Start | bc7364bd-e06d-4149-abb5-dab2bfd9ab63
checkpoint-status | e493c89c-1f12-4ff4-b4e2-193f3084a86a |  | checkpoint | Daily pre start meeting completed
text | ac6df0a1-172e-525d-a126-a382a6481fa0 |  | textbox | Date
text | b3999031-db07-5ee3-87b5-ae2bb22a0b98 |  | textbox | Time
text | adec4252-370c-5ed5-a466-dbed34af3680 |  | textbox | Location
text | 76bdc877-8317-5c71-94ea-a131defa5334 |  | textbox | Supervisor / meeting leader
text | b9c249b4-1cff-5c9b-a7aa-1783b2a490de |  | textbox | Project Manager & Construction Supervisor attending
select | 8efd13cf-5f43-50cb-bab2-b04f2d915988 |  | dropdown | Current weather | Rain, Wind
text | 6bb46e6a-5c09-5478-990b-3907b5ebe5bb |  | textbox | Temp
select | 6e5a9ac8-b2da-5fe4-af53-71d292604403 |  | dropdown | Forecast | Rain, Wind
text | af2b6dc7-a1b5-5cb7-b338-d5d77041219b |  | textbox | Temp
button | 2aad485c-5cc6-5908-ab97-c0cc4c70d74d |  | button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
button | 5caaed2b-c5e6-5bc2-b942-9f247c499132 |  | button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
text | 21a619c5-8206-5ddf-b3e9-ed0f5c832aae |  | textbox | Any issues from the previous day
button | 9a5947f7-88c4-546f-9fd6-53dfe16f600b |  | button | Do you need to change SWMS | Yes, No
text | a1c3f4a8-991b-5efb-86c6-82fc0114a00b |  | textbox | First aiders on site today
text | f96c4503-8f9b-57fe-b8da-de9aaafe0641 |  | textbox | Apprentice & who are they assigned to
text | 2632518a-3099-5a3f-bf98-8db8e3ecb717 |  | textbox | Apprentice & who are they assigned to
text | a494ba32-fb2f-5118-aed0-3b92c10b3a67 |  | textbox | Apprentice & who are they assigned to
text | def820f0-1e15-5ff8-9dc6-c4b8ec506416 |  | textbox | Todays tasks / jobs
select | 2738b20d-8565-5af9-9fc4-2a8295eaf890 |  | dropdown | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
button | 0cccff55-2aea-5d41-b7c7-ea880f07bf46 |  | button | SWMS in place for all activities | Yes, No
button | 43ad0c19-6fa9-5be4-877b-5d97e9c01b89 |  | button | Hot works | Yes, No
button | 04215065-b43b-5de5-825f-709227fd4d84 |  | button | Excavation | Yes, No
button | 88cf180a-a673-5876-9867-f97d65f58b55 |  | button | Ladder | Yes, No
button | 324cd5c8-75ea-5d52-8977-0b1abac7c202 |  | button | Core | Yes, No
button | e78ec108-79bd-5323-bf30-8502ef23dcf5 |  | button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
text | 1689f24c-9a32-5e4f-8d33-487440c215c3 |  | textbox | If yes, list the substances
text | bb0b8d03-f08e-570e-9f58-74de0775e466 |  | textbox | Attendees
checklist-flat | 83c05210-9c09-442c-9d3c-e966dd29ff5c |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Toolbox Meeting | c8d9c625-8b65-4950-b9e9-f897f4f89619
checkpoint-status | 0996e7ed-2dee-4234-ad58-c64f61902d97 |  | checkpoint | Toolbox signed off - Attach an forms
text | 6eb57bcf-d188-5df0-8cf6-582d7e971448 |  | textbox | Work area
text | d640477e-e179-53e9-ab23-7cd04beaa933 |  | textbox | Supervisor
text | 4fc684b0-01eb-5769-929d-c5a6af76b6e1 |  | textbox | Date
text | 094ee930-07d1-5a92-8b27-40e95ff124a3 |  | textbox | Time am / pm
text | 346e1432-cf96-5902-be6a-209c2e64fad0 |  | textbox | Actions from last meeting
text | 799ce208-dadd-5656-942c-bfb1fea785e6 |  | textbox | Injuries last week
text | a9720e29-1e63-5552-b36b-aa27af7d9f90 |  | textbox | Near misses last week
text | 473e8c5e-a4b8-50a9-91d8-05bf8ae685d6 |  | textbox | Safety Items discussed
text | 8fd95bd4-f5b1-5fe8-a84e-d3f87c6f7c97 |  | textbox | Comments from the floor
text | 57d98aa9-33d2-59b2-8fdf-ca4a15988d2d |  | textbox | New business
text | e1066c14-13a0-5154-be39-5ddedb31bb57 |  | textbox | Attendees
checkpoint-status | 389b3f95-8147-4bd4-a88b-1cd1a41a5e26 |  | checkpoint | Attendance verified
checklist-sectioned | 598ad65f-cc7a-4937-8757-53eb2cf07700 |  | checklist | Stairs Checklist |  |  |  |  | Yes | Stairs Checklist | db8ad7aa-7ce2-4e78-9ff9-1b0b83e849bb
checkpoint-group | bafff220-c506-4ff7-896c-e824008ce010 |  | section | Phase 1
checkpoint-status | 053f02fd-8c81-4fba-9771-05b94b20d0c8 |  | checkpoint | Area accessible & ready
checkpoint-status | 15790bb3-ab77-4066-be20-cdd22b97942f |  | checkpoint | Drawing references entered
text | c0d453ad-e4b2-5e8f-bdac-d9ea14415f88 |  | textbox | Architectural
text | eccc1d7a-c54d-5c4d-9e73-83ded710116e |  | textbox | Structural
text | 72d7d6b2-800c-5364-a333-c2da0c1be8d9 |  | textbox | Other
checkpoint-status | 5b910937-8815-4a94-874c-cf6f22f5b84e |  | checkpoint | Current plans in use
checkpoint-status | b383e386-0af3-4b9a-b9fc-c53239f5f648 |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | e6d1ce3d-70c7-4a79-81e4-c882f7a887ae |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | ba41e9d5-66ea-42fc-9cdb-80ccc77cbcb9 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | c75e4794-9d02-4e0f-9c7f-a8b9e4946e12 |  | checkpoint | Base of stairs cleaned
checkpoint-status | e9f04abf-3851-464b-bfcf-e34194b10efb |  | checkpoint | Riser heights confirmed
checkpoint-status | 56e19b28-aa9e-4a9a-83e9-ff35eb51adbe |  | checkpoint | Going lengths confirmed
checkpoint-status | 72ebac6c-5e7a-4cde-98ca-0ae23e7c47d6 |  | checkpoint | Correct Class of Finish
checkpoint-group | 9a59806f-8cb3-4b2a-93f7-e030241070ad |  | section | Phase 2
checkpoint-status | ee7ffda7-5b40-4626-ac8f-f0ecfdb54540 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 5b46d236-38b7-4296-85d5-c04ec3786cf4 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 2b9597da-a12d-4f0f-b9c0-481ab98e90f7 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 228ebce9-08bc-490d-a90d-1b07cc53e398 |  | checkpoint | Riser heights confirmed
checkpoint-status | 1575d2d4-3079-4187-a6db-c80042682b17 |  | checkpoint | Going lengths confirmed
checkpoint-status | 8b78353d-3448-4451-884d-b1b4c4c8bd59 |  | checkpoint | Correct Class of Finish