## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | bd543337-3eb7-4440-8d3e-c81d22533b78 |  | checklist | Progress Claim Checklists |  |  |  |  | Yes | Add Progress Claim Checklists | 0ed2f427-e731-4aa7-a9ad-30809c0d5dcc
checkpoint-status | 08054a0e-6561-466b-ae1e-7a14091db95f |  | checkpoint | Please add Comments / Photos
select | 0334c6a3-3940-5ffe-acc9-50c7d6a067b0 |  | dropdown | General | Site Establishment / Prefab, Systems
select | b2ba408b-9658-556f-9c54-4c7d05905332 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 05e83bf4-3ebc-5c96-8d60-c0eb984c0fc2 |  | textbox | General Notes
checkpoint-status | b80245c8-c809-45a2-bc42-3589142aa62e |  | checkpoint | Please add Comments / Photos
select | 209f937b-2ab7-54fb-a9bf-ca0992a684e1 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4,5,6,7,8,9,10,11,12,13,14,15,16,17 Roof Plant Deck
select | bd853fb3-8dd4-5fa4-bce2-03c82a045395 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | e0135f1f-cf1d-5002-b38e-e52a8f99ed37 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | cfaebe88-e9a2-5f8d-a588-bf450c78b909 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | c97baf07-ca4d-5308-802e-4886c16e2012 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 43a46f1c-e2d2-5415-ad5e-9f7d29d26345 |  | textbox | General Notes
checkpoint-status | 5b8df1b0-a6e9-4f2a-868e-d4f0a4a5c57f |  | checkpoint | Please add Comments / Photos
select | 669ac896-0a23-54aa-af9c-6ed15fdc7028 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4,5,6,7,8,9,10,11,12,13,14,15,16,17 Roof Plant Deck
select | b8d9c5ed-a095-595c-9955-b45e33c9e1a0 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | a84cf8f1-dccf-51ec-9f32-706602aae6a4 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 9b0c8aaa-a9ef-58b5-948e-93ccf0534e02 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | dbec6e42-88c1-537b-a42d-9f2f22908827 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 2e69016b-2f32-510a-ac28-b563898ecf4e |  | textbox | General Notes
checkpoint-status | c3aedfb1-ce5b-47ba-84b7-cf9384f5bf44 |  | checkpoint | Please add Comments / Photos
select | f66e83f1-1b7e-5b6f-bc39-77978fa6e48e |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4,5,6,7,8,9,10,11,12,13,14,15,16,17 Roof Plant Deck
select | c10842ca-ba72-5f68-bdb0-2fcbc66e3c5e |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 8eea4276-4725-5a2a-ba98-96cddf4ce510 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 27aa4c3e-a719-54d5-9edb-6accf7c8f927 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 80784fd8-733f-5f46-b6c3-601b1dceae28 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 28570ae5-6a0c-5da4-8da7-29d1df4ca8e0 |  | textbox | General Notes
checkpoint-status | 3c1f0379-117e-4554-b1b3-03c35227454e |  | checkpoint | Please add Comments / Photos
select | 09b12b0c-81a1-59a3-8788-daafb5fdab7f |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4,5,6,7,8,9,10,11,12,13,14,15,16,17 Roof Plant Deck
select | e0769adc-2f88-51ac-8855-d4b032303b13 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 9c3e5f9d-4745-5270-9a6b-37dee36a308d |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 9e74191a-57a1-5219-9c72-614da1c0c7ae |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 341734e0-8a0e-55ba-a99c-649fe825995e |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 9a3cd899-251b-58ba-b086-127d66754f6c |  | textbox | General Notes
checkpoint-status | bf64fe3d-2fcd-40f2-8748-e12beaabf642 |  | checkpoint | Please add Comments / Photos
select | 40342b9a-e846-500c-810d-3108470d6c19 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4,5,6,7,8,9,10,11,12,13,14,15,16,17 Roof Plant Deck
select | cd26670e-6bd5-58d2-8bba-b13559e4fd6a |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 1594ab8e-7178-5ae5-9138-84c5932e2c1c |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 62fe55d2-e0a0-50ca-9c1d-14bb4f666eea |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 91a387fa-224e-5784-9713-d6badf6cf169 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 3614a2eb-e73d-5c55-a806-eb5bd45cbfd2 |  | textbox | General Notes
checkpoint-status | 4d75d563-1b17-4385-911f-3c43d40a4de1 |  | checkpoint | Please add Comments / Photos
select | 77a1d1e9-ca9a-5b92-81ba-10d0c63a085b |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4,5,6,7,8,9,10,11,12,13,14,15,16,17 Roof Plant Deck
select | 71dd22da-015d-534f-8b63-62f6b2eeda1d |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 4cb83e85-a2ed-519a-8483-edd253198327 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 671e3999-2a60-5869-b252-bdba34ea43b4 |  | textbox | General Notes
checkpoint-status | f96dc449-07aa-4e5c-9f68-9766fd3347a0 |  | checkpoint | Please add Comments / Photos
select | a50110be-d342-5876-9d6a-65c9417d6a24 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4,5,6,7,8,9,10,11,12,13,14,15,16,17 Roof Plant Deck
select | 8e409bc7-d835-5257-b6ed-51a6bcb3c93b |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | c1efed20-5886-529f-9c30-ff1ee48cc43c |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 24c1bfaf-a1e9-5cde-9753-aa58e40d2928 |  | textbox | General Notes
checklist-flat | 6a243ef6-1b5d-492d-83a9-750f0b1c6a58 |  | checklist | Site Diary |  |  |  |  | Yes | Add Site Diary | 1da8f21e-1a88-4330-95be-f9cfdba5b5b3
checkpoint-status | 122e805f-9c75-41c9-b181-475e21f4ddea |  | checkpoint | Areas of work accessible for the day
select | 9f38e2ff-56f8-5144-acf4-5ecc38a5b644 |  | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | 9e3e447e-2787-5749-9bf5-4cb1fccb8274 |  | textbox | Date
text | 5763cbc9-45e0-597c-9ad6-401fa76c6e20 |  | textbox | Year
text | a42ced2a-e826-5a5e-bca6-2a4b4a615fe4 |  | textbox | Number of workers on site
text | 6cb7fda9-0fbe-5f40-9f0d-fc4fba75e00c |  | textbox | HSR on site today enter name
text | d0c01000-d069-57af-b2a9-668f54b80de2 |  | textbox | First Aider on site today enter name
text | f6a4572f-1558-5228-9454-4593a897aba9 |  | textbox | Injury on site today enter name
checkpoint-no-status | c047bf81-2718-4247-b873-d729d8fa5b11 |  | checkpoint | Work area 1 details entered
text | 25a59188-c370-5681-ae87-dfe0cd600161 |  | textbox | Area
select | 175f37e3-24d0-5060-ae58-f3ae9f795c6c |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 3ae822de-7363-586a-85b5-3ad2d104d46a |  | textbox | Comments
checkpoint-no-status | 9a53f32f-0f5a-4d61-bbba-20793097a037 |  | checkpoint | Work area 2 details entered
text | 6fb6e5ad-c251-5daf-a23f-3bd64d2a33a5 |  | textbox | Area
select | b9b8ea0d-f9c8-5d35-ad30-2d5db653369f |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 2b6466d6-586d-5cf4-a7f1-e04b9d57eed4 |  | textbox | Comments
checkpoint-no-status | 31d5ffda-84d4-44a9-8a2f-7ad7f2459848 |  | checkpoint | Work area 3 details entered
text | b7f59c66-8fea-5ba7-a13b-2cd109cf1dd7 |  | textbox | Area
select | 9402c5b1-bfad-5787-86b2-f592bf879088 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 4007d28f-de04-51af-b43e-76a7ae5f1add |  | textbox | Comments
checkpoint-no-status | a68ed31b-81ba-428b-8ce8-49eb8e8c1598 |  | checkpoint | Work area 4 details entered
text | 8891758b-9f08-595c-ab21-55c07f704e0f |  | textbox | Area
select | 8b9a2ffc-f6cf-5d65-9bdf-c495e7fd1243 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | d76faccc-27e7-59ef-b43b-ff4c8ad36dbf |  | textbox | Comments
checkpoint-no-status | 37acae3f-8ca9-4e6d-9c52-014315555e1a |  | checkpoint | Work area 5 details entered
text | 9ef28ebf-9caa-5897-844e-db8c3ab344be |  | textbox | Area
select | e6282fe4-31af-5ffb-9d54-349678afd34a |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | f5bd588f-6cea-5683-9555-4da88e6a0610 |  | textbox | Comments
checkpoint-no-status | 6de6b19b-fbbe-4900-b8a5-0a40cf87099c |  | checkpoint | Work area 6 details entered
text | dba83ebc-2b35-54d9-84df-191d1accc4fa |  | textbox | Area
select | f1e89470-5fc4-5b46-93b5-7542c0f62229 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | f329ff1c-739f-5a56-95e6-f95d8bc0a45f |  | textbox | Comments
checkpoint-no-status | 74a30757-7963-460e-bc45-99a7b43a76d4 |  | checkpoint | Work area 7 details entered
text | c060b570-d4f6-5401-9122-b47aa4301db8 |  | textbox | Area
select | 2e2c09f0-16f4-5ecf-9521-2d8ef354c5dc |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 0c4a5b9f-e837-5c60-8a44-19843a51c015 |  | textbox | Other
checkpoint-no-status | 214ef50b-7b4d-4599-abb4-b0758d95d7c9 |  | checkpoint | Work area 8 details entered
text | b596f758-61fb-5e9b-919c-14f92ec035cf |  | textbox | Area
select | 218ed5d4-f6ad-52bf-bc8e-ed30003c86fd |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 596b740a-7dec-5ce6-928e-288149179a6d |  | textbox | Comments
checkpoint-no-status | 2637eb2c-225c-4e42-b70a-3834820200d3 |  | checkpoint | Weather conditions entered
select | 519438c9-67ff-556e-8aa3-dbf7334cdc1c |  | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | 4a8bfa18-1722-570b-b5b2-e5516d824d33 |  | textbox | Min temp predicted
text | aa964013-3cad-5e8c-a032-198850d4a71c |  | textbox | Max temp predicted
checkpoint-no-status | 28263d8e-0752-41f7-b349-4700d859fa8e |  | checkpoint | Delays from inclemency
text | b3610c29-2a02-5ea0-8b7f-00d47552e228 |  | textbox | Total Hours of delay
select | a8ca07f3-6946-5682-9ab8-684a3f13b426 |  | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | 838dae43-b06e-46f0-ac41-6bcc9dd4879f |  | checkpoint | Delays from Builders or Others
text | 92b5b900-e8fb-5cab-9174-44e2be12385d |  | textbox | Total Hours of delay
select | 264832b6-0120-5013-bc34-f2bff4a00ba9 |  | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist-sectioned | f061572e-35d4-47ee-a7ad-9b81ffe21ddc |  | checklist | Screens |  |  |  |  | Yes | Screens | 267345e0-4955-4ce5-a318-9a85e72f56be
checkpoint-group | 7176fd8c-8d41-4721-a62f-d18dfd7dddda |  | section | Pre Lift
checkpoint-status | a474900b-8235-413c-9397-ee1f03a9b9ec |  | checkpoint | Area accessible & ready
text | 9781a97a-03d6-56b0-b155-19b4bb4be18d |  | textbox | Screen number
checkpoint-status | 0346b117-7d81-4ffa-8a04-af51b6ff9bd3 |  | checkpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 84913055-77f0-4b93-ae34-8536401f8278 |  | checkpoint | Signage in place
checkpoint-status | 9a625927-a611-43d1-86be-8977fb33c734 |  | checkpoint | Exclusion Zone with name and number of supervisor– Ground level and Slab level
checkpoint-status | 53ff8d56-2a49-4492-871c-5389221e3831 |  | checkpoint | Spotters in place
checkpoint-status | 3d41b1f4-821f-4b98-a1d1-48667c9defb2 |  | checkpoint | WMS ready and signed on to
checkpoint-status | e994ce57-1c15-4101-b247-c399dbdadf8f |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | d1649c2d-365c-45c7-9d87-782385e7b289 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 9a3b9bc9-4765-4486-9496-30faf34a346f |  | checkpoint | Edge protection installed on Level/s to be exposed once lifted
checkpoint-status | e28de0b6-3b35-4ebf-b55c-cd7a2cfe7c64 |  | checkpoint | Deflector shields removed
checkpoint-status | f02af683-2f12-4bdd-8da7-600b7c2d2f4a |  | checkpoint | Radio communication woking between screen crew
checkpoint-status | 8bc76c3c-95da-4420-b9d2-bf5264c3025a |  | checkpoint | Hydraulic lifting Apparatus installed correctly if using lifter
checkpoint-status | cea2733a-9bff-43fc-aa4d-35f7b0eb5224 |  | checkpoint | Screen Free from Debris
checkpoint-status | ec41f007-eab5-449f-879f-9030ed587064 |  | checkpoint | All wire infills detached
checkpoint-status | d425bc02-4e25-4096-87db-2845c3e590a4 |  | checkpoint | Confirm ready for lift with all involved - Team Leader
checkpoint-status | ce6fea1f-9001-4f23-9e30-10cdd84eb7e6 |  | checkpoint | Work at heights permit completed - attach or take photo of permit
checkpoint-group | c432d4d4-87e6-461b-86ca-bfecba1b42f3 |  | section | Post Lift
checkpoint-status | 0e015f4c-05fa-4f7a-97d0-d1e3fc8af681 |  | checkpoint | Ensure all gaps are closed
checkpoint-status | 1ec05b4e-1bdb-4bd1-9e31-f30b9503cda9 |  | checkpoint | Mesh to be install where required
checkpoint-status | 878a5909-7e58-450a-a148-c1487c35c7a3 |  | checkpoint | Double check all needles are secure and double nuts in place
checkpoint-status | 5e1a35a8-70c9-4ff8-897f-0eaaacf1319d |  | checkpoint | Clean and clear area
checkpoint-status | cef5e7a0-5a3c-4a0f-ae47-9a225d113d13 |  | checkpoint | Remove exclusion zones and barricades
checkpoint-status | 7a33f252-5234-47e2-a19e-8b518d6d6449 |  | checkpoint | Bar caps for protruding z bars
checklist-flat | 47c12e5a-8c81-4ce6-bb9f-a776d2b9fb8f |  | checklist | Suspended Slab Checklist |  |  |  |  | Yes | Suspended Slab Checklist | 38354ac3-3f9d-42fe-8917-b336c1d366ed
checkpoint-status | 249c48ad-86fc-4b35-9926-a7bc82711da3 |  | checkpoint | Area accessible & ready
checkpoint-status | dcba3be8-5b70-4201-9d26-387002234b56 |  | checkpoint | Drawing references entered
checkpoint-status | 245b9248-f3d5-4633-814b-031634e194ac |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 74b5c5b3-fd1b-479b-9078-acd56629dfa4 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | 44f48dc9-58a7-4f31-b85b-60acaecb1760 |  | checkpoint | Grids marked by builder
checkpoint-status | a82e36f5-7169-4239-947f-f5b8b63ba0d8 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 003e37c0-015d-4c23-95c7-7ce44b6811b5 |  | checkpoint | Fillet & drip mould installed
checkpoint-status | 9d112d4b-613a-4b69-8a2b-4dfe87a61509 |  | checkpoint | Check set down position & RL
checkpoint-status | ebba6ced-3d4e-4acd-a66c-1b9bbf4429b2 |  | checkpoint | Check penetrations installed
checkpoint-status | 7c4d3be5-377c-48e5-a68d-af6ea3fa7df7 |  | checkpoint | Prop drop head wedges are secure
checkpoint-status | 63abdb19-3c38-4690-ae99-88b3aa15312f |  | checkpoint | Column blockouts installed
holdpoint | d5166240-81f0-406f-b370-f11128dcde9e |  | signoff | Inspection by site engineer
checkpoint-status | 7eb0f66f-b002-4505-995e-d5b285a18622 |  | checkpoint | check back propping as per design
checkpoint-status | 4310d318-2f1d-41b6-91af-bf84d8d1906c |  | checkpoint | Blow off deck
holdpoint | ce922afd-9324-4da1-b1f1-ffef56d57356 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 62b66205-2204-4a24-ba1b-4ad0a43f1935 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | ad922412-64ec-4959-954a-8a2a1deee43d |  | checkpoint | Correct Class of Finish
checkpoint-status | f3ee4d09-3a7b-47e5-bf2b-a03505e8805c |  | checkpoint | Stripping, cleaning & materials removed
checklist-sectioned | c913bbd1-2299-4126-8302-22d7090afba5 |  | checklist | General Incident Notification |  |  |  |  | Yes | General Incident Notification | 44f7bcb8-4d6b-4350-8007-c340942aaa6f
checkpoint-group | 7be3b428-b957-4526-947a-000162879b12 |  | section | Details of the person completing this form
checkpoint-status | 623b80aa-7d41-4880-a76d-65c138f3d500 |  | checkpoint | Attach any relevant photos or documents
text | 1f173d14-761a-5dd6-a039-32f7c2b66981 |  | textbox | Name
select | a1fa773a-1a7b-5ba6-936c-00f9be770b75 |  | dropdown | Position | Site Manager, Project Manager, Construction Manager, EHS Advisor, Other
text | 692fc316-9ce7-57ca-be4c-69c6a25f6c41 |  | textbox | Contact number:
text | e51b1b1f-b1c0-54b6-b161-ac5c15bfe9f5 |  | textbox | Completion date
holdpoint | 735de714-67b6-4a47-aea5-883a9ba611dc |  | signoff | Signature Required
checkpoint-status | c44b4a58-3204-4f39-8bef-7f18cbe1e180 |  | checkpoint | Report reviewed by (mark if applicable)
boolean | 73466984-e38c-528d-8720-8672de39e5c1 |  | tickbox | Site Manager
boolean | 9726aeea-0b03-521a-b88a-220ab01cd0f5 |  | tickbox | Construction Manager
checkpoint-status | e43da2d4-4247-4016-9a6e-ccab668e250b |  | checkpoint | EHS ADVISER ONLY – Head Office
text | e2ef83f2-a969-516c-b03a-ce46c9321fe8 |  | textbox | Date received
text | 20a53823-719c-5b57-9740-7e03cc2ae995 |  | textbox | Date closed (Final)
text | 40b249f3-4b81-5c96-9552-48a401eb952e |  | textbox | Date submitted to EHS Administration
checkpoint-status | a0e5d4fc-17d0-48ce-ac7b-1a62c5705d1f |  | checkpoint | EHS ADMINISTRATION ONLY Head Office
text | 74fdb73f-7e0c-574f-841a-0e2c49956b8f |  | textbox | Date received
text | 1f93c8e5-0b03-5b21-9e2b-948239c2d02e |  | textbox | Date processed
checkpoint-status | 8cc53556-85f7-4ba9-9bf5-f76d43b783ca |  | checkpoint | EHS REVIEW ( EHS Manager)
boolean | 2a98b050-d6c4-5233-b6e3-17afd755bd38 |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 9149302b-6240-54f7-88c4-28a29bbe1356 |  | tickbox | No
checkpoint-status | cfed2f36-b4dd-4dc6-bfef-24184f5fe293 |  | checkpoint | EHS System / SWMS amendment required?
boolean | 76742ff5-cea2-578b-a5f0-c758c057ac2a |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 4c2f1a69-fcbc-5c0d-aa62-f304b56f8bed |  | tickbox | No
text | d3023cc8-e541-5432-94eb-b7f96b5df8a5 |  | textbox | Head Office EHS Manager sign off date
checkpoint-group | 406ba6a5-e4a1-453d-b435-34ccbba76232 |  | section | Incident Type
checkpoint-status | f9441d51-a179-43be-959b-642e439abf21 |  | checkpoint | Was a person injured as a result of the incident? - If PASS Only complete an Accident/Incident Notification Report (Form No. 01a) - If FAIL complete this form
checkpoint-status | 0de07160-a6ed-4fa8-aa40-4c114b3a171f |  | checkpoint | Has an environmental issue arisen from this event? If PASS Only complete an Environmental Incident Notification and Investigation Report (Form No 01b) - If FAIL Complete this Form.
checkpoint-group | 1d951924-155a-46f7-a33f-4383ca4091f0 |  | section | Project Details
checkpoint-status | efb1c076-3d27-4d47-aaa0-535e4e072fb2 |  | checkpoint | Report Status and Date:
boolean | fbd9e4f8-d51b-5df3-8101-27b43b04799c |  | tickbox | Initial
text | 8e0c4516-2e76-556c-bd44-fc4d0ddc15c0 |  | textbox | Date
boolean | c12a2c66-d3ab-51c3-a36c-ed1f97e0eb39 |  | tickbox | Interim
text | f8af5f0a-8e47-528b-95f8-3454fc2fdd31 |  | textbox | Date
boolean | 416e175e-b13a-51f7-a009-dc6850e29c4a |  | tickbox | Final
text | b554466e-2ef3-5540-8a95-c2ae0b9a1249 |  | textbox | Date
checkpoint-group | 06076ba7-3464-4fb4-9ed8-7f64a96bb6fe |  | section | Incident Details
checkpoint-status | 6043035c-931f-4df0-8bc7-bfbded2d698c |  | checkpoint | Date/Time of the Incident
text | f46ef44d-b9f4-55ff-976b-0004965b03b2 |  | textbox | Date
text | 246b6ae9-c3fe-56f6-885b-936678424d27 |  | textbox | Time
text | bd600ca9-ed94-5561-9999-440666c45dc7 |  | textbox | Site location of the Incident
text | cdcdc3d6-8fa5-56d1-88e0-9a1d3d4b436b |  | textbox | Detail how the Incident happened
checkpoint-status | a85e43d5-fd32-471c-89f2-96bf6c40e688 |  | checkpoint | Services affected by the event
boolean | 7d980aa4-b3a8-5d85-9f43-b194b5953b5a |  | tickbox | Electricity
boolean | cf726a90-938a-5f52-afa6-ed3b4ae9527a |  | tickbox | Potable Water
boolean | a5fa5c81-6f01-5084-8a83-2905ec78be8e |  | tickbox | Storm Water
boolean | d07250ff-495b-5d7c-b117-41218c7c5ffd |  | tickbox | Sewer
boolean | 4dade4c8-eae5-5619-8d52-207f0ade09d6 |  | tickbox | Fire Mgt Services
boolean | 3b90e5a0-8b6d-52f5-8f03-eaef194e53d9 |  | tickbox | Fire/Smoke Alarms
boolean | 9bfc3bae-4ce7-556a-8c67-352258245590 |  | tickbox | Air-conditioning
boolean | 5909a147-546f-5cb9-9f6e-b1c22e2e7fba |  | tickbox | Security/Access
boolean | bb601bb6-1a58-5b76-bd3b-5a736ba1fe2c |  | tickbox | Communications
boolean | 61d3ca19-7765-5e58-8ced-bf456c7a0638 |  | tickbox | Gas
boolean | 22f5d8b9-ca0e-5688-82b8-bd84f76ad828 |  | tickbox | Other
boolean | 4747c30c-a336-533c-ba56-e99cbc797495 |  | tickbox | N/a
checkpoint-status | c69c0455-0588-4abc-a9eb-f31742291446 |  | checkpoint | Detail the factors that contributed to the Incident
boolean | 578168bf-82a9-5aa7-ac75-6d907cf4c8cf |  | tickbox | Design/Layout
boolean | 175fc2ed-2780-53fa-afbc-927c6bb28550 |  | tickbox | Equipment
boolean | 0b926953-8615-5a80-9eba-54692df8bfc8 |  | tickbox | Operator error
boolean | 86ea1fdc-06f1-56b3-b6c8-47601a95ec75 |  | tickbox | PPE
boolean | 3b9679b6-f8d7-52ae-a0be-0bf454d18717 |  | tickbox | Training
boolean | dc389518-6d64-552d-be50-98466d011191 |  | tickbox | Supervision
boolean | 6cdae7fe-e917-5e93-aa54-69f291bd770f |  | tickbox | Unknown location
boolean | 86e46b41-ef97-574a-838a-226d87555f0c |  | tickbox | Other unspecified
boolean | 371eb0eb-d603-5a04-8a6d-2fc77fe396da |  | tickbox | Housekeeping
boolean | 7fd8972b-f371-5d6c-b8e6-05db1417ff4f |  | tickbox | Procedure (WMS)
boolean | 53e3f072-42a3-58fb-be38-fe9110c5e442 |  | tickbox | Weather conditions
checkpoint-status | 73754709-3726-42ef-96b7-25458cc7244f |  | checkpoint | Was a WMS supplied for this type of work?
checkpoint-status | 549cea91-2c33-4ac7-a81e-87be0c6707d4 |  | checkpoint | Was the WMS approved by Principle Contractor
checkpoint-status | 87eb5e4f-dd78-4713-99c0-f2cfc97a68fb |  | checkpoint | Was the WMS signed by all personnel involved in the activity?
checkpoint-status | daa50812-98d0-4e75-834d-b1feea7fc995 |  | checkpoint | EHS Improvement Notice
checkpoint-status | 2d1e361f-1ca6-4e0f-9fc3-9913cc01bea2 |  | checkpoint | Was the work activity being performed in accordance with the WMS?
checkpoint-status | 2f142417-681a-4d40-ac05-22761dde07e5 |  | checkpoint | Was a Tool Box Talk held relating to this work activity?
checkpoint-status | 32abe35a-f4a9-4d7c-a08a-b23b9eae48cb |  | checkpoint | Was any external certification required for this work?
boolean | 0def7d08-7cce-5ad6-adfe-f2729bba49b4 |  | tickbox | If Yes, was it obtained prior to works commencing?
checkpoint-status | 51b50619-293b-4909-9992-fc189f8b7fbe |  | checkpoint | Was any monitoring required for this type of work?
boolean | cba5379c-223f-5aa6-be4d-9abd9054d7b0 |  | tickbox | If Yes, was it in place?
checkpoint-status | 4b18e307-ac1c-417c-8721-575059276c14 |  | checkpoint | Was an Authority to Work Permit required?
boolean | d9c2fd29-3e33-5f21-a934-62911a889846 |  | tickbox | If Yes, was a Permit issued?
checkpoint-status | 9e9b9796-f35b-4f45-a7d8-36b6f84f3316 |  | checkpoint | Were any Regulatory Permits required for this work?
boolean | 417b026b-8a0d-55cf-9606-f7617a682c78 |  | tickbox | If Yes, was a Permit obtained?
checkpoint-status | a43e4687-c4d3-45d8-82da-1ff039bb9a09 |  | checkpoint | Was a Notice of Impacting Activity required?
boolean | e63e2c0a-92eb-51ae-87cb-65e3ffdd6983 |  | tickbox | If Yes, was it issued?
checkpoint-status | 0ffb1217-6aca-486b-933c-a77406ed2556 |  | checkpoint | Estimated time impact of the event
boolean | 092a9f21-97c2-5d5c-b901-f8e49396b17e |  | tickbox | No impact. No loss of production.
boolean | 9601c0e7-54c3-58e3-ba61-cdcf34534c0e |  | tickbox | Limited impact. Production loss in localised area.
boolean | 6d652116-e53b-505a-88a7-2929404049e1 |  | tickbox | Major impact. Production loss across project site.
checkpoint-status | 1df1208d-4898-4f71-bc69-0cb8dd444e96 |  | checkpoint | Details of any persons involved in the Incident - Attach Statement forms to this report
text | d823e307-a69c-599c-a028-1cf29f81922e |  | textbox | Full Name
text | 70a15afb-1dac-5dbd-b628-7fa58844ed7c |  | textbox | Company
text | c0feaf97-77ac-5c09-9d31-0b7e533e7c39 |  | textbox | Contact No.
button | c0b6759c-b022-5708-9262-18245cf7d826 |  | button | Statement | Yes, No
text | e8158626-5d4a-59bb-bf38-94cfab3ec29a |  | textbox | Full Name
text | 1c4d535f-963d-518b-9ef0-0cbf7e495f5d |  | textbox | Company
text | 9f05824c-1aac-5bde-9094-2e76f6ce0681 |  | textbox | Contact No.
button | b69d4de4-de78-5522-a45e-7c37d74cb4c2 |  | button | Statement | Yes, No
checkpoint-status | e5227950-de34-416a-bddc-b4b58e48e64f |  | checkpoint | Details of any witnesses to the Incident - Attach Statement forms to this report
text | 237e5ee2-27df-54bf-8944-9529e8efaf2b |  | textbox | Full Name
text | 6d286b15-b5c0-5e92-8989-9334d2aab099 |  | textbox | Company
text | e5ccd465-ccc4-5f7d-ae1a-ba3b48e18050 |  | textbox | Contact No.
button | 754eaac0-f137-5b9b-b36c-e2d0a8519199 |  | button | Statement | Yes, No
text | 9fad4f2d-83f0-52dc-9b68-1f67c191e329 |  | textbox | Full Name
text | 3fef7105-56e9-5ef6-91ed-0f074df25147 |  | textbox | Company
text | a8045c48-a6f4-5f74-a43c-94099b36f6e8 |  | textbox | Contact No.
button | 02ebe7e3-8d9e-51d2-8486-ba3838230cdd |  | button | Statement | Yes, No
checkpoint-status | d816996c-b4d1-4256-8cb6-a48cf6174d4e |  | checkpoint | What actions have been implemented to prevent similar Incident
boolean | 3c55f730-c55b-5444-889e-b3ad0f9ab42a |  | tickbox | Equipment change
boolean | 0b81303e-4e8f-5ca7-9359-29124c281f01 |  | tickbox | Certification obtained
boolean | 3425f727-8965-5ab7-8346-9f27ccc12d08 |  | tickbox | WMS change
boolean | 0f2049d5-cddf-5b04-909a-6e672b295cec |  | tickbox | PPE change
boolean | 2192028f-440f-55ee-b79c-2d6fff65c5a2 |  | tickbox | Site Meeting
boolean | 845bcd55-a1c1-5bdd-bc1d-2f00abc59096 |  | tickbox | Toolbox Talk
boolean | 931b3ec6-b6be-5932-95d8-f6975b09b7cb |  | tickbox | Housekeeping
boolean | c0063800-044e-5b5a-bb04-32f98fd44e38 |  | tickbox | Training
boolean | f4cd21d2-28f3-57fd-9e28-66cddc1e2f9b |  | tickbox | Other
checkpoint-status | c9aa69dc-4310-4a2c-9b66-2e5fa4c7a203 |  | checkpoint | Has an EHS Instruction been issued to the P/C company or Bosform?
checkpoint-status | afbe2c87-cfc8-438a-8d02-58e888c41093 |  | checkpoint | Has an EHS Improvement Notice been issued to the Bosform?
checkpoint-status | ebbca55d-8ff9-478a-a2eb-1ad345d7f6f2 |  | checkpoint | Has a Risk/Hazard Assessment been completed?
checkpoint-status | b351bcba-39c8-4482-b710-717553b866fd |  | checkpoint | What Hierarchy of Control measures were considered in the corrective action
boolean | d186c924-a5c9-5d76-b014-284581bf0808 |  | tickbox | Elimination
boolean | b5b4256c-6976-5711-88a8-54b18d354bdd |  | tickbox | Substitution
boolean | 24a32e0c-61ce-5c34-8ff4-939039e3c12c |  | tickbox | Engineering
boolean | dc1ec8b4-3dfb-5b88-83c0-584faa948346 |  | tickbox | Administration
boolean | 402f9a4f-1930-556f-a8d9-e95253bc6fe2 |  | tickbox | PPE
text | 426a8773-df17-545e-9ac9-b03b1a05edc5 |  | textbox | Date of action
text | 40cc0596-28bf-5245-aaaa-0f0ffbd8d165 |  | textbox | Responsible company/s
text | b617f0a8-523d-5eb2-99f2-606d5c09aa9e |  | textbox | Review date
checkpoint-status | a9cbbbb1-f0bc-44fd-a7bc-b9ca95d1463e |  | checkpoint | Statement/s
checkpoint-status | e1a3099b-0a1f-435f-adab-4ff62db607d7 |  | checkpoint | Monitoring certificates
checkpoint-status | 867d7923-c564-4199-92a8-c83b36a3220c |  | checkpoint | Site Induction forms
checkpoint-status | 9dbb45fe-9f06-47e0-9fdd-6d36a5705281 |  | checkpoint | WMS relevant to the activity
checkpoint-status | cfda9b80-27bf-473a-bb45-646a3f735613 |  | checkpoint | Tool Box Talk or Meeting form/s
checkpoint-status | 1b8fdcb0-d9c5-4df8-9431-2a1013646a3d |  | checkpoint | Engineer certification
checkpoint-status | 1413bbca-d2fe-4b49-8faf-e7f12a7db120 |  | checkpoint | Photos
checkpoint-status | d81bb7f5-7701-4cf6-9415-9e1b968c4739 |  | checkpoint | EHS Instruction
checklist-sectioned | 06b37cec-544f-47de-ac15-0fed9cf3edf5 |  | checklist | Stairs (in-situ) Checklist |  |  |  |  | Yes | Stairs (in-situ) Checklist | 4e647d9e-cbf7-4d11-8f43-0fc9be98e278
checkpoint-group | 357b49a2-8396-46ac-a22f-46daaf8b976a |  | section | Phase 1
checkpoint-status | 6dc61051-b351-4fc2-b936-9065f40c7f66 |  | checkpoint | Area accessible & ready
checkpoint-status | d0a4fb40-639e-4a73-ba44-9a18db691907 |  | checkpoint | Drawing references entered
text | e1300877-21bf-59db-85cd-c818a62ca584 |  | textbox | Architectural
text | 9d81fbdb-9915-504c-94c3-693b87a700ee |  | textbox | Structural
text | 6bcfd8d7-37c5-5995-9075-4050a473a7dd |  | textbox | Other
checkpoint-status | 0bb46a7c-ac7b-4ef8-9c3a-7910e70de5d1 |  | checkpoint | Current plans in use
checkpoint-status | b5c4c643-0bc3-4deb-ad7f-366b3854ec33 |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | 4586dbeb-55d7-492b-8f7a-6cccc8b41407 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 81eacbde-394e-4e32-be13-a614bcb3752b |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 2bcdbdbb-9d93-4840-b98c-64dbef0363de |  | checkpoint | Base of stairs cleaned
checkpoint-status | b13b71c1-827e-4ec5-83b3-6e0a1296e67e |  | checkpoint | Riser heights confirmed
checkpoint-status | d931ea74-00c4-4e98-9a46-df147f4e1271 |  | checkpoint | Going lengths confirmed
checkpoint-status | 080cc2c8-e577-4c9d-a9df-83da1ce10528 |  | checkpoint | Correct Class of Finish
checkpoint-group | 753934ae-e924-4e6a-98cd-870b2b460293 |  | section | Phase 2
checkpoint-status | 42d17048-2a69-481f-aa4a-186d1dce29d3 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 7f2d19f3-56ca-4004-a7df-d3e0d7b50b99 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 7f51a0c3-34ae-4c48-a6d9-919b8f4baee3 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 3831abd6-3441-4f38-8237-247282c76558 |  | checkpoint | Riser heights confirmed
checkpoint-status | aab13618-d3fe-4ffb-9534-b18519a12095 |  | checkpoint | Going lengths confirmed
checkpoint-status | 2283547c-5435-4f80-a919-3d7a3ad04320 |  | checkpoint | Correct Class of Finish
checklist-flat | 4a440939-c139-4a7b-84e2-1470a98a5bfc |  | checklist | S.O.G Checklist |  |  |  |  | Yes | S.O.G Checklist | 68d6af79-3631-489e-847a-b88230d63037
checkpoint-status | 8175840d-ef07-467d-86ac-b8f91dad5647 |  | checkpoint | Area accessible & ready
checkpoint-status | 3c341dd8-c03a-4a45-a2a1-42a64f8922fe |  | checkpoint | Drawing references entered
text | 39f9d591-368b-5317-be32-95753e6bbeb0 |  | textbox | Architectural
text | 21ca0c5f-479f-5dfd-958a-fb6c3439c8a3 |  | textbox | Structural
text | c0ac511f-936c-5f1a-a0f3-0e0f6347b738 |  | textbox | Other
checkpoint-status | b555e0af-aecb-45d6-8fe6-c8bdf27dc1ca |  | checkpoint | Current plans in use
checkpoint-status | 9c7f51f3-8230-4e68-9e99-3dbc9ddd41db |  | checkpoint | Survey points give for grids
checkpoint-status | 87fd6711-5697-493c-88bc-fcc5e4e3ff85 |  | checkpoint | Surveyors points given for edge boards
checkpoint-status | 01e6ef3c-bda6-4a67-867e-2705d43083a0 |  | checkpoint | Datum RL supplied by surveyor
checkpoint-status | 4dabc4f0-033d-4d9b-b216-b9a7bde2ad83 |  | checkpoint | Edge boards plumb & straight
checkpoint-status | f4e2a100-9bfa-4e20-a736-3f89ff2c9df9 |  | checkpoint | Step downs secure & correct RL
checkpoint-status | 173cd16d-845c-414e-a3c1-3fbeec59272f |  | checkpoint | Dowels installed on pour joins
checkpoint-status | efeecf0b-dcd7-44c9-b757-d03053519d60 |  | checkpoint | Column blockouts installed
checkpoint-status | 85b203de-955c-473e-9b0b-2ebb5678a728 |  | checkpoint | Correct Class of Finish
checklist-sectioned | f21b8dd6-33dd-449c-b05c-39b8a976b991 |  | checklist | Hoist |  |  |  |  | Yes | Hoist | 72a09fe7-bf1a-4da4-83f8-90d1981d33c4
checkpoint-group | a323dc84-e609-4b8d-a8da-6ea996d6c027 |  | section | Install
checkpoint-status | 6a94b3dd-b79f-400a-8260-d39cb3e53864 |  | checkpoint | Area accessible & ready to receive hoist
text | d7c8b96a-9645-502b-a42a-30066f7ea1f1 |  | textbox | Hoist ID. Number
checkpoint-status | eb28869f-b2b1-43d2-b041-c55641d60dda |  | checkpoint | Adequate Crane or Franna to install (heaviest lift required 4.5 tonne)
button | bfdf221a-4f7b-5473-8088-2812bbc4643b |  | button | Copy the Certificate of service and service history onsite | Yes, No
text | 3df8ff70-4f76-5605-a3ee-d7ae8e7100b9 |  | textbox | Name and Number of Rigger
checkpoint-status | 0d1685b8-3a1f-44c0-8476-24b214a483d7 |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
holdpoint | 6162b4b9-2b16-45a1-89b1-82733128b858 |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 5bc3ecd0-5d85-49d1-85a3-2694b25c1bd6 |  | checkpoint | Scaffolder on site to assist in edge protection if required
checkpoint-status | 946ccd4d-42c6-4b43-a011-91e30984790a |  | checkpoint | Signage in place
button | c22cf144-821c-59d3-b626-3ff972729cd8 |  | button | 3 Phase power accessible and adequate circuit breaker 75 start Amps at power sorce | Yes, No
checkpoint-status | 6e4444ae-7f55-4e81-93a3-b1559765a1c5 |  | checkpoint | Exclusion Zone around required area
checkpoint-status | fb84b2ce-7149-42d8-a7ea-3bdbcd7aec5f |  | checkpoint | WMS ready and signed on to
checkpoint-status | 8dd391e9-b5e2-45ee-a4a4-56aa62072929 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | d8bec51c-8d28-442d-96dc-627448c223cd |  | checkpoint | All loose materials removed from edge
checkpoint-status | 7c8703a6-a492-4d86-a28a-d8b6d6a2f150 |  | checkpoint | Gates installed
holdpoint | 645f7714-e3ae-4a73-a658-9408a896ead7 |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | da67b3d9-35e5-4037-86db-8da695b75e0c |  | checkpoint | Log book for hoist is onsite and in good condition
button | d19cbf11-d4eb-5343-8d88-0b131c0e014e |  | button | Copy of Bosform commissioning sheet on site and completed | Yes, No
checkpoint-group | 3e1a9ec9-6664-40d3-b69e-3265b918967f |  | section | Hoist Jump and Dismantle
checkpoint-status | 0de09df2-09c7-449f-a2d4-df1846ec506d |  | checkpoint | Ensure exclusion zones are in place
checkpoint-status | 6d6ec3da-cb67-4627-880a-a7e0ab79007c |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 0bfaf2c6-fdb9-439f-bc23-f35705400b27 |  | checkpoint | All loose materials removed from edge
text | 88bb75f7-7853-5df4-a0ef-7a96ad170efa |  | textbox | Name and Number of Rigger
checkpoint-status | 1804300a-8634-4f90-8cba-b22fb2790858 |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
checkpoint-status | 980d763d-7a57-4592-9507-56e1b257e53a |  | checkpoint | Scaffolder on site to assist in edge protection if required
text | 29392fd2-57bd-5d39-a6db-22bbf35a2f21 |  | textbox | Level Number to be Jumped to
checkpoint-status | 02c026a2-fd1a-417f-b8cd-042e1db7b564 |  | checkpoint | Gates installed on Level/s to be exposed once lifted
holdpoint | e10d5428-2816-4a55-a431-f47f332a4939 |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 3768f035-2f02-4670-a2ab-18747c1a926e |  | checkpoint | Signage in place
button | d8500f09-ddf4-5e9e-a003-73febad6bca6 |  | button | Hoist Screen installed if required | Yes, No
holdpoint | 565a1836-b9b5-4423-a74c-c5dee7825e0d |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | 43382066-9e0c-4356-b853-4368b89253c0 |  | checkpoint | Remove exclusion zones and barricades
checklist-sectioned | 8e901e4e-3aee-4b4a-95cb-a458415e82ed |  | checklist | Core Lids Checklist |  |  |  |  | Yes | Core Lids Checklist | 73e377f8-47ec-4b27-a067-4aa42f458d5a
checkpoint-group | 7af2925b-8f3b-4d0c-af9d-eb5e22cef495 |  | section | Phase 1
checkpoint-status | 1cc55b1c-e27a-4295-b439-4375c8b0a60d |  | checkpoint | Area accessible & ready
checkpoint-status | 2af101de-c4cb-4943-bffe-acce02aaa59c |  | checkpoint | Drawing references entered
text | 1d84cf72-0c58-5cc8-9164-da62e68a1e96 |  | textbox | Architectural
text | 4162667f-a4e7-5300-b02b-39337e80c1f3 |  | textbox | Structural
text | 5e2907d7-6882-5821-9f68-db6cd75bf6ab |  | textbox | Other
checkpoint-status | 46c2d781-4fd6-477c-ae32-286f039125d1 |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 2292532a-a917-4d3d-9f0b-c03e7231cace |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | 54e43a8d-6c4a-4136-9d27-59b114ee0b08 |  | checkpoint | Grids marked by builder
checkpoint-status | 2aad55f7-e70d-421e-8e74-d92c37fddbd0 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 3cb21bd6-abcc-49e8-be22-3c02e5fbd758 |  | checkpoint | Fillet & drip mould installed
checkpoint-status | 61809d7f-1fd7-4d8e-bddd-cf8c17f26789 |  | checkpoint | Check set down position & RL
checkpoint-status | 2c9de5c5-1534-472b-9360-5e8e272db08c |  | checkpoint | Check penetrations installed
checkpoint-status | 449f2b17-439a-47db-bb67-26147ae131c1 |  | checkpoint | Column blockouts installed
checkpoint-group | c961b0c7-08d6-4b11-9698-d7c0affb277b |  | section | Phase 2
checkpoint-status | bc5a471d-d028-47de-adf8-8cb671924ccd |  | checkpoint | Check back propping as per design
checkpoint-status | 1f348dcc-eba7-4544-92a8-b9c63be1aed9 |  | checkpoint | Blow off deck
holdpoint | ad34990b-103d-4f17-bb24-231912cb2ec7 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 8a1fdde3-6764-46c2-90e1-201cb44d6454 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | 964daadb-8355-47f9-8bb4-6350bc448f80 |  | checkpoint | Correct Class of Finish
checkpoint-status | bddaa27a-902f-4802-a99c-1368def8c3dc |  | checkpoint | Stripping, cleaning & materials removed
checklist-flat | 8913f14c-590f-4e3e-8c37-b3eae98a7310 |  | checklist | Walls Checklist |  |  |  |  | Yes | Walls Checklist | 7b835917-e874-49ad-a654-768e1454bc58
checkpoint-status | 47b9cb5a-0329-42bf-934a-a7838cf05d47 |  | checkpoint | Area accessible & ready
checkpoint-status | 2f65ae39-0ec7-43b7-9c26-2ed00c4b5496 |  | checkpoint | Drawing references entered
text | f70485c7-ff40-57f2-b38b-afc4da8ecfec |  | textbox | Architectural
text | a2255356-5000-5681-b447-ad231dbd81f9 |  | textbox | Structural
text | fb8c72ae-c11e-5a33-9daf-a4625ec058a2 |  | textbox | Other
checkpoint-status | a20d37b0-6ca9-4bf6-b3b3-023ffbffc98d |  | checkpoint | Current plans in use
checkpoint-status | b7b01c80-5735-4659-a05d-28afd216a64b |  | checkpoint | Survey points given for 2 points
checkpoint-status | d4e41a7c-fd8c-4a7a-909c-ac3b24c9508d |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status | 03665436-4fe7-4073-bfe5-b36ae7101d90 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 15abab6d-418e-4526-9891-54444b474bd9 |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status | 4e17fff7-98da-4ed6-95e2-b988ac621415 |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status | a24c07f6-0760-4863-b6a8-1b24495fbb29 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | ce126373-3040-460b-8102-ebc0cf2d9e3a |  | checkpoint | Base of walls cleaned
holdpoint | 913f8999-7bbb-4e81-b3a7-b4ca3691cd10 |  | signoff | Inspection by site engineer
checkpoint-status | 07a1f7c3-79c0-4588-b1d6-3fea191d6087 |  | checkpoint | Closing shutter installed
checkpoint-status | 3ed16d03-d212-489f-a129-4616656b73dd |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status | 7ed83f27-3540-4dce-aedf-6ddc1452dc8e |  | checkpoint | Correct Class of Finish
checklist-flat | 0fc3adf9-f2af-47af-b264-aadb1c7c56af |  | checklist | Variation / Site Instruction |  |  |  |  | Yes | Add Variation / Site Instruction | 7bd4136d-eb9b-47b3-88da-1269b32d319e
checkpoint-status | c4204880-4418-42a4-93ae-c0520741d529 |  | checkpoint | Variation / SI Details Entered
label | c5ffd25e-4253-551b-9a67-cb718f14058d |  | note | Please take before photos
radio | 398d67cb-bda0-545e-aaa2-47045c3c25b1 |  | radio | Work type: | Site Instruction, Variation Work
text | c6c28c3e-26d1-58e6-8e28-ccb3661a1730 |  | textbox | Attention:
text | 12f728fb-cc3b-5e29-aaa2-d2c3a7fc448b |  | textbox | Area/Location
text | 81156039-dd75-599d-b56f-206e753a19ff |  | textbox | Date
text | 7950929b-8b13-5a97-9b93-8c50e65ec9a5 |  | textbox | Scope of work
text | 12382e79-c635-512b-aed5-d4e1074dc77f |  | textbox | Normal Hours
text | 78e4e927-14f4-5d36-826d-4c82ee147046 |  | textbox | Overtime Hours
text | 2b24b103-d686-57db-a36a-a38be80fe784 |  | textbox | Material to complete task
checkpoint-status | b5982442-160f-42c9-90a6-9b8d679771a7 |  | checkpoint | Reference/SI Number Entered
text | 32d91750-6bda-5cb2-a1fa-83be8f645d66 |  | textbox | Reference/SI Number
checkpoint-status | 45b61d06-96af-43ee-89c2-9d9fb4cc612b |  | checkpoint | Variation / SI Work Completed
checkpoint-status | cee8e8d7-e55d-458b-9783-b0bc782d068c |  | checkpoint | Values added (Office use only)
text | be62e857-32db-5f1b-b33a-af5e1b9a24f9 |  | textbox | Labour Value
text | 8e514697-986a-55e6-aaf4-a6cc91d616b9 |  | textbox | Material Value
text | d957bccc-7fd2-54e7-a3ff-9649d70dbf22 |  | textbox | Measured Items
text | 2cddfc60-d302-53b3-8cea-29acc2218cac |  | textbox | Total Variation Value
checklist-sectioned | 6fcfc1f9-eafe-4101-80cd-45bfab13887a |  | checklist | Jump System / Climb Track Checklist |  |  |  |  | Yes | Jump System / Climb Track Checklist | 7cadc179-fabc-4615-85b6-a8b07861c1bf
checkpoint-group | c75ab329-efb6-4acb-80ee-b51e3a84c7fa |  | section | Pre Lift
checkpoint-status | f0c5e447-90fc-4a10-b2c6-e364b65eefec |  | checkpoint | Confirm concrete strength MPA 15 has been reached at connection points (Builder to supply)
checkpoint-status | 4fa4b97a-0a63-4f35-a0dd-287b8a6aca09 |  | checkpoint | Signage in place (Stripping in progress/Jumping in progress/ No access)
checkpoint-status | dfcb3f99-ed1d-48ad-b28b-29e6665c3439 |  | checkpoint | Exclusion Zone in place
checkpoint-status | d8f37787-97dc-4363-be0d-15911821845b |  | checkpoint | Spotters in place on slab below jump (outside exclusion zone)
checkpoint-status | 4657f825-7b13-4460-8262-68ea817e1bd6 |  | checkpoint | All Platforms cleaned and clear from rubbish
checkpoint-status | 352ecbcf-7294-43c6-8664-34bafc68ef96 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 5c8a2c69-7d10-4f7e-a7a3-44d6c2c2b535 |  | checkpoint | Clear communication between team leaders and Crane crew (toolbox talk)
checkpoint-status | 9ccd3720-485d-46dd-82db-48e24f336fbb |  | checkpoint | Ladders available and secured
checkpoint-status | 068703d3-4eef-45c9-a410-bcef9418baca |  | checkpoint | Flipper systems lubricated
checkpoint-status | dd1377f4-d429-4446-b847-a7365e6f4a3d |  | checkpoint | Trailing Decks clean of debris
checkpoint-status | 106bcac5-4fb2-4f02-802d-15156ae329a8 |  | checkpoint | Trailing decks clear of protruding ferrals in walls above
checkpoint-status | 3cc33b1d-3498-43ef-9068-906d6915600a |  | checkpoint | Check exclusion zones in pit below are in place
checkpoint-status | dc2c8895-41a9-4bd5-9bf6-2484f0319a91 |  | checkpoint | Plumber to check pipes to water cooler
checkpoint-status | c7ad8893-843a-48e3-87e4-022e7c0bdea0 |  | checkpoint | Transfer RL heights
checkpoint-group | a64aa82d-0226-4120-bf2f-b2cd2092e1fe |  | section | Post Lift
checkpoint-status | 406aa65e-4f9f-4767-883d-ced429ac784e |  | checkpoint | Confirm connection points are secure and all engaged
checkpoint-status | 2055a0a4-49c4-466e-8241-25b8f38bce34 |  | checkpoint | Confirm mesh secured to doors and penetrations
checkpoint-status | bd116b50-caf5-4465-b7f9-14f99ae776ac |  | checkpoint | Signage in place
checkpoint-status | 188169e9-ec9b-4169-8095-886dc5b27283 |  | checkpoint | Screens and mesh infills are in place and secure
checkpoint-status | 5b773f03-d57d-4c1b-bf64-35c023d9478f |  | checkpoint | Loose materials are stacked and secure each day
checkpoint-status | 00ec0c94-af48-4da3-b08f-ee6935feb9ae |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | a675066e-1ce7-4cc9-91d2-f0c4d622af68 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 5316a10f-6a27-4665-8501-b9b929f46652 |  | checkpoint | Loads on platforms not exceeded
checkpoint-status | ffc26fbe-3995-4d92-beec-12e4ed0b0384 |  | checkpoint | Ladders available and secured
checkpoint-status | 894333b4-c1fc-4d58-b7f6-3c295a2593b4 |  | checkpoint | Access is clear and marked
checkpoint-status | c075d31c-2a1e-4723-9e4a-830f69d71b75 |  | checkpoint | Power Board connected
checkpoint-status | 9c2440b7-3375-4aa3-a461-0bf7ff939258 |  | checkpoint | Confirm ready for lift with all involved - Team Leaders
checklist-flat | 14649648-0cca-4fc9-97cd-25dadd5dc472 |  | checklist | Daily Pre Start |  |  |  |  | Yes | Add Daily Pre Start | 8c8a27c8-a5a5-4891-bcf3-8adf7a8eb7cd
checkpoint-status | 07c5d1e3-bfea-4e1e-bb0f-4253088de470 |  | checkpoint | Daily pre start meeting completed
text | 6811c1bd-0aa8-585c-9221-a7e5823623f3 |  | textbox | Date
text | 96b6823e-50ed-5215-9fd4-86e57af9e0bb |  | textbox | Time
text | cee9f272-a7d3-5cc6-be12-de2af939dbe4 |  | textbox | Location
text | 46cb2853-c94f-56fc-a113-ed85729ae0e9 |  | textbox | Supervisor / meeting leader
text | ce67912a-3873-52e6-9f9b-77c2859ade14 |  | textbox | Project Manager & Construction Supervisor attending
select | f695ae8e-2c31-5fcc-86d3-e1da33440d26 |  | dropdown | Current weather | Rain, Wind
text | b617e924-fe80-50cc-91dc-0a96dac78b8d |  | textbox | Temp
select | eca57bfa-33f3-53f9-be80-55eaa1ddb0db |  | dropdown | Forecast | Rain, Wind
text | 185bf669-c1ca-5e92-b079-a4d9ad21037c |  | textbox | Temp
button | 92b1dc9a-1922-5b69-8afd-d241687173b5 |  | button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
button | 6124d3b1-1dda-530d-be60-8c0bc1030a9e |  | button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
text | cf08422c-eecd-5c74-9458-06593cc68264 |  | textbox | Any issues from the previous day
button | 0dcf0ffd-0e1a-5c1f-a8f1-a59b5b6f8a9a |  | button | Do you need to change SWMS | Yes, No
text | 912a6566-a730-5ec8-8b5b-5d825ae70300 |  | textbox | First aiders on site today
text | 5bccf8d4-84b7-51ae-ac53-afa4a60a6f97 |  | textbox | Apprentice & who are they assigned to
text | a2ebdc50-515c-52eb-a114-d997fc2c9002 |  | textbox | Apprentice & who are they assigned to
text | fabee71d-31e0-5670-8ba4-0d8e10969736 |  | textbox | Apprentice & who are they assigned to
text | 7b257ae9-ac4b-5808-a6dd-c58b8662c111 |  | textbox | Todays tasks / jobs
select | f61805d8-99f6-5f84-b92d-3fc106c926fd |  | dropdown | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
button | 04af29d6-645c-52bd-a932-8112f39314df |  | button | SWMS in place for all activities | Yes, No
button | b1fab1e3-0f14-550a-944a-b766ee5369e9 |  | button | Hot works | Yes, No
button | 7bac45f8-34ee-5a67-8af9-6988ea2d2848 |  | button | Excavation | Yes, No
button | 1ff6d28e-1d6e-509d-87df-b0c07c06d5c2 |  | button | Ladder | Yes, No
button | 3cf20aa4-b70e-55c5-8114-6a82fb2ec150 |  | button | Core | Yes, No
button | 6cbfba21-9a60-5d94-8cd4-1fb1e147cffe |  | button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
text | 2b111740-a12b-5819-abc1-3804a48e5ba9 |  | textbox | If yes, list the substances
text | bbc1bf78-9680-5c13-abb0-17545475df60 |  | textbox | Attendees
checklist-flat | e02ce76e-aa33-40e9-a3bd-3b16fb042f76 |  | checklist | Weekly Labour Hire Control |  |  |  |  | Yes | Weekly Labour Hire Control | 8ee04aaf-b52f-4307-bc4e-1e3561f2818e
checkpoint-status | e5e5b6dc-1eed-4eba-9017-88dc207fd331 |  | checkpoint | Tuesday
text | 9271cae0-dbd7-52e4-adfe-4acca328d062 |  | textbox | Date
text | 0561343a-bddd-5229-98ad-e52fccb0061d |  | textbox | General Comments
checkpoint-status | e3621f89-e78c-41e2-9b1f-f617fd5962d7 |  | checkpoint | Wednesday
text | 69e37cd6-58e1-5adb-ba6d-1aa8836fb1e6 |  | textbox | Date
text | 58dd3dec-d644-5ac6-bbc0-e8bbb4245ab1 |  | textbox | General Comments
checkpoint-status | 01347d37-2465-475f-95f8-13403ed61f48 |  | checkpoint | Thursday
text | d9f4ed58-1701-541f-afd7-510947166583 |  | textbox | Date
text | b589b202-92b4-5a50-8df8-93b8a96960f6 |  | textbox | General Comments
checkpoint-status | 1b1df3fc-8812-495a-9d32-d7792d8feee8 |  | checkpoint | Friday
text | ab03a4e7-f21d-5bf7-a889-3d0b441a1eed |  | textbox | Date
text | 38e8be6e-a3c3-5256-97de-f667b5b9879d |  | textbox | General Comments
checkpoint-status | 66df5736-02d3-4fff-87de-a8274943a680 |  | checkpoint | Saturday
text | b2da838c-a7c0-5729-a557-3716d3a99667 |  | textbox | Date
text | 2a975aba-84b7-5652-a928-a1b7693bbd08 |  | textbox | General Comments
checkpoint-status | ec3dbf4b-8b0a-4f6c-8122-cbbd4629dbf6 |  | checkpoint | Monday
text | 49ea3d5c-8ba2-591f-8d2f-73c9c93f5d1e |  | textbox | Date
text | aa574422-5103-5b63-b35a-a9c1d1dbfa4f |  | textbox | General Comments
checkpoint-status | db16bc12-4034-404e-b9bb-8d3a6ee1e7d4 |  | checkpoint | Tuesday
text | 86e57437-a9af-51ae-a609-b37fb0314014 |  | textbox | Date
text | 6b9cebf6-be2c-56bc-8ace-24ad9935450b |  | textbox | General Comments
checkpoint-status | 4b946bfb-2f51-429b-817e-5174a6501818 |  | checkpoint | Please Attach Time Sheet
holdpoint | 516b640c-524e-4429-b6ee-e49a2b679236 |  | signoff | Client Confirmation Signature
checklist-flat | 5032e59c-75ea-496d-9c48-132967cfcd13 |  | checklist | Deck Handover |  |  |  |  | Yes | Add Deck Handover | a3bfebb9-9e71-4c0d-9366-bac915bcfcc3
checkpoint-status | 644442bd-7c3d-4afb-bd83-ef9d49d625e7 |  | checkpoint | Communication between all trades
checkpoint-status | f7ea606a-3e44-4539-ab1a-c5e28b69b013 |  | checkpoint | Signage and barricades in place
checkpoint-status | b6ecb1b6-aae5-4470-bddd-d645572239b8 |  | checkpoint | Deck clean and clear of materials
checkpoint-status | 13944d9a-eb33-47d1-a4c8-f8f354c06a34 |  | checkpoint | Loose materials are stacked and secure
checkpoint-status | 59b98a2a-fc9d-4f0f-962e-a704555170f8 |  | checkpoint | Any backpropping required to handle loads of reo and other equipment
checkpoint-status | 4882a659-3e67-4fc5-a857-fa847e531f10 |  | checkpoint | Designated walkways established
checkpoint-status | ee35ce5e-3f53-4fb2-b091-56f1f4ad4477 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 4d758e84-caf9-4dea-a9ad-6387c2ca2fac |  | checkpoint | Are all penetrations covered and secured
checkpoint-status | cad32916-d858-4d37-931e-649fdd4cb8fd |  | checkpoint | Rubbish bin on Deck
checkpoint-status | f08afd97-b404-410a-bdcb-f34ca0de78ef |  | checkpoint | Perimeter Screens / Edge protection installed
checkpoint-status | c9ca0838-194e-4473-8892-52270b6dc767 |  | checkpoint | Correct spacing of frames, props and timbers
checkpoint-status | 96bd64a4-e66c-4ed7-a4eb-b3499c0a7e86 |  | checkpoint | Correct joist and bearer sizes
checkpoint-status | 5d67f562-15dd-464c-847a-43a119283fb0 |  | checkpoint | Acceptable jack extensions
checkpoint-status | f4be055d-ebcb-45b6-ba49-23e39abc43ad |  | checkpoint | Quality of materials
checkpoint-status | 8348eb76-a427-45c0-9389-550c1a469ca7 |  | checkpoint | Adequate bracing to ensure stability
holdpoint | 30842281-1ccb-4b97-9ab5-3e2f328bbf7e |  | signoff | Deck Handover signed off
checklist-flat | 072bf92b-c894-44c1-8426-f3717634c931 |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Add Toolbox Meeting | d9e3691c-93ae-4f4d-b2eb-8df9e85c5a6a
checkpoint-status | 00e96cf5-4100-44fb-876b-0731be71a810 |  | checkpoint | Toolbox signed off - Attach an forms
text | dbb5731a-cfad-55bc-b044-221f612e4be1 |  | textbox | Work area
text | 5b07d088-f079-561a-9cfa-d251630e5014 |  | textbox | Supervisor
text | f2df4417-41b0-549d-8c96-12347fd20c9a |  | textbox | Date
text | 34429e2b-9504-5603-9e9c-565db302db35 |  | textbox | Time am / pm
text | 93e534be-8256-5b45-8859-c3ce0aba6059 |  | textbox | Actions from last meeting
text | 4eabf20c-7622-5c96-a794-58be78cc43dd |  | textbox | Injuries last week
text | 5cc5b522-a9e9-5a6b-9d4a-52cce65398c2 |  | textbox | Near misses last week
text | 36853cf9-d2ae-5916-b939-e2dcf37679d9 |  | textbox | Safety Items discussed
text | 6e3a4dfd-61db-5e58-a7f1-d6fb18d7b02a |  | textbox | Comments from the floor
text | ceedda91-93dd-523b-8738-593435f33fdf |  | textbox | New business
text | 606b0796-ebcc-55b8-8802-637cf3af56da |  | textbox | Attendees
checkpoint-status | d8327bfd-0216-49d6-8fea-6b162fbe4ea1 |  | checkpoint | Attendance verified
checklist-flat | ca6906b2-d817-429e-a018-0f61ab878890 |  | checklist | Injury Form |  |  |  |  | Yes | Add Injury Form | df59a1da-fd93-4d8f-8446-1feeb50a8b99
checkpoint-status | 259d15e4-97ed-49ac-8c1a-5471d21a2416 |  | checkpoint | Injury form completed
text | 06595751-5652-53d4-8217-c9cfc9f3bc38 |  | textbox | Date of incident
text | 4f0e87d1-3db9-58f5-b33e-15ecbe1fbc7f |  | textbox | Time
text | 49cbc5c5-aaa1-5bd6-b5b7-ef6c85ca9ae8 |  | textbox | Site location of the accident / incident
text | 3eafb0ca-4d01-57a4-96c5-01f8208d4abf |  | textbox | Detail of how the accident / incident happened
label | b96a2d44-b64d-5cfd-87eb-a283aaeae968 |  | note | Details of injured person
text | af7ef79a-d36c-5b2a-a7d2-d14785789cb0 |  | textbox | First name
text | c2aacb84-869a-5a88-a500-1438e87259f6 |  | textbox | Last name
text | 3d0b1121-10f7-5da9-8df4-67eb87ce6f24 |  | textbox | DOB
text | 60925921-b3ee-5e0d-8069-464d46cec605 |  | textbox | Contact No
text | b8f99bbc-8e21-547d-bb00-29c500a0ee4b |  | textbox | Address
text | 52b24271-e290-5388-bc06-a56e62c64256 |  | textbox | Company
text | a03975e8-2a8d-5083-a8c6-ceedcc34291a |  | textbox | Trade
text | fa828de2-cc00-5435-8f75-83b0957b494a |  | textbox | Date Inducted
select | 75286646-6c85-5bd6-b692-c092ec4b1a7b |  | dropdown | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
select | 3942d4c2-252d-5f54-a8db-ed494094fe0a |  | dropdown | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
select | 07f343b4-e2f5-5e4f-96e8-5af184817b64 |  | dropdown | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
text | fe2952ca-6c0b-5df8-973e-583b4c8163ae |  | textbox | Initial treatment given
text | 6ddd06a4-27a4-59dd-8b63-5225ab6aaaa3 |  | textbox | Was follow up treatment provided
text | 5d225217-d4d3-5552-bb2f-4691d810e23a |  | textbox | Medical centre / Doctor / Hospital attended
text | a8b91d17-a72e-54f3-ae99-1ad3215807fd |  | textbox | Date / time attended
button | 30f211d4-08ed-5145-a61b-334635080528 |  | button | Regulator notified | Yes, No
label | e32511ea-e713-5047-baca-b078e7210e13 |  | note | Witness details
text | a45dda0d-dd9e-5d73-a7b4-3a4237a7a20d |  | textbox | Witness name & contact details
text | 3f2e41af-a332-5c5b-9150-119719942f1c |  | textbox | Witness name & contact details
select | 6b33ac3b-cc7b-5552-aeef-a54219486ac7 |  | dropdown | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
text | 30236bb6-5b93-51de-a4dc-10915efa9b08 |  | textbox | Other
label | 30282d44-d965-58ec-b18b-cb3f64da8dc0 |  | note | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
checkpoint-status | 45c5af12-00ca-42b5-b343-2af37173fe16 |  | checkpoint | Signature of injured worker
checkpoint-status | 5b9fc911-7f41-4649-90db-210de18df79c |  | checkpoint | Person completing this form
checklist-sectioned | 8b03514d-b3e9-4fb0-95c9-cb687dca88ec |  | checklist | Stairs Checklist |  |  |  |  | Yes | Stairs Checklist | ee5fd48c-7595-4cc4-8e6a-10dd1b6dc4a8
checkpoint-group | 77498e38-3ee2-444b-9b3f-7b37a9041455 |  | section | Phase 1
checkpoint-status | 7a818f5a-9573-45f3-bfd4-b82796e10588 |  | checkpoint | Area accessible & ready
checkpoint-status | 6fecc837-f06d-4d17-abaf-994e283aa493 |  | checkpoint | Drawing references entered
text | 8ed4bfe9-2264-5578-b7b3-723d306c5e67 |  | textbox | Architectural
text | 3abac417-a2ad-5655-bf21-a96c5e45f7a1 |  | textbox | Structural
text | 4c989f07-80d4-5a79-a656-1f638ef5885b |  | textbox | Other
checkpoint-status | 96f6cdf0-11a7-4651-b378-63c9a0a03b64 |  | checkpoint | Current plans in use
checkpoint-status | b289ebc0-2aaf-43a8-97cf-9dbd94b0b949 |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | f34f9558-fbd6-49a8-be02-9a64d353d83e |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | ec662ed9-1c02-4424-9067-8ca1037d0ce8 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 1073631b-1856-4a43-b9bd-8cfd039e5f56 |  | checkpoint | Base of stairs cleaned
checkpoint-status | f1b3c16f-ce02-47a4-8025-0f839a49cbdc |  | checkpoint | Riser heights confirmed
checkpoint-status | 3a86601f-fbef-4881-84c0-b7f6c8e4385f |  | checkpoint | Going lengths confirmed
checkpoint-status | c0a7c3f2-d585-4c53-a729-fb04b340b036 |  | checkpoint | Correct Class of Finish
checkpoint-group | 8f6960f1-df72-438c-a9d3-0907fc29c883 |  | section | Phase 2
checkpoint-status | 6f0ddedf-1d66-4394-92d8-42d2b581e1eb |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 70f7fdbd-45c3-4231-9881-5768fd820616 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 6dc31861-8a8c-4c5d-b2ec-a8ea14f9fcff |  | checkpoint | Base of stairs cleaned
checkpoint-status | e41bc373-302d-498d-bfae-f7ec5550af1b |  | checkpoint | Riser heights confirmed
checkpoint-status | f1e399e2-b06e-42ef-bbdd-33501706f2da |  | checkpoint | Going lengths confirmed
checkpoint-status | a5810360-4efd-49c6-8ab9-6e8d2d46b11d |  | checkpoint | Correct Class of Finish
checklist-flat | a22a13b6-4b9e-4d26-af44-c18e60291397 |  | checklist | Columns Checklist |  |  |  |  | Yes | Columns Checklist | f305c82d-0c21-4610-bf94-31768068bffc
checkpoint-status | 974a7264-f4ee-43d3-a425-decad3c59745 |  | checkpoint | Area accessible & ready
checkpoint-status | dac8921c-b29e-4f21-a71e-2e9e7fada47e |  | checkpoint | Drawing references entered
text | 86494f89-2399-587d-be6f-69c6d04d705b |  | textbox | Architectural
text | fb24321e-ee3b-5e13-a398-10058fb0d027 |  | textbox | Structural
text | d21965e8-9ec4-5b22-b0f5-c413d9a1ad52 |  | textbox | Other
text | 6012505b-241a-5f05-a6c1-ae9b2a0b2e61 |  | textbox | Column No
checkpoint-status | c43da712-8688-4f45-8fbd-da776d3412b7 |  | checkpoint | Current plans in use / Latest drawings checked and referenced
checkpoint-status | 465bbc01-ef8b-46fa-b86d-096811c6c046 |  | checkpoint | Survey points given for 2 points
checkpoint-status | 3becb23e-c1b1-48d0-9f2a-aa66053e83b9 |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status | 32aa7eeb-3a21-44c4-8f0e-20d8b52b69a2 |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint | 32d61a1c-563b-42a4-8040-6216ece42cfa |  | signoff | Inspection from site engineer
checkpoint-status | 4a9fc165-985c-4e1e-a137-534e062ec506 |  | checkpoint | Column box cleaned & oiled
checkpoint-status | 0d100f4c-6ed1-496c-91ee-7d23f8e81f51 |  | checkpoint | Placement of column box over cage
checkpoint-status | 2bd67f6f-ea57-421f-befd-9b30be454cd9 |  | checkpoint | Bracing props secured
checkpoint-status | 95d64270-676a-4b11-8962-ebb48c088565 |  | checkpoint | Column plumbed
checkpoint-status | db6b6722-6ec9-49fb-84a5-f8c03c4a8e69 |  | checkpoint | Correct class of finish