## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 44ac46d7-4b3e-4f4e-9fa1-63b5d8c2f101 |  | checklist | Deck Handover |  |  |  |  | Yes | Deck Handover | 0fc5cea5-e946-4355-93f0-9b503b4f848f
checkpoint-status | faa6542c-7ce1-449f-a235-e75ffb068c37 |  | checkpoint | Communication between all trades
checkpoint-status | 344787c9-95ce-4ed7-a0fc-e0eb3c14f408 |  | checkpoint | Signage and barricades in place
checkpoint-status | 2aab45f9-8a01-4599-8acf-5de49a94ec83 |  | checkpoint | Deck clean and clear of materials
checkpoint-status | 74cb1ed7-a3f8-4113-b288-2929fb7c7709 |  | checkpoint | Loose materials are stacked and secure
checkpoint-status | f7f09823-a895-414e-b7c5-b65158fa9853 |  | checkpoint | Any backpropping required to handle loads of reo and other equipment
checkpoint-status | 039fdef4-2ea1-4157-bd75-3d038307446e |  | checkpoint | Designated walkways established
checkpoint-status | b87c4fbc-95d0-48ae-a21a-fa2c50fcb785 |  | checkpoint | All loose materials removed from edge
checkpoint-status | c056def0-1a0b-45cb-897f-8915e9544e76 |  | checkpoint | Are all penetrations covered and secured
checkpoint-status | dd8ffe92-68f1-4879-b114-8171ba5e4e05 |  | checkpoint | Rubbish bin on Deck
checkpoint-status | 26ba851f-e38c-4845-8b56-3788aaa79d2a |  | checkpoint | Perimeter Screens / Edge protection installed
checkpoint-status | c5db772f-9303-4e94-b9b0-7d9bd7b2aaa5 |  | checkpoint | Correct spacing of frames, props and timbers
checkpoint-status | d5f4ab3d-37de-4262-bdab-fefd69456329 |  | checkpoint | Correct joist and bearer sizes
checkpoint-status | 36703001-4097-4e7e-9567-cc6bc6fb2d98 |  | checkpoint | Acceptable jack extensions
checkpoint-status | 8e737b1c-17a7-4c86-966a-32cc9f658412 |  | checkpoint | Quality of materials
checkpoint-status | b4218e53-e7b6-434a-900f-11a8b92156b9 |  | checkpoint | Adequate bracing to ensure stability
holdpoint | 12c5b1a9-5172-43a9-80b1-55d0be28c5b5 |  | signoff | Deck Handover signed off
checklist-flat | 8f5715a9-71d8-4e90-9af8-28942321ede6 |  | checklist | Suspended Slab |  |  |  |  | Yes | Suspended Slab Checklist | 2281e23f-a87f-4e4f-b0bb-ff7192182d21
checkpoint-status | 724fcf24-0e73-4df3-8d40-16ff31043179 |  | checkpoint | Area accessible & ready
checkpoint-status | 879109f8-83a5-4b36-ae20-d568c7476351 |  | checkpoint | Drawing references entered
checkpoint-status | 4e4553e9-b487-4f71-960d-aa4f658955e7 |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 5e0a9ff7-7ab0-4dda-8a76-e75ce4e76b19 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | d00332b0-34e1-4bfa-a2b7-3ebc5ca384a5 |  | checkpoint | Grids marked by builder
checkpoint-status | e820220c-93ff-4a76-b6da-ceb7c27867fc |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | f58d8691-c327-4565-81d7-74e72c97fd27 |  | checkpoint | Fillet & drip mould installed
checkpoint-status | c1eed98a-607f-4a8d-a783-14bef0877f43 |  | checkpoint | Check set down position & RL
checkpoint-status | 6e74c252-fb4b-4289-84d0-8479643d3b79 |  | checkpoint | Check penetrations installed
checkpoint-status | b2bbdffc-edc0-4734-aaa1-dfc810e9f680 |  | checkpoint | Prop drop head wedges are secure
checkpoint-status | 5f0a2879-a10d-4fe1-857e-595eb75fd610 |  | checkpoint | Column blockouts installed
holdpoint | 89246de3-5163-46c1-b44a-c1a657388371 |  | signoff | Inspection by site engineer
checkpoint-status | 4471f3c4-78f8-43df-b5c4-45e458b090b8 |  | checkpoint | check back propping as per design
checkpoint-status | 5b2dfbc9-856a-445c-a39c-3c3f4e8caf3e |  | checkpoint | Blow off deck
holdpoint | d6fc1369-ac3e-475a-b82d-851993d21bea |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 6ca259a4-39de-4dbb-a889-c148611bd676 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | 848f18b1-5041-4153-adcd-bf3634cd13ce |  | checkpoint | Correct Class of Finish
checkpoint-status | 357d26f6-31b5-4726-8a73-d408be6041f0 |  | checkpoint | Stripping, cleaning & materials removed
checklist-flat | e6e9982b-be41-40e6-81b2-a8ab21b2375b |  | checklist | Columns |  |  |  |  | Yes | Columns Checklist | 2a8f2a4c-1908-466c-abed-23c23cb9dd9a
checkpoint-status | e43bfbd0-6e6e-437a-9eda-b4f3fa3b302f |  | checkpoint | Area accessible & ready
checkpoint-status | 2926cfc7-9387-426d-a4e4-0a4d3b2f4265 |  | checkpoint | Drawing references entered
text | c3184719-3807-5580-b165-d74d83056d3c |  | textbox | Architectural
text | 9f4b66f6-3867-543d-8090-3ab8b1508b14 |  | textbox | Structural
text | 4927f110-520d-504d-b60b-c8b4f533ce43 |  | textbox | Other
text | d6e3a147-6fa0-57fc-8ccd-0bc3bc9be7c7 |  | textbox | Column No
checkpoint-status | d56a9690-aeff-44c3-9a1f-3c9567d4ca9f |  | checkpoint | Current plans in use / Latest drawings checked and referenced
checkpoint-status | 095f7b91-e860-40b7-a25b-414c31ba7679 |  | checkpoint | Survey points given for 2 points
checkpoint-status | 24a24f88-1897-45b5-ba4a-cf8bd2f86fed |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status | 62dd1324-ad21-4fa6-9e84-b450f011348c |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint | 66e26ebe-7840-4617-bfbe-3b069b8f5d04 |  | signoff | Inspection from site engineer
checkpoint-status | 3537e531-b113-4b0e-83fb-ccd7e83e18dd |  | checkpoint | Column box cleaned & oiled
checkpoint-status | 7e7dba77-cf4b-423b-a525-53537f00e4d1 |  | checkpoint | Placement of column box over cage
checkpoint-status | 93bc2ecb-52da-47a9-bf50-efb8b98af514 |  | checkpoint | Bracing props secured
checkpoint-status | bec6ad04-96d6-4899-bfa9-3073a2751c7e |  | checkpoint | Column plumbed
checkpoint-status | 1ce6dd1f-d393-42b6-b1b6-37cd9e5ea123 |  | checkpoint | Correct class of finish
checklist-flat | deb9eab6-3272-47a2-88b1-0c7fe82bc6b6 |  | checklist | Injury Form |  |  |  |  | Yes | Injury Form | 2c3e4fac-624b-4c76-8a1d-935c00f5a8c9
checkpoint-status | d6f171b5-ee00-47df-89bb-055f9416ab70 |  | checkpoint | Injury form completed
text | 1ec72ad3-0bbb-596a-b899-dfd0fad881e1 |  | textbox | Date of incident
text | 7f7258c8-37cb-53ff-b138-b128a4a05619 |  | textbox | Time
text | 8d751b05-8bb2-5a8c-b53e-8011a2923d4b |  | textbox | Site location of the accident / incident
text | b74533bf-36f3-524d-8713-bad5d3f1d222 |  | textbox | Detail of how the accident / incident happened
label | d339f5f7-7ac6-56ea-a802-067fe5c68b85 |  | note | Details of injured person
text | d2ba988c-a2d7-50a7-8c75-c9fab508e5b6 |  | textbox | First name
text | 771ce320-ee99-51b1-8a4b-47812e09be7d |  | textbox | Last name
text | 8494f3d7-57c3-5997-ba09-22fe6be308a2 |  | textbox | DOB
text | de9a25ad-cd2d-58c0-b394-338ea4c3cc62 |  | textbox | Contact No
text | a2c78b85-644b-533d-8e84-a6c0ea71ee3b |  | textbox | Address
text | 205e6d9b-abd5-5e82-8c93-90a3e966f2e6 |  | textbox | Company
text | eadb7c75-d072-52ae-8874-99b9bbdff00f |  | textbox | Trade
text | 4fae3d7c-f56d-5393-8a72-f3ca6a088031 |  | textbox | Date Inducted
select | 6b9d4f85-d717-51d4-9809-58b565c63915 |  | dropdown | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
select | 9e9d000e-03d0-5f06-ac44-fc80e8eb9fa2 |  | dropdown | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
select | 2e367c01-8c80-5111-8b58-191424aa4892 |  | dropdown | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
text | fdf80ab7-50ea-5668-8274-b2928529dde5 |  | textbox | Initial treatment given
text | c6dca3f2-f735-51c4-b5ea-bfdfabd7ab1c |  | textbox | Was follow up treatment provided
text | bc75942c-2206-5e08-954e-10587974ea47 |  | textbox | Medical centre / Doctor / Hospital attended
text | 27fd1024-456d-5feb-90e7-868f0eef56f6 |  | textbox | Date / time attended
button | a7df1c77-0ce7-5cde-9c96-37dd86538641 |  | button | Regulator notified | Yes, No
label | a9a820a9-9d2c-532a-b9a7-c1a1779d8c08 |  | note | Witness details
text | 96665950-0c17-5d26-92e8-4b33e4be1104 |  | textbox | Witness name & contact details
text | a45d37f7-9f74-51d7-86d2-edf55b42338f |  | textbox | Witness name & contact details
select | 23ec13ee-2a3b-5da6-ba51-4a5ae6f7600d |  | dropdown | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
text | e6c72cd8-1976-54a4-86a5-6e3c2cc4a2c3 |  | textbox | Other
label | 937e9cc9-2b7f-5c46-b45e-c7422a1ba024 |  | note | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
checkpoint-status | 13256db9-114e-44a8-9cc8-9a5ed84ddae5 |  | checkpoint | Signature of injured worker
checkpoint-status | 7dee868f-03fa-4d87-be93-983cc05e0f32 |  | checkpoint | Person completing this form
checklist-sectioned | 113957c0-a878-4899-9051-773729f8ae28 |  | checklist | Screens |  |  |  |  | Yes | Screens | 2ecf5681-9239-4a6c-b583-c9426bb711a0
checkpoint-group | d8fac5de-747d-4c8b-871c-c123abcf7a9b |  | section | Pre Lift
checkpoint-status | 796986d7-3769-4bf1-8604-0f74d2b2159d |  | checkpoint | Area accessible & ready
text | abbbd500-ced3-562f-a8ca-fa2667715729 |  | textbox | Screen number
checkpoint-status | 2a046457-71fc-49ab-9515-bf2ea5a90a8d |  | checkpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 6cdb5d86-7fad-4433-b1be-64e1dd301b8c |  | checkpoint | Signage in place
checkpoint-status | 5c95eeee-02b9-45ff-a46c-099ed546809c |  | checkpoint | Exclusion Zone with name and number of supervisor– Ground level and Slab level
checkpoint-status | d9a9f746-4b0f-4eb9-a3b8-c41dd8628d93 |  | checkpoint | Spotters in place
checkpoint-status | 047e5af6-db6e-4686-8907-57383fc1448a |  | checkpoint | WMS ready and signed on to
checkpoint-status | 979edb69-6780-4969-a340-12bb12834025 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 9d93c2d7-5b6c-4773-b32b-896032ef3a34 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 49c95215-aba4-4266-879f-8478c83f372d |  | checkpoint | Edge protection installed on Level/s to be exposed once lifted
checkpoint-status | a0f74cec-0025-4649-99e4-21489facbc73 |  | checkpoint | Deflector shields removed
checkpoint-status | 665de34d-19d8-4778-962b-2cd7d3b4ffac |  | checkpoint | Radio communication woking between screen crew
checkpoint-status | ed58fcd6-621d-42c0-adb5-601d3f7877d4 |  | checkpoint | Hydraulic lifting Apparatus installed correctly if using lifter
checkpoint-status | 0d927b5d-5970-4731-8850-405533999b76 |  | checkpoint | Screen Free from Debris
checkpoint-status | 66b2cd4f-1dc8-4908-956b-667e4763f14a |  | checkpoint | All wire infills detached
checkpoint-status | dd85cba1-f617-4b32-a0b0-8dcf89ebf020 |  | checkpoint | Confirm ready for lift with all involved - Team Leader
checkpoint-status | 3c40860e-0000-43f4-be43-9b1cfe7cc240 |  | checkpoint | Work at heights permit completed - attach or take photo of permit
checkpoint-group | 1cc1cf4a-28ea-4762-a259-aab739a2e7e8 |  | section | Post Lift
checkpoint-status | 0628a550-91f1-4185-845b-a0987148aa66 |  | checkpoint | Ensure all gaps are closed
checkpoint-status | ecb8fc9c-ebd6-4c80-907d-41b20c81ea03 |  | checkpoint | Mesh to be install where required
checkpoint-status | 963d749b-2021-4e0c-92cc-e834eb34e489 |  | checkpoint | Double check all needles are secure and double nuts in place
checkpoint-status | bfd5dde6-37a8-451a-a266-3ebe7360f302 |  | checkpoint | Clean and clear area
checkpoint-status | 9556f1e8-08e4-4c0e-a12d-b1be093b1edd |  | checkpoint | Remove exclusion zones and barricades
checkpoint-status | f80af9fe-1747-4d8c-bee6-7e607d9caf90 |  | checkpoint | Bar caps for protruding z bars
checklist-sectioned | 5bb8f3d8-0899-4188-8b07-02a259676511 |  | checklist | General Incident Notification |  |  |  |  | Yes | General Incident Notification | 44f7bcb8-4d6b-4350-8007-c340942aaa6f
checkpoint-group | 1bbbc7c8-a750-4ff4-8d7a-29a875d65d4a |  | section | Details of the person completing this form
checkpoint-status | 58e0e847-70b0-4d17-b722-3bf7a617fef4 |  | checkpoint | Attach any relevant photos or documents
text | 1f173d14-761a-5dd6-a039-32f7c2b66981 |  | textbox | Name
select | a1fa773a-1a7b-5ba6-936c-00f9be770b75 |  | dropdown | Position | Site Manager, Project Manager, Construction Manager, EHS Advisor, Other
text | 692fc316-9ce7-57ca-be4c-69c6a25f6c41 |  | textbox | Contact number:
text | e51b1b1f-b1c0-54b6-b161-ac5c15bfe9f5 |  | textbox | Completion date
holdpoint | 0137d768-bdeb-4975-915d-ed2232d94350 |  | signoff | Signature Required
checkpoint-status | 96a3c95c-4065-4b4f-aba7-4e163e098d39 |  | checkpoint | Report reviewed by (mark if applicable)
boolean | 73466984-e38c-528d-8720-8672de39e5c1 |  | tickbox | Site Manager
boolean | 9726aeea-0b03-521a-b88a-220ab01cd0f5 |  | tickbox | Construction Manager
checkpoint-status | 942669c1-7d78-495f-9335-b9b9fe830144 |  | checkpoint | EHS ADVISER ONLY – Head Office
text | e2ef83f2-a969-516c-b03a-ce46c9321fe8 |  | textbox | Date received
text | 20a53823-719c-5b57-9740-7e03cc2ae995 |  | textbox | Date closed (Final)
text | 40b249f3-4b81-5c96-9552-48a401eb952e |  | textbox | Date submitted to EHS Administration
checkpoint-status | b6f69276-fb31-469c-b00e-cdd1be3e3557 |  | checkpoint | EHS ADMINISTRATION ONLY Head Office
text | 74fdb73f-7e0c-574f-841a-0e2c49956b8f |  | textbox | Date received
text | 1f93c8e5-0b03-5b21-9e2b-948239c2d02e |  | textbox | Date processed
checkpoint-status | 6af10ae1-d95c-4064-9e90-1f0e01d1a69b |  | checkpoint | EHS REVIEW ( EHS Manager)
boolean | 2a98b050-d6c4-5233-b6e3-17afd755bd38 |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 9149302b-6240-54f7-88c4-28a29bbe1356 |  | tickbox | No
checkpoint-status | 3d37e2fc-b5fc-40de-8569-c25e4e50e94f |  | checkpoint | EHS System / SWMS amendment required?
boolean | 76742ff5-cea2-578b-a5f0-c758c057ac2a |  | tickbox | Yes - If Yes, Reference No in comment
boolean | 4c2f1a69-fcbc-5c0d-aa62-f304b56f8bed |  | tickbox | No
text | d3023cc8-e541-5432-94eb-b7f96b5df8a5 |  | textbox | Head Office EHS Manager sign off date
checkpoint-group | 92b2e345-3925-4632-922d-bb5b2c11be22 |  | section | Incident Type
checkpoint-status | e9cd78da-8e04-43f7-878a-fad10f2c6707 |  | checkpoint | Was a person injured as a result of the incident? - If PASS Only complete an Accident/Incident Notification Report (Form No. 01a) - If FAIL complete this form
checkpoint-status | 4a664111-575c-4f8e-8eaf-5b83162c9837 |  | checkpoint | Has an environmental issue arisen from this event? If PASS Only complete an Environmental Incident Notification and Investigation Report (Form No 01b) - If FAIL Complete this Form.
checkpoint-group | 2796b4ef-1670-4d41-9f85-b35c73054561 |  | section | Project Details
checkpoint-status | e5227496-9271-4f07-a5bd-e91fa8109e7a |  | checkpoint | Report Status and Date:
boolean | fbd9e4f8-d51b-5df3-8101-27b43b04799c |  | tickbox | Initial
text | 8e0c4516-2e76-556c-bd44-fc4d0ddc15c0 |  | textbox | Date
boolean | c12a2c66-d3ab-51c3-a36c-ed1f97e0eb39 |  | tickbox | Interim
text | f8af5f0a-8e47-528b-95f8-3454fc2fdd31 |  | textbox | Date
boolean | 416e175e-b13a-51f7-a009-dc6850e29c4a |  | tickbox | Final
text | b554466e-2ef3-5540-8a95-c2ae0b9a1249 |  | textbox | Date
checkpoint-group | 191f1d93-6920-43d9-9fc4-d3dd8dfa23e8 |  | section | Incident Details
checkpoint-status | 4a3617a6-56a7-408b-834a-ff43c3e1c863 |  | checkpoint | Date/Time of the Incident
text | f46ef44d-b9f4-55ff-976b-0004965b03b2 |  | textbox | Date
text | 246b6ae9-c3fe-56f6-885b-936678424d27 |  | textbox | Time
text | bd600ca9-ed94-5561-9999-440666c45dc7 |  | textbox | Site location of the Incident
text | cdcdc3d6-8fa5-56d1-88e0-9a1d3d4b436b |  | textbox | Detail how the Incident happened
checkpoint-status | 9f99907a-961e-4854-a4df-35841329d587 |  | checkpoint | Services affected by the event
boolean | 7d980aa4-b3a8-5d85-9f43-b194b5953b5a |  | tickbox | Electricity
boolean | cf726a90-938a-5f52-afa6-ed3b4ae9527a |  | tickbox | Potable Water
boolean | a5fa5c81-6f01-5084-8a83-2905ec78be8e |  | tickbox | Storm Water
boolean | d07250ff-495b-5d7c-b117-41218c7c5ffd |  | tickbox | Sewer
boolean | 4dade4c8-eae5-5619-8d52-207f0ade09d6 |  | tickbox | Fire Mgt Services
boolean | 3b90e5a0-8b6d-52f5-8f03-eaef194e53d9 |  | tickbox | Fire/Smoke Alarms
boolean | 9bfc3bae-4ce7-556a-8c67-352258245590 |  | tickbox | Air-conditioning
boolean | 5909a147-546f-5cb9-9f6e-b1c22e2e7fba |  | tickbox | Security/Access
boolean | bb601bb6-1a58-5b76-bd3b-5a736ba1fe2c |  | tickbox | Communications
boolean | 61d3ca19-7765-5e58-8ced-bf456c7a0638 |  | tickbox | Gas
boolean | 22f5d8b9-ca0e-5688-82b8-bd84f76ad828 |  | tickbox | Other
boolean | 4747c30c-a336-533c-ba56-e99cbc797495 |  | tickbox | N/a
checkpoint-status | 32b3a83e-9ed6-46a7-b431-390adb227b48 |  | checkpoint | Detail the factors that contributed to the Incident
boolean | 578168bf-82a9-5aa7-ac75-6d907cf4c8cf |  | tickbox | Design/Layout
boolean | 175fc2ed-2780-53fa-afbc-927c6bb28550 |  | tickbox | Equipment
boolean | 0b926953-8615-5a80-9eba-54692df8bfc8 |  | tickbox | Operator error
boolean | 86ea1fdc-06f1-56b3-b6c8-47601a95ec75 |  | tickbox | PPE
boolean | 3b9679b6-f8d7-52ae-a0be-0bf454d18717 |  | tickbox | Training
boolean | dc389518-6d64-552d-be50-98466d011191 |  | tickbox | Supervision
boolean | 6cdae7fe-e917-5e93-aa54-69f291bd770f |  | tickbox | Unknown location
boolean | 86e46b41-ef97-574a-838a-226d87555f0c |  | tickbox | Other unspecified
boolean | 371eb0eb-d603-5a04-8a6d-2fc77fe396da |  | tickbox | Housekeeping
boolean | 7fd8972b-f371-5d6c-b8e6-05db1417ff4f |  | tickbox | Procedure (WMS)
boolean | 53e3f072-42a3-58fb-be38-fe9110c5e442 |  | tickbox | Weather conditions
checkpoint-status | 2116fc0d-bbda-4a5f-be89-9d2210caf508 |  | checkpoint | Was a WMS supplied for this type of work?
checkpoint-status | 9b73da13-138c-4aae-818b-1fbf8220efc2 |  | checkpoint | Was the WMS approved by Principle Contractor
checkpoint-status | 60805594-6fa3-4313-a5dc-8967ea45a7d2 |  | checkpoint | Was the WMS signed by all personnel involved in the activity?
checkpoint-status | d530c853-ce3a-420d-8bc4-29a52f9b05fe |  | checkpoint | EHS Improvement Notice
checkpoint-status | dcd70dcf-bda5-4e5d-b48a-a6990e5f9c01 |  | checkpoint | Was the work activity being performed in accordance with the WMS?
checkpoint-status | 8c6fa8d7-ab0f-4d68-9c87-4b8a976adb89 |  | checkpoint | Was a Tool Box Talk held relating to this work activity?
checkpoint-status | 1ade845e-0e21-45ee-8f96-e97f772e6ef3 |  | checkpoint | Was any external certification required for this work?
boolean | 0def7d08-7cce-5ad6-adfe-f2729bba49b4 |  | tickbox | If Yes, was it obtained prior to works commencing?
checkpoint-status | 6b8d166f-702a-43d3-a1e4-c15439b8608a |  | checkpoint | Was any monitoring required for this type of work?
boolean | cba5379c-223f-5aa6-be4d-9abd9054d7b0 |  | tickbox | If Yes, was it in place?
checkpoint-status | 87ce8a72-6bb3-4c53-9364-70d609e4068f |  | checkpoint | Was an Authority to Work Permit required?
boolean | d9c2fd29-3e33-5f21-a934-62911a889846 |  | tickbox | If Yes, was a Permit issued?
checkpoint-status | a7ce2a26-31ca-4af6-8d11-8fad38c28c80 |  | checkpoint | Were any Regulatory Permits required for this work?
boolean | 417b026b-8a0d-55cf-9606-f7617a682c78 |  | tickbox | If Yes, was a Permit obtained?
checkpoint-status | 9d2eb1fb-0419-4bca-8b41-57570b8f9a81 |  | checkpoint | Was a Notice of Impacting Activity required?
boolean | e63e2c0a-92eb-51ae-87cb-65e3ffdd6983 |  | tickbox | If Yes, was it issued?
checkpoint-status | 907f588c-656c-45d6-948c-601cc5499ac1 |  | checkpoint | Estimated time impact of the event
boolean | 092a9f21-97c2-5d5c-b901-f8e49396b17e |  | tickbox | No impact. No loss of production.
boolean | 9601c0e7-54c3-58e3-ba61-cdcf34534c0e |  | tickbox | Limited impact. Production loss in localised area.
boolean | 6d652116-e53b-505a-88a7-2929404049e1 |  | tickbox | Major impact. Production loss across project site.
checkpoint-status | 8a5b7974-d698-4566-9e3b-adfaedf9f8c7 |  | checkpoint | Details of any persons involved in the Incident - Attach Statement forms to this report
text | d823e307-a69c-599c-a028-1cf29f81922e |  | textbox | Full Name
text | 70a15afb-1dac-5dbd-b628-7fa58844ed7c |  | textbox | Company
text | c0feaf97-77ac-5c09-9d31-0b7e533e7c39 |  | textbox | Contact No.
button | c0b6759c-b022-5708-9262-18245cf7d826 |  | button | Statement | Yes, No
text | e8158626-5d4a-59bb-bf38-94cfab3ec29a |  | textbox | Full Name
text | 1c4d535f-963d-518b-9ef0-0cbf7e495f5d |  | textbox | Company
text | 9f05824c-1aac-5bde-9094-2e76f6ce0681 |  | textbox | Contact No.
button | b69d4de4-de78-5522-a45e-7c37d74cb4c2 |  | button | Statement | Yes, No
checkpoint-status | 66b1cd37-7b26-4c10-94d1-35530f424f03 |  | checkpoint | Details of any witnesses to the Incident - Attach Statement forms to this report
text | 237e5ee2-27df-54bf-8944-9529e8efaf2b |  | textbox | Full Name
text | 6d286b15-b5c0-5e92-8989-9334d2aab099 |  | textbox | Company
text | e5ccd465-ccc4-5f7d-ae1a-ba3b48e18050 |  | textbox | Contact No.
button | 754eaac0-f137-5b9b-b36c-e2d0a8519199 |  | button | Statement | Yes, No
text | 9fad4f2d-83f0-52dc-9b68-1f67c191e329 |  | textbox | Full Name
text | 3fef7105-56e9-5ef6-91ed-0f074df25147 |  | textbox | Company
text | a8045c48-a6f4-5f74-a43c-94099b36f6e8 |  | textbox | Contact No.
button | 02ebe7e3-8d9e-51d2-8486-ba3838230cdd |  | button | Statement | Yes, No
checkpoint-status | 07211830-9ef2-4ed1-99fb-ca51181684f3 |  | checkpoint | What actions have been implemented to prevent similar Incident
boolean | 3c55f730-c55b-5444-889e-b3ad0f9ab42a |  | tickbox | Equipment change
boolean | 0b81303e-4e8f-5ca7-9359-29124c281f01 |  | tickbox | Certification obtained
boolean | 3425f727-8965-5ab7-8346-9f27ccc12d08 |  | tickbox | WMS change
boolean | 0f2049d5-cddf-5b04-909a-6e672b295cec |  | tickbox | PPE change
boolean | 2192028f-440f-55ee-b79c-2d6fff65c5a2 |  | tickbox | Site Meeting
boolean | 845bcd55-a1c1-5bdd-bc1d-2f00abc59096 |  | tickbox | Toolbox Talk
boolean | 931b3ec6-b6be-5932-95d8-f6975b09b7cb |  | tickbox | Housekeeping
boolean | c0063800-044e-5b5a-bb04-32f98fd44e38 |  | tickbox | Training
boolean | f4cd21d2-28f3-57fd-9e28-66cddc1e2f9b |  | tickbox | Other
checkpoint-status | dc2f0393-31e2-4017-b4b6-09b21f5099e3 |  | checkpoint | Has an EHS Instruction been issued to the P/C company or Bosform?
checkpoint-status | dec8a271-369f-4e10-9e92-c7a8b65e5bd6 |  | checkpoint | Has an EHS Improvement Notice been issued to the Bosform?
checkpoint-status | b8e72a4a-8f41-47e4-9a9f-71de90d8fe14 |  | checkpoint | Has a Risk/Hazard Assessment been completed?
checkpoint-status | c73a215e-0685-45a1-b5c9-9201cc1a4786 |  | checkpoint | What Hierarchy of Control measures were considered in the corrective action
boolean | d186c924-a5c9-5d76-b014-284581bf0808 |  | tickbox | Elimination
boolean | b5b4256c-6976-5711-88a8-54b18d354bdd |  | tickbox | Substitution
boolean | 24a32e0c-61ce-5c34-8ff4-939039e3c12c |  | tickbox | Engineering
boolean | dc1ec8b4-3dfb-5b88-83c0-584faa948346 |  | tickbox | Administration
boolean | 402f9a4f-1930-556f-a8d9-e95253bc6fe2 |  | tickbox | PPE
text | 426a8773-df17-545e-9ac9-b03b1a05edc5 |  | textbox | Date of action
text | 40cc0596-28bf-5245-aaaa-0f0ffbd8d165 |  | textbox | Responsible company/s
text | b617f0a8-523d-5eb2-99f2-606d5c09aa9e |  | textbox | Review date
checkpoint-status | 40b571a1-9eea-4612-8db5-69b508238dd1 |  | checkpoint | Statement/s
checkpoint-status | 76772fff-2ee5-4773-8d16-ae40de646858 |  | checkpoint | Monitoring certificates
checkpoint-status | 9ce9b65b-8653-4cfd-bd1e-f8eb66e09aa0 |  | checkpoint | Site Induction forms
checkpoint-status | 21633727-3027-4a05-bf83-0d3525f86785 |  | checkpoint | WMS relevant to the activity
checkpoint-status | 37eacabd-cf16-48d7-b4b7-b0d090c1f264 |  | checkpoint | Tool Box Talk or Meeting form/s
checkpoint-status | c35b51f5-39ee-406a-ba21-a97ad2e2a697 |  | checkpoint | Engineer certification
checkpoint-status | 5b0e14fb-7504-4d84-a8f4-c53be3fae489 |  | checkpoint | Photos
checkpoint-status | 3f572944-e981-4245-86cb-de6d40c8b405 |  | checkpoint | EHS Instruction
checklist-sectioned | 8798f0ac-9654-4c22-bd95-4c6df651110d |  | checklist | Core Lids |  |  |  |  | Yes | Core Lids Checklist | 7096d687-2876-4d4a-a247-8f30d7e9347f
checkpoint-group | c43c99bb-026e-47f3-8e25-6169d0bb124c |  | section | Phase 1
checkpoint-status | 8179da47-7c1b-426b-aa95-29b8618a8c5a |  | checkpoint | Area accessible & ready
checkpoint-status | 38f912f4-5b8b-4d60-acc7-6b8f1bebbd60 |  | checkpoint | Drawing references entered
text | 3ccad895-1e2c-5eb8-9d36-b84f66e16daf |  | textbox | Architectural
text | bb24fe5f-943d-515c-acf5-01d214ef61bf |  | textbox | Structural
text | 2e7c96ea-67e0-58fe-8d6d-c5116fc9b728 |  | textbox | Other
checkpoint-status | b56dac20-7eb1-47ee-9239-729052ff8816 |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 3defd2b6-8158-4d71-8a96-4d0c97856955 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | 730251b1-a083-41c5-9576-064c97929af9 |  | checkpoint | Grids marked by builder
checkpoint-status | b169d58e-8d4f-43c9-9cbf-95fe300859ff |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 9afadb04-479b-4288-8ab6-f93fb00d5c9d |  | checkpoint | Fillet & drip mould installed
checkpoint-status | f954f2a9-5cd9-4192-aceb-c246e1db3aff |  | checkpoint | Check set down position & RL
checkpoint-status | f1f8e7f9-aa5d-4739-82cc-7163f59a91e8 |  | checkpoint | Check penetrations installed
checkpoint-status | 5f7212d8-956f-4a73-be54-b2a2e89ec7d4 |  | checkpoint | Column blockouts installed
checkpoint-group | 8b16591d-4105-458f-9200-ccacb35bd567 |  | section | Phase 2
checkpoint-status | 3b4594fc-80ea-481e-a3c7-88f844fc88a8 |  | checkpoint | Check back propping as per design
checkpoint-status | 3c344422-211e-4541-8e30-55b82238c9c4 |  | checkpoint | Blow off deck
holdpoint | 98a91c8c-5a6b-4d98-a489-4f91a6356e55 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 77d44f4d-9621-418e-965f-c8aec11fb30e |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | 3e2ec9a5-563e-4ff9-a114-718ebc295859 |  | checkpoint | Correct Class of Finish
checkpoint-status | 5cd6ebc9-081e-4b57-86a2-3e1335f65edb |  | checkpoint | Stripping, cleaning & materials removed
checklist-sectioned | a636012c-f065-44aa-b9b7-56b9002f0984 |  | checklist | Stairs |  |  |  |  | Yes | Stairs Checklist | 8f3777b4-ef24-42d3-aa9c-482f18db9052
checkpoint-group | 9b4bd528-0e3f-474d-b80e-f68397056534 |  | section | Phase 1
checkpoint-status | 73fd70d2-7d93-4a24-8491-83242bbb9da6 |  | checkpoint | Area accessible & ready
checkpoint-status | 31cc8110-8900-4606-ad57-2ef53c445614 |  | checkpoint | Drawing references entered
text | 2faf2515-75cd-5e8d-956e-0872039bf3ce |  | textbox | Architectural
text | 17a42bef-e5ec-51aa-b500-50303a5a8137 |  | textbox | Structural
text | e1f67df7-2330-57e0-b71e-81380db9c71b |  | textbox | Other
checkpoint-status | 516b2b40-f653-4f7e-b38d-ee574119c6c5 |  | checkpoint | Current plans in use
checkpoint-status | 445e6d94-3809-44ce-8e84-8766dc7f9eef |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | 7fc58834-b835-4c06-89e8-226103e7b710 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | d86389ed-5c46-4dc5-865a-fc80e4066308 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 9b640254-0782-4e55-970b-cda723fb1e27 |  | checkpoint | Base of stairs cleaned
checkpoint-status | d510dd95-6299-4654-8608-42b1b76f79be |  | checkpoint | Riser heights confirmed
checkpoint-status | 6e69fc20-e0dc-4d5c-800b-2fe92c5f223e |  | checkpoint | Going lengths confirmed
checkpoint-status | 78b988eb-87a9-416f-bd70-9376aced21b7 |  | checkpoint | Correct Class of Finish
checkpoint-group | 8f52aecb-fc96-4ae9-8d8c-d9167dbe9a7f |  | section | Phase 2
checkpoint-status | 3fbe8eb6-25de-43f0-aa1a-a08315fd8133 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | b08eb4f6-678a-4f50-a94a-600cf2f98c52 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 9df74aec-a88b-4e97-93ea-1b4fe220e918 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 3c3a5e6d-fc07-4fb0-a926-9fbdd8725d71 |  | checkpoint | Riser heights confirmed
checkpoint-status | 68fbf034-3032-445a-9ab1-e248993b51dc |  | checkpoint | Going lengths confirmed
checkpoint-status | ba10f661-0fc5-432c-8405-6eba4901a219 |  | checkpoint | Correct Class of Finish
checklist-flat | 414a2ffe-529d-4aa9-bc04-15281dd576ea |  | checklist | Progress Claim |  |  |  |  | Yes | Progress Claim Checklist | a0018bd6-2bcf-4ae6-9e33-36229d78edcf
checkpoint-status | f55268e1-07de-43a6-8944-98cb9ee380c4 |  | checkpoint | Please add Comments / Photos
select | 10c73db1-3c43-57a0-bbe7-92a70a6ea758 |  | dropdown | General | General, Submissions, Site Establishment, Design Off Site Fabrication including Design & Commissioning
select | 82bac1c2-6acb-5f1d-b9f4-6d24e57956f0 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 21e33ba9-bb79-5289-b280-6453fa5801a6 |  | textbox | General Notes
checkpoint-status | 336296a5-7824-4f01-beac-510fa3710422 |  | checkpoint | Please add Comments / Photos
select | eef817b9-1250-5606-beb5-b52c9e9aab94 |  | dropdown | Level | SOG B-2, B-1, Ground, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 68b47ac2-c61b-5634-b228-a69695a1e844 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | 5395a5a9-6e24-544a-a441-d0b52d291895 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 515aa1c7-2a78-5244-9bdc-12859c08b506 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | f79a59b6-07dc-5309-83c6-284bf0dc0b32 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 7cff6fcf-bf27-545e-b6ec-ab48cbfbd27b |  | textbox | General Notes
checkpoint-status | a054dc30-81b3-4ee8-839e-2e7921862b74 |  | checkpoint | Please add Comments / Photos
select | 27e7e509-14c2-5f0c-9c2c-3ed419550c69 |  | dropdown | Level | SOG B-2, B-1, Ground, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | c2fba03b-cbfd-5759-83b9-090988f9ab7d |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | f2b49790-67f0-5a17-9470-883891151456 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 6ba31d5b-f55a-55dd-b9fb-869023ae1bb4 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 83340364-52cc-52c5-a8f1-eb843543637b |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 8886a838-e513-550e-bad5-5033526c234b |  | textbox | General Notes
checkpoint-status | 6088a362-46ca-41e5-b493-8825b575ff25 |  | checkpoint | Please add Comments / Photos
select | 828320a6-e0ee-5b78-b95a-3ea728c96f2e |  | dropdown | Level | SOG B-2, B-1, Ground, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 33d62627-0257-594b-a805-67d43811178c |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | 2bf53b11-876f-5740-9983-5187c4756a4b |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 31c170e8-32e9-5789-9fa1-e9a4fa588034 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 0d09feb4-ffbd-516b-98da-9c86f6a1aa94 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 24db5302-2c90-54ba-8b4a-7c4efa16c367 |  | textbox | General Notes
checkpoint-status | 74d80cb7-5a09-413b-add1-119b28c9c19d |  | checkpoint | Please add Comments / Photos
select | 8c2b98c5-9a51-5864-b738-162945e58e54 |  | dropdown | Level | SOG B-2, B-1, Ground, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 8553f332-8e85-5c39-945a-3bc6fc1cd815 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | d52124e4-23d4-566b-9ef9-51e8d50b7930 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | d3a8dd1d-7deb-5db5-bc8f-8433d789f812 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 54570dcd-6e97-50a8-834f-d96759d9f89c |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 72af8760-dae8-52a9-a18a-47416da70158 |  | textbox | General Notes
checkpoint-status | d7ff9bea-1d3a-4460-be1d-ea77730b5c2f |  | checkpoint | Please add Comments / Photos
select | 6da1c757-261d-5b94-acf7-1609de5a21fc |  | dropdown | Level | SOG B-2, B-1, Ground, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 04bc790e-dfd0-534a-8de2-f13352cf040e |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | d8bb1ad3-1ec7-53b7-9522-f33ae03bb6d1 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 49339809-779d-5f7e-ba81-5498f930a93b |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 8df945b2-49e0-53a0-b174-fc167c8ea28b |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | ba0b4811-eb51-5dcf-9ab2-61c28e72b87e |  | textbox | General Notes
checkpoint-status | 88a9180a-7dd9-4573-b38f-6ae8632d4005 |  | checkpoint | Please add Comments / Photos
select | c057d5cd-4a48-53e0-bec5-f6f605438d09 |  | dropdown | Level | SOG B-2, B-1, Ground, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 5f8b261a-568c-5ab3-9b96-0fd58707f0f0 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | ab7e6107-55e4-5449-8e6b-72126d050b17 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 08390e20-9eaa-57eb-b6c9-e7514ecbb2a5 |  | textbox | General Notes
checkpoint-status | 37e28701-4c73-4511-8496-63d2a7d45a14 |  | checkpoint | Please add Comments / Photos
select | 4f802a97-fd21-5f76-9f3d-8d1c76b1a645 |  | dropdown | Level | SOG B-2, B-1, Ground, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | d70b0b0c-8965-596f-8b61-4ad9dc688015 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | be2e8259-34b3-521e-865e-9c89e02861be |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | f602cdc9-963b-50e9-8978-258d36b6ac55 |  | textbox | General Notes
checklist-sectioned | 3a3e807d-2284-47e1-b93d-b9824c749c94 |  | checklist | Jump System / Climb Track |  |  |  |  | Yes | Jump System / Climb Track Checklist | a1313eb5-465e-475f-a94e-8d7805af8a91
checkpoint-group | 9ac38f7e-c50f-4880-b3ff-1416cb58dc62 |  | section | Pre Lift
checkpoint-status | 1761436f-69f5-459f-9a00-4c8933a5e6c3 |  | checkpoint | Confirm concrete strength MPA 15 has been reached at connection points (Builder to supply)
checkpoint-status | 60b8ef7a-9821-4a3f-8c8d-57e70af02937 |  | checkpoint | Signage in place (Stripping in progress/Jumping in progress/ No access)
checkpoint-status | 467acbf8-1328-4861-bcbe-188d0eca700c |  | checkpoint | Exclusion Zone in place
checkpoint-status | b023a07b-bea8-4c49-963c-9a79cdf0e012 |  | checkpoint | Spotters in place on slab below jump (outside exclusion zone)
checkpoint-status | fb3cbec6-1be2-470d-8890-5263d1b71302 |  | checkpoint | All Platforms cleaned and clear from rubbish
checkpoint-status | 6a4304b0-6d73-41fd-b5c1-b21070a267a8 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 7e468368-da09-49c2-afd0-c514acac8589 |  | checkpoint | Clear communication between team leaders and Crane crew (toolbox talk)
checkpoint-status | 96dcfee4-6712-4eb5-9d90-f65b7fcb9127 |  | checkpoint | Ladders available and secured
checkpoint-status | 0599926d-b20e-41aa-b53c-3686eda9a3bb |  | checkpoint | Flipper systems lubricated
checkpoint-status | 009bae99-5713-4e97-9249-ddd490274cad |  | checkpoint | Trailing Decks clean of debris
checkpoint-status | d9459e71-cf5d-4ec7-a30c-ea0d5be7a05a |  | checkpoint | Trailing decks clear of protruding ferrals in walls above
checkpoint-status | 10a3500b-1e63-4399-b0b9-53c02e2be12f |  | checkpoint | Check exclusion zones in pit below are in place
checkpoint-status | 9f27a4c8-4744-4ea8-920c-21d1a4a50cc1 |  | checkpoint | Plumber to check pipes to water cooler
checkpoint-status | 129468f3-6496-4ee6-b422-41a14b87ca54 |  | checkpoint | Transfer RL heights
checkpoint-group | f83b9384-f503-405f-82c3-7b4e7de32d8f |  | section | Post Lift
checkpoint-status | 07da6550-0efe-4a6a-8ddf-54a6b5bcaf97 |  | checkpoint | Confirm connection points are secure and all engaged
checkpoint-status | d3d97222-bb9a-44b0-838f-c0af55504d7e |  | checkpoint | Confirm mesh secured to doors and penetrations
checkpoint-status | bfc904c4-fedb-4f4d-ac60-81efb09ae578 |  | checkpoint | Signage in place
checkpoint-status | b0137279-90c8-405b-a27d-854f1f2d12ea |  | checkpoint | Screens and mesh infills are in place and secure
checkpoint-status | 8fda8ea6-6b08-4787-b370-292000da0e4a |  | checkpoint | Loose materials are stacked and secure each day
checkpoint-status | 91292f6a-d9ae-4bdc-9792-00ab4fa9eadc |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | d5167629-bc47-47fa-bdaf-6a917d2a90a0 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 4a50120b-302d-46b2-90c8-47ce41b11db2 |  | checkpoint | Loads on platforms not exceeded
checkpoint-status | 8ad94a33-5929-4ebe-9dfd-f7c6b6c1c8c9 |  | checkpoint | Ladders available and secured
checkpoint-status | b660d5ed-7ed5-4bdd-9ccf-c206e63fdf85 |  | checkpoint | Access is clear and marked
checkpoint-status | 59d4c9f9-96c7-4458-8000-3a51940dded2 |  | checkpoint | Power Board connected
checkpoint-status | 2b9248e8-9e93-4337-9c26-26110db21ad0 |  | checkpoint | Confirm ready for lift with all involved - Team Leaders
checklist-flat | b9898760-5c52-4363-ac34-d7b5d3c2c011 |  | checklist | Daily Pre Start |  |  |  |  | Yes | Daily Pre Start | bfee7721-3eb3-4b0c-b28c-b1f987a67c2c
checkpoint-status | ac449473-1fed-4c5f-98d1-820596a0b827 |  | checkpoint | Daily pre start meeting completed
text | 5971a391-1058-5aee-8a42-fec43a86e238 |  | textbox | Date
text | 5810429e-cff6-5f80-9123-7df1901db76b |  | textbox | Time
text | e9b14b11-2e2f-5947-9588-92d7bad40686 |  | textbox | Location
text | aeaec6f9-752e-5973-a30a-88b2bf9a90b7 |  | textbox | Supervisor / meeting leader
text | 55bdc9cc-90ea-5ef1-b905-9bcea9d74d24 |  | textbox | Project Manager & Construction Supervisor attending
select | e0062c20-1928-549d-9fb9-4880a1aff991 |  | dropdown | Current weather | Rain, Wind
text | 5841b6b9-886b-5425-b19d-567d87a41ede |  | textbox | Temp
select | 3c49413b-514b-5773-a8b7-4c4242a4ed48 |  | dropdown | Forecast | Rain, Wind
text | 3ad5ad22-2bea-5bf9-acc4-a1fdbe59a9c0 |  | textbox | Temp
button | 3d66a409-f3dd-58ce-9cb6-0170ace31da8 |  | button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
button | 23206602-947e-5179-804f-f46df774a6dd |  | button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
text | 0aee9781-00b1-5774-91b9-c5df99230926 |  | textbox | Any issues from the previous day
button | 05e1dddc-0e0d-57da-aa5b-413dfff486c1 |  | button | Do you need to change SWMS | Yes, No
text | 548c8ec1-f9cc-5676-9093-58a210b4ac50 |  | textbox | First aiders on site today
text | 3396d812-248e-5e95-a6e3-b480875fe2ac |  | textbox | Apprentice & who are they assigned to
text | dd4133ae-264c-5091-8080-3140d7b0f541 |  | textbox | Apprentice & who are they assigned to
text | ce8ae67e-c806-5adf-a280-89805e201ead |  | textbox | Apprentice & who are they assigned to
text | 66b10a29-65a4-5d6d-9991-391f763da381 |  | textbox | Todays tasks / jobs
select | f141a7f8-14f0-59c4-95ab-48c7085b1efc |  | dropdown | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
button | 1177beca-01e4-57fc-ba70-10c4f6eb481e |  | button | SWMS in place for all activities | Yes, No
button | f43c573c-fdfa-57bd-ab8a-0a68ed4c4ec0 |  | button | Hot works | Yes, No
button | 6feeb415-a90b-54be-8c13-b4190f866130 |  | button | Excavation | Yes, No
button | 55537920-bc82-5efa-962f-c79a1d3e5f46 |  | button | Ladder | Yes, No
button | 4a677a75-1bb6-500f-b5cf-9f1320236c8c |  | button | Core | Yes, No
button | c1014a18-a557-59d6-8897-67450fd1176e |  | button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
text | 4e41a3eb-1534-5247-b0a5-76dfd59d9220 |  | textbox | If yes, list the substances
text | d18bf92e-98d8-5cb5-8b74-244b3373e511 |  | textbox | Attendees
checklist-flat | 464cd95c-2135-4f11-8fa8-195daf784115 |  | checklist | Weekly Labour Hire Control |  |  |  |  | Yes | Weekly Labour Hire Control | c68a18db-2d72-4722-9124-6dd5847748d7
checkpoint-status | 28e8d80b-94f5-4c05-a3fd-ca478d8072fe |  | checkpoint | Tuesday
text | 365cd41f-cef5-52c1-af46-5b520330bdfa |  | textbox | Date
text | 27336a57-a407-53cd-954f-85f09d13d80c |  | textbox | General Comments
checkpoint-status | 2bcd4674-b3a3-43ee-bac1-1b6d6d872296 |  | checkpoint | Wednesday
text | 047750dc-6e19-57a6-8412-888692e45259 |  | textbox | Date
text | 1782b5ac-cb26-57f1-9b39-41901bd468be |  | textbox | General Comments
checkpoint-status | 2cc72fac-2222-444e-ab84-f1c1380b3c7d |  | checkpoint | Thursday
text | 9a67bba6-9969-520b-8966-2caf158c354c |  | textbox | Date
text | d7dfa1ed-4d60-50cf-b7ac-867178ae994c |  | textbox | General Comments
checkpoint-status | 8d50bd2d-9085-4fcd-a54d-90cefabb74e1 |  | checkpoint | Friday
text | 89679d37-bfe3-5793-b7df-d26d70941434 |  | textbox | Date
text | a68f789c-7a3b-50c7-8dd7-e92f271824a2 |  | textbox | General Comments
checkpoint-status | fd2e9cac-b0ff-496a-a3fc-6388f6906d3b |  | checkpoint | Saturday
text | 4f1b0eb2-d7f5-5abe-9158-898dc98f968e |  | textbox | Date
text | 70f07508-2f66-5ea5-854f-44ffe4aa056b |  | textbox | General Comments
checkpoint-status | a54fd231-4c9c-4695-bb1a-b54f0f667a51 |  | checkpoint | Monday
text | b00b0d7c-0159-5fb8-8ac0-7a9e1db34de4 |  | textbox | Date
text | e709c22d-bb9b-5b4c-bef9-60f09ea6f7dc |  | textbox | General Comments
checkpoint-status | 0ccc6deb-3f55-40f0-8dc7-9cc86cfde1cd |  | checkpoint | Tuesday
text | bebfb082-4e76-5add-a076-902eed29cabe |  | textbox | Date
text | d221bfa1-0ccd-5076-b817-eeb95e1b2bdf |  | textbox | General Comments
checkpoint-status | 0d484e44-c117-48d1-8443-8804bc40fead |  | checkpoint | Please Attach Time Sheet
holdpoint | 8c88e21e-ff6b-4f8d-941f-e4d5dda2fa29 |  | signoff | Client Confirmation Signature
checklist-sectioned | 96f71974-b93c-4395-af22-5208b8f18aa1 |  | checklist | Hoist |  |  |  |  | Yes | Hoist | c72ab422-f22a-4517-ace5-fca9203642d5
checkpoint-group | bf5f56cd-4529-48a8-b303-8ebcc3654490 |  | section | Install
checkpoint-status | 05dcbdba-925b-42f1-a872-efd440a1a087 |  | checkpoint | Area accessible & ready to receive hoist
text | b39c154a-d114-5c64-a9d1-e594402ff6de |  | textbox | Hoist ID. Number
checkpoint-status | edde161e-ebe2-4e0a-b798-1f688547d1dc |  | checkpoint | Adequate Crane or Franna to install (heaviest lift required 4.5 tonne)
button | e746aa93-7fcf-53ec-84e5-d97756fc38f3 |  | button | Copy the Certificate of service and service history onsite | Yes, No
text | a67b9036-ea68-5b47-86eb-975d2f9be359 |  | textbox | Name and Number of Rigger
checkpoint-status | 1a6a1e8c-05fb-44c2-a9a5-5b16438590a8 |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
holdpoint | e40cb7cd-427f-4138-b040-e4e9920f9b6d |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 53ea5fa5-f840-4cb5-b4d4-9e171b02ce52 |  | checkpoint | Scaffolder on site to assist in edge protection if required
checkpoint-status | 588581d3-a39b-4e31-b653-0a5a4e6433aa |  | checkpoint | Signage in place
button | c79cddb3-7fb8-5122-92aa-1603ff43d969 |  | button | 3 Phase power accessible and adequate circuit breaker 75 start Amps at power sorce | Yes, No
checkpoint-status | c4a4ffc1-b9b9-489c-9701-aa8c3185f2c6 |  | checkpoint | Exclusion Zone around required area
checkpoint-status | d6377000-7307-4aeb-b846-e142b262778d |  | checkpoint | WMS ready and signed on to
checkpoint-status | 39f62cf6-4575-4d5e-a060-a2b3bbec765f |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | bf206b56-5101-4e6e-ac7f-f77124d07a35 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 4e42ccd1-6d50-45fb-809f-2e014a80db01 |  | checkpoint | Gates installed
holdpoint | 0e1f008b-d0a3-42a5-b26c-90a10385c29e |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | dac9f5f0-7290-40d3-afac-3b14214bcee6 |  | checkpoint | Log book for hoist is onsite and in good condition
button | 726a6950-f427-54b9-b498-a28bbe6ed6c6 |  | button | Copy of Bosform commissioning sheet on site and completed | Yes, No
checkpoint-group | 3ec9a53f-e6ce-4dc6-8b4b-c43415de7e68 |  | section | Hoist Jump and Dismantle
checkpoint-status | bd9eed77-965e-4493-bdc8-9b31de7cc7b0 |  | checkpoint | Ensure exclusion zones are in place
checkpoint-status | e8d17133-28ad-4675-966f-4b5a0bb510a7 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | fef4b719-e12c-44ef-a63d-13f31ce0764e |  | checkpoint | All loose materials removed from edge
text | 14c82e83-e408-5f93-a436-b7908db82d58 |  | textbox | Name and Number of Rigger
checkpoint-status | 3d777ae5-30e6-4d0b-aa98-c436dfa4069a |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
checkpoint-status | 83933e8b-2592-433a-9bb1-77e9b0933382 |  | checkpoint | Scaffolder on site to assist in edge protection if required
text | 43b3601a-6b18-582b-aa79-20655fbe1b68 |  | textbox | Level Number to be Jumped to
checkpoint-status | 99f02c90-f01d-4537-836e-7b44371dc918 |  | checkpoint | Gates installed on Level/s to be exposed once lifted
holdpoint | cd003425-1866-4ecd-84eb-8e3aa70d9b0d |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | c6529f97-8d92-40a8-855c-28efd8f8fcdc |  | checkpoint | Signage in place
button | e5c7b0d6-3d4f-56dd-a067-dd85f570dac3 |  | button | Hoist Screen installed if required | Yes, No
holdpoint | 31234824-d2e9-48b4-81ad-83588c892723 |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | 9eb53c80-cfe3-4886-b2a8-53d22213de34 |  | checkpoint | Remove exclusion zones and barricades
checklist-flat | c2cfe997-489e-4911-888a-f389f966e9cd |  | checklist | S.O.G |  |  |  |  | Yes | S.O.G Checklist | d12099b8-80e8-4869-aa9e-fd28f213afe1
checkpoint-status | ff9363ee-06bc-4d8f-a352-f9868ac2e4ef |  | checkpoint | Area accessible & ready
checkpoint-status | 0c3a194c-aca0-4fa2-a3ab-4d1d911efe5c |  | checkpoint | Drawing references entered
text | 5f189d25-82a4-5114-b5d7-605a67c04744 |  | textbox | Architectural
text | 46e5da48-75c3-5f56-ba3c-cfaa15cbc785 |  | textbox | Structural
text | 12d7ebc0-60fb-5b04-a555-4d5742f2ecd3 |  | textbox | Other
checkpoint-status | 0f1f74c1-2579-448b-99d6-c9d69f67c9cb |  | checkpoint | Current plans in use
checkpoint-status | 2e16486e-7ddd-4e1d-af25-6c1e965344e2 |  | checkpoint | Survey points give for grids
checkpoint-status | 2b4db5b8-c3ce-42fb-acee-0812d8e69c94 |  | checkpoint | Surveyors points given for edge boards
checkpoint-status | a9df6083-e8ed-43b6-a9fd-11daa67412e5 |  | checkpoint | Datum RL supplied by surveyor
checkpoint-status | 7a2984c7-b71b-44d9-b572-0aacc7ffb199 |  | checkpoint | Edge boards plumb & straight
checkpoint-status | 0de3b56f-f754-4d85-b929-46679a8dd8d3 |  | checkpoint | Step downs secure & correct RL
checkpoint-status | 4deb42e6-0a4c-4c2a-bfbc-6a2013e0e5d1 |  | checkpoint | Dowels installed on pour joins
checkpoint-status | b6dbac11-d1c2-4710-9746-d972cd09872a |  | checkpoint | Column blockouts installed
checkpoint-status | 7bdc7968-bc50-4cf3-a88e-1d90a03d9d96 |  | checkpoint | Correct Class of Finish
checklist-flat | 2a3400ee-948a-4318-9598-4ad6e5350f01 |  | checklist | Walls |  |  |  |  | Yes | Walls Checklist | d55603ac-6eec-4e29-b7eb-5ddf408ccb3c
checkpoint-status | 733807cf-385c-40df-9657-f31e1a9774a4 |  | checkpoint | Area accessible & ready
checkpoint-status | 0c5bee43-1b3e-4c8e-a7cd-e533223fc226 |  | checkpoint | Drawing references entered
text | bce59db8-637b-5179-8685-1c7564438ba8 |  | textbox | Architectural
text | 77650119-ebf2-58d9-b63c-80a31ecc371e |  | textbox | Structural
text | 275d56be-c60b-5d7c-9769-45d607bf82b0 |  | textbox | Other
checkpoint-status | 760e0f79-fe21-4381-b75e-d81f63ebaacb |  | checkpoint | Current plans in use
checkpoint-status | d63b79db-4865-43b6-90a6-4f7e17d3dc99 |  | checkpoint | Survey points given for 2 points
checkpoint-status | 97ce37d0-edc7-42b7-9c38-57f11c999954 |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status | 8035b570-9bc9-4883-8e48-6d11fd4c80b2 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 20cf2fb1-5568-4ba7-8b5d-e0bd0787f84d |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status | 39a9b9b4-cf57-4e94-a770-bc9cd95bc3fb |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status | 1c90d6aa-71bf-4e29-8480-79d63db29fb6 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 77acdc48-72dd-481e-a01c-8e769a7c67e5 |  | checkpoint | Base of walls cleaned
holdpoint | e9d868a4-c089-44a7-afe8-c5604b956cff |  | signoff | Inspection by site engineer
checkpoint-status | 439a2043-9fdf-4b13-bdcb-5bfaaf41990c |  | checkpoint | Closing shutter installed
checkpoint-status | b6887b55-7e4d-4ba4-8f92-388e8404614f |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status | cc300bf8-3c5a-44a5-934c-b03df3cbbed0 |  | checkpoint | Correct Class of Finish
checklist-flat | e300209c-6c21-49e7-b749-c15e7f3144e5 |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Toolbox Meeting | e88db07f-3c9e-4394-b79d-2ff83b73b8a2
checkpoint-status | 76b863a1-179a-4eac-bdd4-3a05395d9abf |  | checkpoint | Toolbox signed off - Attach an forms
text | 68cd6dfb-a1dc-578c-a674-5f8cbed8f941 |  | textbox | Work area
text | 2bbc846c-f529-55fb-a41f-25b156daa175 |  | textbox | Supervisor
text | 1c096243-7376-5213-a07b-0c39bcba83a5 |  | textbox | Date
text | 6c8ce754-955c-5235-8563-4a38869cbc5d |  | textbox | Time am / pm
text | ad453b7b-35d9-52a1-9784-da7682374110 |  | textbox | Actions from last meeting
text | 41f80bb1-c315-5928-aa30-b266bbebaa16 |  | textbox | Injuries last week
text | 5de599ca-6647-59fa-8986-c159f5a66c72 |  | textbox | Near misses last week
text | eba4da5b-076c-5ab1-a37c-108fe27e7b01 |  | textbox | Safety Items discussed
text | f4df8d81-369d-59d4-9e66-e1e91c619e54 |  | textbox | Comments from the floor
text | eeb61b83-6fd7-514e-af18-7d57c3f3da01 |  | textbox | New business
text | 1112ace9-04fb-5569-9567-a6a097819afc |  | textbox | Attendees
checkpoint-status | cfb99904-2ecd-4a17-ac67-6b3c39a9f562 |  | checkpoint | Attendance verified
checklist-flat | 8053c32f-5698-48b7-a3ff-0fea79581d99 |  | checklist | Progress Claim |  |  |  |  | Yes | ZProgress Claim Checklists (archived) | f8302530-8ef3-4ea5-988d-84876db3a0aa
checkpoint-status | d42f4074-29d6-4a6d-99f0-406ed7278e72 |  | checkpoint | Please add Comments / Photos
select | e1ed9fb8-a478-510e-9023-1e4a161f4680 |  | dropdown | General | General, Submissions, Site Establishment, Design Off Site Fabrication including Design & Commissioning
select | b5688831-5993-5f50-8b35-81b75624ef0e |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 86c83301-7ffc-5224-8be2-7dc28160fe6a |  | textbox | General Notes
checkpoint-status | 28a3e1b5-e60f-41ef-b10d-b031579f759b |  | checkpoint | Please add Comments / Photos
select | 6d4223a2-0107-5bad-9b12-f9cfa32f4ef3 |  | dropdown | Level | SOG, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 7b33bfbb-e3b1-58fa-9e39-e0754c8cd15c |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | d77bb415-d181-59ae-a41b-dc760938b7bb |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | bcd382ef-7a8c-53f0-9651-4252a40167af |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 429d04a1-a094-596c-86f7-8721e124e223 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 3744a3aa-0c74-550e-bc9c-940d513e8a62 |  | textbox | General Notes
checkpoint-status | 20dbde47-e57c-44d8-8656-f33b456ac2ce |  | checkpoint | Please add Comments / Photos
select | 3dc2688d-2482-5600-80a4-228d7e01a5dc |  | dropdown | Level | SOG, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 464d15a5-8bed-54a5-af73-0948ab5fee8e |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | 411ce9ff-db34-5d34-a5e0-a170431050f3 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 383a6d4a-5acc-5ccb-9fc8-88589287914a |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 75a2af33-e7c3-524c-ab1f-ac14403c7924 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 995acc83-a58b-545f-a85f-1252615c71d9 |  | textbox | General Notes
checkpoint-status | 285c5d9e-fdeb-43b3-87f6-244a971fb94f |  | checkpoint | Please add Comments / Photos
select | 9d05aa69-bcb8-53ca-83af-dbb9ee02303c |  | dropdown | Level | SOG, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | a084db8a-bcdd-5de0-9b56-e01b806c9bb1 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | 798c2ba4-44d6-5241-a6b3-0869c4b61582 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | ae5013ab-01e2-53c8-a241-8b8e2f685724 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | c392ae96-a18b-5963-9507-873a73c679a4 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 992f05b1-9c6b-5f4a-a5b8-30eb0647f4bb |  | textbox | General Notes
checkpoint-status | ded36fd5-3c15-4022-9b55-36c3980aca33 |  | checkpoint | Please add Comments / Photos
select | 43ee10dd-fa17-5c5e-8592-4fa3106a3397 |  | dropdown | Level | SOG, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 95222f34-e075-5e34-8346-dcb9678b69cf |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | a9186988-41bc-508b-9e2f-46449a47afe5 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 9ad7b32e-1c52-5342-9a1e-f9fc295f1c8d |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 055c92c0-9888-5cbc-a332-f1fc220b1eb3 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 189697e4-789c-57f5-8f2a-b71f367b3523 |  | textbox | General Notes
checkpoint-status | b3510053-e0c6-4091-9fc5-70f9a77badcc |  | checkpoint | Please add Comments / Photos
select | f08dfad3-718a-59dd-a3dc-91750d73535f |  | dropdown | Level | SOG, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 78e76e40-07eb-5c6b-884f-da847bd58519 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | 1a23915e-c149-5ae0-968d-29c439be6a60 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 85beef2c-1bdf-5bd7-a06a-a6258b5dbcfc |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 66801d9e-8904-5e09-8b23-c8d7b2f5bcc7 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | b8da4d4c-c0ff-5096-a96b-3fbe1cddce69 |  | textbox | General Notes
checkpoint-status | 3cbc0718-2b9e-4c35-b5fe-032fcc5b286c |  | checkpoint | Please add Comments / Photos
select | 60e06d82-0a0e-5229-9bc0-5e6b25d0a24e |  | dropdown | Level | SOG, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | e4c42821-cdce-5a7f-bdf6-1bfb52d7a694 |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | 229fef3c-eaf0-5383-abeb-e974c9dac7af |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 0a823ffe-dcec-5f16-b8fe-2da6cd0f1cbc |  | textbox | General Notes
checkpoint-status | 9c1ff523-9e0d-4026-b0e0-679a4d5a316a |  | checkpoint | Please add Comments / Photos
select | a3419643-0ee0-5f3f-818a-dc0d4f48e1cf |  | dropdown | Level | SOG, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, Plant Deck
select | 5a3296a8-383f-5b93-b64e-2f44545ef72e |  | dropdown | Description of Works | Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only)
select | 55384505-4044-55de-951e-0a8bb5c4af44 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 1f75c87b-5c3a-5ee4-b04f-641cf9699453 |  | textbox | General Notes
checklist-flat | d585c6d8-357d-43eb-bc53-539fc7d3089a |  | checklist | Site Diary |  |  |  |  | Yes | Site Diary | fb110b24-1bd7-48a0-aca5-d16916236cba
checkpoint-status | c9263893-6f47-4a03-ab11-e5bfd9206c7a |  | checkpoint | Areas of work accessible for the day
select | dd75bb25-0e94-5997-8b15-2a49de3bfe2d |  | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | 7e3f0463-4788-5c30-8395-20dcd20d4730 |  | textbox | Date
text | db158241-e633-527a-ac2e-b821aec7beab |  | textbox | Year
text | 6e476c07-b643-53ee-a916-382254082a22 |  | textbox | Number of workers on site
text | f568b517-0fa5-5109-bf4f-522ec8558ac9 |  | textbox | HSR on site today enter name
text | 7f0e5ab2-9b27-565d-89fa-d4568a1956a7 |  | textbox | First Aider on site today enter name
text | c4e46d5c-c7e7-5304-9aaf-5acc16cad894 |  | textbox | Injury on site today enter name
checkpoint-no-status | cdf98b81-00ee-452e-bb8f-597a7305c7d2 |  | checkpoint | Work area 1 details entered
text | f68ef190-e827-58f2-83ce-ff1648e10502 |  | textbox | Area
select | 9fab2cc6-ad45-57c1-9502-9ab5e48a4cfb |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 84afadad-29aa-56dd-b3c1-940c1f44b7e8 |  | textbox | Comments
checkpoint-no-status | 9ca0b2ed-f522-496e-b8df-5b75df89087c |  | checkpoint | Work area 2 details entered
text | c812cc73-b039-584c-b0f7-22cca829ad65 |  | textbox | Area
select | 1ef44825-273e-549f-ac20-d9cff35201f1 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 1dfbb2dc-c182-5eff-98c8-58c9003f2c21 |  | textbox | Comments
checkpoint-no-status | 0483450e-21be-40ad-80cf-6738726532d7 |  | checkpoint | Work area 3 details entered
text | 4f12651b-4480-58dd-a025-d24fd2863bf3 |  | textbox | Area
select | 8b71289d-a2d1-52c5-a21f-890dbd19c4c8 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 19cc6617-f0b3-5bb2-bc37-251e05b0bbcf |  | textbox | Comments
checkpoint-no-status | 6316c2ed-0735-45b7-aad4-64cb111f534b |  | checkpoint | Work area 4 details entered
text | 10af72fc-832d-5341-bc0c-3019dcbb7a6b |  | textbox | Area
select | c4a589c9-3018-5c0a-91d9-a3387f9ef157 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 3a6d6321-539e-59d8-9638-5c0dcf729da5 |  | textbox | Comments
checkpoint-no-status | 58e0eb1c-dff6-4c02-9fc6-1f9c11f301ad |  | checkpoint | Work area 5 details entered
text | 42f6d30d-06f5-5d87-b6a9-c83c16d953c8 |  | textbox | Area
select | e787e76d-1fce-5940-b5dc-b2d391748b60 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 49a53fef-d44f-590b-9550-d61caa781fb0 |  | textbox | Comments
checkpoint-no-status | c842d5db-ce8c-4f99-9b90-f083aa851227 |  | checkpoint | Work area 6 details entered
text | eda4f157-4ddd-5a43-86d6-985adc52bd02 |  | textbox | Area
select | a52a407a-c25e-5e65-944c-72630c2631ba |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 43c97cfc-4c70-5e1e-b5c5-07e7b40d4fe3 |  | textbox | Comments
checkpoint-no-status | 7fd12570-5504-4121-832a-a08da6a63658 |  | checkpoint | Work area 7 details entered
text | 85c5f963-db0c-5049-8d91-0a68a038623a |  | textbox | Area
select | d2515a28-22c2-54c9-9128-3fab80b864f3 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | a7327b3b-8a91-58be-be48-a757341c7152 |  | textbox | Other
checkpoint-no-status | 5711f719-fd5c-4329-bcd1-b9b006bdea2c |  | checkpoint | Work area 8 details entered
text | 20e88c59-e05a-5bb2-842c-114bee736834 |  | textbox | Area
select | b0cedb93-4903-5986-8ae7-26122835d808 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 18ede5e8-3525-5595-9a03-243e87aaf466 |  | textbox | Comments
checkpoint-no-status | d8d62f6b-798c-40d2-b6d3-b7218279fd88 |  | checkpoint | Weather conditions entered
select | d6efad2e-a04b-5f0f-9779-0d4872589ef1 |  | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | 2234ae9b-a338-537b-b12b-555712d729e4 |  | textbox | Min temp predicted
text | b5ad1933-2afc-59a1-b63c-06e1a782c4cc |  | textbox | Max temp predicted
checkpoint-no-status | 52483fdc-c07a-444a-9fe5-a4b03f8a2730 |  | checkpoint | Delays from inclemency
text | ddd88245-296d-5e52-9845-121842c63924 |  | textbox | Total Hours of delay
select | 8e57b759-b89e-5af9-8c49-88f7a8e0b193 |  | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | 184c9661-ba67-4e4e-ba58-8cf7ec59d2b5 |  | checkpoint | Delays from Builders or Others
text | 56f5677d-e3e3-5175-9443-2ac470d701fd |  | textbox | Total Hours of delay
select | d2796738-50cb-5144-9c20-cf404bb87748 |  | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist-sectioned | 67f192f9-90a7-426e-8c5a-6273ee946cb0 |  | checklist | Stairs (in-situ) |  |  |  |  | Yes | Stairs (in-situ) Checklist | fe80471b-b5eb-4133-b0e9-4ed224b2f8f5
checkpoint-group | 55191384-85bd-4256-9b98-e9803c69f4a1 |  | section | Phase 1
checkpoint-status | abda07da-81b8-4c20-a0bf-26c7a54a143a |  | checkpoint | Area accessible & ready
checkpoint-status | e9f91665-70e7-4d9e-8755-7aec16a9271b |  | checkpoint | Drawing references entered
text | 5f0e3c54-2ec0-51f1-9922-c37d51135b94 |  | textbox | Architectural
text | 7cf5aaeb-52f8-520b-9fb1-7151aa36292e |  | textbox | Structural
text | 440864ad-6f9d-5f4a-b4db-ab0cfc709838 |  | textbox | Other
checkpoint-status | 5cc1080a-6c6a-41ef-befe-f4ef2cd5855d |  | checkpoint | Current plans in use
checkpoint-status | 4d32f390-c3b0-4522-a39b-1c8ba830e88f |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | 11578ab8-1b79-426a-b73a-2d21ae5fb1ea |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | d49de26c-861c-4db9-9f2f-aaf2f7b6e8b8 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | eeacb3d5-f473-4a1e-ad47-c2af95fcd78e |  | checkpoint | Base of stairs cleaned
checkpoint-status | cdce2730-4da4-42e2-97e9-59bc01658646 |  | checkpoint | Riser heights confirmed
checkpoint-status | 85fdfbd0-495d-4283-83b0-4d5b2cc0aee8 |  | checkpoint | Going lengths confirmed
checkpoint-status | b8388778-46f1-418e-8c81-22264bc1123a |  | checkpoint | Correct Class of Finish
checkpoint-group | ea437886-f364-41e8-8ecd-22cfbd6fbb0c |  | section | Phase 2
checkpoint-status | 64e84d8b-777e-43d0-9cc0-4d2f9a548f9f |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | dc37faca-62d8-4e66-91fa-221bba573ab7 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | adbe448c-115c-4a96-9215-61f82567604e |  | checkpoint | Base of stairs cleaned
checkpoint-status | 424c55ec-3d9e-4501-a846-8911cf49e010 |  | checkpoint | Riser heights confirmed
checkpoint-status | 710413ef-205f-4337-b5d8-a2dbc4e337f6 |  | checkpoint | Going lengths confirmed
checkpoint-status | 5dffe8ca-67e7-4a13-a71d-86d09a27b94e |  | checkpoint | Correct Class of Finish