## Dermafil (Concrete Lid)
type | name | values | prefix | postfix | usage count
checklist-flat | Torch-On Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
button | Substrate free from pooling or ponding water | Yes,No
button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
button | Adequate fall in substrate | Yes,No
checkpoint | Priming
label | Record batch numbers
button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
button | Primer given adequate time to cure as per manufacturers specification | Yes,No
button | Area completed and suitable for membrane application - photos attached below | Yes,No
checkpoint | Dermafil Installation
label | Record batch numbers
button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
button | Termination pressure bar installed where required - photos attached below | Yes,No
checkpoint | ILD Testing
button | ILD test requested | Yes,No
button | ILD test performed | Yes,No
text | Any rectifications performed
button | ILD test report issued | Yes,No
checkpoint | Protection
button | Casali Protector installed - photos attached below | Yes,No
checkpoint | Area completed to manufacturer's specification - photos attached below
label | Attach Client Signature Below

## Eradix (Backfilled Downturns)
type | name | values | prefix | postfix | usage count
checklist-flat | Torch-On Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Diaphragm Wall Preparation
button | Transition compound to D-Wall installed as per manufacturer's specification | Yes,No
checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
checkpoint | Priming
label | Record batch numbers
button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
button | Primer given adequate time to cure as per manufacturers specification | Yes,No
button | Area completed and suitable for membrane application - photos attached below | Yes,No
checkpoint | Eradix Installation
label | Record batch numbers
button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
button | Termination pressure bar installed where required- photos attached below | Yes,No
checkpoint | ILD Testing
button | ILD test requested | Yes,No
button | ILD test performed | Yes,No
text | Any rectifications performed
button | ILD test report issued | Yes,No
checkpoint | Protection
button | Casali Protector installed - photos attached below | Yes,No
checkpoint | Area completed to manufacturer's specification - photos attached below
label | Attach Client Signature Below