## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 29f5dd57-1f81-4fe4-a637-bd2f58ded404 |  | checklist | ITP 4 - Set Out - Penetrations & Fire Collars |  |  |  |  | Yes | ITP 4 - Set Out - Penetrations & Fire Collars | d07175d4-ef3c-4fc1-9868-2411295448fe
checkpoint-group | 8e36b4a9-e961-453f-907a-c1516d3ef7d6 |  | section | Survey & Set Out Works
checkpoint-status | 414ea9bc-0998-4a38-a1dd-c5fa6e0bbae1 |  | checkpoint | Take dimensions off drawings and record any remarks / deviations prior to installing
select | e2a0f185-8c88-5ccc-a4d8-28e66da8b01a |  | dropdown | Set Out | Survey Plotted, Manual Set Out
checkpoint-status | fbf9b0d8-ae3e-42f7-80ad-f8a09b352518 |  | checkpoint | Photo of title block to include drawing number & revision
checkpoint-group | e70fa68b-8354-46d3-b628-b67a693d2691 |  | section | Structural Interface
checkpoint-status | 3f03edb9-e433-49f7-b34b-048f069a10cc |  | checkpoint | Consult structural drawings to ensure no structural effect with penetration or cast in position
checkpoint-status | 7ff081e6-679f-45fd-97ad-ba80b61791ad |  | checkpoint | Ensure pipework within set downs and beams are cast in/out of set downs where required and indicated on penetration drawings
checkpoint-status | dc235f9f-6674-4bd0-8a22-a292f0f397eb |  | checkpoint | Check that penetration does not clash with elements downstairs e.g. Walls, Beams ETC
checkpoint-group | 638dae63-3433-4f5c-adbd-c8aecfea1de1 |  | section | Fire Collar Installation
checkpoint-status | 78e5c5b4-4a20-4770-9148-e6b23f7a80ba |  | checkpoint | Ensure that fire collar is installed as per manufacturer's specifications and is spatially acceptable
select | c451ad52-c729-58bb-b461-b9ffd412787d |  | dropdown | Fire Collar Type | Promat, Snap, Hilti, Other
checkpoint-group | 6b6ae843-e529-4553-a6b6-7827b75fb899 |  | section | Pipe Insertion to Collars
checkpoint-status | e1b7708f-51e0-46ef-8501-41efd0a0ea93 |  | checkpoint | Ensure pipe is fitted correctly
checkpoint-status | b5841c9b-567a-440a-8eed-67f8f1681033 |  | checkpoint | Ensure pipe is fitted to maximise the efficiency of the next sequence of work e.g. Pipe is easy to knock through
checkpoint-group | 983d972b-3ae9-44d7-9033-021c6957a85c |  | section | Cast in Conduits
checkpoint-status | 9ab77cc6-459f-486d-bdb8-79d08d640758 |  | checkpoint | Ensure conduit is within wall or carcass range
checkpoint-status | 77e2e370-d490-4694-b0ba-e61860f1dedd |  | checkpoint | Use 15/45 degree bends on all changes in direction
checkpoint-group | 6dc6353b-f3cb-4012-b7f3-0f331b4f2c1b |  | section | Cast in Balcony Outlets
checkpoint-status | ad5ad629-3eb5-4505-8d45-291a8e4fc5f1 |  | checkpoint | Ensure pipe is supported correctly without affecting balcony soffit
checkpoint-status | a0cf4e15-505f-468c-a1af-1a6df741eee7 |  | checkpoint | Ensure pipes are not damaged after top steel and set downs are installed.
checkpoint-group | cd4a095a-933b-4383-a938-4e725e7e545b |  | section | Safewaste or Puddle Flange Installation
checkpoint-status | ff71b9db-ea90-49fc-9d1f-4419206a98b8 |  | checkpoint | Ensure safewaste or puddle flange is installed to all required outlets
checkpoint-status | 238dd3da-389d-45ca-b164-70e20467e6f7 |  | checkpoint | Ensure safewaste or puddle flange is installed to the correct height
checkpoint-status | 31442896-8c9f-4cf2-a8f8-c51ea7a789e8 |  | checkpoint | Spray all floor wastes to identify falls
checkpoint-group | f18f7cda-bdf5-440e-9ddb-78772d7793b3 |  | section | All Pipes & Casting Capped & Supported
checkpoint-status | b8ed855e-dacf-4574-ad2d-2175d3e53365 |  | checkpoint | Ensure no open ends by installing dust cap or duct tape on risers
checkpoint-group | c923537f-5cc2-4aee-9a60-6604831592f4 |  | section | Pipe Sleeves
checkpoint-status | bde050d6-7bed-49be-8f98-539976224da3 |  | checkpoint | Ensure all sleeves installed in in situ walls at the correct height
checkpoint-group | 218dbe17-9d3f-4dc5-b74c-52ca5ef22c01 |  | section | Castin Downpipes
checkpoint-status | 7998b18b-1738-458e-bd0f-744f6b3a73bb |  | checkpoint | Ensure pipes are clear of any obstructions prior to extending riser
checkpoint-status | 5c96aa6e-6526-4f65-a27a-56710f76ab21 |  | checkpoint | Ensure pipe is fitted correctly where agreed by structural engineer
checkpoint-status | 7bdb1945-f1fc-4805-8b9c-c5f7ca47c4f2 |  | checkpoint | Ensure pipes are wrapped where required
checkpoint-status | 718e855b-526a-4e17-bcd9-081abe76e881 |  | checkpoint | Ensure downpipes capped and taped to riser
checkpoint-status | 1d613844-593e-4e49-ae31-b7f53d794a9e |  | checkpoint | Ensure pipe is filled with water for concrete pour where required
checkpoint-group | cf5fa9d7-1c95-4079-af34-f2944083c35b |  | section | Inspect Pipework
checkpoint-status | 3fbd2ace-6de3-421d-9094-736195dd6a28 |  | checkpoint | Complete all required inspections by third parties (client, authorities, builder, etc)
holdpoint | d8faf36f-c2b2-432e-bad2-9484f86e5727 |  | signoff | Work verified by Scentre Group
checkpoint-group | ad351670-11e0-4e90-b9b3-92754f9fb0a4 |  | section | Photos
checkpoint-status | e3119fb7-3d7f-40c3-83c7-8992409ee6da |  | checkpoint | Ensure photos are taken of entire installation inc fire collars and casting prior to concrete pour
checkpoint-status | 28b1c209-2e02-4eec-b367-054f4e4c25ca |  | checkpoint | Works verified as conforming (McPherson Plumbing Representative) Name: