## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Excavation & Shoring (V140421) |  |  |  |  | Yes | Excavation & Shoring (V140421) | 04530aab-0bc8-416f-84d5-85519be86bdd
checkpoint-group |  |  | section | Shoring
checkpoint-status |  |  | checkpoint | Locate all existing services
checkpoint-status |  |  | checkpoint | Confirm set out - Ensuring piling/spring remains within inside boundary
checkpoint-status |  |  | checkpoint | Confirm any vibration limitations/requirements
checkpoint-status |  |  | checkpoint | Confirm boundary set back to shoring wall
button | 45f10ccd-5bd6-5697-b3ac-fe82025ae5ee |  | button | RL levels to top of shoring wall confirmed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Confirm de-stressing procedure for anchors with engineer
label | abd0d55b-7f1c-57d3-a7be-4b6c165bdec2 |  | note | Engineer procedure notes added below
checkpoint-status |  |  | checkpoint | Confirm level of excavation aligns with shoring wall levels/location
checkpoint-group |  |  | section | Excavation - Pre-Commencement
checkpoint-status |  |  | checkpoint | Confirm dial before you dig documents are onsite - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm correct disposal of classified material
checkpoint-status |  |  | checkpoint | Obtain geotech report, including load bearing capacity
label | e904a2b0-e4b1-5122-b205-a841841f42b0 |  | note | Geotech report referenced or attached below
checkpoint-group |  |  | section | Excavation Works
checkpoint-status |  |  | checkpoint | Collection of tip dockets - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm set out of boundaries & marked out
checkpoint-status |  |  | checkpoint | Confirm actual RL is within design tolerance
button | 1e0c5ee5-fdc1-5181-aeea-bd7996a04598 |  | button | Confirm set out of footings and pads | Yes, No, N/A
button | 9da68205-1286-58e0-b642-5b00a198edea |  | button | Confirm set out of in ground drainage | Yes, No, N/A
label | 01d8afbe-58e3-5a0b-9128-077de155f2a6 |  | note | Excavation of footings not to exceed size as detailed on structural drawings
checkpoint-status |  |  | checkpoint | Certifier to inspect foundation in accordance with specifications
checkpoint-status |  |  | checkpoint | Geotech inspection of footings etc
label | 8c510e5f-4e72-5db7-949f-97932139ce8c |  | note | Geotech report referenced or attached below
checkpoint-status |  |  | checkpoint | Confirm top of concrete footings is below surrounding finishes
checkpoint-status |  |  | checkpoint | Confirm sub-base is in line with engineers specifications/requirements
text | 003531a2-f571-582f-b2d5-39deba4cf4a2 |  | textbox | Minimum thickening (MM)
checkpoint-status |  |  | checkpoint | Civil engineer inspection carried out - Attached below as applicable
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | c5cdcd89-1413-51d0-80c5-2a97570d246d |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 87c74fea-1299-502f-8399-a4f5f458f910 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Ground Beams |  |  |  |  | Yes | Ground Beams | 157e3e98-2606-45b3-85fa-876c7ddbb681
checkpoint-status |  |  | checkpoint | Any services (overhead/below ground) considered & isolated if required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation - depths and locations confirmed prior commencement
button | acc4c548-d948-5793-9598-2689eaad8b62 |  | button | Footing RL Confirmed | Yes, No, N/A
button | 1a0e8308-2450-5ffd-9e3a-a8a170bde876 |  | button | Any services (overhead / below ground) considered and isolated where required before excavation commences | Yes, No, N/A
button | 7f229a6b-a7b1-565c-94f6-aae8e6ce8712 |  | button | Approval given to commence detailed excavation | Yes, No, N/A
button | c61c7b0e-8373-592b-a879-a168d4f51b52 |  | button | Excavation checked, correct and approved | Yes, No, N/A
button | b788610e-6107-50ac-801d-dd74da7828c2 |  | button | Depth correct (allow for site concrete if required) | Yes, No, N/A
button | 40fee61b-53a0-5dcd-b591-1aaba1582af8 |  | button | Width correct (allow for boxing if required) | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Formwork correctly Installed
button | eace45d7-812b-5dad-b5cd-cd5dc37a078c |  | button | Set out - correct levels | Yes, No, N/A
button | 9ea95ba0-8084-5aff-8e19-4d7cbf3c54da |  | button | Inserts, pockets, fixings, rebates etc | Yes, No, N/A
button | eb41eddf-8d5b-5170-a3fd-c26f6c7403f3 |  | button | Bracing, Fixing Propping & Supports | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Reinforcement installed as per plan including cover & chairs
button | 9160da4d-95b2-5d81-9c3a-1db1ce182239 |  | button | Reo spacing & grade as per specifications | Yes, No, N/A
button | 464a2576-e1a7-5aa0-9b1a-a1c6480d080d |  | button | Starter bars, dowel bars, & mesh installed as per specifications | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Concrete strength/ Slump confirmed
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Final sign off - All ground beams completed as per the above ITP - Add general photos/comments below
label | 465a9b2e-b831-51c0-b1a0-5c1f63ea1960 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Framing |  |  |  |  | Yes | Framing | 16f1a523-acf7-46ea-9814-4cbc2dbf54fb
checkpoint-status |  |  | checkpoint | All studs are set out correct, and are plumb level and square
checkpoint-status |  |  | checkpoint | All studs are installed as per manufacturer's recommendations and the BCA
checkpoint-status |  |  | checkpoint | All noggins are installed correctly
checkpoint-status |  |  | checkpoint | All sarking has been installed as per manufacturers recommendations
checkpoint-status |  |  | checkpoint | Penetration through fire rated wall have been treated
checkpoint-status |  |  | checkpoint | Door frames have been installed plumb level, square and in wind
checkpoint-status |  |  | checkpoint | All window and sliding door openings are as per plan and line up with above elements
checkpoint-status |  |  | checkpoint | All studs are level and in wind
checkpoint-status |  |  | checkpoint | All internal walls have been studded out and are as per plan
checkpoint-status |  |  | checkpoint | Weep holes have been installed correctly and at right height
checkpoint-status |  |  | checkpoint | Door frames to be infilled
checkpoint-status |  |  | checkpoint | Insulation installed as per AS/BCA (party walls & external)
checkpoint-status |  |  | checkpoint | Acoustic practices to be as per Australian Standards & BCA
checkpoint-status |  |  | checkpoint | Final sign off - All framing work completed as per the above ITP
label | 4bbaf11d-cb90-5574-a364-455010688591 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Capping Beam (V140421) |  |  |  |  | Yes | Capping Beam (V140421) | 1beb21d7-3d8d-473f-87bf-aee196d0fffc
checkpoint-group |  |  | section | Prior to Capping Beam Operations
checkpoint-status |  |  | checkpoint | Confirm RL’s of capping beam
button | 69bbc2b1-1834-5600-806c-2da990e190e6 |  | button | Confirm excavation for capping beam has been complete and ready for formwork to commence | Yes, No, N/A
button | eb049e00-c240-518a-bc62-e5800661f562 |  | button | Set out of capping beam complete | Yes, No, N/A
button | c149d449-33c4-58ae-b967-7db68307dd79 |  | button | Confirm engineers design of capping beam | Yes, No, N/A
label | ba6b5903-4559-563e-a02f-accdb1c270a1 |  | note | Attached/referenced below as applicable
checkpoint-status |  |  | checkpoint | Attach structural engineer inspection prior to concrete pour (All items closed out)
label | fa18ed97-9bce-504c-ad88-a6b196d53214 |  | note | Engineer inspections attached/referenced below
checkpoint-status |  |  | checkpoint | Concrete pre-pour checks - As per below
button | 1b6d2af5-95dd-51b3-ac5d-e196377eb003 |  | button | Confirm mPa, slump and agg size of concrete prior to ordering | Yes, No, N/A
button | 089da3c7-ec7b-551d-8970-b74c90005bfb |  | button | Confirm formwork faces are clean and will provide required class finish | Yes, No, N/A
button | 61c0b166-e2f7-5402-8dcf-f1d27c8eb0a7 |  | button | Confirm formwork is adequately braced to reduce blow-out occurrence | Yes, No, N/A
button | f02201f9-de3a-5e88-8b7f-99b91ea865c0 |  | button | Confirm pile connection bars are clean and free of debris | Yes, No, N/A
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group |  |  | section | After Capping Beam Poured
checkpoint-status |  |  | checkpoint | Attach surveyors spot check – Confirm tolerance of finished concrete surfaces – Ensure no movement to the capping beam during pour
label | 167a6a00-71e2-5172-9662-af342c3b0aaf |  | note | Confirm surveyor spot checks levels and attach markup
checkpoint-status |  |  | checkpoint | Confirm stripping is complete All exposed faces are clear of formwork
button | 676d445f-f586-5460-880f-120211c654d2 |  | button | Confirm vibration was adequate – no air pockets, agg evenly distributed If not, comment rectification method required | Yes, No, N/A
button | f7982d84-d55c-5fe7-86c8-4028d8c8cf4e |  | button | Confirm no blow-out occurred If occurred, comment rectification method required | Yes, No, N/A
button | ec616e66-95f7-50cf-a729-e8839ab7d7ca |  | button | Confirm finish of concrete is adequate (broom/trowel/helicopter finish) | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day
text | 2ff400c8-90cb-5ddb-b941-04b520e800ee |  | textbox | Test Strength Mpa
label | 063c9b32-e9b2-5be2-aa85-a49c9be6ed24 |  | note | Attach concrete test result
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 days
text | eda54071-399f-5aba-915a-9d591908eaa0 |  | textbox | Test Strength Mpa
label | 6f1ab64d-c057-5564-bf96-5035b92a06a9 |  | note | Attach concrete test result
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 days
text | 32f1c07d-95a8-5dcb-812f-359a9bf890a1 |  | textbox | Test Strength Mpa
label | 2b119396-0e00-52a1-9e97-3e63fb53514d |  | note | Attach concrete test result
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | bc2579a5-f254-5e9e-9290-3a9c7f693458 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 93db0405-261b-54a6-9b82-44227a14d467 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Pre Wall Linings |  |  |  |  | Yes | Pre Wall Linings | 1d9fde2e-354b-4152-bfd0-38eca87591d5
checkpoint-status |  |  | checkpoint | Ensure FER, FEBQ & alternate solution reports have been read & requirements complied with
button | 50999600-c9ad-51d9-beca-e294e185aca2 |  | button | Ensure all penetrations have been installed at a 90 degree | Yes, No
button | 94576a6b-aa52-526f-abf1-62ee91e76d5e |  | button | Ensure all penetrating pipes fire collars are installed in accordance with C3.15 of the BCA | Yes, No
button | df001cf1-b289-5d10-95ce-d8d127357f36 |  | button | Ensure all penetrating floor waste pipes have floor waste fire collars installed in accordance with C3.15 of the BCA | Yes, No
button | 56d73c5b-cc86-5299-84ac-18d56ca160fd |  | button | Ensure that penetrations around fire hydrant pipes have been filled | Yes, No
button | 9ed9c05e-516b-5def-815a-32cdba27eba7 |  | button | Remove redundant fire collars | Yes, No
button | 1c7f451d-8621-568f-8765-7822be5e281d |  | button | Fill redundant Penetrations with concrete (min 200mm Thick) | Yes, No
checkpoint-status |  |  | checkpoint | Ensure all copper pipes & hydrant pipes have been insulated when passing thru a fire collar in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications & clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint-status |  |  | checkpoint | Ensure that suitable access is provided to mechanical fire dampers in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure that services within the fire stairs are boxed out with a two way fire rated system (where required)
checkpoint-status |  |  | checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure that NBN collars have been installed with grafitex on both sides of the hebel walls in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Check that PEX pipes are adequately sealed in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Check that fire doors have been filled
checkpoint-status |  |  | checkpoint | Final sign off - All pre wall linings work completed as per the above ITP
label | 47af364c-530e-577e-ad14-52e8149f2f6e |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Courtyard Surfaces ITP |  |  |  |  | Yes | Courtyard Surfaces ITP | 1e79e095-e451-4273-baf4-36928f0e4b60
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | ae388c2b-5d6d-591f-8b6a-91b06707b9f7 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application "No access waterproofing work in progress"
label | 4ad49702-d5d6-5b95-b415-edb3485c6d75 |  | note | Attach relevant photos below
button | ed2352d9-95d4-5d03-a5d0-e17b67dd850d |  | button | Membrane system & methodology checked off AGainst Aland standard | Yes, No
button | b4455298-40dd-5a23-8239-317ac9d09a0d |  | button | Surface preparation as per application guide | Yes, No
checkpoint-status |  |  | checkpoint | Substrate clean, dry & free from dust
button | 779bdb0c-53d0-5961-885d-780fcfd01d5d |  | button | Ensure no high points or crevices are in the substrate | Yes, No
button | 1315c5af-c764-5e5e-8204-5cb3e5bf01cf |  | button | Ensure substrate is structurally sound & ready to receive membrane | Yes, No
button | ecc19266-7fb0-58a3-adbb-03b6185bc2ca |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to primer | Yes, No
label | 5be0c7ca-539e-5e41-9b74-9acbac305faa |  | note | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint-status |  |  | checkpoint | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
label | 92c9e099-eb6f-584e-89ed-192f7709e5a2 |  | note | (PrimeSeal MC to all surfaces at a rate of 3‐4m2/Ltr ‐Alternative primers Multiseal ‐ Primeseal SP at a rate of 5‐8 m2/Ltr)
checkpoint-status |  |  | checkpoint | All corners, joints, gaps & cracks to be treated with a flexible polyurethane sealant resiflex FC
label | dcb42f99-c2d0-5bfa-86f8-80fe87a03759 |  | note | Apply selected Membrane as per datasheet & application guidelines Ensure sealant has fully cured before installing membrane
checkpoint-status |  |  | checkpoint | Ensure Humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to first coat
checkpoint-status |  |  | checkpoint | First coat of selected Membrane to entire areas as per DURAM recommendations
label | ae9265c3-5b30-5c10-ba79-b7575d9b97d3 |  | note | Note A total dry film thickness of min 12mm (1200 microns) in two finished coats As such at min
label | 006bb2d1-74ad-5e4c-b070-70d4d8452d73 |  | note | Wet Film Thickness of min 075mm (750 microns) per coat is required ‐ Apply membrane at a coverage of 075 ‐ 1 Ltr / m2 per coat
button | aec98501-e5d8-5b41-a6c6-92bf20407ef4 |  | button | Allowing the membrane coat to dry min 12 hours check the tackiness before applying next coat | Yes, No
button | bb0f3bd6-5242-5115-b4c6-dd1ae38e4fb7 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to second coat | Yes, No
checkpoint-status |  |  | checkpoint | Second coat of selected Membrane to entire areas as per DURAM recommendations
label | 3f833130-ec0f-5d4e-9902-9cba2f74f503 |  | note | Note ‐ a total dry film thickness of min 12mm (1200 microns) in two finished coats As such at min
label | e5815bc6-b2f6-591f-906c-c595d182b063 |  | note | Wet Film Thickness of min 075mm (750 microns) per coat is required ‐ Apply membrane at a coverage of 075 ‐ 1 Ltr / m2 per coat
button | 97cf3f00-ac92-5261-9629-b023715f8a70 |  | button | The membrane is to be applied in a minimum of 2 coats at a total coverage of 12 to 2 litres per m2 or relevant product TDS 12 to 2 litres per m2 or relevant product TDS | Yes, No
button | 94ed4a38-7baa-5ba2-9a7d-e902395f1b9d |  | button | Allow 2nd coat of Multithane UV min 12 hours but no longer than 24 hours before installing Multithane ATC top coat | Yes, No
button | 564672f4-6223-5a74-bf9b-712cfc50d5e8 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to final coat | Yes, No
checkpoint-status |  |  | checkpoint | Apply final coat of Multithane ATC at a coverage rate of 3 ‐ 4 m2/ltr
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instrument
checkpoint-status |  |  | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | c5af1bc6-0ace-5093-b755-5da309fc03a9 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checkpoint-group |  |  | section | Surface Finish & Sign Off
checkpoint-status |  |  | checkpoint | Wastes installed correctly to specification (Correct height / level/ location)
boolean | ee9fd917-9414-5a70-b376-2c9bf7c0a37d |  | tickbox | Waterproofer pushes sponge down 100mm and finishes his membrane & flood test
boolean | 0ed163a3-0f56-5985-8526-fd94ceddb0b3 |  | tickbox | Waterproofer removes sponge and releases water and puts the sponge back in ensuring there are no debris left in the pipe
boolean | be24c949-da5e-53bd-a73f-a045f9435c50 |  | tickbox | Aland cleans and removes the sponge
checkpoint-status |  |  | checkpoint | Waterproofing membrane completed and ready for Pebble Washed Aggregate topper
checkpoint-status |  |  | checkpoint | Pebble surface installed to specification(s) - Correct level and finish
label | 032fdeb9-8f65-50bb-880b-e699de27962a |  | note | Attach photos /comments below
checkpoint-status |  |  | checkpoint | Final Sign Off - All courtyard works completed to specification and as per above ITP
label | cefa66fc-2201-5d8b-999e-c9d471ce8398 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Shotcrete |  |  |  |  | Yes | Shotcrete | 2188b37d-0340-4d17-8800-bdea53a2f01a
checkpoint-group |  |  | section | Pre - Spray
checkpoint-status |  |  | checkpoint | Ensure services/drainage correctly installed
checkpoint-status |  |  | checkpoint | Location of spray & heights checked and confirmed
checkpoint-status |  |  | checkpoint | Starter bars installed correctly
checkpoint-status |  |  | checkpoint | Correct mesh installed to meet required specification
checkpoint-status |  |  | checkpoint | Covers checked and acceptable for respective area
checkpoint-group |  |  | section | Shotcrete Spray
checkpoint-status |  |  | checkpoint | Correct concrete delivered, attach delivery dockets
checkpoint-status |  |  | checkpoint | Spray application correct & spoil removed
checkpoint-status |  |  | checkpoint | Spray completed and required finish achieved - correct heights achieved
checkpoint-status |  |  | checkpoint | Final sign off - All shotcrete completed as per the above ITP - Add general photos/comments below
label | dc16ffa7-4107-5ec8-b293-ddf4abc73be6 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Grease Arrestor Room (v040521) |  |  |  |  | Yes | Grease Arrestor Room (v040521) | 229f9490-9654-44f0-be22-be367459a0eb
checkpoint-status |  |  | checkpoint | Ensure grease arrestors are installed as per plans
checkpoint-status |  |  | checkpoint | Isolation valves installed on all grease arrestors
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service, no damage to external board has occurred during installation
button | 78250e66-d55b-5cc9-9a2f-2afee20997b1 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | 9119bf0c-5db1-5a76-889c-5e9f95b96016 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 2d56b9d4-a8a9-5382-bbf3-ed0d5613d06f |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | e5b5f675-605c-5e15-89c8-c4b120ea09a3 |  | button | Cables are labelled as per specified requirements | Yes, No
button | c39084f3-5da4-5e92-97b7-2f33f278351f |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | 9cbba3c3-af16-539d-a9f1-9d05d368281b |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Ensure adequate ventilation fans have been installed and are functioning correctly
checkpoint-status |  |  | checkpoint | Final sign off - Grease arrestors installed as per the above ITP - Add general photos/comments below
label | 23d3e17e-6096-5929-b832-0a4ed287475f |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Blade Walls (Ability to Add) |  |  |  |  | Yes | Blade Walls (Ability to Add) | 23639f4b-2d0f-4968-b9f6-563950a075c5
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | cebdbb98-2856-59ec-acbe-35462e8991d8 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Survey points given for 2 points
checkpoint-status |  |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status |  |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status |  |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status |  |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status |  |  | checkpoint | Couplers & rebate boards installed
checkpoint-status |  |  | checkpoint | Base of walls cleaned
checkpoint-status |  |  | checkpoint | Closing shutter installed
checkpoint-status |  |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status |  |  | checkpoint | Correct Class of Finish
checkpoint-status |  |  | checkpoint | Final sign off - Walls completed as per the above ITP - Add general photos/comments below
checklist-flat |  |  | checklist | Carpet |  |  |  |  | Yes | Carpet | 2576e906-7f3b-475b-a219-a0cbb747c259
checkpoint-status |  |  | checkpoint | Correct underlay installed to specification(s)
checkpoint-status |  |  | checkpoint | Correct carpet (Colour & Type) installed to Specification(s)
checkpoint-status |  |  | checkpoint | Carpet installed as per manufacturer's instructions
label | 4b9d445e-a753-58fe-a8f8-324695aab09b |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Commissioning Documentation |  |  |  |  | Yes | Commissioning Documentation | 269be151-ed9f-4fba-bde6-7195bb73e7f2
checkpoint-status |  |  | checkpoint | Commissioning documentation attached below
text | 9382b984-b171-5409-8ca5-21f2c2bbaf7f |  | textbox | Company Documentation relates to
checklist-flat |  |  | checklist | Rain Water Pump Room (v040521) |  |  |  |  | Yes | Rain Water Pump Room (v040521) | 2c906582-4dd7-46d9-bb0a-e1a41b53e19d
checkpoint-status |  |  | checkpoint | Ensure rain water pumps are installed as per plans
checkpoint-status |  |  | checkpoint | Pump isolation valves installed on all pumps
checkpoint-status |  |  | checkpoint | All pipe work tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service, no damage to external board has occurred during installation
button | b31cda65-9073-5ac1-8c10-af98313fdbea |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | 425ad8d8-cef6-50ea-8b0f-63d532527317 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | ad75470e-1e95-58d1-8a5c-83b6e675aad9 |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | d8757407-100b-5824-a0bb-6cb662093ac3 |  | button | Cables are labelled as per specified requirements | Yes, No
button | e7cd6769-e3d7-5c89-9ee5-b2df78938aa1 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | d5520a6a-fc58-5b52-aeda-d98efbd8ef79 |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Final sign off - Rain water pumps installed as per the above ITP - Add general photos/comments below
label | c39ebdd5-bd40-5caa-822a-cbc050ae9d8b |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | In-Ground Sewer ITP (V140421) |  |  |  |  | Yes | In-Ground Sewer ITP (V140421) | 2fb8dc1a-5055-479f-ad04-bd5ac4c5cfb6
checkpoint-group |  |  | section | Pits and Pipes
checkpoint-status |  |  | checkpoint | Is Approval from Local Water Authority Required If so please provide permit
holdpoint |  |  | signoff | Sign Off Required
checkpoint-status |  |  | checkpoint | Details
text | 6b20a615-653c-52c2-85f3-109042fc8c51 |  | textbox | Engineering plan number(s)
text | 1a0198f3-bc02-5939-82b4-647d37c5f04d |  | textbox | Name of certified drainlayer
text | acef9c98-d6d5-5a93-b941-7c07739b19b1 |  | textbox | Location (pit to pit)
text | 92799a73-34be-5bb5-9a87-c7a5db298cdb |  | textbox | Delivery Date (Pits and Pipes)
text | 2b338a74-18f4-5166-8c4f-963b759eec6e |  | textbox | Is work area clear and available for construction
text | cf94d4e8-a4d9-5c4a-83b2-eca086b50731 |  | textbox | Do you have the appropriate plant / equitment to perform scope of works Provide details
checkpoint-group |  |  | section | Trench / Excavation Methodology
checkpoint-status |  |  | checkpoint | Method
boolean | 6355bfe1-f08a-59ba-aae0-9b0382d221d5 |  | tickbox | Shield
boolean | cfb96554-aa25-58ea-b8b2-bbab8a5494c7 |  | tickbox | Bench
boolean | 2515da93-377e-5d30-b304-dffcdf4a408e |  | tickbox | Batter
boolean | b0843d5d-941d-5761-ac8d-a9607ee9da50 |  | tickbox | Other
text | de60d5d2-92c9-57dc-96fb-3a73468bbf7d |  | textbox | If other, please specify
boolean | 37ce299c-d367-5a94-911a-046eeb0803ca |  | tickbox | Certified / Tagged lifting Equitment
checkpoint-group |  |  | section | Product / Material check
checkpoint-status |  |  | checkpoint | Pits
text | afe9e63e-886d-56f4-b322-122eeaa1e465 |  | textbox | Type
text | b1e866e6-fa13-5ee0-919d-50e50e867395 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Pipes
text | d8d1fb81-7162-59d2-8065-7a88696d4f77 |  | textbox | Type
text | 9fb6dd1a-2062-586a-a537-e4c253ae5c3d |  | textbox | Size
checkpoint-status |  |  | checkpoint | Lot / Building Connections
text | 8de1d7ed-184c-5d86-9b77-c2d511d57e13 |  | textbox | Type
text | 9a8349c1-7563-5fe8-b2ac-595fc49e12e1 |  | textbox | Lot number location
checkpoint-status |  |  | checkpoint | Bends
text | 2f8f9b75-ead7-5a16-9c89-a56d58f5af7e |  | textbox | Type
text | b2cf33e9-3868-5abb-8e1c-8c809d504068 |  | textbox | Size
text | a439cc6e-4ae3-5591-a422-3b914a506591 |  | textbox | Location
checkpoint-status |  |  | checkpoint | Quality Onsite Visual Inpection of Products/Materials - Defects to be Notified
text | 8132388c-7df7-5015-bdb0-b44cffc9edaf |  | textbox | Surveyors name
checkpoint-status |  |  | checkpoint | Set out / Off Set Check
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pit Installation
checkpoint-status |  |  | checkpoint | Pits
text | 6b4b1fc3-06a9-536f-aa00-e886539eca62 |  | textbox | Bedding and backfill type as per detail
text | 28a1ca36-b1b9-5281-b08c-c3b112beec38 |  | textbox | If under cutting required, note metreage and depth ( Approval Required)
boolean | 2f30eed4-eb15-5905-b9b8-8e147b1fccd8 |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
boolean | a95b33d8-69df-53c8-9c7b-118f04246d76 |  | tickbox | External Concrete Bandage
boolean | d625458f-62b4-5b46-bd40-1e411ef6362c |  | tickbox | Internal Benching
boolean | 8878db82-d250-5f0c-9898-fc35212edb13 |  | tickbox | Internal Plastering / Render / Sealent
boolean | 840a2856-cbab-514c-8b48-f134afb59a5b |  | tickbox | Sealant Between Riser
boolean | c1d3e13a-4c6d-5440-8fae-9d52471dc091 |  | tickbox | Steps Required
text | a1227c74-3ae1-5c43-b439-81fb585eb20a |  | textbox | Have pits been secured and covered through the construction phase to elemenate debris/silt
text | 7e0af5b0-1a9b-5665-a1a8-c8afbc690abb |  | textbox | Pressure testing
checkpoint-status |  |  | checkpoint | Pipe invert levels through pit as per design
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pipe Installation
checkpoint-status |  |  | checkpoint | Pipes
text | 185b27ed-00c3-52ac-8bc6-148d5fbae701 |  | textbox | Are pipes free and clean of debris before installation
text | 4270bd7a-36fb-5381-b264-70ffcc3b38f6 |  | textbox | Bedding and backfill type as per detail
text | c657be21-d6f3-53db-b9e7-3eccccc43d32 |  | textbox | If under cutting required, note metreage and depth ( Approval Required)
boolean | 7b321e96-3d3b-5be9-be46-e5b6c1375f30 |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
checkpoint-group |  |  | section | Drainage Check
checkpoint-status |  |  | checkpoint | Backfill to be compacted in 150mm Layers as per detail
text | 29a68306-b103-531e-a998-4a5e02849b08 |  | textbox | Grade and Alignment Check
text | c8c01ca4-831e-5e51-9438-e5bff8f8468e |  | textbox | As-built measurements / Pick up Recorded Before Backfilling
text | 0a619345-ced5-598b-80fe-950d0f6339af |  | textbox | Invert/ RL check
text | f456cecc-514b-5d88-a4fe-405447326690 |  | textbox | Pressure Testing
text | ea5f52fd-f873-565f-8c31-aade12bd63f6 |  | textbox | CCTV Pipe Inspection / data and comments supplied
checkpoint-status |  |  | checkpoint | Progress Photos
checkpoint-group |  |  | section | Service Connections
checkpoint-status |  |  | checkpoint | All Connections, Bends, Junctions installed
text | d02ea922-fe27-5b51-8e28-b6cf782e4e1d |  | textbox | As-built measurements / Pick up Recorded Before Backfilling
holdpoint |  |  | signoff | Sign Off Required
checklist-sectioned |  |  | checklist | Pad Footings, Strip Footings, Lift Pits & Piles (V140421) |  |  |  |  | Yes | Pad Footings, Strip Footings, Lift Pits & Piles (V140421) | 330fc5c2-c80c-4725-a1d4-f5ae5f13e80d
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Attach mark-up plan
checkpoint-status |  |  | checkpoint | Confirm RL of sub-base
checkpoint-status |  |  | checkpoint | Confirm position of footing is in accordance with architectural setout design
checkpoint-status |  |  | checkpoint | Confirm starter bars to columns and walls installed in correct location
checkpoint-status |  |  | checkpoint | Check for reinforcement cover as per structural documents (especially at steps and ramps)
checkpoint-status |  |  | checkpoint | Obtain certificate from Structural Engineer and Geotechnical Engineer prior to concrete pour Attach certificates
checkpoint-status |  |  | checkpoint | Confirm waterproofing details installed as per manufacturer's specifications Attach waterproofer completed ITP (Applicable to Lift Pit Only)
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 6478f1fd-4160-5ff6-916e-535a289e795e |  | note | Attach photos prior to concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces
boolean | 68f53b6a-9af7-51f3-b338-bb1cd56a1b4b |  | tickbox | 50mm +/- in correct plane
boolean | 4d20d72b-98a7-5adb-b19f-18d99fff0742 |  | tickbox | 50mm +/- from 30m straight edges
checkpoint-status |  |  | checkpoint | Obtain all concrete tests to be carried out on all concrete pours
label | 6c57b303-57f4-513d-93d1-bdcd9d4b028e |  | note | Attach Concrete Docket/results below
checkpoint-status |  |  | checkpoint | Check concrete strength results complete with specification
label | 513304dd-28e4-5b5d-a21a-45043c2377fd |  | note | Attach results below as applicable in line with specifications
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 3e1f57f4-ec2f-574e-af78-9d1d530d9a86 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 6c7735d2-7ae4-5e15-8054-32d51d75f0c3 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Electrical Rough In |  |  |  |  | Yes | Electrical Rough In | 3330553a-024f-48d3-875c-41455797265a
checkpoint-status |  |  | checkpoint | Power points have been installed as per the electrical plans including shaving cabinet strip light
checkpoint-status |  |  | checkpoint | All points & switches are in a functional area
checkpoint-status |  |  | checkpoint | All comms are installed to allow for good detailing around
checkpoint-status |  |  | checkpoint | GPO's are correct for air conditioning & functional
checkpoint-status |  |  | checkpoint | NBN provision conduits (draw‐wire) 1mm installed
checkpoint-status |  |  | checkpoint | Fire rating peno's completed in lobbies
label | 8f54ac35-8870-5352-ae61-910c33cee2d4 |  | note | Relevant photo's/register has been completed
checkpoint-status |  |  | checkpoint | Final sign off - All electrical work completed as per the above ITP
label | 1c1b8601-b049-5019-8904-4beb85c9b3ea |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Storage Lockers |  |  |  |  | Yes | Storage Lockers | 347e4904-9f78-4e8a-a4b4-8e5a9aea6a25
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 6377e193-48c6-5b89-aed0-b9780b5f9b60 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Storage lockers installed to manufacturers instructions & standards
checkpoint-status |  |  | checkpoint | Final sign off - All storage lockers installed as per the above ITP - Add general photos/comments below
label | cd057800-5f7b-5af0-abd5-927c6846e33b |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Floor Wastes |  |  |  |  | Yes | Floor Wastes | 36502225-008e-4f44-9fb1-344fab587b2f
checkpoint-status |  |  | checkpoint | Plumber checks all pipes for any cracks, or imperfections
button | 7a050a7b-6b4c-5bf0-9299-5fa9a685bff4 |  | button | Plumber completes stack work | Yes, No
button | 1570ae38-e3ea-508a-9517-e551969095df |  | button | Plumber cuts waste flush with concrete and puts sponge inside | Yes, No
button | 90521a53-7ce4-59a1-a5a5-48b69ab291c2 |  | button | Plumber caps off all other pipes | Yes, No
checkpoint-status |  |  | checkpoint | Waterproofer pushes sponge down 100mm and finishes his membrane & flood test
checkpoint-status |  |  | checkpoint | Waterproofer removes sponge and releases water and puts the sponge back in ensuring there are no debris left in the pipe
checkpoint-status |  |  | checkpoint | Tiler accepts that the waste is clean and has a sponge in it
checkpoint-status |  |  | checkpoint | Tiler completes his works (ie sand cement & tile)
checkpoint-status |  |  | checkpoint | Aland cleans and removes the sponge
checkpoint-status |  |  | checkpoint | Final sign off - All floor wastes completed as per the above ITP
label | 42f519e6-5d2d-5cdd-8159-c39be2568334 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Rock Anchoring |  |  |  |  | Yes | Rock Anchoring | 38f75794-ca14-40af-820a-c310c5250398
checkpoint-group |  |  | section | Locate
checkpoint-status |  |  | checkpoint | Locate all existing services
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Confirm set out and RL
checkpoint-status |  |  | checkpoint | Confirm type of anchor to be used
checkpoint-status |  |  | checkpoint | Confirm the working load of the anchor/ tendon
checkpoint-status |  |  | checkpoint | Confirm minimum depth for anchors
checkpoint-status |  |  | checkpoint | Confirm angle of anchors
checkpoint-status |  |  | checkpoint | Confirm strength of grout required
checkpoint-status |  |  | checkpoint | Confirm de-stressing procedure for anchors with engineer
label | 3d1edd74-babd-515a-8c5d-0f4568da9f11 |  | note | Engineer procedure notes added below
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm anchors are not damaged during insertion into bore hole
checkpoint-status |  |  | checkpoint | Confirm number of strands is in accordance with engineer drawings
checkpoint-status |  |  | checkpoint | Confirm bore hole is being flushed clean – water/ air
checkpoint-status |  |  | checkpoint | Confirm grouting is taking place same day
checkpoint-status |  |  | checkpoint | Confirm bond and free lengths have been met in accordance with engineer drawings
checkpoint-status |  |  | checkpoint | Confirm grout testing is taking place (results to be returned 28 days later)
checkpoint-status |  |  | checkpoint | Confirm design boreholes design depth has been reached and do not require re-drilling
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Confirm grouting is reaching required strength after 7 days
checkpoint-status |  |  | checkpoint | Confirm stressing works have been completed
checkpoint-status |  |  | checkpoint | Confirm testing has been completed and passed loading test
checkpoint-status |  |  | checkpoint | Confirm anchors have not moved during testing
checkpoint-status |  |  | checkpoint | Confirm if additional anchors are required
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 8c109f09-13f7-5122-9d4f-33ce179bbe04 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 9d212b59-412f-5df4-b14b-e36a56406baf |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Water Connection |  |  |  |  | Yes | Water Connection | 3a5003f4-0955-45c1-89a3-01b7f1ab043b
checkpoint-status |  |  | checkpoint | Water has been installed throughout complex
checkpoint-status |  |  | checkpoint | Water has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for water install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - Water has been tested & installed as per the above ITP - Add general photos/comments below
label | f8690f2e-b7d4-53b5-b9ea-a939f77a687f |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | MSB & Comms Room |  |  |  |  | Yes | MSB & Comms Room | 3abc4d90-5bd1-41dc-9cc9-de14dac8c5b5
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation
button | deda999d-5520-5900-856d-c750f47176b6 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | 43c19b3f-8205-595b-af1c-d40dc2897db0 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 075905f3-c20b-5dda-9245-8e41a00f498a |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | cbbf690b-750c-5f00-b877-144fdfdf9b26 |  | button | Cables are labelled as per specified requirements | Yes, No
button | 3dbb4ed7-34b4-541a-b3e7-7648ff3e2119 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | 51b68334-bbf1-5644-9aa3-36dde46c7a36 |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Ensure all comms has been tested & commissioned
checkpoint-status |  |  | checkpoint | Ensure ventilation and exhaust fans are installed as per plans
checkpoint-status |  |  | checkpoint | Ensure FCU's (if required) are installed, tested & commissioned to provide sufficient cooling within MSB & Comms room
checkpoint-status |  |  | checkpoint | Final sign off - MSB & Comms room equipment installed as per the above ITP - Add general photos/comments below
label | 35d7dbcb-0a8b-54f6-8747-3e2bbc8638a7 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Toilet |  |  |  |  | Yes | Toilet | 3c644e44-13f7-4c20-97a7-7ba0199c8a84
checkpoint-status |  |  | checkpoint | Floor wastes checked - Any issues comment/photo below
checkpoint-status |  |  | checkpoint | All rough-in pipework is colour coded to ensure no cross connections
checkpoint-status |  |  | checkpoint | All Water & Gas risers are complete
checkpoint-status |  |  | checkpoint | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Ensure all services that go through fire rated walls to be treated with collars/fire rated sealant
checkpoint-status |  |  | checkpoint | Ensure rough in has been done as per specs
checkpoint-status |  |  | checkpoint | Final sign off - All plumbing work completed as per the above ITP - Add general photos/comments below
label | 177953af-9bcd-5f57-a9e1-e0803605a191 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Basement Fire System |  |  |  |  | Yes | Basement Fire System | 3f12706c-f6d7-4267-9c21-eeee3e8a7d65
checkpoint-status |  |  | checkpoint | Confirm any pipework and cabling penetrating partition walls are sealed through penetration with Intumescent fire mastic
checkpoint-status |  |  | checkpoint | Sprinkler rough in complete
checkpoint-status |  |  | checkpoint | Sprinkler droppers / heads installed
checkpoint-status |  |  | checkpoint | Sprinkler floor isolation valve assembly installed
checkpoint-status |  |  | checkpoint | Sprinkler valves installed
checkpoint-status |  |  | checkpoint | Sprinkler tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Feed hydrant installed
checkpoint-status |  |  | checkpoint | Feed hydrant commissioned
checkpoint-status |  |  | checkpoint | All hoses installed as per plan
checkpoint-status |  |  | checkpoint | All hoses installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Pipework tested - Test results attached below
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | Magnetic door holder fitted and functioning correctly on all fire exits
checkpoint-status |  |  | checkpoint | Final sign off - Fire system installed as per the above ITP - Add general photos/comments below
label | 9ebd7b70-03a3-55e2-9c8b-1e27d3216362 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Strut |  |  |  |  | Yes | Strut | 42bb2256-c89c-4795-ad84-021a091f5f46
checkpoint-status |  |  | checkpoint | Local batter to top of pile
checkpoint-status |  |  | checkpoint | Install piles for shoring
checkpoint-status |  |  | checkpoint | Construct capping beam
checkpoint-status |  |  | checkpoint | Excavate batter, construct foundation pile, and install strut
checkpoint-status |  |  | checkpoint | Remove soil and rock
checkpoint-status |  |  | checkpoint | Pour B2 part slab
checkpoint-status |  |  | checkpoint | Construct B1 slab leaving void for strut
checkpoint-status |  |  | checkpoint | Uninstall strut when basement 1 slab has reached 25mpa
checkpoint-status |  |  | checkpoint | Infill voids
checkpoint-status |  |  | checkpoint | Construct ground floor slab
checklist-sectioned |  |  | checklist | Detailed Excavation (V140421) |  |  |  |  | Yes | Detailed Excavation (V140421) | 4753a13e-8854-479a-b195-5afff6cb11ad
checkpoint-group |  |  | section | Excavation - Pre-Commencement
checkpoint-status |  |  | checkpoint | Confirm dial before you dig documents are onsite - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm correct disposal of classified material
checkpoint-status |  |  | checkpoint | Obtain geotech report, including load bearing capacity
label | 470acccf-a75b-598a-890d-1eea580be0a0 |  | note | Geotech report referenced or attached below
checkpoint-group |  |  | section | Excavation Works
checkpoint-status |  |  | checkpoint | Collection of tip dockets - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm set out of boundaries & marked out
checkpoint-status |  |  | checkpoint | Confirm actual RL is within design tolerance
button | 034f1667-2c46-5db1-9f84-845ab9364355 |  | button | Confirm set out of footings and pads | Yes, No, N/A
button | 6e61b261-3e32-5559-9fb7-cacb1aadb345 |  | button | Confirm set out of in ground drainage | Yes, No, N/A
label | 1dad8cff-7d95-5310-a21e-3a35f712d03f |  | note | Excavation of footings not to exceed size as detailed on structural drawings
checkpoint-status |  |  | checkpoint | Certifier to inspect foundation in accordance with specifications
checkpoint-status |  |  | checkpoint | Geotech inspection of footings etc
label | 1c33b081-0a4c-5ce1-a0c1-b30df5facb77 |  | note | Geotech report referenced or attached below
checkpoint-status |  |  | checkpoint | Confirm top of concrete footings is below surrounding finishes
checkpoint-status |  |  | checkpoint | Confirm sub-base is in line with engineers specifications/requirments
text | ebe5b4ea-cbde-5b55-a9c3-511f0960c567 |  | textbox | Minimum thickening (MM)
checkpoint-status |  |  | checkpoint | Civil engineer inspection carried out - Attached below as applicable
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 8a878f4c-38c3-5b42-afcc-faa6b67732a6 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | ead6b379-d424-5c80-b97f-2707d760d0a0 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Mechanical Rough In |  |  |  |  | Yes | Mechanical Rough In | 491b289d-a0ef-4c91-b6af-d7b0e4677dbf
checkpoint-status |  |  | checkpoint | All aircon has been roughed in & tested
checkpoint-status |  |  | checkpoint | All aircon vents are in correct spot
checkpoint-status |  |  | checkpoint | All service risers have been installed
checkpoint-status |  |  | checkpoint | Ensure all ducting sealed & sparged
checkpoint-status |  |  | checkpoint | All services that go through fire rated walls to be treated with collars/fire rated sealant
label | 0baa8306-b9c1-5098-8b43-1be05a6cec3c |  | note | Relevant photo's/register has been completed
checkpoint-status |  |  | checkpoint | Duct work to be tear free & sealed prior to cleaning
checkpoint-status |  |  | checkpoint | Final sign off - All mechanical work completed as per the above ITP
label | f23346a4-975d-5ab1-9825-981d25c30799 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Storage Room |  |  |  |  | Yes | Storage Room | 4a4b961e-e5fe-4527-b906-87268a2c198e
checkpoint-status |  |  | checkpoint | Storage lockers installed to manufacturers instructions & standards
checkpoint-status |  |  | checkpoint | Final sign off - All storage rooms installed as per the above ITP - Add general photos/comments below
label | e8c25980-937f-5dc3-8347-df4affafb47c |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Bike Rack |  |  |  |  | Yes | Bike Rack | 4d6c904d-c711-4a7e-8cb6-d1eb677a1477
checkpoint-status |  |  | checkpoint | Bike rack installed to manufacturers instructions & standards - Attach photos below
label | ec7b84df-244c-5db7-887b-f8201ec92b7b |  | note | Ensure adequate fixings have been used & are tight
checklist-sectioned |  |  | checklist | External Shade |  |  |  |  | Yes | External Elements Installation Checklist | 55acc827-84c7-4acd-8691-cac0b05a1145
checkpoint-group |  |  | section | Westside
checkpoint-status |  |  | checkpoint | Slab edge installation Completed
checkpoint-status |  |  | checkpoint | Vertical Full height sunshades installed
checkpoint-status |  |  | checkpoint | BMU Brackets installed
checkpoint-status |  |  | checkpoint | All end caps to feature completed
checkpoint-status |  |  | checkpoint | All external trimming completed
checkpoint-status |  |  | checkpoint | All external sealing completed
checkpoint-group |  |  | section | Eastside
checkpoint-status |  |  | checkpoint | Horizontal sunshade installed
checkpoint-status |  |  | checkpoint | Vertical fins detail installed
checkpoint-status |  |  | checkpoint | All end caps to feature completed
checkpoint-status |  |  | checkpoint | All external trimming completed
checkpoint-status |  |  | checkpoint | All external sealing completed
checklist-flat |  |  | checklist | Pad Footings |  |  |  |  | Yes | Pad Footings | 594182f0-1d7f-4b74-9119-e8b1ddc98eb4
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
button | da996e3a-d52e-5913-9475-0f1fd6f20d8e |  | button | Footing RL Confirmed | Yes, No, N/A
button | a6e20d19-fc77-509f-a355-19d44241553e |  | button | Any services (overhead / below ground) considered and isolated where required before excavation commences | Yes, No, N/A
button | 472ae75d-60cf-54b8-bdaf-de8448e517cf |  | button | Approval given to commence detailed excavation | Yes, No, N/A
button | de2119a9-56c5-54f4-8ba6-a710e269abfa |  | button | Excavation checked, correct and approved | Yes, No, N/A
button | 079b3f0a-2b09-55a9-9120-07b6666a9d2d |  | button | Depth correct (allow for site concrete if required) | Yes, No, N/A
button | 2725c445-d6e9-52c1-a534-50402e9a6f8d |  | button | Width correct (allow for boxing if required) | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Pads/ footings battered/ edges left free of spoil
checkpoint-status |  |  | checkpoint | Detailed excavation spoil removed and work area left clean and tidy
checkpoint-status |  |  | checkpoint | Blinding installed and documented if required/ Dockets and photos scanned
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
button | f34ab49d-7049-5dcb-8963-cee7c435d3e8 |  | button | Formwork sufficiently fixed and braced | Yes, No, N/A
button | b7b0050e-6a66-51d5-9693-414e64c78e65 |  | button | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place | Yes, No, N/A
button | d57b074d-4c12-5729-a2d7-4404e3498d95 |  | button | Service penetrations formed correctly and locations checked/correct | Yes, No, N/A
button | 32b29859-9524-5573-ad97-6bebcdfd5a4a |  | button | Any control joints/ stop ends installed accurately and correctly braced | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Reinforcement installed as per plan including cover & chairs
button | c8ef95f7-872c-5949-adbb-51713f714380 |  | button | Reo spacing & grade as per specifications | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Starter bars, dowel bars, & mesh installed as per specifications
checkpoint-status |  |  | checkpoint | Concrete strength/ Slump confirmed
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Final sign off - All pad footings completed as per the above ITP
label | 418f8cb6-5bc7-551b-98af-67688c516ee2 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Tiling |  |  |  |  | Yes | Tiling | 66bc46fe-92e1-4bca-8847-594e956bde70
checkpoint-status |  |  | checkpoint | Correct tiles are being used in correct areas
button | af1a67b4-0d10-50ff-8a7a-5e6bd18ce927 |  | button | 5mm expansion to all junctions | Yes, No
button | 21673de4-233d-5eb3-acf0-4c5831017582 |  | button | 1.5mm spacers being used | Yes, No
button | 022eb065-b584-5c55-8e2e-ab6b20290b3b |  | button | Tile lips are within tolerances | Yes, No
button | d3215c45-90fa-5aea-8ee2-6f4b45038c59 |  | button | Correct tiles are being used in correct areas | Yes, No
button | 2b9f098b-dc2b-5bf5-9d31-2fd8015615b6 |  | button | Angles & trims are straight & free off any defects | Yes, No
checkpoint-status |  |  | checkpoint | All floors fall to wastes & don't hold water
button | e725ed48-caef-5727-ad4b-d4ffc5398265 |  | button | Floor wastes are installed & free of any defects | Yes, No
button | 0605d484-a0c7-571d-ac26-8cb857ffb130 |  | button | Wastes are free of any rubbish | Yes, No
button | 1bd880c0-bd93-5572-a8e4-88447a937e86 |  | button | Check all falls to floor wastes to comply with BCA | Yes, No
checkpoint-status |  |  | checkpoint | Ensure all tiles are fixed correctly
button | ed8c84b9-294e-5375-9ee1-2d847323ada1 |  | button | Check all tile lips are within tolerances | Yes, No
button | 5064bd96-8232-5c64-a4b9-c3fe86f4e90d |  | button | Check that glue has been applied notch trowel in accordance with manufacturer's specifications | Yes, No
button | 5bc61fe1-554d-5bd5-afed-2d764fb8eedd |  | button | Walls have been laid straight & plumb, reveals are square | Yes, No
button | 2c7e4241-28e8-5277-add0-1c3175fd463a |  | button | Tiles have been laid 1m below 1m offset line | Yes, No
button | b6371628-1943-531e-a241-28138f190bfa |  | button | Tiles have been laid to marker lines on mixers | Yes, No
button | 73e7b75f-a4ba-514b-8566-550ffa72cbe3 |  | button | Full tile bond on door frames & work away to ensure cuts are in corners | Yes, No
button | 9bb2cb51-19e1-5b01-bcec-51ed27c38f4b |  | button | Double check tile batch before use in area | Yes, No
button | baabbd99-afce-56de-b0d1-4526ae7075ca |  | button | Check all tile lips are within tolerances | Yes, No
checkpoint-status |  |  | checkpoint | Ensure floor wastes are clean & free from any debris, area left clean
checkpoint-status |  |  | checkpoint | Final sign off - All tiling work completed as per the above ITP
label | 5777c197-7954-5dc2-82e2-1ca087b90522 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Bulk Excavation |  |  |  |  | Yes | Bulk Excavation | 6b79fc92-ee19-455b-8153-635376bb2e57
checkpoint-status |  |  | checkpoint | Confirm dial before you dig documents are onsite - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm correct disposal of classified material
checkpoint-status |  |  | checkpoint | Obtain geotech report, including load bearing capacity
label | 2c0744ff-9343-54a6-b9fe-4521087c7275 |  | note | Geotech report referenced or attached below
checkpoint-status |  |  | checkpoint | Collection of tip dockets - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm set out off boundaries & marked out
checkpoint-status |  |  | checkpoint | Confirm Bulk RL is within detailed excavation zones/limits
checkpoint-status |  |  | checkpoint | Civil engineer inspection carried out - Attached below as applicable
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 6d921344-e2cb-5713-b892-350253815453 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | b4ec9eb9-19c8-511d-9e95-e69b619bc0b5 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Fire Pump Room (V90421) |  |  |  |  | Yes | Fire Pump Room (V90421) | 6f4d5544-c69d-41ef-ac2f-e3f9973603c7
checkpoint-status |  |  | checkpoint | Fire pump isolation valves installed on all pumps
checkpoint-status |  |  | checkpoint | All pipe work tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Pour concrete plinth for each fire pump
label | 6b6e4b81-28d7-563f-ae42-72916b9c0b34 |  | note | Check height and dimensions as per drawings/specifications
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation
button | 11df7538-5afd-5faf-b360-69ba4418d4f0 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | abfd66e5-ac5d-5549-b793-c855b17633e1 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 63a543ea-5d24-5b9f-806b-d93f7f330291 |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | b3ecda70-4500-55fb-b4c0-7f5a6e389286 |  | button | Cables are labelled as per specified requirements | Yes, No
button | 5a9e7c61-97f2-5d17-9c22-dfb42fbe3f09 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
checkpoint-status |  |  | checkpoint | Ensure 1m Clearance around fire pumps
checkpoint-status |  |  | checkpoint | Ensure minimum 2m Height clearance - To floor or finish above
checkpoint-status |  |  | checkpoint | Ensure safety signage is installed and visible as per plans
checkpoint-status |  |  | checkpoint | All PvC pipes to be fire rated within pump room
checkpoint-status |  |  | checkpoint | FIP commissioned & is recognising fire pumps within the system
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | Final sign off - Fire pumps installed as per the above ITP - Add general photos/comments below
label | 6cbf168f-3481-58c1-bfe2-7bcc0cf318fe |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Caretaker Toilet |  |  |  |  | Yes | Caretaker Toilet | 71facb27-3e90-4ded-82a5-4b97ba3f190f
checkpoint-status |  |  | checkpoint | Floor wastes checked - Any issues comment/photo below
checkpoint-status |  |  | checkpoint | All rough-in pipework is colour coded to ensure no cross connections
checkpoint-status |  |  | checkpoint | All poly pipes located in framing to ensure no screw fixings will penetrate them
label | e4a0c00c-1262-5786-bd55-5df6cb14e86a |  | note | Any pipe running through a wall must be at 90 degrees
checkpoint-status |  |  | checkpoint | All Water & Gas risers are complete
checkpoint-status |  |  | checkpoint | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Ensure all services that go through fire rated walls to be treated with collars/fire rated sealant
checkpoint-status |  |  | checkpoint | Ensure rough in has been done as per specs
checkpoint-status |  |  | checkpoint | Final sign off - All plumbing work completed as per the above ITP - Add general photos/comments below
label | cb61c3a1-668d-5d9b-8ccf-631f0c8bae79 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Brick Work |  |  |  |  | Yes | Brick Work | 74272f27-60f7-4b56-b2c0-ee28cda562ad
checkpoint-status |  |  | checkpoint | Inspect building materials to confirm supply meets Aland Constructions quality standards if not contact supplier immediately, e.g. chips, breaks, inconsistent shape or sizing.
checkpoint-status |  |  | checkpoint | Confirm site set out is correct, wall positions, windows and doors openings
checkpoint-status |  |  | checkpoint | Confirm bond and joint finish
checkpoint-status |  |  | checkpoint | Confirm masonry material to be laid, e.g. block, face brick, commons and locations for each type.
checkpoint-status |  |  | checkpoint | Ensure all finished surfaces are protected, e.g. window glazing, and jambs
checkpoint-status |  |  | checkpoint | Confirm mortar mix, e.g. to site specifications and or AS3700
checkpoint-status |  |  | checkpoint | Confirm locations of any penetrations, e.g. wall vents
checkpoint-status |  |  | checkpoint | Check that the external skin overhang if any conforms with Australian Standards
checkpoint-status |  |  | checkpoint | Confirm locations of control joints and articulation joints including use of expansion ties.
checkpoint-status |  |  | checkpoint | Confirm if upper level shelf angles are required and locations & material specified to be used.
holdpoint |  |  | signoff | Signed off by Aland
checkpoint-status |  |  | checkpoint | Confirm face bricks are selected from random pallets to ensure brick colour is blended through feature walls
checkpoint-status |  |  | checkpoint | Lay bricks/blocks up to DPC
checkpoint-status |  |  | checkpoint | Install one-piece DPC Internal and external corner flashings with 600mm minimum overlaps.
checkpoint-status |  |  | checkpoint | Ensure flashings are boxed up against sliding door jambs
checkpoint-status |  |  | checkpoint | Lay bricks/blocks allowing for weep holes
checkpoint-status |  |  | checkpoint | Lay bricks ensuring cleaning of cavities.
checkpoint-status |  |  | checkpoint | Ensure mortar doesn’t breach cavity & touch cavity insulation
checkpoint-status |  |  | checkpoint | Confirm size and type of wall & header tie to be used including checking for durability rating required (I.e. R2 / R3 or R4)
checkpoint-status |  |  | checkpoint | Ensure wall ties are installed at correct spacings both vertically & horizontally. Check engineer requirements
checkpoint-status |  |  | checkpoint | Ensure all walls are plumb straight, square, and or as detailed on plan.
checkpoint-status |  |  | checkpoint | Ensure a 50mm cavity minimum width is achieved
checklist-sectioned |  |  | checklist | External Facade |  |  |  |  | Yes | External Facade | 746f3ab1-64e8-4e21-9908-baa0032f20ba
checkpoint-group |  |  | section | Hebel Work
checkpoint-status |  |  | checkpoint | Ensure hebel installed plumb & level with adjoining surfaces
checkpoint-status |  |  | checkpoint | Ensure gap between hebel & concrete 10‐15mm (max) & consistent
checkpoint-status |  |  | checkpoint | Ensure hebel panels are in full & not cracked
checkpoint-status |  |  | checkpoint | Final sign off - All hebel work completed as per the above ITP
checkpoint-group |  |  | section | Render Work
checkpoint-status |  |  | checkpoint | Ensure to use right dulux product & system as per specification & scope of works
checkpoint-status |  |  | checkpoint | Expansion cuts are consistent up & down & to substrate & also same cut thickness
checkpoint-status |  |  | checkpoint | Ensure surfaces flat & level & free of imperfections
checkpoint-status |  |  | checkpoint | Once render applied ‐ render allowed to sufficiently dry before primer coat
checkpoint-status |  |  | checkpoint | Primer Coat ‐ even consistent coverage on render
checkpoint-status |  |  | checkpoint | Membrane Texture Coat ‐ consistent coverage & texture, no roller marks, consistent sheen level
checkpoint-status |  |  | checkpoint | Paint thickness test to be carried out & report to be crossed checked DGain Alands external render & paint specification schedule
checkpoint-status |  |  | checkpoint | Final sign off - All render work completed as per the above ITP
label | c6e66ccb-9efc-509d-99dd-5f02d276a218 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Driveways /Footpaths /Hard surfaces |  |  |  |  | Yes | Driveways /Footpaths /Hard surfaces | 7663dbce-67a5-4d04-8dd5-94db9c0cba8e
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | f872f9c1-82f9-5716-beab-cd535a779c7b |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | All Surfaces have been poured as per specifications
checkpoint-status |  |  | checkpoint | All Surfaces are at the correct level/falls as per specifications
checkpoint-status |  |  | checkpoint | All Surfaces finishes are to specification
checkpoint-status |  |  | checkpoint | Final sign off - Driveways has been completed as per the above ITP - Add general photos/comments below
label | d8affa7f-b061-54b7-bab1-406416677f17 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Inspection Checklist |  |  |  |  | Yes | Inspection Checklist | 77210da9-4e69-434a-8450-f1d84025403a
checkpoint-status |  |  | checkpoint | Inspection Details
text | b775c41d-5ca8-50e2-aaa7-12d2910b4807 |  | textbox | Date of Inspection
text | 47d6119b-17ec-56ef-bd5f-e1c35dfa8d37 |  | textbox | Inspection Type (Code)
text | 8d3ce670-5b92-50f1-bfb1-615d20d90ab1 |  | textbox | Person/Company Inspecting
text | b2de4569-4e5a-5e12-9f86-a51b2785967e |  | textbox | Area inspection relates to
checkpoint-status |  |  | checkpoint | Inspection outcome
select | c73ce7aa-bcc4-5f88-a438-0403fcda81f9 |  | dropdown | Inspection Result | Pass, Partial Pass, Fail, N/A
text | 983b9676-52ab-5e3f-a403-206e1b4d6c6c |  | textbox | Reason if Partial Pass or Failed
boolean | 7bc990f7-36ad-5700-b728-49eaf47faf9d |  | tickbox | Inspection report attached below
label | 2239aa91-5d34-5f09-a933-8a87c3d5d8ec |  | note | Remedial items to be photographed & Commented below
holdpoint |  |  | signoff | Request Sign-Off (3rd Party)
checkpoint-status |  |  | checkpoint | All Relevant Observation(s) Closed-Out & evidence attached - if applicable (Pass once completed)
holdpoint |  |  | signoff | Request Sign-Off (3rd Party)
checklist-flat |  |  | checklist | Bathroom & Laundry Waterproofing |  |  |  |  | Yes | Bathroom & Laundry Waterproofing | 79651b49-3b2e-4ea4-b0e3-93c4192248f4
checkpoint-status |  |  | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application "No access Waterproofing work in progress"
label | e870f325-c7c7-5c5c-b468-65781f66e765 |  | note | Attach relevant photos below
button | bbd21404-7f3e-534d-806f-23014a753b39 |  | button | Membrane system & methodology checked off AGainst Aland standard details & MSDS & guidelines | Yes, No
button | 2ab3a524-0b9f-50d9-968e-634b5e30e360 |  | button | Surface preparation as per application guide | Yes, No
button | 43dda6e7-f291-5019-b20d-f17f3210483a |  | button | Substrate clean, dry & free from dust. | Yes, No
button | 87b305dc-6da5-5cde-88d3-81a1a66cce7b |  | button | Ensure no high points or crevices are in the substrate | Yes, No
button | f6d56d39-6786-5959-bfa3-78d92b3d689c |  | button | Ensure substrate is structurally sound & ready to receive membrane | Yes, No
button | bf1f9fcf-f8c9-5504-8f50-7f29299a28a9 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to primer | Yes, No
button | 41be716a-d94a-5deb-b693-50ec260c3112 |  | button | Do not proceed if above has not been signed off | Yes, No
checkpoint-status |  |  | checkpoint | Apply primer
button | e7d96ad3-0e1f-55b2-83aa-9d65328bdd95 |  | button | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations | Yes, No
button | 91cd2382-6e0c-56ef-ade1-73aeccb118e3 |  | button | Shower angle in correct position & level | Yes, No
button | 535e6f25-6724-5702-b688-49a593beeabd |  | button | Door angle is in correct position & level | Yes, No
button | 11712cc3-f79b-5f2b-965d-2a0f8db9d3fa |  | button | Door & shower angle are 3 mm gauge aluminium | Yes, No
button | 6619c4ef-eecb-52a3-b6fd-c3fdbac43fba |  | button | All corners have polyurethane bond breaker installed with min 15mm radios | Yes, No
button | 908677c9-2995-545a-a481-eef78b8b7ed8 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to first coat | Yes, No
checkpoint-status |  |  | checkpoint | Apply first coat of membrane & turn membrane up the walls / pipes as required.
label | a6aadda4-7b91-5902-b435-db4c127fc8af |  | note | All floor wastes membranes to be turned down into floor waste
checkpoint-status |  |  | checkpoint | Waterproof walls of shower section up to ceiling. Seal taps & the like. 2x coats required
button | 5eb16ed6-a428-5ab7-8d27-f9d9025a0792 |  | button | Min 150mm kicker has been waterproofed (do width of roller 230mm) | Yes, No
button | bb69df64-2aa7-5d9f-ba08-3047ac77afcc |  | button | Min 1500mm past shower screen has been waterproofed | Yes, No
button | 69bec043-25a4-550d-814c-0cb38654e54d |  | button | Waterproof all shower & adjacent walls | Yes, No
button | fcf74c76-52f3-576e-af8b-a1ab053d4ccc |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to final coat | Yes, No
checkpoint-status |  |  | checkpoint | Apply final coat of membrane
button | 06776e70-8327-545f-afdc-3c79ac313b02 |  | button | Allow curing in accordance with manufacturers specification 24‐48 hours min | Yes, No
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument
label | 300f5778-4260-5b6d-b8b7-32b7044fb00f |  | note | Total dry film thickness of 1.2mm (1200 microns) in two finished coats. As such at min.
label | 6c0055a2-31fc-5e79-a54d-9c88b2487d27 |  | note | Wet film thickness of 0.75mm per coat is required ‐ Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
checkpoint-status |  |  | checkpoint | Rectification of defective works for failure of flood test & all works completed
checkpoint-status |  |  | checkpoint | Final sign off - All bathroom & laundry waterproofing work completed as per the above ITP
label | 9952e18f-3ee0-56bd-b5f3-7353126ddd07 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Corridor/Common Area Fire System |  |  |  |  | Yes | Corridor/Common Area Fire System | 7f6edf63-8bba-44be-84d7-054d33a124cf
checkpoint-status |  |  | checkpoint | FIP installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | FIP tested & commissioned
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors rough in completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | All fire signage installed correctly and visible
checkpoint-status |  |  | checkpoint | Magnetic door holder fitted and functioning correctly on all fire exits
checkpoint-status |  |  | checkpoint | Final sign off - Fire system installed as per the above ITP - Add general photos/comments below
checklist-flat |  |  | checklist | Post Wall Linings |  |  |  |  | Yes | Post Wall Linings | 8131230f-6d19-4a10-89a1-4d4ff7310ab9
checkpoint-status |  |  | checkpoint | Insulation has been installed
checkpoint-status |  |  | checkpoint | Insulation has been installed snug between framing members with no gaps
checkpoint-status |  |  | checkpoint | Fire rated walls have been sheeted to the ceiling
checkpoint-status |  |  | checkpoint | Fire rated walls have been fire caulked
checkpoint-status |  |  | checkpoint | Bathroom walls & ceilings have been sheeted with blue watercheck plasterboard
checkpoint-status |  |  | checkpoint | Bathroom's sheeted - Set to the floor to allow for good waterproofing junction
checkpoint-status |  |  | checkpoint | Ensure MSDS & installation guide has been followed
checkpoint-status |  |  | checkpoint | Final sign off - All post wall work completed as per the above ITP
label | 14eab098-5710-59c6-815d-c12f8ae02b2b |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Mandatory Inspections |  |  |  |  | Yes | Mandatory Inspections | 85cb13a4-5ac7-4bd7-b722-738ed4ee29bd
checkpoint-status |  |  | checkpoint | Consent
text | b77dba71-2470-54f3-9ee4-9ac142dd2f0a |  | textbox | DA/CDC No
text | 411c7069-d10e-5a02-b114-d5799d2ae9c9 |  | textbox | CC No
label | 36e9d25d-66b4-5294-bc77-52cdc590adad |  | note | The Following are Critical Stage Mandatory Inspections - They are required pursuant to Section 65 (b) of the Act & Clause 162A of the Regs
label | 31e89db7-6c60-5f44-bdfd-e9002a519fd7 |  | note | In the case of a class 2, 3 or 4 building
checkpoint-status |  |  | checkpoint | (a) after the excavation for, and prior to the placement of, any footing, and
checkpoint-status |  |  | checkpoint | (b) prior to covering of fire protection at service penetrations to building elements that are required to resist internal fire or smoke spread, inspection of a minimum of one of each type of protection method for each type of service, on each storey of the building comprising the building work, and prior to covering the junction of any internal fire-resisting constructions bounding a sole-occupancy unit, and any other building element required to resist internal fire spread, inspection of a minimum of 30% of sole-occupancy units on each storey of the building containing sole-occupancy units, and
checkpoint-status |  |  | checkpoint | (c) prior to the covering of waterproofing in any wet areas, for a minimum of 10% of rooms with wet areas, and
checkpoint-status |  |  | checkpoint | (d) prior to covering any stormwater drainage connections, and
checkpoint-status |  |  | checkpoint | (e) after the building work has been completed and prior to any occupation certificate
checklist-flat |  |  | checklist | Apartment Fire System |  |  |  |  | Yes | Apartment Fire System | 87fb7121-f84c-4259-8c1c-cda99ff3bb1b
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors rough in completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Sprinklers rough in completed
checkpoint-status |  |  | checkpoint | Sprinklers fit off completed
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | All fire signage installed correctly and visible - If applicable
checkpoint-status |  |  | checkpoint | Final sign off - Fire system installed as per the above ITP - Add general photos/comments below
label | d3530977-5e1c-5ee9-ad72-0ddfceb50081 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Soft Landscaping |  |  |  |  | Yes | Soft Landscaping | 88a96b75-0cc7-40be-8523-9c2ad9f4367d
checkpoint-status |  |  | checkpoint | Ensure all plants are planted as per drawings
checkpoint-status |  |  | checkpoint | Irrigation installed as per drawings
button | 6236b813-987e-59b5-85a7-783ef50f8af5 |  | button | Irrigation leak tested | Yes, No
checkpoint-status |  |  | checkpoint | Outdoor furniture installed as per plans
checkpoint-status |  |  | checkpoint | Final sign off - All soft landscaping completed as per the above ITP - Add general photos/comments below
label | 55ea6d2b-760e-5510-b789-ef82166be73d |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Balcony & Podium Waterproofing |  |  |  |  | Yes | Balcony & Podium Waterproofing | 8dd4aa88-1546-41ab-a48a-de04325fc346
checkpoint-status |  |  | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | ce9351ad-3b97-513b-a744-419d59e6c63d |  | note | Attach relevant photos below
checkpoint-status |  |  | checkpoint | Membrane system & methodology checked off AGainst Aland standard details & MSDS & guidelines
button | 55d97e74-c08a-5382-85ed-b5aedfbf2bd8 |  | button | Surface preparation as per application guide | Yes, No
button | de5fd4cd-ceb3-527d-a344-b5266d2a6ef7 |  | button | Substrate clean, structurally sound & ready to receive membrane | Yes, No
checkpoint-status |  |  | checkpoint | All corners, joints, gaps & cracks to be treated with a flexible polyurethane sealant Resiflex FC ‐apply selected Membrane as per datasheet & application guidelines
label | 57486688-5c6d-53ab-b48b-bc481bfce1fc |  | note | Ensure sealant has fully cured before installing membrane
label | ee1c4c04-6647-53ad-9379-5ab7ebb05631 |  | note | Ensure Humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to primer
label | 45126b53-8393-5d75-a4db-f32a72a63949 |  | note | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint-status |  |  | checkpoint | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
label | fca983b5-4068-5d53-9d60-5cfa947143b5 |  | note | PrimeSeal MC to all surfaces at a rate of 3‐4m2/Ltr
label | d8cd0e4d-5391-5569-b109-2e4f591e80e4 |  | note | Alternative primers Multiseal ‐ Primeseal SP at a rate of 5‐8 m2/Ltr
checkpoint-status |  |  | checkpoint | Balustrade base i.e. shoe base or angle base installed & grouted with structural grout (as required)
label | 4ee032a1-e73d-56a2-94bd-401f57f337d5 |  | note | Joint between bottom of base & substrate to be no greater than 10mm
checkpoint-status |  |  | checkpoint | Overflow at the ends of balustrades in place
label | 0e025741-9ed6-5899-9956-a7ea1c21b6c3 |  | note | Approximate width of over floor to be 50mm
label | f9cf446a-5a2a-5088-8aa4-9121319ca6b0 |  | note | Height of overflow must be lower than the bottom of subsill
label | 0626bf5f-950a-5838-81d2-2da8759f6c92 |  | note | Angle to be installed between end of base & wall with top of angle to be at FFL
checkpoint-status |  |  | checkpoint | First coat of selected Membrane to entire areas as per DURAM recommendations
label | bb2dd54f-dd27-587f-b8f7-701121e470f7 |  | note | Note ‐ a total dry film thickness of min 1.2mm (1200 microns) in two finished coats. As such at min. Wet Film Thickness of min 0.75mm (750 microns) per coat is required
label | b01e3eed-f67b-578a-a62b-7fa6d912ae34 |  | note | Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
button | b4b9abc5-b242-591d-8b57-89da7665a089 |  | button | Allow the membrane coat to dry min 12 hours check the tackiness before applying next coat | Yes, No
button | c2c83a90-543c-5e41-a636-f407791038a4 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to second coat | Yes, No
checkpoint-status |  |  | checkpoint | Second coat of selected Membrane to entire areas as per DURAM recommendations
label | 18ca852b-9262-55bc-8511-8aa66e0ec019 |  | note | Note ‐ a total dry film thickness of 1.2mm (1200 microns) in two finished coats. As such at min. Wet Film Thickness of 0.75mm per coat is required
label | f526abc5-39c8-545d-a82e-fdfc226b1fac |  | note | Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
button | 4b2b6cb6-9d97-5f05-8ac3-607112812742 |  | button | The membrane is to be applied in a minimum of 2 coats at a total coverage of 1.2 to 2 litres per m2. or relevant product TDS | Yes, No
button | 412b9ebb-f0fd-584c-aa9e-dba857895d59 |  | button | Allow 2nd coat of Multithane UV min. 12 hours BUT no longer than 24 hours before installing Multithane ATC top coat | Yes, No
checkpoint-status |  |  | checkpoint | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to final coat
checkpoint-status |  |  | checkpoint | Apply final coat of Multithane ATC at a coverage rate of 3 ‐ 4 m2/lte
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument
checkpoint-status |  |  | checkpoint | Rectification of defective works for failure of flood test & works complete
checkpoint-status |  |  | checkpoint | Ensure screed is fully dry ready for sealer application
checkpoint-status |  |  | checkpoint | Crystoflex membrane applied (note allow sufficient time for curing minimum 24 Hours)
checkpoint-status |  |  | checkpoint | Final sign off - All balcony & podium waterproofing work completed as per the above ITP
label | 837499d4-7343-5986-b795-5df974b12569 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Underground Fire Service Checklist (V140421) |  |  |  |  | Yes | Underground Fire Service Checklist (V140421) | 90eb90bf-88dc-42f9-a4ff-1976092e7750
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching operations @ 15M deep or greater
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-status |  |  | checkpoint | Site survey and confirm extent of works
checkpoint-status |  |  | checkpoint | Confirm area of work is accessable and acceptable to commence
checkpoint-status |  |  | checkpoint | Exclusion zone erected
checkpoint-status |  |  | checkpoint | Trench shoring/shield is on site
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Bedding material is correct type, grade and depth
checkpoint-status |  |  | checkpoint | Fire service installed to correct depth of cover
checkpoint-status |  |  | checkpoint | Service indicator tape installed
checkpoint-status |  |  | checkpoint | joints are correct
checkpoint-status |  |  | checkpoint | Risers are in correct location - provide photos
checkpoint-status |  |  | checkpoint | Fire service tested to AS/NZS35002018, AS24192017 Provide Photos
checkpoint-status |  |  | checkpoint | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes prior to concrete
checkpoint-status |  |  | checkpoint | clean up of work area
holdpoint |  |  | signoff | Completion sign off
checkpoint-status |  |  | checkpoint | Independent inspection and testing complete
checkpoint-status |  |  | checkpoint | General photos, comments & observations during Cold Water Rough-In (Add below)
checkpoint-status |  |  | checkpoint | Underground Fire Service completed to specification/drawings & Area left clean/tidy
label | 2454f7ac-73a6-5310-919c-bf0b8a947bf4 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Gas Connection |  |  |  |  | Yes | Gas Connection | 962973ca-2e7c-46df-a547-b73814e750bf
checkpoint-status |  |  | checkpoint | Gas has been installed throughout complex
checkpoint-status |  |  | checkpoint | Gas has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for gas install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - Gas has been tested & installed as per the above ITP - Add general photos/comments below
label | 45b8f319-ec2b-5713-b9f3-0575605d791f |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Precast |  |  |  |  | Yes | Precast | 999285ae-00c9-43ac-9ff2-2ac819a4e470
checkpoint-group |  |  | section | Pre - Erection
checkpoint-status |  |  | checkpoint | Latest drawings include bracing design
checkpoint-status |  |  | checkpoint | Precast Panels certification obtained
checkpoint-status |  |  | checkpoint | Set up of exclusion zone - Off-loading area
checkpoint-status |  |  | checkpoint | Set up of exclusion zone - work area
checkpoint-status |  |  | checkpoint | Crane slewing zone checked
checkpoint-status |  |  | checkpoint | Survey datum and grids checked
checkpoint-status |  |  | checkpoint | Support structure as per engineer design
checkpoint-status |  |  | checkpoint | Precast element set-out complete
checkpoint-group |  |  | section | Precast Element Erection
checkpoint-status |  |  | checkpoint | Shims set to levels & within limits
checkpoint-status |  |  | checkpoint | Dowel preparation complete as per drawings
checkpoint-status |  |  | checkpoint | Crane positioned as per chart check
checkpoint-status |  |  | checkpoint | Panel's lifted off truck as per SWMS
button | 845e0e32-a5e6-58d6-aa24-902b184471e3 |  | button | Panels lowered into position | Yes, No
checkpoint-status |  |  | checkpoint | Dowel alignment checked
button | b0455fa7-86ee-52db-92e5-93c93e32fd9e |  | button | Horizontal alignment checked | Yes, No
button | e277086c-bd44-5ea8-9f98-6c76d7a69b20 |  | button | Vertical alignment checked | Yes, No
checkpoint-status |  |  | checkpoint | Bracing installed, pins, locks & bolts in place
checkpoint-status |  |  | checkpoint | Panels dowels grouted
checkpoint-status |  |  | checkpoint | Dry pack grout to panels underside
checkpoint-status |  |  | checkpoint | Brackets installed and grouted
checkpoint-status |  |  | checkpoint | Braces removed
checkpoint-status |  |  | checkpoint | Caulking internally as per approved spec
checkpoint-status |  |  | checkpoint | Caulking externally as per approved spec
label | db8c855e-b529-5787-937d-f8b757c2bf9d |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
holdpoint |  |  | signoff | All work completed as per ITP
checklist-flat |  |  | checklist | Mechanical Fan Room |  |  |  |  | Yes | Mechanical Fan Room | 9f986c29-a17b-466e-938d-1576e1630899
checkpoint-status |  |  | checkpoint | Ensure all mechanical fans have been tested & commissioned
button | 026e40dc-d6c5-5ff2-8572-827933c48164 |  | button | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation | Yes, No
button | 180f3f94-a4f8-5d5b-b714-fa333259a309 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | 912db33f-4288-5567-8058-9672848cd174 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 028879c6-3d28-5983-a6fa-53e0d5629cff |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | 7eb148ae-6d8d-54ef-94f5-81c8f70af665 |  | button | Cables are labelled as per specified requirements | Yes, No
button | e90e96ad-663a-5c88-8484-8a67e4499f69 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
checkpoint-status |  |  | checkpoint | Ensure safety signage is installed and visible as per plans
checkpoint-status |  |  | checkpoint | Final sign off - All mechanical fans are installed as per the above ITP - Add general photos/comments below
label | 35069d0d-3e5d-549b-9244-5749131c926c |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | KONE - Lifts |  |  |  |  | Yes | KONE - Lifts | 9fbd8dae-1722-4b4a-aba2-764d28a08a66
checkpoint-group |  |  | section | Pre
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | ed95a408-dca7-53d8-bee4-c1bdb9710b0e |  | textbox | Drawing & revision number(s)
checkpoint-group |  |  | section | Complete before KONE starts on site
checkpoint-status |  |  | checkpoint | Waterproof the pit & shaft
checkpoint-status |  |  | checkpoint | Weather & water protect lift lobby areas on all floors
checkpoint-status |  |  | checkpoint | Complete all penetrations as per KONE drawings
checkpoint-status |  |  | checkpoint | If steel construction - provide fixing points for rail brackets & lift doors according to KONE drawings
checkpoint-status |  |  | checkpoint | Provide accurate grid, datum & RL lines
checkpoint-status |  |  | checkpoint | Provide lighting in the lift lobbies & stairwells
checkpoint-status |  |  | checkpoint | Provide permanent access stairs to all floors
checkpoint-status |  |  | checkpoint | Provide public access to top floor life door with the control cabinet Control cabinet must not be in a private dwelling space
checkpoint-status |  |  | checkpoint | Build in all lifting points por beams as shown on KONE's drawings
checkpoint-status |  |  | checkpoint | Provide access so that equipment can be installed into the lift well Special holes may be required Guide rails are 5m long
checkpoint-status |  |  | checkpoint | Guard lift door openings in accordance with AS4431
checkpoint-status |  |  | checkpoint | Provide space for our site personnel accommodation that is safe, clean & dry
checkpoint-status |  |  | checkpoint | Provide on site water, lighting & sanitation
checkpoint-status |  |  | checkpoint | Provide adequate space for storage of all lift equipment & all tools near the site accommodation that is secure, safe & dry (approx 50 sqm per lift)
checkpoint-status |  |  | checkpoint | Remove all builders equipment, materials & rubbish from the lift well & lobby areas in front of the lift well doors
checkpoint-status |  |  | checkpoint | Install permanent sub mains & dedicated telephone line to the top floor served terminating at the location nominated by KONE & provide 415V (5%) 3 phase + neutral + earth power supply Max fault level of 6kA
checkpoint-group |  |  | section | Complete while KONE is working onsite & prior to practical completion
checkpoint-status |  |  | checkpoint | Protect lift doors, architraves & lift fixtures from damage prior to lift hand over
checkpoint-status |  |  | checkpoint | KONE to place rubbish & excess packaging into bins on site provided by Aland
checkpoint-status |  |  | checkpoint | Security sub contractor to finalise security interfacing & operation
checkpoint-group |  |  | section | Complete at any time that is suitable for Aland
checkpoint-status |  |  | checkpoint | Supply & install any associated wiring that is required external to the lift shaft
checkpoint-status |  |  | checkpoint | Install any fire control equipment if required
checkpoint-status |  |  | checkpoint | If a lift is required to operate during a fire, then isolate those lift lobbies from fire & smoke in accordance with the BCA part E2 & recommendations of EN811 appendix G & Fig 2
checkpoint-status |  |  | checkpoint | Make good & clean up where lobby finishes meet architraves & lift call buttons etc
checklist-sectioned |  |  | checklist | Formwork & Reinforcing |  |  |  |  | Yes | Formwork & Reinforcing | a1350fad-358d-417b-b26f-ca0ba50aae2b
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Confirm Class of formwork to all faces, as per the latest specifications
checkpoint-status |  |  | checkpoint | Confirm RL's of soffit & beams
checkpoint-status |  |  | checkpoint | Confirm any penetration sizing for any hoist/crane penetrations
checkpoint-status |  |  | checkpoint | Ensure formwork frames installed to enable clear & labelled access under deck for other personnel & for inspections
checkpoint-status |  |  | checkpoint | Ensure all formwork surfaces are cleaned & no rubbish remains on any soffits,sides,base of work
checkpoint-status |  |  | checkpoint | Ensure bases of all columns/walls are cleaned out prior to pouring
checkpoint-status |  |  | checkpoint | Check formwork is completed as per specified Class
checkpoint-status |  |  | checkpoint | Ensure no rubbish or excess water is present prior to concrete pour
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Post concrete pour
checkpoint-status |  |  | checkpoint | Formwork stripped in a safe manner
checkpoint-status |  |  | checkpoint | All timbers de - nailed
checkpoint-status |  |  | checkpoint | Final sign off - All formwork & reinforcement completed as per the above ITP
label | 92d28353-3b1d-52de-9bbf-4eb20c952fc7 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | NBN Connection |  |  |  |  | Yes | NBN Connection | a463e001-0c5f-4920-9d93-4c7a28c481da
checkpoint-status |  |  | checkpoint | NBN has been installed throughout complex
checkpoint-status |  |  | checkpoint | NBN signal has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for NBN install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - NBN has been tested & installed as per the above ITP - Add general photos/comments below
label | a2b1689d-ebc9-5a80-97bb-4e99eba10447 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Underground Gas Checklist (V140421) |  |  |  |  | Yes | Underground Gas Checklist (V140421) | a9df67f8-c9f6-4f7b-9e0f-35973ed89e27
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching operations @ 15M deep or greater
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-status |  |  | checkpoint | Site survey and confirm extent of works
checkpoint-status |  |  | checkpoint | Confirm area of work is accessable and acceptable to commence
checkpoint-status |  |  | checkpoint | Exclusion zone erected
checkpoint-status |  |  | checkpoint | Trench shoring/shield is on site
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Bedding material is correct type, grade and depth
checkpoint-status |  |  | checkpoint | Gas service installed to correct depth of cover
checkpoint-status |  |  | checkpoint | Service indicator tape installed
checkpoint-status |  |  | checkpoint | joints are correct
checkpoint-status |  |  | checkpoint | Risers are in correct location - provide photos
checkpoint-status |  |  | checkpoint | Gas service tested to AS/NZS 56012013 Provide Photos
checkpoint-status |  |  | checkpoint | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes prior to concrete
checkpoint-status |  |  | checkpoint | clean up of work area
checkpoint-status |  |  | checkpoint | General photos, comments & observations during Cold Water Rough-In (Add below)
checkpoint-status |  |  | checkpoint | Underground Gas completed to specification/drawings & Area left clean/tidy
label | 6d542556-59f9-559b-83d5-648ed699f970 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Suspended Slab - FULL (V140421) |  |  |  |  | Yes | Suspended Slab - FULL (V140421) | aa08029a-4348-4aec-b5be-7e71cc3e1e09
checkpoint-group |  |  | section | Prior to Deck Handover
checkpoint-status |  |  | checkpoint | Confirm deck is safe, handrails installed and edge protection is provided to full perimeter of deck
checkpoint-status |  |  | checkpoint | Confirm means of access to deck
checkpoint-status |  |  | checkpoint | Confirm Formworkers Deck Handover Certificate and ITP is received and sighted
label | e0887ff7-2bad-562e-a588-8811cd426654 |  | note | Attached below as applicable
button | e74250b7-3d80-53cc-abff-f8260b65f981 |  | button | Attach Deck Handover Certificate | Yes, No, N/A
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 7df5507b-95ff-597d-a204-d06a9b50bc4c |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Materials used complies with design documentation
checkpoint-status |  |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status |  |  | checkpoint | Grids marked by builder
checkpoint-status |  |  | checkpoint | Confirm As-Built Survey of deck is complete
label | 812c1ec5-08b1-583d-a9c2-214a23dbf4a1 |  | note | HOLD POINT - Attach As-Built Survey of Deck
checkpoint-status |  |  | checkpoint | Confirm Form Worker has received As-Built Survey of deck, and has rectified errors prior to any trades commencing on deck
checkpoint-status |  |  | checkpoint | Confirm all beams and decks constructed as per Structural Concrete Profiles
checkpoint-status |  |  | checkpoint | Install slip joints to all load bearing walls and corbels where required
checkpoint-status |  |  | checkpoint | Clean off decks and beams prior to pour, and ensure all exposed off-form soffits are free of any dust, stains and rust marks Hose down if necessary
checkpoint-status |  |  | checkpoint | Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary Cross-check the following drawings
boolean | b581f119-78ff-563c-8c17-0b18ae91e43f |  | tickbox | Hydraulic Drawings
boolean | 49f19275-1bd1-5207-b882-b0d435c5fd2f |  | tickbox | Architectural Concrete Outlines
boolean | 62c3a12b-e40f-5a9b-903e-e0e0392e73c1 |  | tickbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Check top RLs for all reinforcement, ensuring adequate concrete cover Confirm with Concreter
checkpoint-status |  |  | checkpoint | Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits
checkpoint-status |  |  | checkpoint | Attach Formwork ITP
checkpoint-status |  |  | checkpoint | Attach Formwork Engineer sign off certificate Confirm that certificate references props, braces and compliance with design & AS3610
label | 8dddd43d-f524-5632-9a6e-915ac411dda2 |  | note | Attach Formwork Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach ALL Services Hydraulic ITP (for cast-in elements), include relevant mark-ups below
checkpoint-status |  |  | checkpoint | Attach Precast ITP (for cast-in elements), including relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Reo Fixing ITP
checkpoint-status |  |  | checkpoint | Attach Principal Structural Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | f21af78b-5075-554c-ab31-8023ffcb67ea |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Attach Post Tensioning Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | 92c526e9-97f0-5ed6-bca9-a216acef169c |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
text | 98ce31ca-1714-5921-8d5a-ef0b266310c1 |  | textbox | Total m3 (as measured by Site Engineer)
text | 310a4873-e35b-515b-b1f4-6bf12264b00d |  | textbox | Total m3 (as measured by Foreman)
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg size of concrete prior to ordering
text | 17b786bc-6d1f-5c70-89c8-8d8c04adf8e7 |  | textbox | MPa
text | 070229b4-bb6f-550b-b471-914c2f1ceb3a |  | textbox | Slump
text | 3a42781b-080d-5ab6-b024-1e88f920acaf |  | textbox | Agg
checkpoint-group |  |  | section | During to Concrete Pour
checkpoint-status |  |  | checkpoint | Ensure concrete truck dockets have correct concrete strength, and attach delivery docket from each batch
checkpoint-status |  |  | checkpoint | Confirm concrete has falls to drainage points in slab
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour
boolean | b6d461e7-0352-5ef4-b1d8-51accff3a17c |  | tickbox | Formworker
boolean | 8e86e79f-9192-5886-8400-01cf3823c580 |  | tickbox | Electrician
boolean | b4593f80-9998-55b6-b38e-cc799f6e45a3 |  | tickbox | Plumber
boolean | b4c2c74a-63ad-5bf2-a0fb-8b0014e1a2d6 |  | tickbox | Post Tensioner
boolean | dbf77729-e566-5746-9320-76192bb4cc22 |  | tickbox | Precast Installer
checkpoint-status |  |  | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry
checkpoint-status |  |  | checkpoint | Confirm that all protection to precast panels is maintained at all times during concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
label | 80ba2c1b-1155-5b25-9a39-9c653b4310d7 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are in accordance with the specifications
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | 0b9fb2bb-a0a3-5e60-a85a-a7110eb627cd |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | ef28d299-a877-5bee-8cf3-47e50f93f0a6 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | d0c75f8b-1154-5d64-b395-37f9024f79f8 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | 52c8ccd4-9a18-5954-9443-49d6d8e7937a |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | 01abcdca-5c37-5fac-978f-93eeb86c5725 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 656cfabd-ae4f-5c3e-b514-3f8bb0469b06 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | d2b5dbc1-b68b-5e3d-aabd-758eca2e45f5 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Joinery Fit Out |  |  |  |  | Yes | Joinery Fit Out | ab44b929-8b4f-45fc-adaf-a9a41d8f400f
checkpoint-status |  |  | checkpoint | Shower screen has been installed level & tested
checkpoint-status |  |  | checkpoint | Door hardware has been installed & tested
checkpoint-status |  |  | checkpoint | Window & slider frames have been installed & fixed correctly
checkpoint-status |  |  | checkpoint | Sliders have visibility decals installed
checkpoint-status |  |  | checkpoint | All kitchen joinery & installed
checkpoint-status |  |  | checkpoint | Final sign off - All joinery fit out work completed as per the above ITP
label | 5f6fb286-3b8a-51b2-a501-28be1488eb72 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Suspended Slab |  |  |  |  | Yes | Suspended Slab | b05122be-0623-45e9-beaf-0d19a28a2fdd
checkpoint-status |  |  | checkpoint | Materials used complies with design documentation
checkpoint-status |  |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status |  |  | checkpoint | Grids marked by builder
checkpoint-status |  |  | checkpoint | Surveyor points given for outside of building
checkpoint-status |  |  | checkpoint | Fillet & drip mould installed
checkpoint-status |  |  | checkpoint | Check set down position & RL
checkpoint-status |  |  | checkpoint | Check penetrations installed
checkpoint-status |  |  | checkpoint | Column blockouts installed
holdpoint |  |  | signoff | Request Sign Off from Site Engineer
checkpoint-status |  |  | checkpoint | Check back propping as per design
checkpoint-status |  |  | checkpoint | Blow off deck
checkpoint-status |  |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status |  |  | checkpoint | Correct Class of Finish
checkpoint-status |  |  | checkpoint | Stripping, cleaning & materials removed
checkpoint-status |  |  | checkpoint | Final sign off - Suspended slab completed as per the above ITP - Add general photos/comments below
label | 7990cb8d-d0d8-56d0-974d-ca13025db7cb |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Carpark & Line Markings |  |  |  |  | Yes | Carpark & Line Markings | b38b4a44-5261-4d49-8a59-435674df66c8
checkpoint-status |  |  | checkpoint | Ensure all emergency lighting in car park has been installed as per plan
checkpoint-status |  |  | checkpoint | Check that all boom gates have been installed & tested
checkpoint-status |  |  | checkpoint | Check that all security systems within car park have been installed & tested
checkpoint-status |  |  | checkpoint | Check that all garage doors in car park have been installed & tested
checkpoint-status |  |  | checkpoint | Ensure all safety bollards in car park has been installed as per plan
checkpoint-status |  |  | checkpoint | Ensure all signage in car park has been installed as per plan
checkpoint-status |  |  | checkpoint | All line markings are completed in correct colour/Area according to specifications
checkpoint-status |  |  | checkpoint | All Numbering completed in correct colour/Area according to specifications
checkpoint-status |  |  | checkpoint | Final sign off - All line markings completed as per the above ITP - Add general photos/comments below
label | 0b16d9a0-5b47-5caf-891b-ec6683774c56 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Stairs |  |  |  |  | Yes | Stairs | b5d13f84-66d9-44a8-9cdf-710ca27d18c4
checkpoint-status |  |  | checkpoint | Land stringers & backdrops secured
checkpoint-status |  |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status |  |  | checkpoint | Couplers & rebate boards installed
checkpoint-status |  |  | checkpoint | Riser heights confirmed
checkpoint-status |  |  | checkpoint | Going lengths confirmed
checkpoint-status |  |  | checkpoint | Correct Class of Finish
checkpoint-status |  |  | checkpoint | Couplers & rebate boards installed
checkpoint-status |  |  | checkpoint | Riser heights confirmed
checkpoint-status |  |  | checkpoint | Going lengths confirmed
checkpoint-status |  |  | checkpoint | Ensure lighting has been installed in stairwells as per plans
checkpoint-status |  |  | checkpoint | Final sign off - All stairs completed as per the above ITP
label | e083a59f-7bb3-5649-adc9-53cbe58bd847 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Floor Wastes |  |  |  |  | Yes | Floor Wastes | b83e1114-af39-4c13-93d8-4456fd40c2fc
checkpoint-status |  |  | checkpoint | Plumber checks all pipes for any cracks, or imperfections
button | 94ca8170-c7d8-5266-89f6-0c2528d8c224 |  | button | Plumber completes stack work | Yes, No
button | 3c25a507-4189-5f06-a0bf-1a3e6842fc24 |  | button | Plumber cuts waste flush with concrete and puts sponge inside | Yes, No
button | a9f6335f-7310-5b1b-bea2-d61c2d3a618f |  | button | Plumber caps off all other pipes | Yes, No
checkpoint-status |  |  | checkpoint | Waterproofer pushes sponge down 100mm and finishes his membrane & flood test
checkpoint-status |  |  | checkpoint | Waterproofer removes sponge and releases water and puts the sponge back in ensuring there are no debris left in the pipe
checkpoint-status |  |  | checkpoint | Tiler accepts that the waste is clean and has a sponge in it
checkpoint-status |  |  | checkpoint | Tiler completes his works (i.e sand cement & tile)
checkpoint-status |  |  | checkpoint | Aland cleans and removes the sponge
checkpoint-status |  |  | checkpoint | Final sign off - All floor wastes completed as per the above ITP
label | 31d3a8d0-f701-5da0-9b00-9aa3de8799b9 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Internal Painting |  |  |  |  | Yes | Internal Painting | bb7f82ab-39e8-48f1-aab9-e218150574fe
checkpoint-status |  |  | checkpoint | Ensure to use right product & system as per specification & scope of works
checkpoint-status |  |  | checkpoint | Provide adequate ventilation & removal of waste disposed correctly
checkpoint-status |  |  | checkpoint | Final sign off - All internal painting work completed as per the above ITP
label | cea394c4-7c03-5798-9fc6-59af025ad6a0 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Power Connection |  |  |  |  | Yes | Power Connection | be47c51d-d131-49a8-9cfb-1434734fbf9b
checkpoint-status |  |  | checkpoint | Power has been installed throughout complex
checkpoint-status |  |  | checkpoint | Power has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for power install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - Power has been tested & installed as per the above ITP - Add general photos/comments below
label | fd5661a3-0e48-55ba-a7ca-7aa614ed27ff |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | SOG |  |  |  |  | Yes | SOG | beec3e86-a39b-4b28-a205-72fabb2d610e
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Materials used complies with design documentation
checkpoint-status |  |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status |  |  | checkpoint | Grids marked by builder
checkpoint-status |  |  | checkpoint | Confirm As-Built Survey of deck is complete
label | 6d3750e7-c7c4-5fc9-86e8-d6ca3ddd523a |  | note | HOLD POINT - Attach As-Built Survey of Deck
checkpoint-status |  |  | checkpoint | Confirm Form Worker has received As-Built Survey of deck, and has rectified errors prior to any trades commencing on deck
checkpoint-status |  |  | checkpoint | Confirm all beams and decks constructed as per Structural Concrete Profiles
checkpoint-status |  |  | checkpoint | Install slip joints to all load bearing walls and corbels where required
checkpoint-status |  |  | checkpoint | Clean off decks and beams prior to pour, and ensure all exposed off-form soffits are free of any dust, stains and rust marks Hose down if necessary
checkpoint-status |  |  | checkpoint | Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary Cross-check the following drawings
boolean | 337c210d-0583-5073-958e-855ffeccea22 |  | tickbox | Hydraulic Drawings
boolean | 77988f86-e5d6-5937-84fc-37c827ae19ff |  | tickbox | Architectural Concrete Outlines
boolean | 424d5508-4d28-558d-b6fe-ab7f24832b40 |  | tickbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Check top RLs for all reinforcement, ensuring adequate concrete cover Confirm with Concreter
checkpoint-status |  |  | checkpoint | Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits
checkpoint-status |  |  | checkpoint | Attach Formwork ITP
checkpoint-status |  |  | checkpoint | Attach Formwork Engineer sign off certificate Confirm that certificate references props, braces and compliance with design & AS3610
label | 5a953e21-5225-5fc0-9cce-ce45e2b2b80c |  | note | Attach Formwork Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach ALL Services Hydraulic ITP (for cast-in elements), include relevant mark-ups below
checkpoint-status |  |  | checkpoint | Attach Precast ITP (for cast-in elements), including relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Reo Fixing ITP
checkpoint-status |  |  | checkpoint | Attach Principal Structural Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | ff2b3166-7328-59cb-825a-60ec5bbd2176 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Attach Post Tensioning Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | f4d73a54-aa4f-5423-9f46-add514046141 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
text | 1deaeabe-948f-561c-a9fe-b67d4f4825b4 |  | textbox | Total m3 (as measured by Site Engineer)
text | 252cd264-9597-5c04-8764-385151f9fee6 |  | textbox | Total m3 (as measured by Foreman)
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg size of concrete prior to ordering
text | dc5cb0fa-c6b1-5a1e-8d7e-1d6eefbd74fa |  | textbox | MPa
text | 9bf71feb-38ab-5347-986a-590eb5d4c736 |  | textbox | Slump
text | ffe1bae3-d268-5e5e-837d-58e5bf22727f |  | textbox | Agg
checkpoint-group |  |  | section | During to Concrete Pour
checkpoint-status |  |  | checkpoint | Ensure concrete truck dockets have correct concrete strength, and attach delivery docket from each batch
checkpoint-status |  |  | checkpoint | Confirm concrete has falls to drainage points in slab
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour
boolean | 646e9786-43dc-58b8-a79d-6d6330015e14 |  | tickbox | Formworker
boolean | c5d4809b-b4e9-5442-963f-d4e989dc4f83 |  | tickbox | Electrician
boolean | 5ee8c4ef-bf83-5994-ad3b-0a3d2cc8bc59 |  | tickbox | Plumber
boolean | c2915fe5-d6f6-5caa-9e7d-b45ca8171c18 |  | tickbox | Post Tensioner
boolean | 32a63929-9c80-5a0d-bc1f-ee0e013acdae |  | tickbox | Precast Installer
checkpoint-status |  |  | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry
checkpoint-status |  |  | checkpoint | Confirm that all protection to precast panels is maintained at all times during concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
label | 53a26941-5d3d-5ac2-afe7-5281eb750be6 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are in accordance with the specifications
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | d554e224-a375-5ebe-92b2-1f6f10798970 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | a9b8ce76-c4d7-585b-9ce4-c7341d004290 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | 4a8dd70e-e113-5d74-b0c2-5b9a88167910 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | 557da339-afcc-56bc-82a6-aedf272e10d4 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | 7b011f36-adcf-563a-b0dd-f8aaa12a70b1 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 4786c283-4346-5c7d-a0b5-211d51b2c07e |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 2e735e5d-1cd6-5a8f-9773-16f9ab155bbf |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Building Authority Checklist |  |  |  |  | Yes | Building Authority Checklist | c1a68cfe-01bc-4bf3-84fe-db178356c5f3
checkpoint-status |  |  | checkpoint | Ensure all Aland documentation is registered with the council - Atatched below
checkpoint-status |  |  | checkpoint | Electrical Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Hydraulic Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Mechanial Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Fire Services Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Lifts Compliance Documentation reviewed and attached
checklist-flat |  |  | checklist | Underground Water Checklist (V140421) |  |  |  |  | Yes | Underground Water Checklist (V140421) | c1fcd439-3e68-4ad3-bc31-da480eed7ed4
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching operations @ 15M deep or greater
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-status |  |  | checkpoint | Site survey and confirm extent of works
checkpoint-status |  |  | checkpoint | Confirm area of work is accessable and acceptable to commence
checkpoint-status |  |  | checkpoint | Exclusion zone erected
checkpoint-status |  |  | checkpoint | Trench shoring/shield is on site
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Bedding material is correct type, grade and depth
checkpoint-status |  |  | checkpoint | Water service installed to correct depth of cover - Provide photos
checkpoint-status |  |  | checkpoint | Service indicator tape installed
checkpoint-status |  |  | checkpoint | joints are correct - Provide photos
checkpoint-status |  |  | checkpoint | Risers are in correct location - provide photos
checkpoint-status |  |  | checkpoint | Water service tested to AS/NZS 35002018 Provide Photos
checkpoint-status |  |  | checkpoint | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes prior to concrete
checkpoint-status |  |  | checkpoint | clean up of work area
checkpoint-status |  |  | checkpoint | General photos, comments & observations during Cold Water Rough-In (Add below)
checkpoint-status |  |  | checkpoint | Underground Water completed to specification/drawings & Area left clean/tidy
label | 0b426a19-9f5a-5896-8e6f-b54739420415 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Windows/Doors Installation Checklist |  |  |  |  | Yes | Windows/Doors Installation Checklist | c3c5265f-ff83-4173-9d6f-4e9ee917cc0d
checkpoint-status |  |  | checkpoint | Waterproofing angle completed
checkpoint-status |  |  | checkpoint | Structural angle to be installed before subhead and subsill as per Façade Engineers details
checkpoint-status |  |  | checkpoint | Installation of sub-sill and caulked
checkpoint-status |  |  | checkpoint | Water test sub-sill
checkpoint-status |  |  | checkpoint | Installation of sub-head and caulked
checkpoint-status |  |  | checkpoint | Install frames including trims to doors
checkpoint-status |  |  | checkpoint | Install windows and trimming
checkpoint-status |  |  | checkpoint | Install door panels
checkpoint-status |  |  | checkpoint | Installation of all hardware
checkpoint-status |  |  | checkpoint | Ensure all external and internal angles are sealed
checklist-flat |  |  | checklist | Car Wash Bay |  |  |  |  | Yes | Car Wash Bay | c51376c9-02fe-4b06-8afd-ea10f38ec0ec
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | f4f1fb14-f5aa-5406-b3a0-2507679aff4e |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Car wash bay installed as per manufacturer's instructions & standards
checkpoint-status |  |  | checkpoint | Car wash bay tested as per manufacturer's instructions & standards
checkpoint-status |  |  | checkpoint | Car wash bay commissioned as per manufacturer's instructions & standards
checkpoint-status |  |  | checkpoint | Final sign off - Car wash bay installed as per the above ITP - Add general photos/comments below
label | 47b1da45-e047-5d80-a9c5-0c149710784a |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Basement Tanking |  |  |  |  | Yes | Basement Tanking | c62cd780-8e57-4524-984f-000e67961f2a
checkpoint-status |  |  | checkpoint | PE film installed towards substrate, grey side facing installer (Blanket).
checkpoint-status |  |  | checkpoint | Overlap of 100-200mm at ends has been installed.
checkpoint-status |  |  | checkpoint | Substrate clean, dry & free from dust
checkpoint-status |  |  | checkpoint | Bentoseal Paste has been used to seal all penetrations.
checkpoint-status |  |  | checkpoint | Termination of membrane as per manufacturer's details.
checkpoint-status |  |  | checkpoint | Waterstop RX-101 at vertical spray break with 75mm cover has been
checkpoint-status |  |  | checkpoint | Installation of CETCO granules to perimeter floor/wall junctions.
checkpoint-status |  |  | checkpoint | Installation of RX101 to manufacturer's details using Cetseal Bead to secure to substrate.
checkpoint-status |  |  | checkpoint | Transition Sheet installed as per manufacturer's recommendations.
checkpoint-status |  |  | checkpoint | Installation of RX101 to perimeter of pile cap, using CetSeal follows manufacturer's recommendations
checkpoint-status |  |  | checkpoint | Detailing of blanket to perimeter of pile caps as per manufacturer's recommendations.
checkpoint-status |  |  | checkpoint | All Construction joints are cleaned out and ready for membrane Application
checkpoint-status |  |  | checkpoint | All Membrane Application is completed in accordance with CETCO Detail / ALAND SIGN OFF
checklist-flat |  |  | checklist | Services Fit Out |  |  |  |  | Yes | Services Fit Out | cad0330b-f01c-4632-b55f-b3256541123b
checkpoint-status |  |  | checkpoint | All plumbing fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Final running test of all plumbing items
checkpoint-status |  |  | checkpoint | All electrical fitout have been tested
checkpoint-status |  |  | checkpoint | All intercom points are installed & are level & in correct location
checkpoint-status |  |  | checkpoint | All security systems have been installed & tested
checkpoint-status |  |  | checkpoint | NBN has been tested & commision
checkpoint-status |  |  | checkpoint | Air con has been final tested & commissioned
checkpoint-status |  |  | checkpoint | Test fire doors install as per code closing & gapping around door
checkpoint-status |  |  | checkpoint | Fire door hardware test holes, closers & locks
checkpoint-status |  |  | checkpoint | Final sign off - All services fit out work completed as per the above ITP
label | bbeefc2f-15ab-53c5-b7c7-70ca42689c0a |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Columns |  |  |  |  | Yes | Columns | ce261ed1-b90b-43f7-a71c-e54b84acf2d6
checkpoint-group |  |  | section | Pre-Column Pour
checkpoint-status |  |  | checkpoint | Survey points given for 2 points
checkpoint-status |  |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status |  |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint |  |  | signoff | Request Sign Off from Site Engineer
checkpoint-status |  |  | checkpoint | Column box cleaned & oiled
checkpoint-status |  |  | checkpoint | Placement of column box over cage
checkpoint-status |  |  | checkpoint | Bracing props secured
checkpoint-status |  |  | checkpoint | Column plumbed
checkpoint-status |  |  | checkpoint | Correct class of finish
checkpoint-status |  |  | checkpoint | Final sign off - Columns completed as per the above ITP - Add general photos/comments below
label | 98e0646c-1f0c-56bf-a087-ddf75e5cab15 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checkpoint-group |  |  | section | After Column Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
label | 75aed0dd-0e9f-5a2b-ba62-ecb08f8520e4 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are in accordance with the specifications
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | 67a1d3a6-87af-52ae-9076-32c08f796da9 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | 7d449867-4d1b-5ff8-b1e8-8d7353def6f8 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | 55b038d8-1219-5693-a326-6f58c808dfc6 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | ef7791ad-63b3-5a69-b104-2b7518fb9c45 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | cf130230-86cc-50be-a334-1fbda1c58a70 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 1b1b4a86-5b81-5959-b372-5565169a79dc |  | button | Subcontractor Sign Off | Yes, No, N/A
button | fdb3a0b1-1468-549b-925b-383a96b12290 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Detailed Excavations |  |  |  |  | Yes | Detailed Excavations | cf3a3136-8a20-414a-9ca7-99f57096ebe7
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to excavation commencing
checkpoint-status |  |  | checkpoint | Any batters formed correctly
checkpoint-status |  |  | checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
checkpoint-status |  |  | checkpoint | Bulk Excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Final sign off - All detailed excavations completed as per the above ITP
label | 37b71bbf-0fc8-59c3-9811-8cf6ff384bc2 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | In-Ground Stormwater ITP (V140421) |  |  |  |  | Yes | In-Ground Stormwater ITP (V140421) | e2937ec3-0964-4880-8016-08ec25a7e87d
checkpoint-group |  |  | section | Pit and Pipes
checkpoint-status |  |  | checkpoint | Is Approval from Local Water Authority Required If so please provide permit
holdpoint |  |  | signoff | Sign Off Required
checkpoint-status |  |  | checkpoint | Details
text | cc128687-74c8-5966-a60b-69747090ed79 |  | textbox | Engineering Plan Number(s)
text | 68f4453c-9fa0-53e8-ba19-82cef2905cf4 |  | textbox | Name of certified drainlayer and registration number
text | 464edb95-6d11-55ef-8b99-f6e925bbe7f8 |  | textbox | Location (Pit to Pit)
text | 70048c92-d25a-56ec-a0ab-ef29c53e0ecc |  | textbox | Delivery Date (Pits and Pipes)
text | 24693d8b-ea09-55d3-b846-50a4056265e3 |  | textbox | Is work area clear and available for construction
text | b92771cc-e1c5-5ec7-a28a-ac179d8db17a |  | textbox | Do you have the appropriate plant to perform scope of works Provide plant details
checkpoint-group |  |  | section | Trench/Excavation Methodology
checkpoint-status |  |  | checkpoint | Method
boolean | 892c5bbc-1251-5272-9c17-1dad23981efc |  | tickbox | Sheild
boolean | 63352acd-63d2-51a8-846d-61c30d0840a9 |  | tickbox | Bench
boolean | 947b666d-d89f-5447-9670-0075c5a424a7 |  | tickbox | Batter
boolean | 08412142-82bd-5713-b5f8-6e0597eb57f6 |  | tickbox | Other
text | 4f7d799d-8346-570a-b690-afe97f950b56 |  | textbox | If other please specify
boolean | 3f3891c6-3e51-574f-9f87-c04e43355909 |  | tickbox | Certified / Tagged lifting Equipment
checkpoint-group |  |  | section | Product / Material check
checkpoint-status |  |  | checkpoint | Pits
text | 95f5aa0e-5c7f-576c-8dcb-11f7f4624972 |  | textbox | Type
text | 6dcbc6c7-7475-56e4-9ccc-3186449c3679 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Pipes
text | c1774bb0-2f5a-5a1e-8d08-d29d938e8be2 |  | textbox | Type
text | e6790b73-8d7d-5a9e-8771-796025cb0cd9 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Lot Connections
text | df9ef0ef-61bd-500f-9318-6452b924e0ec |  | textbox | Type
text | b94ed568-4b82-5809-8c38-7afb6bcabbc8 |  | textbox | Lot number Location
checkpoint-status |  |  | checkpoint | Bends
text | f908fcb5-e258-52bf-8105-d3dd8fb74aa3 |  | textbox | Location
text | 965fe534-6334-5c10-8040-ab453a9c6ae8 |  | textbox | Type
text | bf206c4a-7a6e-5a53-805e-57257f067e46 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Quality Onsite Visual Inpection of Products / Materials - Defects to be Notified
text | 6cd5e36a-882b-5c1e-bce8-4b554809e5f1 |  | textbox | Surveyors name
checkpoint-status |  |  | checkpoint | Set out / Off Set Check
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pit Installation
checkpoint-status |  |  | checkpoint | Pits
text | 7f745652-c0d4-5d45-978a-8b20af1c9c97 |  | textbox | Bedding and backfill type as per detail
text | b7ff802c-4ef8-5568-a42c-d19c4078088f |  | textbox | Undercut weak unsuitable subgrade note chainage and depth ( Approval Required)
boolean | 4cfc90b5-ec7b-53a6-8d88-b116a42bf1a1 |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
boolean | 6be074e1-8c44-5492-b6a9-1f366323504b |  | tickbox | External Concrete Bandage
boolean | edc86d00-316c-5383-9e48-e97bc3bd7b5a |  | tickbox | Internal Benching
boolean | 34780c2d-bc30-5f9a-af2d-129ed2bec724 |  | tickbox | Internal Plastering / Render / Sealant
boolean | 6a6b27dc-bfb2-5ef4-853c-588095548f2a |  | tickbox | Sealant Between Riser
boolean | ff2c628e-0d5f-59f4-874a-abb2b3ab06c7 |  | tickbox | Steps Required
text | f5cb5d53-4240-5b83-9bfd-a2265caaa2be |  | textbox | Have pits been secure and covered during installation to reduce debris/silt
checkpoint-status |  |  | checkpoint | Pipe invert levels through pit as per design
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pipe installation
checkpoint-status |  |  | checkpoint | Pipes
boolean | 91430fc9-7a1a-5adc-baf8-81f0dc40250d |  | tickbox | Are pipes free and clean of debris before installation
text | 814a2ee6-7829-53f8-a148-869f27b5bbe6 |  | textbox | Bedding and backfill type as per detail
text | 1d8b5042-312a-5a50-a03e-157594a98ecf |  | textbox | Undercut weak unsuitable subgrade note chainage and depth (Approval Required)
boolean | e7caa462-785c-5fad-9643-e304c11c873c |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
checkpoint-group |  |  | section | Drainage Data
checkpoint-status |  |  | checkpoint | Backfill to be compacted in 150mm Layers as per detail
text | 28a4a9c5-f6e5-5829-a72e-336bcc0627d6 |  | textbox | Grade and Alignment Check
text | cd7b5a5b-d7c8-557f-8252-4c9cf2bef580 |  | textbox | Invert / RL Check
text | 56b77e96-2930-5259-bf81-f4d50d9bddc9 |  | textbox | CCTV pipe inspection data and comments supplied
holdpoint |  |  | signoff | Sign Off Required
checkpoint-status |  |  | checkpoint | Progress Photos
checkpoint-group |  |  | section | Service Connections
checkpoint-status |  |  | checkpoint | All Connections, Bends, Junctions installed
text | b2ffb323-1ed4-5399-b1f4-2358142c1a8d |  | textbox | As-built measurements / Pick up Recorded Before Backfilling
holdpoint |  |  | signoff | Sign Off Required
checklist-flat |  |  | checklist | Jump Form |  |  |  |  | Yes | Jump Form | e511eb9b-4e06-40f3-9611-cd25d8fee5d9
checkpoint-status |  |  | checkpoint | Confirm Class of formwork to all faces, as per the latest specifications
checkpoint-status |  |  | checkpoint | Confirm RL's of soffit & beams
checkpoint-status |  |  | checkpoint | Confirm any penetration sizing for any hoist/crane penetrations
checkpoint-status |  |  | checkpoint | Ensure formwork frames installed to enable clear & labelled access under deck for other personnel & for inspections
checkpoint-status |  |  | checkpoint | Ensure all formwork surfaces are cleaned & no rubbish remains on any soffits,sides,base of work
checkpoint-status |  |  | checkpoint | Ensure bases of all columns/walls are cleaned out prior to pouring
checkpoint-status |  |  | checkpoint | Check formwork is completed as per specified Class
checkpoint-status |  |  | checkpoint | Ensure no rubbish or excess water is present prior to concrete pour
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Formwork stripped in a safe manner
checkpoint-status |  |  | checkpoint | All timbers de - nailed
checklist-flat |  |  | checklist | Windows/Doors |  |  |  |  | Yes | Windows/Doors Installation Checklist (old) | e682f7cd-e008-4871-8463-5af58390c36e
checkpoint-status |  |  | checkpoint | Waterproofing angle completed
checkpoint-status |  |  | checkpoint | Installation of sub-sill and caulked
checkpoint-status |  |  | checkpoint | Water test sub-sill
checkpoint-status |  |  | checkpoint | Installation of sub-head and caulked
checkpoint-status |  |  | checkpoint | Install frames including trims to doors
checkpoint-status |  |  | checkpoint | Install windows and trimming
checkpoint-status |  |  | checkpoint | Install door panels
checkpoint-status |  |  | checkpoint | Installation of all hardware
checkpoint-status |  |  | checkpoint | Ensure all external and internal angles are sealed
checklist-flat |  |  | checklist | Cold Water Pump Room |  |  |  |  | Yes | Cold Water Pump Room | e88cec7c-1d09-4c2e-b9fe-23e61db5004d
checkpoint-status |  |  | checkpoint | Ensure cold water pumps are installed as per plans
checkpoint-status |  |  | checkpoint | Pump isolation valves installed on all pumps
checkpoint-status |  |  | checkpoint | All pipe work tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation
button | 25b6f38e-23ee-5ed9-b800-98029bd81f15 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | c4c024ba-de3d-53b7-8da6-8671ba168fe9 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 69430557-1a21-5fcd-8cc4-3a520526e058 |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | 04288a00-e88b-59e6-9742-6b9caac2b75a |  | button | Cables are labelled as per specified requirements | Yes, No
button | 34e744ef-7e1a-5f94-8dd2-751c102f61d1 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | cb23d8ca-2a7a-50a5-a31d-ea2b7f63e555 |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Final sign off - Cold water pumps installed as per the above ITP - Add general photos/comments below
label | a89040e5-5734-51c1-b21c-33529b4d381a |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Plumbing Rough-In |  |  |  |  | Yes | Plumbing Rough-In | f0dd65ec-b81a-4b4a-86ed-75e42df66217
checkpoint-status |  |  | checkpoint | Floor wastes checked - Any issues comment/photo below
checkpoint-status |  |  | checkpoint | 1m offset to floor height has been achieved
checkpoint-status |  |  | checkpoint | Mixers are in correct position (hole allowance to work with tiles)
checkpoint-status |  |  | checkpoint | All wall hung items have been allowed for in setout
checkpoint-status |  |  | checkpoint | All rough-in pipework is colour coded to ensure no cross connections
checkpoint-status |  |  | checkpoint | All poly pipes located in framing to ensure no screw fixings will penetrate them
checkpoint-status |  |  | checkpoint | All Water & Gas risers are complete
checkpoint-status |  |  | checkpoint | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Ensure all services that go through fire rated walls to be treated with collars/fire rated sealant
checkpoint-status |  |  | checkpoint | Pipework tested
checkpoint-status |  |  | checkpoint | Ensure rough in has been done as per specs
checkpoint-status |  |  | checkpoint | Ensure dummy fit‐out has been done
checkpoint-status |  |  | checkpoint | Final sign off - All plumbing work completed as per the above ITP
checklist-flat |  |  | checklist | Shower |  |  |  |  | Yes | Shower | f3ca0466-6cd1-4155-a18d-1b67622dc374
checkpoint-status |  |  | checkpoint | Confirm Material is as per specs
checkpoint-status |  |  | checkpoint | Confirm Layout
checkpoint-status |  |  | checkpoint | Confirm Waterproofing angle to shower screen frame is complete
checkpoint-status |  |  | checkpoint | Confirm Shower frame is secure
checkpoint-status |  |  | checkpoint | Confirm glass is installed correctly & secured
checkpoint-status |  |  | checkpoint | Confirm Silicone applied between glass & frame to secure & seal
checkpoint-status |  |  | checkpoint | Confirm gap is consistent between glass & frame/wall
checkpoint-status |  |  | checkpoint | Confirm Handles installed
checkpoint-status |  |  | checkpoint | Confirm Bathtub installed is as per specs
checkpoint-status |  |  | checkpoint | Confirm bathtub is secure & in place
checkpoint-status |  |  | checkpoint | Confirm bathtub waste is situated correctly above floor waste
checkpoint-status |  |  | checkpoint | Confirm works completed as per ITP above
checklist-sectioned |  |  | checklist | OSD |  |  |  |  | Yes | OSD | f4abd469-f08c-4cfd-8452-6c8cb0bfc567
checkpoint-group |  |  | section | Pre-Commencement
checkpoint-status |  |  | checkpoint | WorkSafe notification before trenching below 1.5m deep has been submitted
button | 09cc3900-d550-5697-b08f-6f337002774c |  | button | If required, trench shields are on site & ready for use | Yes, No
button | 1bc49a13-3992-5870-829d-ec8523d36a01 |  | button | Dig Permit completed by contractor & attached | Yes, No
button | ce0875bf-b473-58c1-9c48-04f16cc9c8e5 |  | button | Exclusion Zones have been erected as required (Attach photos below) | Yes, No
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-group |  |  | section | Detail excavation
checkpoint-status |  |  | checkpoint | Excavation depths & locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Any services (overhead / below ground) considered & isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to contractor to commence detail excavation
checkpoint-status |  |  | checkpoint | Excavation measurements align with drawings
boolean | 0e16e4c3-9315-5727-beac-0f901b18a9fe |  | tickbox | Depth, Width & Length correct
checkpoint-status |  |  | checkpoint | Excavation works - completed to specification/drawings & Area left clean/tidy
label | cd06b13b-9d9c-5746-a467-0d834864ec18 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group |  |  | section | Tanks/ Pumps / Chambers/ Grease arrestor Installation
checkpoint-status |  |  | checkpoint | Bedding material- correct type, grade and depth installed to support service
checkpoint-status |  |  | checkpoint | Product delivered is in good condition and correct as per specifications
checkpoint-status |  |  | checkpoint | Tanks/Pumps/Chambers/Grease arrestor Installed in the correct location and required depth
boolean | ee3bf322-5397-5ae5-a6b3-8f16fe298a91 |  | tickbox | Items are correctly sealed
checkpoint-status |  |  | checkpoint | Conduits installed - Provide photos
boolean | b739f2f2-9ef0-5766-bb3a-9017e3027b4f |  | tickbox | Cables pulled through conduit
checkpoint-status |  |  | checkpoint | Installation 100% Completed - All final checks, documentation completed & attached - (Attach photos below)
label | 2f4f17c2-e318-5f70-a778-faa2f0ff1377 |  | note | FINAL - Pass when work(s) are completed (Any issues please comment below)
checkpoint-group |  |  | section | Backfill
checkpoint-status |  |  | checkpoint | Tanks/ Pumps / Chambers/ Grease arrestor covered and made safe
boolean | d04873ca-1ad9-5c06-9072-4596d6d771cd |  | tickbox | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes before concrete - If applicable
checkpoint-status |  |  | checkpoint | Rissers lagging has been installed - If applicable
checkpoint-status |  |  | checkpoint | HOLD POINT - Subcontractor QA Reviewed (Comment issues below)
boolean | 76ce6597-96ba-5692-8025-bf856fc1f43a |  | tickbox | Test completed by contractor and confirmed to Ryman
label | bce84975-da12-5b96-8bad-8da3eb6c923c |  | note | Once reviewed & approved - Please attach (if applicable)
checkpoint-status |  |  | checkpoint | Works 100% completed to specification/drawings & Area left clean/tidy
label | bea9e3ed-2372-5787-ab94-c4d38be1fdca |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Hydraulic Groundwork |  |  |  |  | Yes | Hydraulic Groundwork | f5e9b150-be54-442a-a964-b2cb1cd05ed1
checkpoint-group |  |  | section | Pre-Commencement
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching below 1.5m deep has been submitted
label | 06bc9d50-e951-5c18-b6a7-5f9ea35c49f2 |  | note | If notification is required attach documents below
button | 06c57301-4d28-5c2d-bb51-1aae6a2329f7 |  | button | If required, trench shields are on site & ready for use | Yes, No
button | 88367c02-8eec-55c2-9ac9-bbde15aa3ffc |  | button | Dig Permit completed & attached | Yes, No
button | 07fe7ded-efca-5051-bee5-d11ed2d2cdfc |  | button | Exclusion Zones have been erected as required (Attach photos) | Yes, No
checkpoint-status |  |  | checkpoint | Works have been coordinated with other trades
checkpoint-status |  |  | checkpoint | Excavation depths & locations confirmed prior to commencement
checkpoint-status |  |  | checkpoint | Approval given to Trade Contractor to commence stormwater installation
checkpoint-group |  |  | section | Excavation Works
checkpoint-status |  |  | checkpoint | Excavation Checked, Correct & Approved
boolean | 82571146-6ded-52b2-a2d4-5dbe7c561317 |  | tickbox | Depth Accurate
boolean | a4cae0e0-0bd3-5ee7-8ef4-cfce3f5461aa |  | tickbox | Width Accurate
checkpoint-status |  |  | checkpoint | Excavation works - completed to specification/drawings & Area left clean/tidy
label | 4f1e1c61-2201-59f0-8cdf-96236b593e63 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group |  |  | section | Stormwater Installation
checkpoint-status |  |  | checkpoint | Pit installation correct
button | 49ca7c74-c09c-5d67-9e09-faa50f108865 |  | button | Pit size correct | Yes, No
button | d6d95b2f-8f08-5534-9798-38bb713ab72f |  | button | Pit location correct | Yes, No
button | 6a84c9d2-fde6-55c8-a4f1-34eba5fa429b |  | button | Pit invert levels correct (In & Out) | Yes, No
button | 42063ae3-804e-5df7-b947-13dec11fa2f6 |  | button | Pit finished RL correct | Yes, No
button | 8f382b3a-37ed-500c-be35-d5a6ad7f0391 |  | button | Pits covered & made safe | Yes, No
checkpoint-status |  |  | checkpoint | Bedding material is installed & correct to support service
checkpoint-status |  |  | checkpoint | Pipe installation correct
button | d82c99fc-ffc6-5295-8df6-b3c3833044cb |  | button | Pipe size correct as documented | Yes, No
button | faff4515-f38b-590d-8836-f3076dc83aba |  | button | Trenches have been backfilled & compacted correctly | Yes, No
button | b6f98eb3-4dbc-560a-9c32-e2b00727c167 |  | button | Service location tape Installed (if applicable) | Yes, No
checkpoint-status |  |  | checkpoint | Provisions for Aggie Pipe Connection installed as documented
checkpoint-status |  |  | checkpoint | Expansion Lagging has been installed where service will be cast into concrete
checkpoint-status |  |  | checkpoint | Stormwater install completed to specification/drawings & Area left clean/tidy
label | 6afa7015-73f9-5570-9f40-dca2f7d2ea9f |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Shotcrete (V140421) |  |  |  |  | Yes | Shotcrete (V140421) | fae85789-b25e-4b6e-8107-c96910a5aeae
checkpoint-group |  |  | section | Prior to Commencing Works
checkpoint-status |  |  | checkpoint | Ensure zone for shotcrete has been excavated
checkpoint-status |  |  | checkpoint | Confirm reinforcement has not moved by concrete placement
button | fe77631a-0df6-5dbd-8364-b814ea522f4c |  | button | Confirm that all mesh has bar chairs tied to steel to prevent dislodgement during shotcrete works | Yes, No, N/A
button | e34a8346-55f9-5d0c-9ec0-3521e0a8beb0 |  | button | Confirm that reinforcement has been installed in accordance to structural engineer details prior to arranging for site inspection | Yes, No, N/A
button | 54a0664a-a88b-5c14-9d07-1b183f1daa35 |  | button | Where recessed column is located, confirm that reinforcement installation allows for rebated shoring zone | Yes, No, N/A
button | 75539662-abb5-58ec-8db3-36a5d06b238f |  | button | Confirm that min 300mm lap has been provided for mesh and plastic membrane at typical horizontal control joint | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Confirm no blow-outs have occurred
checkpoint-status |  |  | checkpoint | Confirm core drain has been installed in accordance with specifications
checkpoint-status |  |  | checkpoint | Confirm plastic membrane to rear face of shotcrete wall has been lapped and taped at joints
checkpoint-status |  |  | checkpoint | Confirm that structural engineer has completed inspection and provided signoff (incl defect closeouts)
label | dd28234d-db06-5610-8bb6-e30ce65d9c0b |  | note | Engineer inspections attached/referenced below
checkpoint-status |  |  | checkpoint | Confirm that inspection photos are taken and attached below
checkpoint-group |  |  | section | Shotcrete Works
checkpoint-status |  |  | checkpoint | Confirm that shotcrete is applied evenly in layers to avoid honeycombing
checkpoint-status |  |  | checkpoint | Ensure that shotcrete wall is troweled to agreed finish
checkpoint-status |  |  | checkpoint | Obtain subcontractor’s installation ITPs and shotcrete mix dockets
label | bfacb5fd-a8e5-5d6d-960d-20f709317040 |  | note | Attached/referenced below as applicable
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | c66d885f-fbba-5d68-a0bc-2a5cfb360cfb |  | button | Subcontractor Sign Off | Yes, No, N/A
button | f0a4d1e4-eb77-5ba3-aa43-83dad2cb800c |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Garbage Room (V90421) |  |  |  |  | Yes | Garbage Room (V90421) | fc4d1535-344a-428e-b8cd-46910b29f9fb
checkpoint-status |  |  | checkpoint | Coving perimeter of the floor
checkpoint-status |  |  | checkpoint | Epoxy floor and wall up to 15m high
checkpoint-status |  |  | checkpoint | Hot & Cold water taps installed
checkpoint-status |  |  | checkpoint | Check for need of hot water tank
checkpoint-status |  |  | checkpoint | All PVC piping to be fire checked
checkpoint-status |  |  | checkpoint | Garbage room exhaust fan installed correctly
checkpoint-status |  |  | checkpoint | Garbage room overhead lighting installed
checkpoint-status |  |  | checkpoint | Signage is clearly installed
checkpoint-status |  |  | checkpoint | Magnetic door holder fitted and functioning correctly on all entry / exit doors
checkpoint-status |  |  | checkpoint | Final sign off - All garbage room work completed as per the above ITP - Add general photos/comments below
label | 9d9e1406-1624-549f-9ac0-4fc311f83454 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | General Waterproofing |  |  |  |  | Yes | General Waterproofing | fcb0881c-6adf-4886-938e-5e9520ddf820
checkpoint-status |  |  | checkpoint | Membrane system & methodology checked off Against Aland standard
checkpoint-status |  |  | checkpoint | Surface preparation as per application guide
checkpoint-status |  |  | checkpoint | Substrate clean, dry & free from dust
checkpoint-status |  |  | checkpoint | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instrument
checkpoint-status |  |  | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | 9e80e4bb-218e-5e5e-81dc-d0eea1696e87 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Balustrade |  |  |  |  | Yes | Balustrade | ff8fdb19-77fb-47be-88d1-2aa77ac617c1
checkpoint-status |  |  | checkpoint | Confirm Location Set out
checkpoint-status |  |  | checkpoint | Setout marks for core-drill
checkpoint-status |  |  | checkpoint | Core drill set-out marks as per structural engineer design
checkpoint-status |  |  | checkpoint | Install balustrades as per setout & Engineers specs
checkpoint-status |  |  | checkpoint | Fill Core holes with structural non-shrink grout
checkpoint-status |  |  | checkpoint | Place protection on Balustrades
checkpoint-status |  |  | checkpoint | Ensure Glazing is as per spec & install once Balustrade Sets & protect. Ensure Rubber is installed
checkpoint-status |  |  | checkpoint | Ensure no cracks in glass
checkpoint-status |  |  | checkpoint | Install Top-rail & Weld 100mm hit & miss