## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | In-Ground Gas/Fire Services (V.151121) |  |  |  |  | Yes | In-Ground Gas/Fire Services (V.151121) | 1c86c1fa-1205-432b-b83e-f5e3cc8e3dc3
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | a706c5ee-b126-55aa-b55b-d6ed40ebe697 |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations completed & checked
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Pressure testing completed
label | 817dac64-daf9-53b9-93bd-e7d510917a11 |  | note | Attach photos of testing apparatus below
text | 4e0227aa-b3cd-5343-a084-ec20845afd04 |  | textbox | Pressure test kPa
checkpoint-status |  |  | checkpoint | Check products for imperfections
label | 1162738b-aa3c-5d7a-81e5-1f139d2ffdb5 |  | note | Any issues, comment / photograph below
checkpoint-status |  |  | checkpoint | Backfill and compaction as per spec.
checkpoint-status |  |  | checkpoint | Inspection by Authority
label | 4754ed75-6856-538a-80c0-c71367ae7ab2 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | 077b0073-9add-528a-a24f-cd3feab9120c |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | ce5724be-4d7e-5d4d-abfa-48145743ed09 |  | note | Click to Attach Signature(s) below
button | 2366cde2-fbd6-52c9-838f-1c75aa74c663 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 1f794b69-56fc-554d-a6db-f3ddf9f4259a |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Below Ground Sewer Drainage (V.081021) |  |  |  |  | Yes | Below Ground Sewer Drainage (V.081021) | 3ad261b0-bd4e-4e79-9554-0bb4c6a4cc71
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | d7cbe7ae-3940-5194-83a3-4b238c3b315c |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Inspection by Authority
label | 6c56a625-b75d-5462-ab9d-e215a04730a8 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | f409947c-f809-5531-9f27-0872612722bd |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | e2afd22c-2860-56d0-b172-522a2416e272 |  | note | Click to Attach Signature(s) below
button | 5c5d15da-62f6-5629-bfed-6cd42ae274a9 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 0be4d156-422b-591f-b45c-3696ddeacfcc |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Hot Water (V.081021) |  |  |  |  | Yes | Hot Water (V.081021) | 3f4f717b-b2ab-4896-b64b-8790e482f887
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | c2b2dd25-4680-5c62-99e0-9ff58aa00c6d |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations/fire collars completed & checked
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Fire penetration caulked
checkpoint-status |  |  | checkpoint | Insulation / lagging installed
checkpoint-status |  |  | checkpoint | Temp control valves installed
checkpoint-status |  |  | checkpoint | Pressure & Temperature testing completed
label | 02d28e1a-234f-5fe9-bc47-73627d1e43a6 |  | note | Attach photos of testing apparatus below
text | cbceb813-2c2f-5c6a-887e-8ae50544d80b |  | textbox | Pressure test kPa
text | 078cfec4-8ab6-5eb1-baa9-f60096b351df |  | textbox | Water temperature
checkpoint-status |  |  | checkpoint | Inspection by Authority
label | fa18eb0e-1ffd-580d-b186-dce7e3d2ad8c |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | 5cf088cb-cada-5380-80d4-4b6aeee9984c |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 67b00c7c-468d-5735-b417-471cca87f223 |  | note | Click to Attach Signature(s) below
button | b4e32ab4-f62b-5453-aefe-444257772c26 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 958bc833-8789-51ed-a377-b4d400937f8d |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Sanitary Fixture (V.081021) |  |  |  |  | Yes | Sanitary Fixture (V.081021) | 3f698c99-bec0-413d-95ab-7b16e1ee6831
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | 0beb97ce-5b12-5c97-911d-bca6d4854622 |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Fittings & fixtures
label | 21a04578-a0d6-599d-bf08-3437efe7cd72 |  | note | As per FFE Schedule
checkpoint-status |  |  | checkpoint | Fixture install completed
label | 8f76fc29-bb68-5260-a79e-b39e28243fed |  | note | As per FFE Schedule
checkpoint-status |  |  | checkpoint | Check products for imperfections
label | 8be8d07f-3332-5db9-8b21-5a5b3cc7e799 |  | note | Any issues, comment / photograph below
checkpoint-status |  |  | checkpoint | Silicone seals completed - Neat & tidy
label | 060ed8ba-8ef0-5576-9f0d-317bea7b37a1 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | de4b05f6-722f-5655-b6ab-e9419c395e6b |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 3e68983a-66b6-5b04-92c1-96812fc87a9f |  | note | Click to Attach Signature(s) below
button | 890fcf2b-e707-5941-b76d-04566effda31 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 3f9089fc-0152-5a22-81b3-1a3133954fc1 |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Concrete Pour (V.081021) |  |  |  |  | Yes | Concrete Pour (V.081021) | 5c688cd4-67fb-47ff-af43-cc54d093ac8f
checkpoint-status |  |  | checkpoint | Details - pass once selected below
select | 41aeb522-90dd-538b-bcc2-ef2a989d76e9 |  | dropdown | Set out and alignment | Survey, Site measure
select | 9e5e6faf-c163-5a3e-af5a-ac5bf6d9c212 |  | dropdown | Materials types | Fire collar, sleeve
checkpoint-status |  |  | checkpoint | Inspection Prior to concrete pour
checkpoint-status |  |  | checkpoint | Inspection Prior to concrete pour
checklist-flat |  |  | checklist | Recycled Water (V.081021) |  |  |  |  | Yes | Recycled Water (V.081021) | 67324f2d-db0e-4c50-9a52-9c4220d16472
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | c0a38175-a534-5423-9b98-57f8fc40f005 |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations completed & checked
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Fittings & fixtures
label | b035fa03-acad-52dd-b32d-cd1d5245a801 |  | note | As per FFE Schedule
checkpoint-status |  |  | checkpoint | Fire collars installed
label | 803be42c-ad87-5f5a-8a24-1cba3ec2344c |  | note | Attach photos of Fire Collars below
checkpoint-status |  |  | checkpoint | Fire penetration caulked
label | c305d565-b127-5eb8-8728-df0c83508b29 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | 24f5a978-12b1-5381-9e11-347df2352c77 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 9b878383-c62a-5da5-b276-d3f5f95d8af6 |  | note | Click to Attach Signature(s) below
button | a6381bf0-e838-5268-9c08-0b3a056ba300 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 236551ec-4e59-52ee-8f74-247827858b0e |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Cold Water (V.081021) |  |  |  |  | Yes | Cold Water (V.081021) | 69b18dd1-fae4-42c9-bfb5-35f6fa9ac55d
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | 2a6287e6-3e8c-5553-b72f-001d8a870e5e |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations/fire collars completed & checked
checkpoint-status |  |  | checkpoint | Correct fittings
label | ff1fdf4b-342c-5417-b4ca-8fd787e522e2 |  | note | As per FFE Schedule
checkpoint-status |  |  | checkpoint | Fire penetration caulked
checkpoint-status |  |  | checkpoint | Pressure & Temperature testing completed
label | 2b966ea3-bcdb-5718-b390-0b0d0bf4f57a |  | note | Attach photos of testing apparatus below
text | 4bbd6809-c2a0-54ed-88aa-20f78f01586d |  | textbox | Pressure test kPa
label | 21a0b76b-7589-5e35-817c-be31fcd0014a |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | 15f8037e-125e-5226-ab9f-2113f7d14e41 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 5e72cce2-c549-5fb3-826a-4e8fa3747426 |  | button | Signature by Builders Site Coordinator | Yes, No
button | fb080164-2eb1-56ce-ad69-3feaedc65ee0 |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Downpipe Installation (V.081021) |  |  |  |  | Yes | Downpipe Installation (V.081021) | 6ea3c9f8-34aa-4750-8d31-a5b86085a36e
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | d5c56eba-2016-5b37-b99b-0a8fb6803090 |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations completed & checked
checkpoint-status |  |  | checkpoint | Fittings & fixtures
label | dc8ee4c1-539c-560a-be56-623ba7d7f1b3 |  | note | As per FFE Schedule
checkpoint-status |  |  | checkpoint | Fire collars installed
label | e116902d-8086-5245-a05b-e89624d624a7 |  | note | Attach photos of Fire Collars below
checkpoint-status |  |  | checkpoint | Fire penetration caulked
checkpoint-status |  |  | checkpoint | Insulation / lagging installed
label | 86e7b29c-0aa5-5260-a329-2c36676e6b23 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | 69bd3c00-503a-5df4-9412-7532906eecbd |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 4e4fbd4d-cd33-5fe5-a2d1-27105a50a0cb |  | note | Click to Attach Signature(s) below
button | 6ba75a49-62db-5d6c-9d26-0c32a66cc1ca |  | button | Signature by Builders Site Coordinator | Yes, No
button | e889471d-222d-545e-9379-aa3bf2a73dbf |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Stormwater Below Ground (V.081021) |  |  |  |  | Yes | Stormwater Below Ground (V.081021) | 7872115e-50e8-44f3-8c95-3bc79ae95fcf
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | 348b2dca-2ad1-51c2-a8ba-043634a57a5e |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | 5c9b64e9-a016-5719-b28b-8a30bf3ed892 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 0ba073c1-6b07-5501-a57b-0e36f6523b18 |  | note | Click to Attach Signature(s) below
button | 365a76f3-136f-5cf0-bc76-46f064d1ef57 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 15a78508-058b-5ce5-9afb-536dd24945b7 |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Syphonic Systems (V.081021) |  |  |  |  | Yes | Syphonic Systems (V.081021) | 7a91d1b4-b459-4aca-a368-67b2a2cc2748
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | 4007b000-4ca8-5526-bcd5-6449ac554c85 |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations completed & checked
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Fittings & fixtures
label | 8c854374-8168-55fc-bc87-e57f3efee59c |  | note | As per FFE Schedule
checkpoint-status |  |  | checkpoint | Fire collars installed
label | f8b08341-9dbe-5dc8-ae7f-18867ba17791 |  | note | Attach photos of Fire Collars below
checkpoint-status |  |  | checkpoint | Fire penetration caulked
checkpoint-status |  |  | checkpoint | Insulation / lagging installed
checkpoint-status |  |  | checkpoint | Inspection by Authority
label | 816281c4-9bf5-5c17-b32f-73b570300b07 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | a1884958-5d72-58d1-84a6-a15169fd4bd2 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 46c67bea-e234-514f-9daf-fa30d80a6fd2 |  | note | Click to Attach Signature(s) below
button | aec49ead-a42a-5c2a-ba49-462f7527f9d2 |  | button | Signature by Builders Site Coordinator | Yes, No
button | cefcbe01-c3a4-5d94-ac01-a29fc2712123 |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Above Ground Sewer Drainage (V.081021) |  |  |  |  | Yes | Above Ground Sewer Drainage (V.081021) | a00d2d19-db18-4549-8dd9-615d859ebc86
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | 290a05c9-ea17-5769-b26e-f5ea70913ced |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations/fire collars completed & checked
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Fire penetration caulked
checkpoint-status |  |  | checkpoint | Insulation / lagging installed
checkpoint-status |  |  | checkpoint | Pressure & Temperature testing completed
label | 8708a26c-2445-50b5-88ec-2699d90cda9b |  | note | Attach photos of testing apparatus below
text | d87569fd-1ebf-5278-a576-2c6757625399 |  | textbox | Pressure test kPa
checkpoint-status |  |  | checkpoint | Inspection by Authority
label | 4f343211-5cf9-5f1f-9365-89dc94b7c671 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | 8626263a-1908-5c02-81c9-4cad32f6261d |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 1f098325-5da8-5033-9659-9c8c214cedee |  | note | Click to Attach Signature(s) below
button | b9ce9024-e1c6-59b5-8676-d695631c01c3 |  | button | Signature by Builders Site Coordinator | Yes, No
button | cf12f5c8-33df-504b-a840-1c2d0d3785be |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Document Attachment Checklist (V.081021) |  |  |  |  | Yes | Document Attachment Checklist (V.081021) | c7fde4cc-bc04-410e-a462-4ef7cad3981d
checkpoint-status |  |  | checkpoint | Documents attached for reference - Pass once attached
checklist-flat |  |  | checklist | Sanitary Waste & Vents (V.081021) |  |  |  |  | Yes | Sanitary Waste & Vents (V.081021) | dfd6cb6a-3323-4881-bd11-c708aa13241b
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | e219bb26-8ea3-530b-8e85-b7fc78ad4e7c |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Structural penetrations completed & checked
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Fittings & fixtures
label | a9d46e94-706b-5d1b-8ffb-dd7901b6dc1a |  | note | As per FFE Schedule
checkpoint-status |  |  | checkpoint | Fire penetration caulked
checkpoint-status |  |  | checkpoint | Insulation / lagging installed
label | a99fe7f8-4d6e-50b3-a923-4a20f3d95ed3 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | c050a06a-4351-51e8-b746-8917abc15ccd |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | f7d3ee3b-8f8a-54f1-9e9d-6ceadb415558 |  | note | Click to Attach Signature(s) below
button | a9015b9e-9ae4-5ab4-a77b-73e0f820be37 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 3f96e683-248e-561d-bae1-95138ec32c7e |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat |  |  | checklist | Stormwater Above Ground (V.081021) |  |  |  |  | Yes | Stormwater Above Ground (V.081021) | eaefc6d4-fb0a-427f-9024-ff27065e8f8e
checkpoint-status |  |  | checkpoint | Set-Out & Alignment
text | 1758579c-3ebd-5293-86f9-6997b39c248a |  | textbox | Drawing & Rev No. (or Photograph below)
checkpoint-status |  |  | checkpoint | Materials type checked & correct
checkpoint-status |  |  | checkpoint | Correct fittings
checkpoint-status |  |  | checkpoint | Fire collars installed
label | 1b3dafc4-46a6-5206-a2b4-962f47e0d927 |  | note | Attach photos of Fire Collars below
checkpoint-status |  |  | checkpoint | Fire penetration caulked
checkpoint-status |  |  | checkpoint | Insulation / lagging installed
label | 88e9726f-f9b3-5f1c-b971-7f19adb31395 |  | note | Inspection attached below as applicable
checkpoint-status |  |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | d4d24bf0-6310-539f-b21f-594904c68db4 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 94bbc404-2a64-53e2-b350-53623abf9619 |  | note | Click to Attach Signature(s) below
button | 16861c0f-cf90-58be-9013-e2e8526bc2fd |  | button | Signature by Builders Site Coordinator | Yes, No
button | 0f752f30-0900-5532-b903-9a1461a47f5e |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No