## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | e6cdac5f-e734-44f6-ba49-78a5bbd7faa0 |  | checklist | Cast-in/Peno + Hydro Test (COMBINED) |  |  |  |  | Yes | Cast-in/Peno + Hydro Test (COMBINED) | 04817ff8-7e41-4a4c-9f20-4854cace81ae
checkpoint-group | 249fcdbc-b2c5-4800-8c60-4f15bc6682f1 |  | section | Cast-Ins/penetrations
checkpoint-status | e1d11d39-1b91-48cd-b0f7-9e01b5d89a78 |  | checkpoint | Are the latest Version of the drawings being used for the work
text | c81a8f80-6566-51a3-b526-56124159c029 |  | textbox | Drawing number/s are noted on ITP
checkpoint-status | 80eb8240-e128-421a-b6db-250cfa2e96aa |  | checkpoint | Location of pipework is as per IFC drawing & CYP site survey set out
button | fb286f32-6330-541c-87af-15884a27870f |  | button | Drain / Penetration type | Permanent, Provisional
checkpoint-status | 3bf0e433-96be-45d1-9cd2-815472899a9a |  | checkpoint | Pipe materials used are as per Tunnel and stations hydraulic services specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
button | d4cd85ca-598c-5c15-b46d-b37704744cd9 |  | button | Pipework material used | HDPE, Cast Iron, Poly
checkpoint-status | c6a72ce1-2742-41e7-ada4-2b6f0c6a8acd |  | checkpoint | HOLDPOINT - Verify steps 1 to 6 are compliant with applicable supporting documentation. Visualised by Nominated CYP Authority
checkpoint-status | f7f6ae21-8548-4b20-9595-327ec6ef7edf |  | checkpoint | Invert levels as per drawings
checkpoint-status | 425ae10c-4a5d-45e5-96a3-c9e4687fc9f0 |  | checkpoint | No damage to pipework or fittings - Attach Photos below
checkpoint-status | f88d38e3-f288-4674-80f0-894a9727abea |  | checkpoint | Correct drainage venting per AS 3500.2 2018 sec 3.9
checkpoint-status | 9ba1b3c9-4e11-4b27-8eec-a333903f0670 |  | checkpoint | Correct fire protection / fire collars as per C3.15 of the BCA AS4072.1
checkpoint-status | e9d2715d-1459-4d46-bde8-7f2b68d37b70 |  | checkpoint | Type & Brand of collar used
checkpoint-status | 5be2afd6-f2a8-40c7-b03b-188d2e5d2947 |  | checkpoint | All points are connected
checkpoint-status | 2f29b975-e6a4-4d82-ad89-903f82844093 |  | checkpoint | Pipework on correct grade as per AS 3500.2 2015 Table 3.4.1
checkpoint-status | 242b896e-2071-43ce-9b64-09d806b0f50f |  | checkpoint | Pipes are clean & Clear of debris - Welded / Glued
checkpoint-status | b9408427-5833-4865-8317-f99805425931 |  | checkpoint | Joint method defect free (Compression band) (Electro fusion) (Glued)
checkpoint-status | 7adc36dc-7692-408a-b2bd-aae6130f4fca |  | checkpoint | Has the pipework been witness marked and signed upon positive visual inspection of chosen method of jointing
checkpoint-status | 12952e9f-2c76-406c-a5b8-6fe28fb96c63 |  | checkpoint | Pressurised pipework to 15 Kpa
label | 6b6b7c28-0841-502b-a201-85eb18bf99e4 |  | note | Settle time for test is 3 min then an additional test time of 5 min Maximum pressure drop is +/- 3 Kpa over a 5 min period
checkpoint-status | d228178c-9723-4160-a23f-f5dee21522f4 |  | checkpoint | Hold Point - CYP Nominated Authority sign off test
label | 42e01aed-4e4b-52b1-9eb8-6910cd0e5752 |  | note | Attach Signature(s) below
checkpoint-status | cd778ef6-2311-4e91-b437-fe1bc30a7757 |  | checkpoint | Pipe clipping on grade as per AS 3500.3 Clause 4.9.6.2
label | b5f1fc95-d30c-5e22-8525-dc9876d2b19b |  | note | Vertical clip spacing as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | 975f438b-ef02-425f-a270-30aa38925e77 |  | checkpoint | Pipe lagged in accordance with tunnel and stations hydraulic services specification
label | 8263d009-1c93-508e-bed3-6626ece02d25 |  | note | Specifications (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
checkpoint-status | 750aceed-2003-4823-8e96-2f7b9ba2d8fb |  | checkpoint | Has excess pipework been picked up for completed works
checkpoint-status | af4e1c93-17de-4eef-8ab6-40832d59e3fe |  | checkpoint | FINAL - Pipework completed to specification/drawings - Area left clean & tidy
boolean | c89ef375-9b1e-5dc1-960b-23c993006671 |  | tickbox | CDC - General photos/comments attached below
boolean | aee82145-6d12-5648-a759-42a2fd508c8d |  | tickbox | CYP Nominated comments - General comments attached below
boolean | d135b3fe-4d4d-525c-8eec-ea5c69d131aa |  | tickbox | SIGN-OFF - CDC & CYP Nominated Signature(s) attached below
checkpoint-group | 54cbe5c2-3caf-4d83-a616-37078132841d |  | section | Hydrostatic Pressure Test
checkpoint-status | 534040d2-1d4c-4e9f-8414-d733fa7d20a2 |  | checkpoint | Test Details - Pass once entered
text | c844de3f-3cf0-5dc2-904f-64311cc627b3 |  | textbox | Location (Area/Level/Zone)
label | 9583d69d-b0f2-5dcb-a684-e9f044538f41 |  | note | Testing Calibration Certificate Uploaded Per Level
text | 44c3c6ae-9e6a-5694-8013-fea22daf47f0 |  | textbox | Service
text | de37f48e-5d05-5828-bddd-24d3a0bb46d6 |  | textbox | Testing Apparatus Type & Number (Input or Attach photo below)
checkpoint-status | bb9e2f15-2972-43b2-9a5c-06ba04bdafc2 |  | checkpoint | Final Hydrostatic/Pressure Test
label | 5d2d6404-54df-587e-afae-941b586ddcb5 |  | note | Minimum 15kPa
boolean | c02bac6d-e5ef-530b-afe3-411cbe48d2c8 |  | tickbox | CDC - General photos/comments attached below
boolean | 4ed7d5b0-62e9-5819-b24b-358c29cfaed0 |  | tickbox | CYP Nominated comments - General comments attached below
checklist-sectioned | 94aa618f-7f2c-450d-8436-4c969c64e710 |  | checklist | PENETRATION 2 |  |  |  |  | Yes | SYS - PENETRATION 2 | 0b2e5797-a7d0-445d-a469-c34c25ecb615
checkpoint-group | 4a288961-8f58-448e-8fec-9f6a312efd44 |  | section | Cast-Ins/penetrations
checkpoint-status | d16fce32-1e4e-411d-bd20-13503330e3d7 |  | checkpoint | Are the latest Version of the drawings being used for the work
text | c81a8f80-6566-51a3-b526-56124159c029 |  | textbox | Drawing number/s are noted on ITP
checkpoint-status | 16621c54-0d96-4389-9f08-85bda3e7a1b6 |  | checkpoint | Location of pipework is as per IFC drawing & CYP site survey set out
button | fb286f32-6330-541c-87af-15884a27870f |  | button | Drain / Penetration type | Permanent, Provisional
checkpoint-status | 0300cd1e-1a94-4b65-857a-6a8ca4369b75 |  | checkpoint | Pipe materials used are as per Tunnel and stations hydraulic services specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
button | d4cd85ca-598c-5c15-b46d-b37704744cd9 |  | button | Pipework material used | HDPE, Cast Iron, Poly
checkpoint-status | 880589b2-b212-4f52-9d61-c4163a403a7e |  | checkpoint | HOLDPOINT - Verify steps 1 to 6 are compliant with applicable supporting documentation. Visualised by Nominated CYP Authority
checkpoint-status | dce16a1f-3869-4e0f-811e-53ce608ecb1b |  | checkpoint | Invert levels as per drawings
checkpoint-status | 608fcba9-22bf-4340-9292-5ea4a1f98ba1 |  | checkpoint | No damage to pipework or fittings - Attach Photos below
checkpoint-status | 3d8c18e3-cb6c-408c-a931-ca8a367690c7 |  | checkpoint | Correct drainage venting per AS 3500.2 2018 sec 3.9
checkpoint-status | 9a927747-36f6-4abe-a1d9-5100bf0a8a05 |  | checkpoint | Correct fire protection / fire collars as per C3.15 of the BCA AS4072.1
checkpoint-status | b13a7bff-2c78-4692-9258-b6f41e0baf7d |  | checkpoint | Type & Brand of collar used
checkpoint-status | aed273af-1362-4b26-b949-fd4261252e9c |  | checkpoint | All points are connected
checkpoint-status | de13d2f9-de55-4e04-8bbd-3171bedd3cf6 |  | checkpoint | Pipework on correct grade as per AS 3500.2 2015 Table 3.4.1
checkpoint-status | 46999201-75b5-44dd-8c1a-e2213064449c |  | checkpoint | Pipes are clean & Clear of debris - Welded / Glued
checkpoint-status | 5893c87d-e95f-43a6-9fef-8bd567b92138 |  | checkpoint | Joint method defect free (Compression band) (Electro fusion) (Glued)
checkpoint-status | d35c6470-048c-46e5-acc2-689ffa2f7d37 |  | checkpoint | Has the pipework been witness marked and signed upon positive visual inspection of chosen method of jointing
checkpoint-status | 0a9908c2-b428-4b92-9369-d6a3fd19b946 |  | checkpoint | Pressurised pipework to 15 Kpa
label | 6b6b7c28-0841-502b-a201-85eb18bf99e4 |  | note | Settle time for test is 3 min then an additional test time of 5 min Maximum pressure drop is +/- 3 Kpa over a 5 min period
checkpoint-status | fe9f4868-41f1-4ebb-98a5-e9ef081d7155 |  | checkpoint | Hold Point - CYP Nominated Authority sign off test
label | 42e01aed-4e4b-52b1-9eb8-6910cd0e5752 |  | note | Attach Signature(s) below
checkpoint-status | 6b7e1eba-3333-4f7c-838e-cb093754c4bb |  | checkpoint | Pipe clipping on grade as per AS 3500.3 Clause 4.9.6.2
label | b5f1fc95-d30c-5e22-8525-dc9876d2b19b |  | note | Vertical clip spacing as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | f98b68cf-9c21-42f0-ac62-d836abade4b8 |  | checkpoint | Pipe lagged in accordance with tunnel and stations hydraulic services specification
label | 8263d009-1c93-508e-bed3-6626ece02d25 |  | note | Specifications (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
checkpoint-status | 8bc34910-7413-464a-88c9-8b0cf5f283f9 |  | checkpoint | Has excess pipework been picked up for completed works
checkpoint-status | 8888a26a-6901-4f74-9879-bfa62dce72bc |  | checkpoint | FINAL - Pipework completed to specification/drawings - Area left clean & tidy
boolean | c89ef375-9b1e-5dc1-960b-23c993006671 |  | tickbox | CDC - General photos/comments attached below
boolean | aee82145-6d12-5648-a759-42a2fd508c8d |  | tickbox | CYP Nominated comments - General comments attached below
boolean | d135b3fe-4d4d-525c-8eec-ea5c69d131aa |  | tickbox | SIGN-OFF - CDC & CYP Nominated Signature(s) attached below
checklist-flat | 945653e9-b19f-4264-b5e2-b979932b61ed |  | checklist | Commissioning (V.061221) |  |  |  |  | Yes | Commissioning (V.061221) | 0e6b1216-2eb7-481d-9ad9-04e6c39cab00
checkpoint-status | a17b3370-213e-4758-bbb6-23134b5f3e3a |  | checkpoint | Check products for imperfections
checkpoint-status | 2138154b-0459-4a53-8760-3406c4a81124 |  | checkpoint | Fixtures location & ixings all correct (as per drawings & samples)
checkpoint-status | 61094b39-582c-4a9f-95d7-0810bbea374d |  | checkpoint | Clean out all strainers / aerators
checkpoint-status | 84aac3c0-f523-4830-8064-811ad3d69934 |  | checkpoint | Check for no cross connections / leaks / access to isolation valves
checkpoint-status | 9136c2c3-222e-4b46-bc21-e46958943466 |  | checkpoint | Floor wastes (clear of debris & draining correctly)
checkpoint-status | ffb41a84-f3c8-43a5-b419-36a7a9dabed4 |  | checkpoint | Quality of silicone seals to fixtures acceptable
checkpoint-status | 3dc3e9bb-ad88-4c15-9de2-cc224608c062 |  | checkpoint | Hot water tempering valve set to 50c (+/- 5c) & DDA thermostatic mixing valve set to 42 degrees.
checkpoint-status | a1662523-3a63-4bbd-bad2-014101af64f4 |  | checkpoint | Water pressure acceptable 350Kpa to 500 Kpa
checkpoint-status | c4adda7a-6ec3-4825-882c-6fabd1ddbc4d |  | checkpoint | Hydraulic Work(s) completed to specification/drawings & Area left clean/tidy
label | f742363a-ebc0-57a8-a848-3ad2a31e205b |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 39cbcaa3-6d12-5b3a-a7fe-8841f76ddf64 |  | note | Click to Attach Signature(s) below
button | b9191a12-48d2-5b30-91f7-8dc651fde593 |  | button | Signature by Builders Site Coordinator | Yes, No
button | 353f317a-3fb9-58ea-9874-f01620d9b4b6 |  | button | CDC Plumbing Signature Sign-Off added below | Yes, No
checklist-flat | 3073f385-bf0c-4ba9-a21d-f58e3eec30f3 |  | checklist | Hydrostatic Pressure Test |  |  |  |  | Yes | Hydrostatic Pressure Test | 23d83996-892a-42e3-a060-27fc71871127
checkpoint-status | 085f4450-bd91-4891-8016-52eadd98ede4 |  | checkpoint | Test Details - Pass once entered
text | fe3708df-6d96-5c6b-b656-665bc6272493 |  | textbox | Location (Area/Level/Zone)
text | 5e2dd2b6-9627-5c8a-add5-210991feb475 |  | textbox | Testing Calibration Tested Date
text | f3c38f2c-4505-5d36-96dc-a6ca196c27a1 |  | textbox | Testing Calibration Due Date
text | c33f587b-fa3f-5d19-b12e-cacd519198c7 |  | textbox | Service
text | 61ddecf7-06d4-5f70-bd37-6e9d143b070b |  | textbox | Testing Apparatus Type
text | e0bd2cd7-9d0e-5fde-b251-54e3ea4997ea |  | textbox | Testing Apparatus Number
checkpoint-status | 88e39d87-c4bf-489d-8bba-873178a4a0eb |  | checkpoint | Preliminary Sectional Air Test to 15kPa
checkpoint-status | c8c98fa6-0793-47ce-968b-50159efdda39 |  | checkpoint | Final Hydrostatic Test
text | b290571b-74b5-5c07-b2f4-83cd85bded2d |  | textbox | Test reading kPa
checklist-flat | 1ba4b700-9279-4491-8bad-aeca1807a466 |  | checklist | Cast-Ins/penetrations CYP Checklist Number CHK/MMTS/00810 |  |  |  |  | Yes | Cast-Ins/penetrations CYP Checklist Number CHK/MMTS/00810 | 3946f95a-86d9-4889-8af9-dbea019fe6f4
checkpoint-status | 3ec679bd-5262-4d0a-8ed3-4cd4b4795f22 |  | checkpoint | Are the latest Version of the drawings being used for the work. Ref: 7.3.1 & 7.3.2 section on Hydraulic Services Specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001)
text | 4a8f5ebe-1fa4-5229-bb2b-0ea2bcf55fa9 |  | textbox | Drawing number
text | a553672d-5452-5d54-8603-b11337d968e6 |  | textbox | Revision
checkpoint-status | 422ec6c2-2350-4c22-8ec5-6c40b3d0e8fd |  | checkpoint | Location of pipework is as per IFC drawing & CYP site survey set out Ref: 8.1.5 & 8.3.3 on Hydraulic Services Specification
select | 8db348e4-be79-519c-8fd5-02ba96b4c05a |  | dropdown | Drain / Penetration type | Permanent,Provisional
checkpoint-status | 073e0145-0d8d-4de4-8138-9b7efd097a15 |  | checkpoint | Pipe materials used are as per Tunnel and stations hydraulic services specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
select | 69f4cb06-d5ae-50b9-a594-06ce130a65ea |  | dropdown | Pipework material used. Ref : 7.9.1 section on Hydraulic Services Specification | HDPE,Cast Iron,Poly
checkpoint-status | ce345537-0f2a-4840-b3cd-64740fed2dd4 |  | checkpoint | HOLDPOINT BELOW - CYP to sign before passing checkpoint
label | 1be621c3-74e5-57ba-bfe1-dcc52b18ca34 |  | note | Visualised by Nominated CYP Authority Only (CYP NA2- Proficiency Level 2)
boolean | be011f9b-8aa8-5ec4-82da-30e2bf95d220 |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
holdpoint | 5035e957-cebc-44c8-8f5b-003a73ad883a |  | signoff | HOLDPOINT - CYP to Verify steps 1 to 6 are compliant with applicable supporting documentation
checkpoint-status | f3c4a539-0966-4b44-b255-eadbe27f0465 |  | checkpoint | Invert levels as per drawings Ref: AS3500.2.2015 Table 3.4.1 and 8.3.8.4 in Hydraulics Services Specification
checkpoint-status | 07798cfd-47ca-4d47-b8fb-83c467b851a3 |  | checkpoint | No damage to pipework or fittings. Ref: Attached Photos below
checkpoint-status | 6daad14f-bd4c-4e79-b891-760adb0050b8 |  | checkpoint | Correct drainage venting per Ref: AS 3500.2 2018 sec 3.9
checkpoint-status | 05da1be1-a884-4fc8-9b57-49f0056dc798 |  | checkpoint | Correct fire protection / fire collars as per Ref: C3.15 of the BCA AS4072.1
checkpoint-status | 2c3bb9ac-97dd-4575-89df-24d06b50d155 |  | checkpoint | Type & Brand of collar used as per Ref: C3.15 of the BCA AS4072.1
checkpoint-status | 2095bf87-0680-46f5-a68c-f3534b327e9c |  | checkpoint | All points are connected
checkpoint-status | d59a87db-3f98-4876-a85b-fef5fcde4684 |  | checkpoint | Pipework on correct grade as per AS 3500.2 2015 Table 3.4.1 and 8.3.8.4 on Hydraulics Services Specification
checkpoint-status | 124ec1dd-f372-4890-a094-ed76a01762ed |  | checkpoint | Pipes are clean & Clear of debris - Welded / Glued Ref: As Per manufacturers requirement
checkpoint-status | e93f0a59-756d-40ff-ba53-e1c77b5fff78 |  | checkpoint | Joint method defect free (Compression band) (Electro fusion) (Glued) Ref: As Per manufacturers requirement
checkpoint-status | 6a48fa9e-13c5-4a75-996d-d55627eced62 |  | checkpoint | Has the pipework been witness marked and signed upon positive visual inspection of chosen method of jointing
checkpoint-status | 5e57d2c1-40c8-4f0a-8268-b83b4e1aab79 |  | checkpoint | Pressurised pipework to 15 Kpa according to AS3500.2 Sec 15 and Ref: 8.1.9, 20.3.6 & 20.3.8 on Hydraulics Services Specification
label | 2b978a2a-7fa1-5323-bb46-b5a4a82e341d |  | note | Settle time for test is 3 min then an additional test time of 5 min Maximum pressure drop is +/- 3 Kpa over a 5 min period
checkpoint-status | ec6bd8ed-9d53-4a3c-a813-436c4195c59c |  | checkpoint | HOLDPOINT BELOW - CYP to sign before passing checkpoint
boolean | f26c982b-b49b-5df4-9f7d-6295296ad553 |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
label | cec041a8-d265-5fc0-8ff8-4201a7f73d4f |  | note | Visualised by Nominated CYP Authority Only
holdpoint | c86d4c65-7bc2-4247-98d3-06ea369c6f07 |  | signoff | HOLDPOINT- CYP Nominated Authority sign off test
checkpoint-status | fc88d32b-2095-46d8-abf5-08bf7cec373a |  | checkpoint | Pipe clipping on grade as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | 3be4c104-44c2-4ca3-ac07-eaad0266b602 |  | checkpoint | Vertical clip spacing as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | de14dc90-b9ca-4caf-a301-a90b409bdde7 |  | checkpoint | Pipe lagged in accordance with tunnel and stations hydraulic services specification
label | 01d50f7b-90b0-5d26-a602-41a4f5f46b33 |  | note | Specifications (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
checkpoint-status | 3003a4b3-5bbe-46a3-8c7f-e240065da846 |  | checkpoint | Pipework to remain full of water during pour. Ref: As Per manufacturers requirement
checkpoint-status | c58f17ff-e512-40b0-8734-1c1613b50619 |  | checkpoint | Has pipework been picked up for completed works (As-built)
checkpoint-status | 756d8021-89a4-4d8f-8e9f-336b6c1f08fb |  | checkpoint | Signoff - CDC to sign before passing this checkpoint
boolean | 727e1f81-ae19-53ac-8784-2f51a61e9169 |  | tickbox | CDC - General photos/comments attached below
label | 32c8b124-5249-5976-bb10-eb33eb5ffeb9 |  | note | SIGN-OFF :Name & Signature attatched below
holdpoint | 896347ed-265d-4ab8-a469-f219955d7f15 |  | signoff | FINAL HOLDPOINT- CDC authority to signoff
checkpoint-status | ca2f0904-3ed7-4e84-a4c1-ba0d417a6443 |  | checkpoint | Signoff - CYP to sign before passing this checkpoint
boolean | 1e8b05f6-a0af-50eb-ac87-d81624755fed |  | tickbox | CYP Nominated comments - General comments attached below
boolean | e1a40939-a499-5a41-96ad-fa09fe5717d0 |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
holdpoint | f51e39d5-bf02-4792-81c8-5b51fb2f74b4 |  | signoff | FINAL HOLDPOINT- CYP nominated authority to signoff
checklist-flat | 66845f53-1f5e-4ef5-ac72-1c74b72c0de5 |  | checklist | Drawing Upload - Checklist (V.101221) |  |  |  |  | Yes | Drawing Upload - Checklist (V.101221) | 3cea862f-6f12-4fc8-95a0-fc340efd1e1d
checkpoint-status | c5a653b6-d3e8-467d-9c4d-cbe71c85bb14 |  | checkpoint | Drawings/comments/signatures - attached below
checklist-flat | fc59e311-4590-4726-9504-d4f2c4a63171 |  | checklist | Document Attachment |  |  |  |  | Yes | Document Attachment Checklist | 4259cfe6-a2ea-499b-a499-12d9c7e8062e
checkpoint-status | 3476aab7-8cd5-4a07-a1c3-b35234fca306 |  | checkpoint | Documents attached for reference - Pass once attached
checklist-flat | 7a4798ee-626d-4739-8e68-98d6ac356187 |  | checklist | Hydrostatic Pressure Test |  |  |  |  | Yes | SYS - Hydrostatic Pressure Test | 79cac826-100b-4888-b491-a68d8b8cd7a1
checkpoint-status | 2bb9c0eb-1465-4d42-a016-f8043ffa8d0e |  | checkpoint | Test Details - Pass once entered
text | 92a004b2-1284-50af-ba95-5b122b0d0126 |  | textbox | Location (Area/Level/Zone)
text | c0392356-c1a2-51c6-bac9-2b79d479bdc6 |  | textbox | Testing Calibration Tested Date
text | 304c6bdd-3e6d-5ada-8743-cdf6cda684f8 |  | textbox | Testing Calibration Due Date
text | 5d6192fd-3a3f-539d-9410-1266f548a4c9 |  | textbox | Service
text | f82a4052-795a-5710-9be3-d22e0af09219 |  | textbox | Testing Apparatus Type
text | dcba2079-6913-574f-a090-c1d220c13769 |  | textbox | Testing Apparatus Number
checkpoint-status | 7fa8f8d0-c2f3-4f0f-9ec3-3a0c2ef25650 |  | checkpoint | Preliminary Sectional Air Test to 15kPa
checkpoint-status | e82a95b5-b8b5-4742-a838-18adcb2e98ac |  | checkpoint | Final Hydrostatic Test
text | 0e1e4381-6a51-5627-a072-230fd71cc558 |  | textbox | Test reading kPa
checklist-flat | fb3d6da4-e024-46db-aba2-8a3a0731977c |  | checklist | Cast-Ins |  |  |  |  | Yes | SYS - Cast-Ins | 81a2392c-a4d4-4499-bb08-bdf3fa2933e4
checkpoint-status | 4cf6f939-2502-4c70-9480-77c6d4794540 |  | checkpoint | Are the latest Version of the drawings being used for the work
text | 0ed66e3d-856a-520e-a849-057f1588f092 |  | textbox | Drawing number/s are noted on ITP
checkpoint-status | fff1d769-a121-40bf-9488-d97c03db5320 |  | checkpoint | Location of pipework is as per IFC drawing & CYP site survey set out
button | eb0742e0-9fbc-5edc-862c-f3766f7fdc79 |  | button | Drain / Penetration type | Permanent, Provisional
checkpoint-status | e77bd5a8-1cf4-4b2c-9e4e-d97ed32a4b95 |  | checkpoint | Pipe materials used are as per Tunnel and stations hydraulic services specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
button | 7520e98b-03df-57cb-8e05-5d997ccedc84 |  | button | Pipework material used | HDPE, Cast Iron, Poly
checkpoint-status | 0c1bbbec-d111-4d8c-ae5e-c2cd9f4abb59 |  | checkpoint | HOLDPOINT - Verify steps 1 to 6 are compliant with applicable supporting documentation. Visualised by Nominated CYP Authority
checkpoint-status | 957dd743-3bde-40f2-98ed-f151b15a698e |  | checkpoint | Invert levels as per drawings
checkpoint-status | 2a3bf592-6eec-4cbb-8167-5f03a34d245d |  | checkpoint | No damage to pipework or fittings - Attach Photos below
checkpoint-status | 7fa88e6b-84ff-4f40-9ba3-1492730b24e0 |  | checkpoint | Correct drainage venting per AS 3500.2 2018 sec 3.9
checkpoint-status | b4af919c-6004-49c3-a5b4-0bcbdb8c362c |  | checkpoint | Correct fire protection / fire collars as per C3.15 of the BCA AS4072.1
checkpoint-status | 79c49997-37d6-4ce4-8dfb-6eef6fc1e48e |  | checkpoint | Type & Brand of collar used
checkpoint-status | 6d76b545-4a53-4396-8770-1d1e2147745b |  | checkpoint | All points are connected
checkpoint-status | a0d6a540-764b-46d3-a7d6-181f3112528a |  | checkpoint | Pipework on correct grade as per AS 3500.2 2015 Table 3.4.1
checkpoint-status | b4ad853c-3bd8-4337-8171-85f5f24b5633 |  | checkpoint | Pipes are clean & Clear of debris - Welded / Glued
checkpoint-status | da1a9279-bea3-487f-adb9-1c178847e9ad |  | checkpoint | Joint method defect free (Compression band) (Electro fusion) (Glued)
checkpoint-status | 24d5fb0c-188d-45d1-a5cb-f7f31b0abdbd |  | checkpoint | Has the pipework been witness marked and signed upon positive visual inspection of chosen method of jointing
checkpoint-status | 9aedfb83-c9fa-4c09-9701-b67f9c1ead25 |  | checkpoint | Pressurised pipework to 15 Kpa
label | c819316b-e8fa-5e59-a98d-83188b63c7e8 |  | note | Settle time for test is 3 min then an additional test time of 5 min Maximum pressure drop is +/- 3 Kpa over a 5 min period
checkpoint-status | 9309bf44-e7cb-4094-8663-a62f9c7d92dd |  | checkpoint | Hold Point - CYP Nominated Authority sign off test
label | 72b5f978-9b93-5826-b274-026b1231dd93 |  | note | Attach Signature(s) below
checkpoint-status | 06734d99-cd5f-4ea6-ae5f-41d1c4848928 |  | checkpoint | Pipe clipping on grade as per AS 3500.3 Clause 4.9.6.2
label | 99aca03e-54b4-5246-91a6-d22dedc5173f |  | note | Vertical clip spacing as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | 0edc59c2-2a95-49ad-adfa-6ccc98274487 |  | checkpoint | Pipe lagged in accordance with tunnel and stations hydraulic services specification
label | 5cacdfce-1549-56e0-a9bd-6d9038e1bd0b |  | note | Specifications (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
checkpoint-status | 4b1642d7-e0de-44f0-bc53-e5e9c6477cd3 |  | checkpoint | Has excess pipework been picked up for completed works
checkpoint-status | 17a36ca6-892b-4cc7-b605-ed42865aa665 |  | checkpoint | FINAL - Pipework completed to specification/drawings - Area left clean & tidy
boolean | b9da1731-9001-59eb-9f78-1caa408eaa24 |  | tickbox | CDC - General photos/comments attached below
boolean | 38f42bae-1868-5d7d-9988-9ef6d6a854ac |  | tickbox | CYP Nominated comments - General comments attached below
boolean | 7f7764d5-0d5a-51bc-ba88-390e2811c87b |  | tickbox | SIGN-OFF - CDC & CYP Nominated Signature(s) attached below
checklist-flat | a09f297d-95dd-46ed-b9a1-720f107e9f47 |  | checklist | Document Attachment Checklist V.010322 |  |  |  |  | Yes | Document Attachment Checklist V.010322 | 8c8de32c-6d0e-4e05-8bcb-e9479a7bfe13
checkpoint-status | f6b3f652-0485-45ae-ac76-7d56d01adba3 |  | checkpoint | Documents attached for reference - Pass once attached
text | eab46571-3ce3-5807-a6a9-393b9e859285 |  | textbox | Drawing No. and Revision noted below
checklist-flat | 1ed2592e-0523-4e4e-81cb-db73a59d0106 |  | checklist | Cast-Ins/penetrations CYP Checklist Number CHK/MMTS/00810 |  |  |  |  | Yes | Cast-Ins/penetrations CYP Checklist Number CHK/MMTS/00810 | 99256858-6491-45c3-a012-dbc76c724355
checkpoint-status | bb97c918-cbab-44f2-ba1e-1c2df6a2fdcd |  | checkpoint | Are the latest Version of the drawings being used for the work. Ref: 7.3.1 & 7.3.2 section on Hydraulic Services Specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001)
text | b099617f-32ae-5513-91d3-6ddf49484a06 |  | textbox | Drawing number
text | 14dad472-b3e1-5788-b22d-a3b0f4b12384 |  | textbox | Revision
checkpoint-status | 9c13906f-a7fe-419e-96be-6e2f29c25ede |  | checkpoint | Location of pipework is as per IFC drawing & CYP site survey set out Ref: 8.1.5 & 8.3.3 on Hydraulic Services Specification
select | 71ca46bb-f75d-5af3-a96f-cd0b5571ac62 |  | dropdown | Drain / Penetration type | Permanent,Provisional
checkpoint-status | e7bcb8ee-038c-4f5e-a0db-cfc9870995aa |  | checkpoint | Pipe materials used are as per Tunnel and stations hydraulic services specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
select | 214aec65-12fc-5813-b630-8c6e376dcb0c |  | dropdown | Pipework material used. Ref : 7.9.1 section on Hydraulic Services Specification | HDPE,Cast Iron,Poly
checkpoint-status | 23b339cc-fd14-4809-9ca4-9b36e3e97cf8 |  | checkpoint | HOLDPOINT BELOW - CYP to sign before passing checkpoint
label | 7c9c905a-7e01-5551-8ca2-51b03e1fb7d3 |  | note | Visualised by Nominated CYP Authority Only (CYP NA2- Proficiency Level 2)
boolean | ac4199ab-58ef-594a-99d0-b6ca2d3a518b |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
holdpoint | bec960ed-4aff-46a0-84cf-47ed73998934 |  | signoff | HOLDPOINT - CYP to Verify steps 1 to 6 are compliant with applicable supporting documentation
checkpoint-status | 222b302b-7b91-44da-b6c4-3bc4102033c0 |  | checkpoint | Invert levels as per drawings Ref: AS3500.2.2015 Table 3.4.1 and 8.3.8.4 in Hydraulics Services Specification
checkpoint-status | ec943ba8-314e-4f1e-a205-e091b1018b31 |  | checkpoint | No damage to pipework or fittings. Ref: Attached Photos below
checkpoint-status | ab2c026b-352e-42dd-ba3f-6eb26eb75387 |  | checkpoint | Correct drainage venting per Ref: AS 3500.2 2018 sec 3.9
checkpoint-status | 161cb35f-c9b7-4e4a-a1ad-068d06c729b6 |  | checkpoint | Correct fire protection / fire collars as per Ref: C3.15 of the BCA AS4072.1
checkpoint-status | 722e3f8e-6f34-4c1c-8b5e-b4b866059ae9 |  | checkpoint | Type & Brand of collar used as per Ref: C3.15 of the BCA AS4072.1
checkpoint-status | 77011615-2758-44b3-ba7b-690441900b53 |  | checkpoint | All points are connected
checkpoint-status | 23afc87f-8fe4-4604-b15c-f551aac27921 |  | checkpoint | Pipework on correct grade as per AS 3500.2 2015 Table 3.4.1 and 8.3.8.4 on Hydraulics Services Specification
checkpoint-status | 2d230f76-3cc7-4aa7-8231-e10ea1c5f2bf |  | checkpoint | Pipes are clean & Clear of debris - Welded / Glued Ref: As Per manufacturers requirement
checkpoint-status | a9e54eda-26eb-48ea-ab0c-b9ee19dd660c |  | checkpoint | Joint method defect free (Compression band) (Electro fusion) (Glued) Ref: As Per manufacturers requirement
checkpoint-status | c9e71ea8-4950-4456-bed4-731447b8ea0e |  | checkpoint | Has the pipework been witness marked and signed upon positive visual inspection of chosen method of jointing
checkpoint-status | cb018c70-5324-4f9e-b25c-db7f6ed0cb39 |  | checkpoint | Pressurised pipework to 15 Kpa according to AS3500.2 Sec 15 and Ref: 8.1.9, 20.3.6 & 20.3.8 on Hydraulics Services Specification
label | e1638979-dd4f-5df9-a809-07a5c0310d3a |  | note | Settle time for test is 3 min then an additional test time of 5 min Maximum pressure drop is +/- 3 Kpa over a 5 min period
checkpoint-status | 2bd2392a-b44a-4423-895b-4792e5065528 |  | checkpoint | HOLDPOINT BELOW - CYP to sign before passing checkpoint
boolean | 082e9c54-33e9-5d35-b9fc-2962804c0e69 |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
label | ab40d235-8928-550d-97df-c1763364d8f0 |  | note | Visualised by Nominated CYP Authority Only
holdpoint | a035ae83-8d34-48ad-9144-3c776659a766 |  | signoff | HOLDPOINT- CYP Nominated Authority sign off test
checkpoint-status | 0c1e5574-9ff7-4cec-a053-74addc8de0d0 |  | checkpoint | Pipe clipping on grade as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | ba1e20fb-8255-4471-883c-fc036021603a |  | checkpoint | Vertical clip spacing as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | 7ee8be4e-207b-4cbe-b83f-ce47ebffa206 |  | checkpoint | Pipe lagged in accordance with tunnel and stations hydraulic services specification
label | a6c1e201-ee74-5eae-b21d-1dd3a7319c70 |  | note | Specifications (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
checkpoint-status | 188bbdb2-fa60-40bd-9541-8bb159e49bd2 |  | checkpoint | Pipework to remain full of water during pour. Ref: As Per manufacturers requirement
checkpoint-status | e9460768-1b5b-40c3-abc9-ad83f3caa964 |  | checkpoint | Has pipework been picked up for completed works (As-built)
checkpoint-status | c3fc3b81-6124-49e4-a8fb-8222e08f8b37 |  | checkpoint | Signoff - CDC to sign before passing this checkpoint
boolean | 69cc3638-659e-5468-a915-865e9de58da2 |  | tickbox | CDC - General photos/comments attached below
label | b67b3a58-933c-55ff-96d3-e39194d6ca78 |  | note | SIGN-OFF :Name & Signature attatched below
holdpoint | 9ed5f452-3093-4bc3-9286-aa59df13031c |  | signoff | FINAL HOLDPOINT- CDC authority to signoff
checkpoint-status | 770dc39e-e00c-4356-9d56-1ff59733fff1 |  | checkpoint | Signoff - CYP to sign before passing this checkpoint
boolean | afaaf231-8986-5749-ac5e-779efd1c238e |  | tickbox | CYP Nominated comments - General comments attached below
boolean | 0cfc363a-fca9-5310-ad97-e2aa78bfec25 |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
holdpoint | e1ea6c65-ae58-4340-9861-ad7ff4a6d5f4 |  | signoff | FINAL HOLDPOINT- CYP nominated authority to signoff
checklist-sectioned | 49b2d099-9800-413a-bbec-6bb73e4cf1ce |  | checklist | Cast-in/Peno + Hydro Test (COMBINED) V.010322 |  |  |  |  | Yes | Cast-in/Peno + Hydro Test (COMBINED) V.010322 | b685a28e-0ec1-46d2-954b-bf4bac8a9f20
checkpoint-group | cfa3f3f6-9af7-462f-a30d-1257a6a3ef7d |  | section | Cast-Ins/penetrations CYP Checklist Number CHK/MMTS/00810
checkpoint-status | 4e2c9cc0-6a44-45ef-a888-731f69e96fbd |  | checkpoint | Are the latest Version of the drawings being used for the work. Ref: 7.3.1 & 7.3.2 section on Hydraulic Services Specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001)
text | b9fa9e56-c8cb-53a9-bbec-24fa07edf0e5 |  | textbox | Drawing number
text | 187150ad-5fd2-5696-9a1f-90777838a244 |  | textbox | Revision
checkpoint-status | 3eab871f-fb64-4899-ad5c-aff84c54b56a |  | checkpoint | Location of pipework is as per IFC drawing & CYP site survey set out Ref: 8.1.5 & 8.3.3 on Hydraulic Services Specification
select | d9e54a8b-be21-5182-96d6-6bbaa3bdb9c8 |  | dropdown | Drain / Penetration type | Permanent,Provisional
checkpoint-status | 66685f6e-ee34-4c75-819a-14a315cbec34 |  | checkpoint | Pipe materials used are as per Tunnel and stations hydraulic services specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
select | a75597c8-d56d-57fe-a0b8-54a2bfa40ad7 |  | dropdown | Pipework material used. Ref : 7.9.1 section on Hydraulic Services Specification | HDPE,Cast Iron,Poly
checkpoint-status | af1df10e-d705-4a49-85f7-b78f061cacd2 |  | checkpoint | HOLDPOINT BELOW - CYP to sign before passing checkpoint
label | 35ad4db7-9188-538b-8fce-83dfd17334cb |  | note | Visualised by Nominated CYP Authority Only (CYP NA2- Proficiency Level 2)
boolean | b8ee64c5-13af-5ab6-a5d5-651429b3e038 |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
holdpoint | 279560da-f654-477a-875f-f186baf8f5a7 |  | signoff | HOLDPOINT - CYP to Verify steps 1 to 6 are compliant with applicable supporting documentation
checkpoint-status | ef009d75-7a6f-4cf4-a627-083b25ab11d4 |  | checkpoint | Invert levels as per drawings Ref: AS3500.2.2015 Table 3.4.1 and 8.3.8.4 in Hydraulics Services Specification
checkpoint-status | b080be18-f8ac-4799-923d-030fc1ff4927 |  | checkpoint | No damage to pipework or fittings. Ref: Attached Photos below
checkpoint-status | 73f8cbb2-1e45-4b7f-88c7-5b1ada0f5d5f |  | checkpoint | Correct drainage venting per Ref: AS 3500.2 2018 sec 3.9
checkpoint-status | 47d1b0b5-c721-4199-89d1-b5e7420dda28 |  | checkpoint | Correct fire protection / fire collars as per Ref: C3.15 of the BCA AS4072.1
checkpoint-status | 3d6d3fe9-7d07-421a-b317-254a1ee66ed4 |  | checkpoint | Type & Brand of collar used as per Ref: C3.15 of the BCA AS4072.1
checkpoint-status | e68c2062-d751-4ad7-b6a9-bf5f538c0062 |  | checkpoint | All points are connected
checkpoint-status | 3a8e72b5-aa6f-4f98-9e63-5d36848c3e34 |  | checkpoint | Pipework on correct grade as per AS 3500.2 2015 Table 3.4.1 and 8.3.8.4 on Hydraulics Services Specification.
checkpoint-status | a2ec2d42-8597-49be-adc8-70dc1becb86e |  | checkpoint | Pipes are clean & Clear of debris - Welded / Glued Ref: As Per manufacturers requirement
checkpoint-status | 6e447615-16e6-4dee-bd22-80fea0aaad67 |  | checkpoint | Joint method defect free (Compression band) (Electro fusion) (Glued) Ref: As Per manufacturers requirement.
checkpoint-status | 0517115e-4126-4202-96cd-bc7f82a31b2b |  | checkpoint | Has the pipework been witness marked and signed upon positive visual inspection of chosen method of jointing
checkpoint-status | 0610c7cf-8fb5-49ca-be33-206b5ff064f9 |  | checkpoint | Pressurised pipework to 15 Kpa according to AS3500.2 Sec 15 and Ref: 8.1.9, 20.3.6 & 20.3.8 on Hydraulics Services Specification
label | 6164b816-9737-5cdc-88d3-1bcb18f57dcf |  | note | Settle time for test is 3 min then an additional test time of 5 min Maximum pressure drop is +/- 3 Kpa over a 5 min period
checkpoint-status | f248df36-34c7-4047-a9fc-fe7ffec08627 |  | checkpoint | HOLDPOINT BELOW - CYP to sign before passing checkpoint
boolean | ec7f787e-a5cd-51b4-acb1-4fa6f6f7d88e |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
label | 03ef35b4-b128-5c90-a963-8c5075708611 |  | note | Visualised by Nominated CYP Authority Only
holdpoint | d8fa9ab7-334a-4a13-947e-57e5bf9dd72e |  | signoff | HOLDPOINT- CYP Nominated Authority sign off test
checkpoint-status | d9c3a882-08e3-400a-bd4b-f45a88c624a2 |  | checkpoint | Pipe clipping on grade as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | 57563ff1-da7a-4079-903a-5763ef997d5d |  | checkpoint | Vertical clip spacing as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | 48d55458-ea2d-4be4-98c0-68ce47edf315 |  | checkpoint | Pipe lagged in accordance with tunnel and stations hydraulic services specification
label | 027dbb9a-b295-53f1-a117-c8318c45c2a6 |  | note | Specifications (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
checkpoint-status | 281d6f93-73ac-4fd5-b548-e083b7a7786c |  | checkpoint | Pipework to remain full of water during pour. Ref: As Per manufacturers requirement
checkpoint-status | 71b60bf3-9727-4144-a9cc-f91088fbf704 |  | checkpoint | Has pipework been picked up for completed works (As-built)
checkpoint-status | 08648c9d-4274-41b2-a1ba-b038b5965c3c |  | checkpoint | HOLDPOINT BELOW - CDC to sign before passing checkpoint
boolean | 08669adf-570c-5e19-a02e-cb1b462771b3 |  | tickbox | CDC - General photos/comments attached below
label | 5907f4be-3b10-544a-9729-4886fe522d8c |  | note | SIGN-OFF :Name & Signature attatched below.
holdpoint | 1b22067e-9775-48d9-a6b1-51fd6bec23ce |  | signoff | FINAL HOLDPOINT- CDC authority to signoff
checkpoint-status | 070e050f-ecda-4a79-899a-fdcae5fa119a |  | checkpoint | HOLDPOINT BELOW - CYP to sign before passing checkpoint
boolean | fc0e642c-4a4f-51f1-bcf5-3df9560cb877 |  | tickbox | CYP Nominated comments - General comments attached below
boolean | 734616d1-93c5-5ddc-a96d-e781a60ba1e5 |  | tickbox | SIGN-OFF - CYP Nominated Name & Signature(s) attached below
holdpoint | 8e32d8aa-67dd-4d7e-8ddf-56ff1b56eba3 |  | signoff | FINAL HOLDPOINT- CYP nominated authority to signoff
checkpoint-group | 9b892656-c933-4a04-924f-64c260f0024e |  | section | Hydrostatic Pressure Test
checkpoint-status | 4278234d-4b6a-46fd-afa4-64468106793e |  | checkpoint | Test Details - Pass once entered
text | 43bd0c58-9e67-5900-8ff0-b159a1508d0e |  | textbox | Location (Area/Level/Zone)
label | f1b56d35-45a1-5972-97af-94a26e197e0e |  | note | Testing Calibration Certificate Uploaded Per Level
text | f0f0c0da-68a8-5f55-b134-e31649ed136a |  | textbox | Service
text | 53691208-655b-5a7b-be6b-dedf0e2dd01e |  | textbox | Testing Apparatus Type & Number (Input or Attach photo below)
checkpoint-status | d69e33ab-986f-4c35-9fd3-dcc9b49c76e1 |  | checkpoint | Final Hydrostatic/Pressure Test
label | e66e491b-38e6-559e-98e1-37728ea65981 |  | note | Pressurised pipework to 15 Kpa according to AS3500.2 Sec 15 and Ref: 8.1.9, 20.3.6 & 20.3.8 on Hydraulics Services Specification
boolean | 77c55b34-6008-5dae-8164-5c4ef3e5915f |  | tickbox | CDC - General photos/comments attached below
boolean | cb35f58e-fd33-5bf8-9ddc-b41b1d90702a |  | tickbox | CYP Nominated comments - General comments attached below
checklist-flat | 03267c1f-a0f5-4400-b17a-c561e63cf363 |  | checklist | Cast-Ins/penetrations ITC-01 |  |  |  |  | Yes | Cast-Ins/penetrations ITC-01 | bb735a66-e2fd-46d6-8c59-a258b9773293
checkpoint-status | e24db06f-640b-47e9-83ba-17f13bd769af |  | checkpoint | Are the latest Version of the drawings being used for the work
text | cdf702e9-a490-5215-9f1a-f8dbb11f5c24 |  | textbox | Drawing number/s are noted on ITP
checkpoint-status | 0f6b4e0c-e66d-4498-8791-ba3202049252 |  | checkpoint | Location of pipework is as per IFC drawing & CYP site survey set out
button | 3c3f9bd5-9859-5402-b25b-ed5ac894444c |  | button | Drain / Penetration type | Permanent, Provisional
checkpoint-status | d1bd2e61-e022-44d1-b1ff-15dc58255fea |  | checkpoint | Pipe materials used are as per Tunnel and stations hydraulic services specification (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
button | 4d33a53f-346a-54d7-b6c5-f065c29582df |  | button | Pipework material used | HDPE, Cast Iron, Poly
checkpoint-status | 6aa2be35-0e6d-450a-8599-5a372e8dab08 |  | checkpoint | HOLDPOINT - Verify steps 1 to 6 are compliant with applicable supporting documentation. Visualised by Nominated CYP Authority
checkpoint-status | 2157d88d-9913-4e0c-9241-bc6472b4560d |  | checkpoint | Invert levels as per drawings
checkpoint-status | 49c9745d-7697-4f3b-942b-8de60825728e |  | checkpoint | No damage to pipework or fittings - Attach Photos below
checkpoint-status | d8637192-9e06-4401-9364-85e78491d1a1 |  | checkpoint | Correct drainage venting per AS 3500.2 2018 sec 3.9
checkpoint-status | 9c9545b4-0fba-41d3-920e-e790ccf72256 |  | checkpoint | Correct fire protection / fire collars as per C3.15 of the BCA AS4072.1
checkpoint-status | 63c17592-bfd5-4271-9a50-7c433327879a |  | checkpoint | Type & Brand of collar used
checkpoint-status | 1cf7996a-43f7-47a1-9a0b-9d70d50a92bd |  | checkpoint | All points are connected
checkpoint-status | eea8865a-74a3-43db-82f1-8e30aa6c597f |  | checkpoint | Pipework on correct grade as per AS 3500.2 2015 Table 3.4.1
checkpoint-status | d2d81e9a-a739-42d6-88d9-4b14c9090fe1 |  | checkpoint | Pipes are clean & Clear of debris - Welded / Glued
checkpoint-status | 6655eec2-a1ca-408a-bd72-8652e1259e8c |  | checkpoint | Joint method defect free (Compression band) (Electro fusion) (Glued)
checkpoint-status | f33a9d05-27cc-46fd-98e9-115567f4890e |  | checkpoint | Has the pipework been witness marked and signed upon positive visual inspection of chosen method of jointing
checkpoint-status | d4cb336d-ae17-4def-8898-c8d167320435 |  | checkpoint | Pressurised pipework to 15 Kpa
label | 8ee63cdd-7d14-5c37-abb9-5e51b6d6f379 |  | note | Settle time for test is 3 min then an additional test time of 5 min Maximum pressure drop is +/- 3 Kpa over a 5 min period
checkpoint-status | c96f92cd-074a-430d-8386-0fa4630f3162 |  | checkpoint | Hold Point - CYP Nominated Authority sign off test
label | a95965a3-33d1-559d-abdc-dd5430fa5197 |  | note | Attach Signature(s) below
checkpoint-status | 2a76fb90-0a88-4943-a1d3-37f7fc181861 |  | checkpoint | Pipe clipping on grade as per AS 3500.3 Clause 4.9.6.2
label | 708e2a9b-35df-531c-a6ab-c00ea0f59ca3 |  | note | Vertical clip spacing as per AS 3500.3 Clause 4.9.6.2
checkpoint-status | eb60ffac-2a04-4cea-9adf-7d1f256ea3d8 |  | checkpoint | Pipe lagged in accordance with tunnel and stations hydraulic services specification
label | b058ce42-f178-5b95-9813-166b7bbefe42 |  | note | Specifications (TAS-CYP-SDU-ZWD-SPC-BSH-SDU-B0001 REV-B)
checkpoint-status | cdaa22d0-2f50-4106-ae98-f15b35d5e2ec |  | checkpoint | Has excess pipework been picked up for completed works
checkpoint-status | 552f675a-fb12-4151-83a3-8f846280f859 |  | checkpoint | FINAL - Pipework completed to specification/drawings - Area left clean & tidy
boolean | f3693323-4caa-56d8-8ce0-07d0dbdbf2d7 |  | tickbox | CDC - General photos/comments attached below
boolean | 6ac3fb95-2adf-57aa-a3e6-0191ff22bca8 |  | tickbox | CYP Nominated comments - General comments attached below
boolean | 017ef787-3fb1-5d25-badf-fa515a54711c |  | tickbox | SIGN-OFF - CDC & CYP Nominated Signature(s) attached below
checklist-flat | fc9b4db8-eda5-4213-bd56-ac2b53e049d7 |  | checklist | Hydrostatic Pressure Test V.010322 |  |  |  |  | Yes | Hydrostatic Pressure Test V.010322 | cf7b206f-3542-41fa-9709-b617e3aaee12
checkpoint-status | d5be49e9-a0f8-43d9-aeba-5964f4071f2a |  | checkpoint | Test Details - Pass once entered
text | 397e0988-74c5-528e-9d67-7594ad0964c7 |  | textbox | Location (Area/Level/Zone)
text | 8ebc75fa-d08d-54a9-ac85-b8a422dd0e5e |  | textbox | Testing Calibration Tested Date
text | 35a01452-98af-51dd-8fea-4a977b00e4c5 |  | textbox | Testing Calibration Due Date
text | ecdd0bd7-6e5c-5e0e-9773-7f08ddccd7d0 |  | textbox | Service
text | 5521fe6d-0eb6-51d4-903c-bf040e3b65b7 |  | textbox | Testing Apparatus Type
text | f98239c6-5f0f-5416-8a93-ea626760f400 |  | textbox | Testing Apparatus Number
checkpoint-status | 77908aec-7fbb-4f4c-ac90-a1590a96c7fa |  | checkpoint | Preliminary Sectional Air Test to 15kPa
checkpoint-status | b9516cdb-0245-471e-b359-2c015326ea98 |  | checkpoint | Final Hydrostatic Test
text | 0b955f69-09e4-59a7-be88-e11132a94b7b |  | textbox | Test reading kPa