## 1. General_Estab_Disestab
1. GENERAL / ESTABLISHMENT / DISESTABLISHMENT
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Responsible | Inspection
[8 empty] | Key | By (Role Key) | Date
1.1 | FOR CONSTRUCTION plans received from Engineer and reviewed by Contractor | Construction Management & Quality Control | Approved plans issued. Queries and issues raised (if any). | Drawing Register | Once - and as new plans are released | Reciept of Approval | Project Manager | Review | Project Manager
1.2 | Site handover completed | Construction Management | Identifiable / foreseeable problems raised, addressed and resolved. All agree to the site being handed over. | Handover Record (email etc) | Once | Site Meeting | Project Manager | Hold Point | Engineer / Hastings Distruct Council
1.3 | Inspection and Test Plan (ITP) completed | Construction Management | Engineer approval of ITP. | Inspection and Test Plan document | Once | Reciept of Approval | Project Manager | Hold Point | Engineer
1.4 | Weekly report completed | Construction Management | Email sent to Engineer (by COB Monday). | Weekly Report | Weekly | Report Submission | Project Manager | Review | Engineer
1.5 | Service locates completed. | Zero Harm | Reciept of plans and onsite marks. | Before U Dig reports, onsite markings | Prior to excavation | Visual Inspection and Plans Obtained | Project Manager | Check | Project Manager
1.6 | Existing services protected | Zero Harm | Services made safe and visiable. | Photos Site Diary | Prior to physical works | Visual Inspection | Project Manager | Check | Project Manager
1.7 | Baseline locations established, survey marks protected. | Quality Control | Site setout complete. Surveyor run through setout with Project Manager. | Site Diary | As required (ongoing) | Visual Inspection | Project Manager & Surveyor | Inspection | Project Manager
1.8 | Stakeholder notification - Client (HDC) - Engineer (Stantec) - Landowners | Stakeholder Management | Stakeholders notified of commencement of works and key project milestones. | Site Diary Emails, letters etc. | Prior to physical works and then as required | Record | Project Manager | Check | Project Manager
1.9 | Dumpsite agreement | Stakeholder Management | Signed agreement. | Signed Agreement | Prior to dumping material | Reciept of Approval | Project Manager | Review | Project Manager
1.10 | Portaloo imported | Zero Harm | Portaloo onsite and servicing schedule agreed. | Photos Site Diary | Once - at establishment and servicing as required | Visual Inspection | Project Manager | Check | Project Manager
1.11 | Site office imported | Construction Management & Zero Harm | Site office onsite. | Photos Site Diary | Once - at establishment | Visual Inspection | Project Manager | Check | Project Manager
1.12 | First aid kit, fire extinguisher, spill kit and water onsite | Zero Harm | Various items onsite. | Photos Site Diary | Once - at establishment | Visual Inspection | Project Manager | Check | Project Manager
1.13 | Silt fence at dumpsite installed | Environmental Management | Silt fence installed. | Photos Site Diary | Prior to dumping material | Visual Inspection | Project Manager | Inspection | Project Manager

## 3. Culvert Install
3. CULVERT INSTALL
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Responsible | Inspection
[8 empty] | Key | By (Role Key) | Date
Subsoil Drainage
3.1 | Set out | Quality Control | Set out of subsoil drainage lines to match plans. | Photos Onsite Inspection Onsite Measurements | For each subsoil drain | Visual Inspection | Project Manager | Visual Verification | Project Manager
3.2 | Subsoil Materials - geotextile | Material Quality | As per project specification: TNZ F/7 Class C geotextile | Photos Onsite Inspection | Prior to install | Visual Inspection Manufacturers Dockets | Project Manager | Visual Verification | Project Manager
3.3 | Subsoil Materials - aggregate | Material Quality | As per project specification: TNZ F/6 20/40 Drainage Material | Photos Onsite Inspection | Prior to install | Visual Inspection | Project Manager | Visual Verification | Project Manager
3.4 | Subsoil Materials - pipe | Material Quality | As per project specification: TNZ F/7 DN160 subsoil drain | Photos Onsite Inspection | Prior to install | Visual Inspection Manufacturers Dockets | Project Manager | Visual Verification | Project Manager
3.5 | Laying Geotextile | Quality Control | Lining the trench as per typical detail. | Photos Onsite Inspection | For each subsoil drain | Visual Inspection | Project Manager | Inspection | Engineer
3.6 | Laying Pipe | Quality Control | Lay pipe as per design and manufacturers specification. Ensure smooth grade (no high points). | Photos Onsite Inspection | For each subsoil drain | Visual Inspection | Project Manager | Inspection | Engineer
3.7 | Inspection prior to backfill | Quality Control | Engineer approval of pipe laying | Photos Onsite Inspection | Prior to backfill | Engineer Approval | Project Manager | Hold Point | Engineer
3.8 | Place Drainage Aggregate | Quality Control | Material placed and compacted around subsoil pipe and as per typical detail. | Photos Onsite Inspection | For each subsoil drain | Visual Inspection | Project Manager | Inspection | Engineer
Culvert
3.9 | Set out | Quality Control | Survey set out of culvert alignment to match plans and electronic setout information. Confirm min. distance from existing culvert is achieved. | Photos Onsite Inspection Onsite Measurements | Before culvert install | Survey Records | Project Manager & Surveyor | Survey Check | Project Manager
3.10 | Bedding Materials - aggregate | Material Quality | As per project specification: TBC - 20/40 Drainage Material | Photos Onsite Inspection | Prior to install | Visual Inspection | Project Manager | Visual Verification | Project Manager
3.11 | Pipe Classification | Material Quality | As per project specification: DN3200 HDPE SN7.57 (from Infrapipe) | Photos Onsite Inspection | On arrival to site and prior to install | Visual Inspection Manufacturers Dockets | Project Manager | Visual Verification | Project Manager
3.12 | Culvert Materials - delivery | Material Quality | Pipes transported to site and off loaded with no damage - ratchet tie downs (not chains), piloted transport Report any damages. | Photos Manufacturers Specs | On arrival and during unloading | Visual Inspection | Transport Company & Onsite Operators | Visual Verification | Project Manager
3.13 | Culvert Materials - onsite storage | Material Quality | Pipe laid down in a safe place - out of traffic lane, not causing water ponding issues, unable to roll away Pipe laid down where damage can not be done - level & firm ground, transport dunnage used, sockets/spigots/ends are free from loads and clear of debris | Photos Manufacturers Specs | As unloaded | Visual Inspection | Project Manager & Onsite Operators | Visual Verification | Project Manager
3.14 | Culvert Placement | Safety Management | Lift plan, appropriately sized crane, tagged lifting equipment, ticket operators. | Lift Plan Site Briefing | Before culvert install | Lift Plan Visual Inspection | Project Manager & Crane Hire Company | Check & Review | Project Manager
3.15 | Depth, grade and alignment | Quality Control | True grade with no humps/hollows. Within tolerances - TBC. | Photos Onsite Inspection Laser Level Check | Before culvert install | Visual Inspection | Drainlayer Foreman | Check | Project Manager
3.16 | Laying and Jointing | Quality Control | Finished joint to be watertight. Sockets facing uphill. Clean barrells, spigots and sockets prior to jointing. Rubber rings in place and free of dust, grease or dirt. | Photos Onsite Inspection | Every length of pipe | Visual Inspection | Drainlayer Foreman | Inspection | Project Manager
3.17 | Inspection prior to backfill | Quality Control | Engineer approval of culvert laying | Photos Onsite Inspection | Prior to backfill | Engineer Approval | Project Manager | Hold Point | Engineer
3.18 | Backfill - refer to Earthworks ITP
3.19 | Confirm Alignment / As-Built requirments | Quality Control | As-built position of culvert within tolerances. | Survey | Prior to backfill | Survey Records | Project Manager & Surveyor | Survey Check | Project Manager
3.20 | RAMM input | Maintenance Provision | Loaded into HDC RAMM system. | RAMM Approval | Prior to practical completion | RAMM Submission | Project Manager & RAMM Team | Check & Review | Engineer / Hastings District Council