## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - 1. General / Establishment / Disestablishment | itp |  |  |  |  | ITP - 1. General / Establishment / Disestablishment
checkpoint | 1.1 - FOR CONSTRUCTION plans received from Engineer and reviewed by Contractor
label | Inspection Point: Quality Control Activity - Construction Management & Quality Control
label | Acceptance Criteria - Approved plans issued. Queries and issues raised (if any).
label | Verifying Document - Drawing Register
label | Frequency - Once - and as new plans are released
label | Inspection Type (Visual, other) - Reciept of Approval
label | Responsible - Project Manager
label | Inspection: Key - Review
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.2 - Site handover completed
label | Inspection Point: Quality Control Activity - Construction Management
label | Acceptance Criteria - Identifiable / foreseeable problems raised, addressed and resolved. All agree to the site being handed over.
label | Verifying Document - Handover Record (email etc)
label | Frequency - Once
label | Inspection Type (Visual, other) - Site Meeting
label | Responsible - Project Manager
label | Inspection: Key - Hold Point
label | Inspection: By (Role Key) - Engineer / Hastings Distruct Council
textbox | Inspection: Date -
holdpoint | HOLD POINT
checkpoint | 1.3 - Inspection and Test Plan (ITP) completed
label | Inspection Point: Quality Control Activity - Construction Management
label | Acceptance Criteria - Engineer approval of ITP.
label | Verifying Document - Inspection and Test Plan document
label | Frequency - Once
label | Inspection Type (Visual, other) - Reciept of Approval
label | Responsible - Project Manager
label | Inspection: Key - Hold Point
label | Inspection: By (Role Key) - Engineer
textbox | Inspection: Date -
holdpoint | HOLD POINT
checkpoint | 1.4 - Weekly report completed
label | Inspection Point: Quality Control Activity - Construction Management
label | Acceptance Criteria - Email sent to Engineer (by COB Monday).
label | Verifying Document - Weekly Report
label | Frequency - Weekly
label | Inspection Type (Visual, other) - Report Submission
label | Responsible - Project Manager
label | Inspection: Key - Review
label | Inspection: By (Role Key) - Engineer
textbox | Inspection: Date -
checkpoint | 1.5 - Service locates completed.
label | Inspection Point: Quality Control Activity - Zero Harm
label | Acceptance Criteria - Reciept of plans and onsite marks.
label | Verifying Document - Before U Dig reports, onsite markings
label | Frequency - Prior to excavation
label | Inspection Type (Visual, other) - Visual Inspection and Plans Obtained
label | Responsible - Project Manager
label | Inspection: Key - Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.6 - Existing services protected
label | Inspection Point: Quality Control Activity - Zero Harm
label | Acceptance Criteria - Services made safe and visiable.
label | Verifying Document - Photos, Site Diary
label | Frequency - Prior to physical works
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.7 - Baseline locations established, survey marks protected.
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Site setout complete. Surveyor run through setout with Project Manager.
label | Verifying Document - Site Diary
label | Frequency - As required (ongoing)
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager & Surveyor
label | Inspection: Key - Inspection
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.8 - Stakeholder notification - Client (HDC) - Engineer (Stantec) - Landowners
label | Inspection Point: Quality Control Activity - Stakeholder Management
label | Acceptance Criteria - Stakeholders notified of commencement of works and key project milestones.
label | Verifying Document - Site Diary, Emails, letters etc.
label | Frequency - Prior to physical works and then as required
label | Inspection Type (Visual, other) - Record
label | Responsible - Project Manager
label | Inspection: Key - Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.9 - Dumpsite agreement
label | Inspection Point: Quality Control Activity - Stakeholder Management
label | Acceptance Criteria - Signed agreement.
label | Verifying Document - Signed Agreement
label | Frequency - Prior to dumping material
label | Inspection Type (Visual, other) - Reciept of Approval
label | Responsible - Project Manager
label | Inspection: Key - Review
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.10 - Portaloo imported
label | Inspection Point: Quality Control Activity - Zero Harm
label | Acceptance Criteria - Portaloo onsite and servicing schedule agreed.
label | Verifying Document - Photos, Site Diary
label | Frequency - Once - at establishment and servicing as required
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.11 - Site office imported
label | Inspection Point: Quality Control Activity - Construction Management & Zero Harm
label | Acceptance Criteria - Site office onsite.
label | Verifying Document - Photos, Site Diary
label | Frequency - Once - at establishment
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.12 - First aid kit, fire extinguisher, spill kit and water onsite
label | Inspection Point: Quality Control Activity - Zero Harm
label | Acceptance Criteria - Various items onsite.
label | Verifying Document - Photos, Site Diary
label | Frequency - Once - at establishment
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 1.13 - Silt fence at dumpsite installed
label | Inspection Point: Quality Control Activity - Environmental Management
label | Acceptance Criteria - Silt fence installed. Silt fence installed.
label | Verifying Document - Photos, Site Diary
label | Frequency - Prior to dumping material
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Inspection
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -