## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 3. Culvert Install | itp |  |  |  |  | ITP - 3. Culvert Install
section | Subsoil Drainage
checkpoint | 3.1 - Set out
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Set out of subsoil drainage lines to match plans.
label | Verifying Document - Photos, Onsite Inspection, Onsite Measurements
label | Frequency - For each subsoil drain
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.2 - Subsoil Materials - geotextile
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - As per project specification: TNZ F/7 Class C geotextile
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Prior to install
label | Inspection Type (Visual, other) - Visual Inspection, Manufacturers Dockets
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.3 - Subsoil Materials - aggregate
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - As per project specification: TNZ F/6 20/40 Drainage Material
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Prior to install
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.4 - Subsoil Materials - pipe
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - As per project specification: TNZ F/7 DN160 subsoil drain
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Prior to install
label | Inspection Type (Visual, other) - Visual Inspection, Manufacturers Dockets
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.5 - Laying Geotextile
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Lining the trench as per typical detail.
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - For each subsoil drain
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Inspection
label | Inspection: By (Role Key) - Engineer
textbox | Inspection: Date -
checkpoint | 3.6 - Laying Pipe
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Lay pipe as per design and manufacturers specification. Ensure smooth grade (no high points).
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - For each subsoil drain
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Inspection
label | Inspection: By (Role Key) - Engineer
textbox | Inspection: Date -
checkpoint | 3.7 - Inspection prior to backfill
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Engineer approval of pipe laying
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Prior to backfill
label | Inspection Type (Visual, other) - Engineer Approval
label | Responsible - Project Manager
label | Inspection: Key - Hold Point
label | Inspection: By (Role Key) - Engineer
textbox | Inspection: Date -
holdpoint | HOLD POINT
checkpoint | 3.8 - Place Drainage Aggregate
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Material placed and compacted around subsoil pipe and as per typical detail.
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - For each subsoil drain
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Inspection
label | Inspection: By (Role Key) - Engineer
textbox | Inspection: Date -
section | Culvert
checkpoint | 3.9 - Set out
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Survey set out of culvert alignment to match plans and electronic setout information. Confirm min. distance from existing culvert is achieved.
label | Verifying Document - Photos, Onsite Inspection, Onsite Measurements
label | Frequency - Before culvert install
label | Inspection Type (Visual, other) - Survey Records
label | Responsible - Project Manager & Surveyor
label | Inspection: Key - Survey Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.10 - Bedding Materials - aggregate
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - As per project specification: TBC - 20/40 Drainage Material
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Prior to install
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.11 - Pipe Classification
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - As per project specification: DN3200 HDPE SN7.57 (from Infrapipe)
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - On arrival to site and prior to install
label | Inspection Type (Visual, other) - Visual Inspection, Manufacturers Dockets
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.12 - Culvert Materials - delivery
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - Pipes transported to site and off loaded with no damage - ratchet tie downs (not chains), piloted transport. Report any damages.
label | Verifying Document - Photos, Manufacturers Specs
label | Frequency - On arrival and during unloading
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Transport Company & Onsite Operators
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.13 - Culvert Materials - onsite storage
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - Pipe laid down in a safe place - out of traffic lane, not causing water ponding issues, unable to roll away. Pipe laid down where damage can not be done - level & firm ground, transport dunnage used, sockets/spigots/ends are free from loads and clear of debris
label | Verifying Document - Photos, Manufacturers Specs
label | Frequency - As unloaded
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager & Onsite Operators
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.14 - Culvert Placement
label | Inspection Point: Quality Control Activity - Safety Management
label | Acceptance Criteria - Lift plan, appropriately sized crane, tagged lifting equipment, ticket operators.
label | Verifying Document - Lift Plan, Site Briefing
label | Frequency - Before culvert install
label | Inspection Type (Visual, other) - Lift Plan, Visual Inspection
label | Responsible - Project Manager & Crane Hire Company
label | Inspection: Key - Check & Review
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.15 - Depth, grade and alignment
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - True grade with no humps/hollows. Within tolerances - TBC.
label | Verifying Document - Photos, Onsite Inspection, Laser Level Check
label | Frequency - Before culvert install
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Drainlayer Foreman
label | Inspection: Key - Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.16 - Laying and Jointing
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Finished joint to be watertight. Sockets facing uphill. Clean barrells, spigots and sockets prior to jointing. Rubber rings in place and free of dust, grease or dirt.
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Every length of pipe
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Drainlayer Foreman
label | Inspection: Key - Inspection
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.17 - Inspection prior to backfill
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Engineer approval of culvert laying
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Prior to backfill
label | Inspection Type (Visual, other) - Engineer Approval
label | Responsible - Project Manager
label | Inspection: Key - Hold Point
label | Inspection: By (Role Key) - Engineer
textbox | Inspection: Date -
holdpoint | HOLD POINT
checkpoint | 3.18 - Backfill - refer to Earthworks ITP
label | Inspection Point: Quality Control Activity - Backfill - refer to Earthworks ITP
label | Acceptance Criteria - Backfill - refer to Earthworks ITP
label | Verifying Document - Backfill - refer to Earthworks ITP
label | Frequency - Backfill - refer to Earthworks ITP
label | Inspection Type (Visual, other) - Backfill - refer to Earthworks ITP
label | Responsible - Backfill - refer to Earthworks ITP
label | Inspection: Key - Backfill - refer to Earthworks ITP
label | Inspection: By (Role Key) - Backfill - refer to Earthworks ITP
textbox | Inspection: Date -
checkpoint | 3.19 - Confirm Alignment / As-Built requirments
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - As-built position of culvert within tolerances.
label | Verifying Document - Survey
label | Frequency - Prior to backfill
label | Inspection Type (Visual, other) - Survey Records
label | Responsible - Project Manager & Surveyor
label | Inspection: Key - Survey Check
label | Inspection: By (Role Key) - Project Manager
textbox | Inspection: Date -
checkpoint | 3.20 - RAMM input
label | Inspection Point: Quality Control Activity - Maintenance Provision
label | Acceptance Criteria - Loaded into HDC RAMM system.
label | Verifying Document - RAMM Approval
label | Frequency - Prior to practical completion
label | Inspection Type (Visual, other) - RAMM Submission
label | Responsible - Project Manager & RAMM Team
label | Inspection: Key - Check & Review
label | Inspection: By (Role Key) - Engineer / Hastings District Council
textbox | Inspection: Date -