## Table 1
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | Project Number -
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Date submitted:
|  |  |  | Construction Process: Traffic Signals |  |  |  |  | Prepared By: Downer New Zealand
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 900 - Traffic Signals |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
900 | Setout, Materials and Preparation
900.1 | Method Statement Development / Job Safety & Environmental Analysis | Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed) | H | NA | NA | Method Statement and JSEA Completed and signed by relevant authority. | MS & JSEA | Contractor | Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
900.2 | Drawings and Specifications | Check drawings are for construction and latest revision. Check Specification is for construction and latest revision | H | NA | NA | Drawings and Specification are the latest revision. | IFC Drawings and Specification | Contractor | Up to date drawings and specification to be reviewed before construction.
900.3 | Power Connection | Ensure power supply is organised and connection is in place | H | once per set of traffic lights | NA | Complete NC1 form and ensure ducting for power is in place. | NC1 Form | WSP / Contractor
900.4 | Comms Connection | Ensure comms connection is organised and ducting is in place | H | once per set of traffic lights | NA | Liase with service provider and organise connection (UCG) Universal communications group. |  | Contractor | Order connection from Chorus
900.5 | Survey Set Out | GPS Setout of the shared services trench location as per the construction drawings. | W | All shared trenches. | Visual Inspection | N/A | Contractor's site diary and/or photos | Contractor | Setout location prior to commencing works.
900.6 | Sediment Controls are in place for the particular section | Check ESCP and ensure any controls needed are in place before excavation. | M | once per section | Visual Inspection | Erosion and Sediment controls are in place prior to starting works. | Contractor's site diary and/or photos | Contractor
Construction and Finshing
900.7 | Element Locations / Positioning / Types | Walk over with TTOC, WSP, TSL & Downer representatives to agree positions of intersection elements | H | Once per set of traffic lights/intersection | Visual Inspection | TTOC, WSP, TSL acceptance. | Written confirmation | Contractor
900.8 | CIS Production | Draft CIS to be produced, independently reviewed and approved. | H | Once per set of traffic lights/intersection | Document Review | Review completed and development approved. | InEight Documents | Contractor
900.9 | Software Testing | Software to be independently tested using traffic signal emulator software (SFT Testing) | H | Once per set of traffic lights/intersection | Document Review | Approval for release received. | SFT Test Result Summary Sheet | Contractor
900.1 |  | SFT files provided to create PROM, bench testing to be completed by TSL | H | Once per set of traffic lights/intersection | Document Review | Pass result for bench test on "Appendix H - Controller Bench Testing Form". | Appendix H NZTA P43 | Contractor
900.11 | Pole - Installation | Ensure poles are plumbed vertical | W | Each pole | Location/Position Acceptance | Plumbed vertical Tolerance: +/- 10mm per 5.0m length | QC Sheets | Contractor
900.12 | Pole - Identification / Finishing | Pole Number Verification | W | Each pole | Visual Inspection | Ensure poles are numbered correctly and match the CIS sheets (pole numbers match program and diagram numbers). | QC Sheets | Contractor
900.13 | Pole - Footings | Footing Type | W | Each pole | Visual Inspection | TSL engineer confirmation that poles are founded securely and have adequatley sized footings for the site conditions. | QC Sheets | Contractor
900.14 |  | Soil Bearing Strength | H | One per pole cluster area (i.e. north-eastern corner, median etc.) | Scala Penetrometer | Average 3 blows / 100mm over 500mm or per comments | Scala Testing | Contractor | Scala results to meet or exceed per below: 0mm - 100mm - ≥ 3 blows per 100mm 100mm - 200mm - ≥ 2 blows per 100mm 200mm - 300mm - ≥ 2 blows per 100mm 300mm - 400mm - ≥ 1 blow per 100mm 400mm - 500mm - ≥ 1 blow per 100mm
900.15 |  | Concrete Foundation Dimensions | W | Each footing not within concrete or asphalt. | Visual Inspection | Where a pole is not surrounded by concrete, the pole must have 500mm2 of concrete surrounding it with a depth of 150mm (20MPa as below). | QC Sheets | Contractor
900.16 |  | Footing Concrete Strength | M | Each footing requiring concrete | Visual Inspection/Concrete Dockets | Confirmation footing concrete strength (where required - i.e. delivery dockets) is min 20MPa at 28days, or as specified in foudation design. | QC Sheets/concrete dockets | Contractor
900.17 | Cabling | Continuous Lengths | M | All lengths | Visual Inspection | Cabling to be continuous lengths from controller to the pole, and from pole to pole (i.e. no joints between poles). | QC Sheets | Contractor
900.18 |  | Looper Feeder Cable Slack | M | All lengths | Visual Inspection | Following cable slacks to be provided: - 1.8m (minimum) at controller base - 0.5m (minimum) inside KSJB | QC Sheets | Contractor
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
900.19 | Cable Termination Chart | Provide cable termination chart in controller cabinet. | H | Each controller cabinet | Inspection | Cable termination chart provided. | QC Sheets | Contractor
900.2 | Earth / Earth Loop Impedance Testing | Complete earth loop impedance testing per 3.15.2 of NZTA P43. | H | Once per set of traffic lights/intersection as specified in 3.15.2 of NZTA P43 | Inspection | Submit results in a report. | QC Sheets | Contractor
900.21 | Loop Testing | 500V test from the isolated conductors down to earth. | H | All loops | Electrical Testing | Result ≥ 10 megaohms. Q ≥ 15 when measured in the kerbside junction box (KJB). Submit results signed by technician who conducted the testing and in a report. | QC Sheets | Contractor
900.22 | Loop Feeder Cable Testing | 500V test from isolated conductors down to earth. | H | All feeder cables | Electrical Testing | Result ≥ 10 megaohms. Resistance of feeder cable ≤ 10 megaohms when measured at the controller. Submit results signed by technician who conducted the testing and in a report. |  | Contractor
900.23 | Log Book | Log book detailing any attendance at site, reason for attending and brief description of work carried out. | H | Once per controller box | Visual Inspection | Log book provided/completed as required. |  | Contractor
900.24 | Site Acceptance Testing | Completion and sign off of TTOC-07 Site Acceptance Test (SAT) documentation. | H | Once per set of traffic lights/intersection | Inspection / Audit | All requirements satisfied and TTOC Traffic Signals Engineer signed acceptance of SAT document. | TTOC-07 SAT | Contractor
900.25 | Electrical certificate of compliance and record of inspection | Complete COC and ROI. | H | Once per set of traffic lights/intersection | Inspection / Audit | Submit COC and ROI. | COC & ROI | Contractor
900.26 | Commissioning | Submit completed and signed Appendix H forms 5 working days prior to commissioning. | H | Once per set of traffic lights/intersection | Document Submission | Submit Appendix H forms to TTOC. |  | Contractor
900.27 |  | Notify TTOC with 48hrs notice before commissioning lights. | H | Once per set of traffic lights/intersection | Inspection | TTOC Acceptance. | Written confirmation | Contractor
Close Out
900.28 | Collate above documentation | Document review | H | Each ITP | Review | All above documentation is shown as attached to this work pack. | Review | Contractor
900.29 | Controller cabinet documents | Controller Cabinet Information | H | At time of commissioning | Review | Laminated copies of below placed in document pocket inside controller cabinet, within two weeks of commissioning: - As-built plans, - Completed cable termination chart - Controller Information Sheet (CIS) - Log-book | Review | Contractor
900.3 | As-built drawings | Survey | H | At completion of construction | Asbuilts to be submitted at the completion of construction, information to be captured regularly. | Asbuilts reviewed and submitted showing final location of all poles, access chambers, KJB, loops, lantern displays and cabinets. Completion and sign off of TTOC-08 Site Asset Collection Sheet/Appendix K of NZTA P43 documentation. | In Eight record | Contractor
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. Contractor's Rep Name: Signature: Date: BBO Engineers Rep Name: Signature: Date: | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
[7 empty] | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
[7 empty] | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.