## Project Breakdown
NARC - Northern Aquatic & Recreation Centre |  |  | Checklists
QA / ITP's
Wet Bar Roof Zone 1
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
Wet Bar Roof Zone 2
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
Dry Bar Roof Zone 3
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
Canopy Roofs
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Dry Bar Walls Zone 3
Dry Bar Plant Wall Cladding
Wet Bar Plant Cladding Zone 1
Air Barrier
|  | Zone 1 | Air Barrier Installation Checklist
|  | Zone 2 | Air Barrier Installation Checklist
|  | Zone 3 | Air Barrier Installation Checklist
Soffit Works
|  | Zone 1 | Soffit / Eave Installation Checklist
|  | Zone 3 | Soffit / Eave Installation Checklist
Variations
Jan '23
Feb '23
Mar '23
Apr '23
May '23
Jun '23
Jul '22
Aug '22
Sep '22
Oct '22
Nov '22
Dec '22
OH&S
Daily Prestart Toolbox Forms
Jan '23
Feb '23
Mar '23
Apr '23
May '23
Jun '23
Jul '22
Aug '22
Sep '22
Oct '22
Nov '22
Dec '22
Weekly Toolbox Forms
Jan '23
Feb '23
Mar '23
Apr '23
May '23
Jun '23
Jul '22
Aug '22
Sep '22
Oct '22
Nov '22
Dec '22
SWMS
Foremans Diary Reports
Jan '23
Feb '23
Mar '23
Apr '23
May '23
Jun '23
Jul '22
Aug '22
Sep '22
Oct '22
Nov '22
Dec '22
COVID Tracking Reports

## Air Barrier
Air Barrier
type | name | values
checklist | Air Barrier Installation
section | Material Inspection:
checkpoint | Proctorgeo 120 Smart Vap Paper
checkpoint | Innova Wrap Vinyl
checkpoint | Proctor AB Tape
checkpoint | 6mm Butyl Tape
section | Installation:
checkpoint | ProctorGeo Smart Vap 120 paper installed to paprapet walls
checkpoint | Innova Wrap Vinyl installed under gutter
checkpoint | Proctor AB Tape installed where required on joins and junctions
checkpoint | Butyl tape installed between Innova Wrap and Kingspan Roof panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Parapet Capping Material 2mm Aluminium
checkpoint | Ridge Capping Material 0.61mm Colorbond
checkpoint | Apron Flashing Material 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Wrap under gutter: Innova Vinyl Wrap
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Insulation under gutter: 60mm Kingspan Kooltherm Insulation
checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint | Gutter Flashing: Colorbond to match
checkpoint | Sumps / Outlets: 0.61mm Colorbond / Syfon
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Soffit Eave Install
Soffit Works
type | name | values
checklist | Soffit/Eave Installation
section | Material Inspection:
checkpoint | Walnut Brown Mondoclad panels
checkpoint | Panel Stifferners
checkpoint | Additional Top Hat supports between steel out riggers
checkpoint | Insulation Sarking
checkpoint | Screw Fixings
section | Installation:
checkpoint | Mondcload Panels installed
checkpoint | Panel Stifferners installed using approved Struc. Silicone
checkpoint | Additional Top Hat supports installed as per Engineers requirements
checkpoint | Screw Fixings installed as per Engineers requirements
checkpoint | Insulation Sarking installed and taped where cut
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: