## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Roof Installation |  |  |  |  | Yes | Wet Bar Roof Zone 1 - Roof Installation | 0710e234-ef99-4a03-8544-847b42a3a0f8
checkpoint-group |  |  | section | Material Inspection:
checkpoint-status |  |  | checkpoint | Roof Panels - Kingspan 120mm PIR Insulated Panel KS1000RW
checkpoint-status |  |  | checkpoint | Coating Type - External Colorbond Surfmist
checkpoint-status |  |  | checkpoint | Coating Type - Internal AquaSafe 25 Hampton White
checkpoint-status |  |  | checkpoint | Roof Screws: Polyplas 192mm Surfmist
checkpoint-group |  |  | section | Installation:
checkpoint-status |  |  | checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint-status |  |  | checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint-status |  |  | checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint-status |  |  | checkpoint | Roof sheet turned up at high end of roof
checkpoint-status |  |  | checkpoint | Roof sheet turned down at gutter end of roof
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 613b7b06-3fd4-555c-9c30-3ac97fdda869 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | cd17850c-d5ec-5de0-8a50-d63ad92274b4 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 2f75bb59-ff2a-5eb4-891d-3644f6dcde78 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | f26a78f6-0914-5976-a187-7e2db62df1e5 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 9571c668-9494-51d5-b638-cc9fc9a1b0d1 |  | textbox | Client Representative:
checklist-flat |  |  | checklist | Tool Box Training |  |  |  |  | Yes | Tool Box Training | 0c4d82bb-9ace-492c-bdd4-94efddecce03
checkpoint-status |  |  | checkpoint | All Tool Box Training Details Complete
text | e8e318fa-6f35-41ed-9c22-d9f0a455ffd8 |  | textbox | Foreman:
text | 58b31bb6-2e96-4f47-aac0-12bfc1518caa |  | textbox | Any OH&S Issues
text | d2720022-ca57-4b1c-af55-ffe2c20a5bfb |  | textbox | Action to be taken
text | 095eb063-2524-4c0c-a9aa-474dbc1a21ee |  | textbox | Suggestions:
text | e46de2dd-e8a8-4cb4-ad81-bfc96b89d97a |  | textbox | Please list all present at your toolbox training session:
text | c63e9a4a-9a78-4d9d-8f3d-be8e2242432d |  | textbox
text | ac0c84cb-98e1-40e7-afbf-393615ef582b |  | textbox
text | 0a7cadc7-362a-4743-9601-258821c71a92 |  | textbox
text | a6d73b42-8fa4-4c59-a3da-ed86f0544882 |  | textbox
text | 1fe233bd-4d90-45d9-b355-2c529a29e3d5 |  | textbox
text | 07b4fe0b-4b5f-4c44-8d85-a3c03cc08466 |  | textbox
text | 41952e8b-c2cb-4ccd-952e-6aca13805eb5 |  | textbox
text | 791a048f-b448-4de1-a3a6-7d74897db20a |  | textbox
text | bccffe50-064a-4057-8447-19bb830d3e7e |  | textbox
text | ad7714dc-d79d-4858-891a-4f1c7554207a |  | textbox
text | 0e5a6828-e97e-4c96-a181-1af5f75c871e |  | textbox
text | 7c0ce756-5407-4f09-8d90-5ff91cf0f383 |  | textbox
text | 706dce3d-7edb-44ac-a9e6-65e40690ffa7 |  | textbox
text | 8b0011af-ce1f-47cf-9116-9c6abc684a94 |  | textbox
text | 86727571-83a8-4ae9-8b0b-224ff82ea981 |  | textbox
label | 494f52fc-2fef-41fd-a2ae-47845a1f5444 |  | note | Add additional attendees in comments below as required
checklist-sectioned |  |  | checklist | Flashing/Capping Installation Checklist |  |  |  |  | Yes | Wet Bar Roof Zone 1 - Flashing/Capping Installation Checklist | 10f04952-9306-4c11-805c-8cec6276a3a4
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Parapet Capping Material 2mm Aluminium
checkpoint-status |  |  | checkpoint | Ridge Capping Material 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Apron Flashing Material 0.61mm Colorbond
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint-status |  |  | checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint-status |  |  | checkpoint | Adequate lap at joins.
checkpoint-status |  |  | checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint-status |  |  | checkpoint | Rivets and fixings sealed where necessary
checkpoint-status |  |  | checkpoint | Adequate support to prevent buckling.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 180ff08d-72d9-57ac-b46c-9cd251fdd0c7 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 5d98d045-f7b2-565f-b127-d51259540247 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 8bda6398-1683-5f86-a9d0-b2f452886c2c |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 9d4b5811-8543-5594-bd09-0a6b17a64798 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | d0655216-fd12-5612-be83-ad24dd0514fb |  | textbox | Client Representative:
checklist-sectioned |  |  | checklist | Box Gutter Installation |  |  |  |  | Yes | Wet Bar Roof Zone 1 - Box Gutter Installation | 1c0f21d1-9455-4f86-8dfd-6017c5151944
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Box Gutter Brackets:
checkpoint-status |  |  | checkpoint | Wrap under gutter: Innova Vinyl Wrap
checkpoint-status |  |  | checkpoint | Gutter Board: Spandek Zincalume
checkpoint-status |  |  | checkpoint | Insulation under gutter: 60mm Kingspan Kooltherm Insulation
checkpoint-status |  |  | checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Gutter Flashing: Colorbond to match
checkpoint-status |  |  | checkpoint | Sumps / Outlets: 0.61mm Colorbond / Syfon
checkpoint-status |  |  | checkpoint | Overflows:
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint-status |  |  | checkpoint | Insulation installed under gutter board
checkpoint-status |  |  | checkpoint | Gutter Board installed
checkpoint-status |  |  | checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint-status |  |  | checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint-status |  |  | checkpoint | Outlets installed to correct sizes.
checkpoint-status |  |  | checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint-status |  |  | checkpoint | Gutter flashing installed.
checkpoint-status |  |  | checkpoint | Area clean and free of debris.
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 1d0c3187-4c99-5e5f-bd6c-8c4e84859840 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | f80a7703-170b-5c89-80ed-752e6879905b |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 9619b037-0be8-5fb6-ac61-4680f8ee9147 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 3d1987b6-656b-5e8f-ab58-fb4b92431dd2 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 11c26746-4520-5332-9d93-8d08e0302846 |  | textbox | Client Representative:
checklist-sectioned |  |  | checklist | Roof Installation |  |  |  |  | Yes | Canopy Roofs - Roof Installation | 1ee9df0c-4c8b-4fb8-ac96-0ec8725d68a7
checkpoint-group |  |  | section | Material Inspection:
checkpoint-status |  |  | checkpoint | Roof Sheets: 0.48mm Kliplok
checkpoint-status |  |  | checkpoint | Coating Type: Standard Colorbond
checkpoint-status |  |  | checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint-status |  |  | checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint-status |  |  | checkpoint | Roof Clip: Galavanised
checkpoint-status |  |  | checkpoint | Roof Screws: 35mm Kliplok screws
checkpoint-group |  |  | section | Installation:
checkpoint-status |  |  | checkpoint | Safety Mesh Installed
checkpoint-status |  |  | checkpoint | Insulation installed
checkpoint-status |  |  | checkpoint | Roof clips installed
checkpoint-status |  |  | checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint-status |  |  | checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint-status |  |  | checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint-status |  |  | checkpoint | Roof sheet turned up at high end of roof
checkpoint-status |  |  | checkpoint | Roof sheet turned down at gutter end of roof
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | c7c4c92e-d66f-52ae-8e0f-7d955863a81e |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | a3242721-440a-591c-9a9d-55993f275b00 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 16efd4c5-e029-5dff-a5c5-6e78940cef42 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 51c4c85c-131a-5991-9bb4-18f7863d3320 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | a41783e5-6d64-5c98-bca3-e95718231835 |  | textbox | Client Representative:
checklist-sectioned |  |  | checklist | Roof Penetrations |  |  |  |  | Yes | Wet Bar Roof Zone 2 - Roof Penetrations | 1f16a80a-a840-497e-9fcf-734ff04b4381
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint-status |  |  | checkpoint | Roof sheets whethered correctly
checkpoint-status |  |  | checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint-status |  |  | checkpoint | Adequate support under soaker to prevent ponding.
checkpoint-status |  |  | checkpoint | Side and front aprons / upstands formed to correct size
checkpoint-status |  |  | checkpoint | to fit the purpose.
checkpoint-status |  |  | checkpoint | Adequate support around penetration to prevent roof
checkpoint-status |  |  | checkpoint | sheet from buckling.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 4263a597-2bc3-5e21-86ae-027d9c8ac281 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | a2f3c29c-a320-544b-a1e1-f973de7f0354 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 5474a02e-edec-5e5b-a695-d820479b56c2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 610db6df-ea4e-5272-ad44-40dc706642cf |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 4a6546a5-b19b-5af6-a4a7-ab44fe243bc4 |  | textbox | Client Representative:
checklist-flat |  |  | checklist | Guardrail Installation Handover |  |  |  |  | Yes | Guardrail Installation Handover | 2afc46cc-3f5e-4dca-8293-fec2f9e82ac2
checkpoint-status |  |  | checkpoint | Roof Edge Protection - Completion of Installation
text | 20d02478-c146-5f6f-a607-8432f0deb247 |  | textbox | Issue Date:
text | ce8b1f9b-32dd-5681-a27f-753d0751e324 |  | textbox | Inspection Date:
text | ad321e21-70f1-5761-b104-5839ab05e345 |  | textbox | No:
text | 390709a9-e4c0-5bdd-8711-cd7b9e781c77 |  | textbox | Time:
label | a575e133-1bc9-5db0-b7d0-913a4146ed0c |  | note | Person or organization requiring the roof edge protection
text | 67425ed7-eae9-5b64-9c68-38de6b3b9497 |  | textbox | Name:
text | b938f532-f2da-5571-a496-c84afee9c73a |  | textbox | Address:
text | 3e164a43-c5ed-5763-9a56-0af116e77c76 |  | textbox | Site Address:
text | b0302ab0-875a-5c9f-bd56-9c8ab8d7d3cd |  | textbox | Location on Site:
text | 7ed958cd-10cb-5089-819f-b95c05b1d969 |  | textbox | Installer organization name:
text | 2b786667-0ca3-507f-a67b-20c5b8ed329c |  | textbox | Phone No:
text | 3b3ad6e4-b695-5663-8a9d-b3d2e1d7e9fa |  | textbox | Address:
select | aa31b952-9bfe-5f15-96c6-51ee4b46367e |  | dropdown | Type of Roof Edge: | Prefabricated proprietary system, Scaffolding
text | 8f224929-84cb-5e35-9e19-13382817c33c |  | textbox | Name of system:
text | a5515089-3e7e-5609-bbf0-11e7fbaff90f |  | textbox | Type of scaffolding:
text | c09f1276-78a8-5146-9044-d977aa530a76 |  | textbox | Name of person in charge of installation:
label | 7e91e1d3-c3c0-5ee2-a429-e78641ad0e2c |  | note | Installer's Statement: All Relevant inspections and checks have been carried out prior to the issue of this Certificate.
text | 1d3d4b77-c34d-5ba0-8edf-2de27cda5ad6 |  | textbox | Certified issued on behalf of:
text | e1cf49ef-971a-5232-883f-7533c06cc62a |  | textbox | By: (Print Name)
text | fd0aee22-04ce-50e3-94b7-4e737a2d46f5 |  | textbox | Certified Received on behalf of:
text | 25cad1af-bfc7-5884-927c-cb646ed15204 |  | textbox | By: (Print Name)
checklist-sectioned |  |  | checklist | Flashing/Capping Installation Checklist |  |  |  |  | Yes | Wet Bar Roof Zone 2 - Flashing/Capping Installation Checklist | 2e1555e7-d953-4bf7-b895-8aa77edf68a3
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Parapet Capping Material 2mm Aluminium
checkpoint-status |  |  | checkpoint | Ridge Capping Material 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Apron Flashing Material 0.61mm Colorbond
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint-status |  |  | checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint-status |  |  | checkpoint | Adequate lap at joins.
checkpoint-status |  |  | checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint-status |  |  | checkpoint | Rivets and fixings sealed where necessary
checkpoint-status |  |  | checkpoint | Adequate support to prevent buckling.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 9b9bc6bf-02bc-5b9f-8379-a9a94b254d09 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 12e44ca0-28fe-5c85-a318-a090a9c36cd0 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | b373c1d4-452e-5210-8bc0-088877e68538 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 4c93db9d-c608-5630-9094-f50b0933a833 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 0da7bf47-48c0-5afd-bac6-55a8f8b6a564 |  | textbox | Client Representative:
checklist-sectioned |  |  | checklist | Roof Installation |  |  |  |  | Yes | Wet Bar Roof Zone 2 - Roof Installation | 33a74965-fe23-4282-b449-6c7051858f44
checkpoint-group |  |  | section | Material Inspection:
checkpoint-status |  |  | checkpoint | Roof Panels - Kingspan 120mm PIR Insulated Panel KS1000RW
checkpoint-status |  |  | checkpoint | Coating Type - External Colorbond Surfmist
checkpoint-status |  |  | checkpoint | Coating Type - Internal AquaSafe 25 Hampton White
checkpoint-status |  |  | checkpoint | Roof Screws: Polyplas 192mm Surfmist
checkpoint-group |  |  | section | Installation:
checkpoint-status |  |  | checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint-status |  |  | checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint-status |  |  | checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint-status |  |  | checkpoint | Roof sheet turned up at high end of roof
checkpoint-status |  |  | checkpoint | Roof sheet turned down at gutter end of roof
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | db60f76c-4305-585a-bb7f-be5ce0c8229e |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 956b8e01-e4a0-5001-ae15-5ad289f85ac6 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | b12935e2-4869-505d-ba82-471453a08c5e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | ecc0a052-27c2-50eb-ae95-6e433cb6cfa6 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | c9f43e51-c496-5fb2-af1f-c25879690e7b |  | textbox | Client Representative:
checklist-flat |  |  | checklist | Offhire Information - |  |  |  |  | Yes | Add Offhire Information | 3c0ec7bb-f018-4c3e-86a9-d84bc4a319b2
checkpoint-status |  |  | checkpoint | All Offhire Information Completed
text | 330033de-1c50-4efc-a10b-db97a835a5b8 |  | textbox | Site:
text | 462b668d-9de8-4db4-811b-39c30587a6e1 |  | textbox | P.O Number:
text | 56c7957b-2d97-48e4-b194-519c76e50e30 |  | textbox | Offhire No.:
text | dc214165-5ced-42fe-8908-ce7b1d2a22c1 |  | textbox | Offhire Date:
text | 63574846-26e3-4cd0-8738-7b9b6fb77572 |  | textbox | Hire Company:
text | 62ee9fef-5892-4ad2-94d7-eb99af6bb771 |  | textbox | Plant/Materials:
text | ae5f3250-30cf-4248-bc0a-50dca8ffd050 |  | textbox | Full/Part Offhire:
text | f020cf20-b785-4e61-af30-90f1dd3e9c2d |  | textbox | Missing Parts:
text | 4416fe74-7eb2-4205-b82b-872b928ff92a |  | textbox | Damage:
checklist-sectioned |  |  | checklist | Box Gutter Installation |  |  |  |  | Yes | Wet Bar Roof Zone 2 - Box Gutter Installation | 3c903d23-d627-4bca-bd49-539dc08124e6
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Box Gutter Brackets:
checkpoint-status |  |  | checkpoint | Wrap under gutter: Innova Vinyl Wrap
checkpoint-status |  |  | checkpoint | Gutter Board: Spandek Zincalume
checkpoint-status |  |  | checkpoint | Insulation under gutter: 60mm Kingspan Kooltherm Insulation
checkpoint-status |  |  | checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Gutter Flashing: Colorbond to match
checkpoint-status |  |  | checkpoint | Sumps / Outlets: 0.61mm Colorbond / Syfon
checkpoint-status |  |  | checkpoint | Overflows:
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint-status |  |  | checkpoint | Insulation installed under gutter board
checkpoint-status |  |  | checkpoint | Gutter Board installed
checkpoint-status |  |  | checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint-status |  |  | checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint-status |  |  | checkpoint | Outlets installed to correct sizes.
checkpoint-status |  |  | checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint-status |  |  | checkpoint | Gutter flashing installed.
checkpoint-status |  |  | checkpoint | Area clean and free of debris.
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 0e111c33-00cb-58f2-b89f-913c79be3c90 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 0423ece3-fc64-5016-aa39-ce755b3835af |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 3cb06340-2a0e-5fdd-9b1b-cd28d1d571d7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 8655f88a-1447-5d95-bcab-c47a46ceb36c |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 031545cb-0a2d-5f81-9bd2-57c9c58ecbd1 |  | textbox | Client Representative:
checklist-sectioned |  |  | checklist | Roof Penetrations |  |  |  |  | Yes | Wet Bar Roof Zone 1 - Roof Penetrations | 45d70f3f-f525-43a6-9721-f09db80dc123
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint-status |  |  | checkpoint | Roof sheets whethered correctly
checkpoint-status |  |  | checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint-status |  |  | checkpoint | Adequate support under soaker to prevent ponding.
checkpoint-status |  |  | checkpoint | Side and front aprons / upstands formed to correct size
checkpoint-status |  |  | checkpoint | to fit the purpose.
checkpoint-status |  |  | checkpoint | Adequate support around penetration to prevent roof
checkpoint-status |  |  | checkpoint | sheet from buckling.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 13161352-92fb-5b90-8c30-12412e5e8e92 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | f63251b2-27d2-5663-82a6-4c9164c57623 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 7eb21fc1-5e13-5616-bbb6-bf87ef8ad035 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 6aaa26f8-c2f2-5a0d-98da-1b215c00ddaa |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | e13572c5-a26b-5d58-b18d-a11bc5eaa163 |  | textbox | Client Representative:
checklist-flat |  |  | checklist | Onsite Material Install Form |  |  |  |  | Yes | Onsite Material Install Form | 47033a2c-7bc1-4725-b05a-c9badaa9ca09
checkpoint-status |  |  | checkpoint | Onsite Material Install Details Completed
text | 2c2bcf36-a746-43d2-8b5b-e2e5fea57742 |  | textbox | Job:
text | 1a84e8de-902d-48d2-a367-caf649b2ec54 |  | textbox | Area:
text | 20ce8b4f-10a0-45ec-a6ce-e6e40a55ffd8 |  | textbox | Details of Works Completed:
text | 710a4748-dda0-45b0-87db-ddbd77da62e1 |  | textbox | Actual Onsite Hours:
text | b14a32aa-f134-49f8-af30-f61169e5eef3 |  | textbox | Allowed or Budgeted Hours:
text | 65f32f89-6513-47b2-aa0e-c5d80adddcd7 |  | textbox | Comments:
checklist-sectioned |  |  | checklist | Roof Penetrations |  |  |  |  | Yes | Dry Bar Roof Zone 3 - Roof Penetrations | 4f999414-abdc-45de-9edf-8b6dc4ac4ad6
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint-status |  |  | checkpoint | Roof sheets whethered correctly
checkpoint-status |  |  | checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint-status |  |  | checkpoint | Adequate support under soaker to prevent ponding.
checkpoint-status |  |  | checkpoint | Side and front aprons / upstands formed to correct size
checkpoint-status |  |  | checkpoint | to fit the purpose.
checkpoint-status |  |  | checkpoint | Adequate support around penetration to prevent roof
checkpoint-status |  |  | checkpoint | sheet from buckling.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 6bbfea2a-3018-569e-9a48-f9b813aea958 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 0ebacfdf-0ce6-57ef-858c-a4cd1ef85abc |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | cbbfb1c3-dfe1-5183-9e47-bfe1764b9dec |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | db90bfc5-80c7-5f7a-88de-ae470d73ed40 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | e24a1b2f-7174-5294-ab33-3a4cc20c847f |  | textbox | Client Representative:
checklist-flat |  |  | checklist | Foremans Diary: |  |  |  |  | Yes | Foremans Diary Checklist | 4fdd496a-845c-47de-9753-1b9b9f2354a0
checkpoint-status |  |  | checkpoint | Foremans diary - all details inputted and complete
text | ed18edcc-2d41-4d63-abb7-1f36ffd96100 |  | textbox | Date:
text | 421fc326-e45e-4e08-b3e9-a48158ae5a20 |  | textbox | Tasks completed productivity feedback: (inc hours worked ordinary time & overtime):
text | f03606e7-7dbe-4a74-a74a-d47a09539e7b |  | textbox | OHS - include comments on accidents and incidents:
text | 1f503e89-3ac9-4e97-aa1a-7452091d1b50 |  | textbox | Quality achievement / issues:
text | 596b84cb-73d0-48eb-ba57-3808666f53ed |  | textbox | Supplier issues:
text | a25d72a2-2d4e-4e06-8c27-ed5f4cb7e51d |  | textbox | No. employees on site:
text | 6165be78-ebb6-4db0-a6f6-d6ba454c3ed4 |  | textbox | No. employee sick / leave:
text | 23af5346-7d8f-423c-a0d4-da060219893c |  | textbox | NCR’s:
text | 5d5a89bc-ccae-4794-93c1-5f6111f1c87c |  | textbox | Hours worked:
text | 7720e2c0-8535-4a3a-b295-dfdbf8892fd5 |  | textbox | Lost time:
text | c5161262-e836-4b6a-adbc-5aa557524b95 |  | textbox | Machinery on hire:
text | 5454a11a-bf58-403b-a4fc-ee4da02a398b |  | textbox | List employees on site:
text | 9c3c4e88-0ab6-4dbf-a289-847a05f9950d |  | textbox | Other:
checklist-flat |  |  | checklist | Variation Contract - |  |  |  |  | Yes | Variation Contract | 52b14531-d459-429c-971f-ef95a1636a19
checkpoint-no-status |  |  | checkpoint | Job Details
text | 5c290ca9-4d15-4085-b8b3-2b580164dc79 |  | textbox | Details of Work (Inc. Location)
text | 736ff74e-eca9-4444-8673-73757bb18e82 |  | textbox | Client:
text | 369c090a-bd1d-49c2-b010-fe3c00fe171a |  | textbox | Project:
text | c87fbe21-d754-4549-ad19-590ce0623821 |  | textbox | Reason for Variation:
text | 1285206f-35b3-414c-89ee-5f2e6353ba0b |  | textbox | Job No:
text | 22c65faf-be1e-4e04-bc86-ced8fe2d2639 |  | textbox | Hours:
text | ebe45398-57be-4bb9-b093-7a4b3db5a73f |  | textbox | Materials Equipment:
text | ab8745e6-1157-4a3c-b0ee-552b7e3a968d |  | textbox | Site Instruction No:
text | 5de6bc0f-0975-4707-996a-8cf1d8e32659 |  | textbox | Agreed Value:
checkpoint-status |  |  | checkpoint | Foreman Sign Off
text | c65d0a84-1d5d-4cd0-a8ba-5861a75214ea |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Project Manager Sign Off
text | 0e07a75b-cd35-4599-a063-de55afbb5ade |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Signature of Authorising Officer
text | 2cb2c7c5-ff73-4847-b7a0-9ec1caa52992 |  | textbox | Name:
checklist-flat |  |  | checklist | Handrail Inspection Report |  |  |  |  | Yes | Handrail Inspection Report | 590bb197-e2e5-4c8f-ae47-d7b575aa50ff
checkpoint-status |  |  | checkpoint | Handrail Inspection Report Complete
text | a1ff4c47-7f23-464e-8f63-228fc612fd0d |  | textbox | Supervisor:
text | e5a5b6a8-cd3c-4601-99fb-741f1f4bd9bc |  | textbox | Foreman:
text | 6c98c32b-8ffa-4741-9a3b-65f6d75b5c84 |  | textbox | Builder:
text | 3aeb70c9-7cac-4056-b694-01ffc226a407 |  | textbox | Inspection by:
text | 9bb10822-8b95-485e-8a4e-60b71fd46b2a |  | textbox | Inspection date:
label | 1876d81b-1d99-4fb0-8a27-9b8a6d7d8091 |  | note | Report to be completed and compliance achieved for all areas of roof with temporary handrail works.
label | b758c6c6-5433-4b56-b10b-5b21a5c0bc46 |  | note | Report to be conducted by a person Authorised, experienced and deemed competent by the Company HSE.
checkpoint-status |  |  | checkpoint | Bolt plate fixings
checkpoint-status |  |  | checkpoint | Rail joiners tight
checkpoint-status |  |  | checkpoint | Rail spacings not over 450mm
checkpoint-status |  |  | checkpoint | Top rail height 900mm -1100mm
checkpoint-status |  |  | checkpoint | Toe board infills if required
checkpoint-status |  |  | checkpoint | Deck clamp installations
checkpoint-status |  |  | checkpoint | Third rail not to exceed 250mm from building
checkpoint-status |  |  | checkpoint | Corner Joins / chain corners tight
checkpoint-status |  |  | checkpoint | V clamps correctly engaged with purlin toe
checkpoint-status |  |  | checkpoint | G clamps correctly engaged with purlin toe
checkpoint-status |  |  | checkpoint | Post distance from corners not exceeding 1mtr
checkpoint-status |  |  | checkpoint | Post spacings not to exceed 3mtr
checkpoint-status |  |  | checkpoint | Panel clamp installations
checkpoint-status |  |  | checkpoint | Support bar installations
checkpoint-status |  |  | checkpoint | Top posts / T posts wing bolts tight
checkpoint-status |  |  | checkpoint | Tele Extensions tight where required
checkpoint-status |  |  | checkpoint | Rail lapping 100mm min lap
checkpoint-status |  |  | checkpoint | Installation Compliance
checklist-sectioned |  |  | checklist | Flashing/Capping Installation Checklist |  |  |  |  | Yes | Dry Bar Roof Zone 3 - Flashing/Capping Installation Checklist | 647c4b77-7a1b-4f9b-bf9b-81f623021d1a
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Parapet Capping Material 2mm Aluminium
checkpoint-status |  |  | checkpoint | Ridge Capping Material 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Apron Flashing Material 0.61mm Colorbond
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint-status |  |  | checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint-status |  |  | checkpoint | Adequate lap at joins.
checkpoint-status |  |  | checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint-status |  |  | checkpoint | Rivets and fixings sealed where necessary
checkpoint-status |  |  | checkpoint | Adequate support to prevent buckling.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | e9c13769-a6ff-5a66-8b49-26e7b567afb5 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 0c98dc62-dc0e-59f6-bf23-f7c6d8f04d05 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | fa35681e-2ef7-5d97-b189-422b228abfab |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | b96552f6-a09a-5e0a-83aa-008d5ea7ff36 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 0626afc3-43ad-5c79-95cd-f5fff7a72458 |  | textbox | Client Representative:
checklist-flat |  |  | checklist | Non Conformance Corrective Action Report - |  |  |  |  | Yes | Add Non Conformance Corrective Action Report | 89c288e3-c10f-4ad2-85aa-1913eeb00fbc
checkpoint-no-status |  |  | checkpoint | Report
text | 3daf672a-729f-4b84-a93b-ff3001cc374b |  | textbox | Report Reference:
text | 800a3bfb-7c7e-432a-99b4-a6721a62a3c8 |  | textbox | Customer Name:
text | 18c2d608-07f2-4a98-ae5f-2834630b914c |  | textbox | Job Number:
text | ed82e4fd-2b87-48b1-88ab-adedb3511af1 |  | textbox | Purchase Order Number:
text | 5aaa33dc-cca0-40aa-82aa-0c8fc595dd9c |  | textbox | Delivery Docket No:
label | 6c88a8b1-6942-4f28-95c4-c6fff3d81118 |  | note | Part
text | a2727390-f900-4b68-9fa9-a5c853540579 |  | textbox | Part Description:
text | c361e607-c5c0-4d35-ac3b-849db32ca4c3 |  | textbox | Part Identification:
label | 95e0e9b2-febc-4e76-ba9d-fbb15fe7d70d |  | note | Non-Compliance
text | b85f5b83-94c1-4b1e-850f-059de0f76d94 |  | textbox | Non-compliance description:
label | c68286d4-fa47-406d-9034-69bf7f7ac97e |  | note | Cause
label | 2567eea0-7dae-4b32-8a96-c18a6cbd2d04 |  | note | Root cause description of the non-compliance:
boolean | 99d5feec-48d5-4ba9-9a00-4d1b5eb5d94f |  | tickbox | Technical Detail
boolean | 36dc5d31-0e93-4aeb-8306-28233639439c |  | tickbox | Production
boolean | 99468aaf-b994-4d31-a3f3-18d15adcb9d4 |  | tickbox | OH&S
boolean | 476c9404-d065-4068-89a9-6c3606242a0a |  | tickbox | Delivery
boolean | 40cd96bc-b14a-41d1-94ab-d36f3ef45319 |  | tickbox | Client Side (Handling/Application)
label | 1dba7939-e418-42c1-aa66-a6a1cc308453 |  | note | Corrective Action
label | 2523c058-4b18-46dc-a1ed-6c806c3af2ae |  | note | Action taken to correct the immediate non-compliance:
label | aad460b2-f1bc-4041-bbde-8e544fa70b6f |  | note | Quality Assurance
boolean | 0c473128-c58b-42d7-a2b0-44fa45e1ba15 |  | tickbox | Rework
boolean | cebcaedd-df59-4ea6-8347-ca9aeb0d441c |  | tickbox | Accepted Under Concession
boolean | cf7b9dec-d9f9-49ad-a6f0-9f7c1cc69c9e |  | tickbox | Replace
boolean | 9a968a92-3245-45ef-b941-48e00d475b5f |  | tickbox | No Action Required
label | 4f3af710-02ce-479d-a400-6163b3617a26 |  | note | OH&S
boolean | 2cdebde5-c434-40cb-bcfd-2375b90e9043 |  | tickbox | Re-Induction
boolean | eb2003e9-2c87-4716-81db-1d1baf2457d7 |  | tickbox | Warning
boolean | 1e2c8d11-d4a4-4602-8f77-3899ca1f307a |  | tickbox | Rectification
boolean | 7423e8d2-c792-4212-a90f-9711e1730549 |  | tickbox | SWMS Review
label | 745657d7-d973-416e-9e82-e4c8d15bc907 |  | note | Preventative Action
text | 8165ef6d-208c-4f61-b7fa-68a4c7eb4930 |  | textbox | Action neccessary to eliminate the root cause of the non-compliance:
label | 17d2c482-3213-49bc-a70b-92f89d5e6a8c |  | note | Verification
text | 3ad3dee8-216f-48d1-aed3-884aa139727b |  | textbox | Verify the corrective and preventative action taken is adequate and effective:
text | f2624c64-9bd2-4df8-9e08-0a5040be24b8 |  | textbox | Manager's Name:
label | 3e4b9a15-d7ac-48cc-b18a-aaeab7b4fa16 |  | note | Customer Validation
text | 88466d1f-d4fe-47e1-88b8-272448e9369c |  | textbox | Validate the corrective and preventative action is adequate and effective:
text | cea878da-18e3-415c-babc-b3202708b4d2 |  | textbox | Representative Name:
checklist-sectioned |  |  | checklist | Roof Installation |  |  |  |  | Yes | Dry Bar Roof Zone 3 - Roof Installation | 9014a95d-4806-4857-ae2c-889464c9b244
checkpoint-group |  |  | section | Material Inspection:
checkpoint-status |  |  | checkpoint | Roof Panels - Kingspan 120mm PIR Insulated Panel KS1000RW
checkpoint-status |  |  | checkpoint | Coating Type - External Colorbond Surfmist
checkpoint-status |  |  | checkpoint | Coating Type - Internal CLEANsafe 15 White Poly
checkpoint-status |  |  | checkpoint | Roof Screws: Polyplas 192mm Surfmist
checkpoint-group |  |  | section | Installation:
checkpoint-status |  |  | checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint-status |  |  | checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint-status |  |  | checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint-status |  |  | checkpoint | Roof sheet turned up at high end of roof
checkpoint-status |  |  | checkpoint | Roof sheet turned down at gutter end of roof
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 8c256cb4-be79-515a-914b-8c7acaa4b20e |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 4bef58a0-dd0f-5593-a29a-148706ce84a0 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | a5a9fcc2-a557-5577-bb9e-a8777b28aef4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | f7af25d2-111e-5313-8c55-eb99caba8aa5 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 78e0be80-e6d0-53ca-95c8-0ef1597d7006 |  | textbox | Client Representative:
checklist-flat |  |  | checklist | JSA - Risk Analysis |  |  |  |  | Yes | JSA Risk Analysis Checklist | 94d05ae1-07b1-47f6-9619-369ac8f991a9
checkpoint-status |  |  | checkpoint | Risk Assessment Details Completed
text | 1451b2b0-6306-4d4e-bac2-9eac9206593c |  | textbox | Assessment conducted by:
label | cf099dfb-4c17-464d-b96b-0bfb40253dfa |  | note | Risk 1
text | 4ca35694-04a7-44ad-a6fb-13106c4bcd45 |  | textbox | Hazard Identification:
text | 099eb477-a6df-4834-b17d-46f5b331b19d |  | textbox | Risk:
text | 430a0dfc-585c-4204-914c-36d81265f276 |  | textbox | Control Method - Safe Work Procedures:
text | 39458537-3056-44c8-885d-d6d33e4d4cbb |  | textbox | Residual Risk:
text | 5a6b50bc-cbb5-45e7-b624-cdaec29ff4ec |  | textbox | Date:
label | bd503c98-318c-47dc-9fbb-d9e7571ae1c8 |  | note | Risk 2
text | 704919be-45db-4a8e-8589-a6d2aeef93cf |  | textbox | Hazard Identification:
text | 0d84ecc7-d700-4585-8717-9704ce8efb43 |  | textbox | Risk:
text | e811a527-5af4-4eed-81b6-8b7e631415d8 |  | textbox | Control Method - Safe Work Procedures:
text | cf298119-f9c0-4dab-8087-fa6a906687c8 |  | textbox | Residual Risk:
text | 146293b7-ea65-47c3-a1fd-3fa53e2311cb |  | textbox | Date:
label | 89f1c99c-b591-4fe1-8c1c-b045e134f51f |  | note | Risk 3
text | 34ddb306-be39-47b3-afc2-6ce0056d2bab |  | textbox | Hazard Identification:
text | bd6df791-a0e0-4f61-aae0-f9b062ba7eb3 |  | textbox | Risk:
text | 1e69daed-4297-4d09-8809-dedfc3f05b72 |  | textbox | Control Method - Safe Work Procedures:
text | 6e11d988-e07c-4cfe-81ad-41a317f84128 |  | textbox | Residual Risk:
text | 05a34b3f-1913-46d2-91ad-820973cb4ca0 |  | textbox | Date:
label | 4d8d0c3f-616c-4b85-b863-f5b43bfe5b66 |  | note | Risk 4
text | cd2e959a-b3f0-4737-99fb-ba8a096f4f37 |  | textbox | Hazard Identification:
text | d7d69b39-fbd8-4d53-a4b8-cba8e8d94ad9 |  | textbox | Risk:
text | 1408e8d4-750c-466f-b581-79992b3ee48f |  | textbox | Control Method - Safe Work Procedures:
text | d837dc22-0dc0-40cc-8176-32d22783ec7e |  | textbox | Residual Risk:
text | 86f855e5-5996-454e-9acb-a6981f18f80f |  | textbox | Date:
label | 0981f4da-32da-41ed-beb5-adbb8d92caab |  | note | Risk 5
text | d4ab69a3-6d20-463b-aba7-2c329ef2cd5d |  | textbox | Hazard Identification:
text | b380995f-baaa-48f2-ac1e-8428dae99131 |  | textbox | Risk:
text | 89362617-21f8-4257-9b72-343dd21c3241 |  | textbox | Control Method - Safe Work Procedures:
text | f74bbb5f-acc6-41d9-8568-76ce297ffa7f |  | textbox | Residual Risk:
text | 2553ed9e-de0e-4e43-8db7-9499f57b4a44 |  | textbox | Date:
label | 3a083378-9de5-4c4e-8bcb-5074654b0b8d |  | note | Risk 6
text | 006e22d3-96cf-45be-b9fd-0a7052444e94 |  | textbox | Hazard Identification:
text | 3da8bbe6-a445-4b72-9c8e-2defb13b95da |  | textbox | Risk:
text | 168c5ebf-7e0f-4f05-a977-99877be3f9d3 |  | textbox | Control Method - Safe Work Procedures:
text | 688eec1b-bafa-4431-9a42-3acb98c1b200 |  | textbox | Residual Risk:
text | 3e252311-c7f6-45e4-9311-e7b7f6b63f02 |  | textbox | Date:
label | a5388e5a-4838-43c0-bcbd-80c817bad75a |  | note | Risk 7
text | e869a263-c6d3-483a-95d8-777f02120037 |  | textbox | Hazard Identification:
text | ec67b482-e600-4b19-ba17-95e4b97f2513 |  | textbox | Risk:
text | f4526ead-a149-44f7-9764-a08703dc533f |  | textbox | Control Method - Safe Work Procedures:
text | 8b45186d-e876-4003-8f37-9e27f431db95 |  | textbox | Residual Risk:
text | 5a0e1b7e-53cc-47b8-9209-208c35674f6b |  | textbox | Date:
checklist-sectioned |  |  | checklist | Box Gutter Installation |  |  |  |  | Yes | Dry Bar Roof Zone 3 - Box Gutter Installation | 9aa547f6-2090-4cc4-bc9c-0c8855e8c871
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Box Gutter Brackets:
checkpoint-status |  |  | checkpoint | Wrap under gutter: Innova Vinyl Wrap
checkpoint-status |  |  | checkpoint | Gutter Board: Spandek Zincalume
checkpoint-status |  |  | checkpoint | Insulation under gutter: 60mm Kingspan Kooltherm Insulation
checkpoint-status |  |  | checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Gutter Flashing: Colorbond to match
checkpoint-status |  |  | checkpoint | Sumps / Outlets: 0.61mm Colorbond / Syfon
checkpoint-status |  |  | checkpoint | Overflows:
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint-status |  |  | checkpoint | Insulation installed under gutter board
checkpoint-status |  |  | checkpoint | Gutter Board installed
checkpoint-status |  |  | checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint-status |  |  | checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint-status |  |  | checkpoint | Outlets installed to correct sizes.
checkpoint-status |  |  | checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint-status |  |  | checkpoint | Gutter flashing installed.
checkpoint-status |  |  | checkpoint | Area clean and free of debris.
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | ef6c5ac9-8250-5b0d-b956-9240839b53f2 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 9709ccd6-19a8-5c48-91c5-5492f720183b |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | a8ab5504-9ecc-5a31-b825-82e3852fb79d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 53434337-a457-5a0d-b1ca-a49dfe5b416b |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | ebe5113a-66d2-5a27-91c0-c79718f59de3 |  | textbox | Client Representative:
checklist-sectioned |  |  | checklist | Wall Cladding |  |  |  |  | Yes | Wall Cladding | 9d50a4d5-5497-4502-a4f7-622e76e08038
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Wall Cladding type: 0.48mm Standard Colorbond Spandek
checkpoint-status |  |  | checkpoint | Top hat support: 120mm & 25mm TopHat
checkpoint-status |  |  | checkpoint | Proctorwrap CW-IT
checkpoint-status |  |  | checkpoint | 130mm Glasswool blanket
checkpoint-status |  |  | checkpoint | ProctorGeo SmartVap 120 with Proctor Air barrier (AB) Tape
checkpoint-status |  |  | checkpoint | Wall Flashing Material: Standard Colorbond
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Is primary structure adequate to support cladding or secondary framing?
checkpoint-status |  |  | checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint-status |  |  | checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint-status |  |  | checkpoint | Wall cladding flashed to make watertight.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | f0a92923-0430-5acc-8763-5524ea44ab52 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 29d5ab5d-1bdd-53e5-81d1-f437cfa46fb9 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 704e6fb3-12ca-5802-b970-b17def23dae4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | decd5a38-28bb-5ce8-b809-f8a2d663caf2 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | a52e2702-51c3-5730-997d-29f9714a7ff6 |  | textbox | Client Representative:
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 70472602-eb8c-5224-8ff0-dc2b042c12b3 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 886ae0bc-c8e9-5018-b666-8449df168633 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 52fa7a99-a75a-5bd7-8c51-f43ef4af4a29 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 861d5aa1-b7a2-504b-96cd-c19b56feacb7 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | b118edc0-44ef-55f0-98a1-a45c2feb8084 |  | textbox | Client Representative:
checklist-sectioned |  |  | checklist | Pre-Start Toolbox |  |  |  |  | Yes | Pre-Start Toolbox | a7e47604-c95a-44ca-82c6-c24643ad87aa
checkpoint-group |  |  | section | Pre-Start Toolbox
checkpoint-status |  |  | checkpoint | Pre-Start Toolbox
text | 7118459a-a4e7-40d1-94b1-41e7b0f67939 |  | textbox | Project:
text | f655f6fb-a725-4dec-870b-00e01ee4f7ce |  | textbox | Location:
text | f8497083-d258-4ede-b801-6ab8d72bdd1c |  | textbox | Job No:
text | bb67e4d0-9de1-4038-b702-d1f95b5b4aab |  | textbox | Supervisor:
text | a986014d-ff66-4da8-9b81-1e158e6b9aa9 |  | textbox | Foreman:
text | 16b60dd0-65bc-4629-877d-5e40abf89864 |  | textbox | Builder:
text | 05a3a4fe-6d45-4c70-aae8-f54e8694a96d |  | textbox | CONDUCTED BY:
text | e41673b7-4d5d-4e63-b112-625a88f9ebd9 |  | textbox | TOOLBOX DATE:
holdpoint |  |  | signoff | Attendees - Add Signature here
checkpoint-group |  |  | section | BEFORE STARTING WORK
checkpoint-status |  |  | checkpoint | Have SWMS been read, signed and methodology understood and agreed to.
checkpoint-status |  |  | checkpoint | Has every worker been inducted into site.
checkpoint-status |  |  | checkpoint | Has consultation been conducted about the task to be undertaken
checkpoint-status |  |  | checkpoint | Does everyone have the necessary training and qualification to perform the task
checkpoint-status |  |  | checkpoint | Does everyone have the correct PPE for the task
checkpoint-status |  |  | checkpoint | Have handrail & wire mesh inspections been completed prior to accessing roof.
checkpoint-status |  |  | checkpoint | Is safe access and egress to all areas acceptable to your work group.
checkpoint-status |  |  | checkpoint | Has the apprentice been allocated an experienced tradesman to work with
checkpoint-status |  |  | checkpoint | Will work area impact overhead powerlines or live electrical wiring and are correct permits and SWMS available.
checkpoint-status |  |  | checkpoint | Have manual handling issues been identified and assessed
checkpoint-status |  |  | checkpoint | Are perimeter exclusion zones required and have they been installed
checkpoint-status |  |  | checkpoint | (Working at height tasks) Have live edges/voids/fall hazards been identified and have they been barricaded / excluded
checkpoint-status |  |  | checkpoint | Have plant pre-start inspection checks been completed, have checks been made to ensure ground conditions are safe for plant operation.
checkpoint-status |  |  | checkpoint | Are safety measures in place for working near a suspended loads
checkpoint-status |  |  | checkpoint | Notes
text | 5aa0558c-56d2-43e5-a8af-bb8c0fdfc0d2 |  | textbox | Notes
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | Handover | a9a5a42c-3227-4781-b9a3-a49d3bff0534
checkpoint-status |  |  | checkpoint | Roof edge protection - Completion of installation
text | 2e1a30b7-10d7-5e7d-b829-7ead5b20465e |  | textbox | Issue date
text | 6d2e9829-b2ef-543e-b7d7-1fc264dcfbd4 |  | textbox | No:
text | e0141eba-201b-51db-b22f-f5f6ab07c0d1 |  | textbox | Inspection date
text | a7054f58-3775-5aa6-8a6c-0c04766631f6 |  | textbox | Time am / pm
text | 68dba10e-407a-5f71-b698-34514472610e |  | textbox | Person or organization requiring the roof edge of protection
text | 9a9cca07-0d16-5306-9bc5-be3e0a7583d9 |  | textbox | Name
text | af02c468-98ab-547d-9acb-4f027a6cbb52 |  | textbox | Address
text | 50e2c50e-fd74-529a-a237-a5e0baf3ef17 |  | textbox | Site address
text | 391889fd-c9c7-5a8d-bb85-07dc5ad7c52a |  | textbox | Location on site
text | 21c08d71-6dc1-5055-a50a-d6906ec10d4f |  | textbox | Installer organisation name
text | c5c835fb-ad99-5398-a6ef-98ac94e13034 |  | textbox | Phone no:
text | d70cca91-2de7-500e-838c-9d0d6dbdc71e |  | textbox | Address
select | cc69d80f-a972-5913-abbd-e4e36fa3a42b |  | dropdown | Type of roof edge protection | Prefabricated proprietary system, Scaffolding
text | 7f4fe641-6135-53cf-82a9-6ad47ab20b84 |  | textbox | Name of system
text | 118afa24-afa1-5799-87dd-70c310b5d0f6 |  | textbox | Type of scaffolding
text | fc250b73-7a8d-5583-90d4-84d418e3d577 |  | textbox | Name of person in charge of installation
label | db4a1d82-3a77-5cbd-a5ed-44e1531cd537 |  | note | Installer organisation name: All relevant inspections & checks have been carried out prior to the issue of this Certificate
checkpoint-status |  |  | checkpoint | Certified issued on behalf of:
checkpoint-status |  |  | checkpoint | Certified received on behalf of
checklist-sectioned |  |  | checklist | COVID Contact Tracing Register |  |  |  |  | Yes | COVID Contact Tracing Register | ab9d3675-c0ad-4975-bdc7-2f80fb73c132
checkpoint-group |  |  | section | Monday - Date:
checkpoint-status |  |  | checkpoint | All COVID Contact Tracing Register details inputted below
text | 74f9af61-a1df-5f4c-9763-895d4301e037 |  | textbox | Building:
text | a8f0914d-a43e-5f96-a6ac-2cf0b1a828e7 |  | textbox | Work Area:
text | ffeaa8f3-4e43-50dd-b040-5c0079e7948e |  | textbox | Employee Names:
text | 3c9709e2-641d-5d28-9891-91248a193b2c |  | textbox | Time Frames:
checkpoint-group |  |  | section | Tuesday - Date:
checkpoint-status |  |  | checkpoint | All COVID Contact Tracing Register details inputted below
text | 28d6670c-29f1-5319-a698-be9645ea0dc0 |  | textbox | Building:
text | 8d08c93d-56bb-5ad5-850f-d33971a8dbb0 |  | textbox | Work Area:
text | 7d740f9e-9731-52ac-937c-b13093c3fd6d |  | textbox | Employee Names:
text | 24ecda1e-8738-5120-8ee4-010c56689377 |  | textbox | Time Frames:
checkpoint-group |  |  | section | Wednesday - Date:
checkpoint-status |  |  | checkpoint | All COVID Contact Tracing Register details inputted below
text | 666f9822-caa0-56fa-859c-cfaaecaec8aa |  | textbox | Building:
text | 7e41b0ab-0b90-5487-9666-209f58544770 |  | textbox | Work Area:
text | 9b250395-d71c-548e-9f3a-d6bd243d3c11 |  | textbox | Employee Names:
text | a142f5fa-88b6-5c11-8b73-e0735d6eca51 |  | textbox | Time Frames:
checkpoint-group |  |  | section | Thursday - Date:
checkpoint-status |  |  | checkpoint | All COVID Contact Tracing Register details inputted below
text | 7471a93f-d6d1-5d94-8e9c-3109c7ad80a6 |  | textbox | Building:
text | ea07444b-fdc5-515b-b862-e0df79548ede |  | textbox | Work Area:
text | 6d1db559-162b-5bad-92c4-36064a688836 |  | textbox | Employee Names:
text | a07a4c78-20e4-5f22-bee5-7948e8446f9e |  | textbox | Time Frames:
checkpoint-group |  |  | section | Friday - Date:
checkpoint-status |  |  | checkpoint | All COVID Contact Tracing Register details inputted below
text | f9f0fd8f-603e-5578-b046-a23d5509fac2 |  | textbox | Building:
text | 166848b0-5073-51a9-8ed3-45c7913a26d1 |  | textbox | Work Area:
text | 77e8c8a0-b517-575b-8467-41e6f561661d |  | textbox | Employee Names:
text | ff1067ab-233f-59e0-946f-72afac3b9a07 |  | textbox | Time Frames:
checkpoint-group |  |  | section | Saturday - Date:
checkpoint-status |  |  | checkpoint | All COVID Contact Tracing Register details inputted below
text | 6bc678aa-8687-5c2c-a924-cbf0a019318f |  | textbox | Building:
text | 28dc38f1-0a90-5cd2-b643-a67d615c3437 |  | textbox | Work Area:
text | 7d5a2586-8e95-5bbb-b438-2bb6d8e846f1 |  | textbox | Employee Names:
text | 7797b4ac-da51-5a55-852b-84384a895f20 |  | textbox | Time Frames:
checklist-sectioned |  |  | checklist | Flashing/Capping Installation Checklist |  |  |  |  | Yes | Canopy Roofs - Flashing/Capping Installation Checklist | e311c8e1-e217-4083-8dff-68306bae0fe8
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint-status |  |  | checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint-status |  |  | checkpoint | Adequate lap at joins.
checkpoint-status |  |  | checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint-status |  |  | checkpoint | Rivets and fixings sealed where necessary
checkpoint-status |  |  | checkpoint | Adequate support to prevent buckling.
checkpoint-status |  |  | checkpoint | Area clean and free of debris
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 921e12d8-c377-5de3-b2b8-bfa7a48b445e |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | ce4c06ef-a34e-577a-92df-2ad650ad2825 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | 2bb578ab-2a32-5cf1-9130-c3211c0792d7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 4a6e5d14-59fb-5c18-972b-35e985a09e0f |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 708e27e6-ee16-5b59-b75b-9b0a38689932 |  | textbox | Client Representative:
checklist-flat |  |  | checklist | Wire Mesh Inspection Report |  |  |  |  | Yes | Wire Mesh Inspection Report | e9c0d486-f3aa-4f39-84c2-65288dcf14ea
checkpoint-status |  |  | checkpoint | Wire Mesh Inspection Report Complete
text | 438ef291-c421-4aed-b3a7-0f8a12670f01 |  | textbox | Supervisor:
text | 638e0f1f-8cce-4ff0-bf31-60a50c80b2f5 |  | textbox | Foreman:
text | 753c3083-28ed-4e4f-8e42-2a7417f99efe |  | textbox | Builder:
text | ceeb7932-b27b-4a36-b99c-fe72cb4a3470 |  | textbox | Inspection by:
text | 24976d8f-8aab-441b-8675-33f7f7e96d59 |  | textbox | Inspection date:
label | 1a1c56f4-fa88-4946-ab8f-5d1490b3ef5d |  | note | Report to be completed and compliance achieved for all areas of roof with wire mesh installation.
label | 8664b4d3-61ba-4301-8e45-48c4463d0f7d |  | note | Report to be conducted by a person Authorised, experienced and deemed competent by the Company HSE.
checkpoint-status |  |  | checkpoint | Lapping adjoining wire
checkpoint-status |  |  | checkpoint | Tension
checkpoint-status |  |  | checkpoint | Maximum span purlin check 1.2m
checkpoint-status |  |  | checkpoint | Ring clamps corrected spacing ( If required)
checkpoint-status |  |  | checkpoint | Mesh material compliance AS/NZS4389
checkpoint-status |  |  | checkpoint | Parallel longitudinal alignment
checkpoint-status |  |  | checkpoint | Transverse wires 90deg to purlins
checkpoint-status |  |  | checkpoint | Transverse wires above logitudinal
checkpoint-status |  |  | checkpoint | Wiring around penetrations reinstated/ repaired?
checkpoint-status |  |  | checkpoint | Tags ends correctly tied
checkpoint-status |  |  | checkpoint | Tie configuration for timber fix correct
checkpoint-status |  |  | checkpoint | Timber fix
checkpoint-status |  |  | checkpoint | Lap twitching - correct spacing spacing if required
checkpoint-status |  |  | checkpoint | Longitudinal joins
checkpoint-status |  |  | checkpoint | Purlin wrapping where required
checkpoint-status |  |  | checkpoint | Twitching required over large penetrations ?
checkpoint-status |  |  | checkpoint | Start Gap
checkpoint-status |  |  | checkpoint | End Gap
checkpoint-status |  |  | checkpoint | Pre-drilled wire strip installed correctly
checkpoint-status |  |  | checkpoint | Job compliance
checklist-flat |  |  | checklist | Hazard Inspection Report |  |  |  |  | Yes | Hazard Inspection Report | f5c54ff7-abb0-496a-8621-d369cc714ec3
checkpoint-status |  |  | checkpoint | Hazard Inspection Report
text | ad0dce7d-1138-55d1-a45a-af553c1b90d7 |  | textbox | Inspection date
text | 20452b4c-2e3b-576a-9c5a-56ab3813f44e |  | textbox | Project
text | e8407934-e25f-5dbc-a2a9-af14d7de78f8 |  | textbox | Work Area
text | fff91cec-a155-53df-8fc5-9809e05ff65d |  | textbox | Identified Hazard
text | 593426ed-2664-54e0-9d63-4a139ee7224c |  | textbox | Corrective Action Required
text | 17109dd1-0b2f-57bc-96b7-c6528db4d1ed |  | textbox | Action By
text | 2967c05b-59be-5c72-b2f0-ac8e2d8fe9f3 |  | textbox | Due Date
checkpoint-status |  |  | checkpoint | Signed off be Foreman
checklist-flat |  |  | checklist | Delivery Docket |  |  |  |  | Yes | Add Delivery Docket | fc099edf-b8ce-4e93-8451-c28db5b70726
checkpoint-status |  |  | checkpoint | Please take photo or attach docket
checklist-sectioned |  |  | checklist | Box Gutter Installation |  |  |  |  | Yes | Canopy Roofs - Box Gutter Installation | fc754af0-62b6-4f2a-8e80-234c020927d9
checkpoint-group |  |  | section | Material Inspection
checkpoint-status |  |  | checkpoint | Box Gutter Brackets:
checkpoint-status |  |  | checkpoint | Insulation under gutter: Sisalation
checkpoint-status |  |  | checkpoint | Gutter Board: Spandek Zincalume
checkpoint-status |  |  | checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Gutter Flashing: Colorbond to match
checkpoint-status |  |  | checkpoint | Sumps / Outlets: 0.61mm Colorbond
checkpoint-status |  |  | checkpoint | Overflows:
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint-status |  |  | checkpoint | Insulation installed under gutter board
checkpoint-status |  |  | checkpoint | Gutter Board installed
checkpoint-status |  |  | checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint-status |  |  | checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint-status |  |  | checkpoint | Outlets installed to correct sizes.
checkpoint-status |  |  | checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint-status |  |  | checkpoint | Gutter flashing installed.
checkpoint-status |  |  | checkpoint | Area clean and free of debris.
checkpoint-status |  |  | checkpoint | Materials in good condition
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | 0bff17f8-62dd-579d-918d-0f2964c54014 |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Inspected and accepted by Authorized Representative
text | 67235daa-5760-591e-b814-473d6a4d766b |  | textbox | Checked and Signed by:
checkpoint-status |  |  | checkpoint | Reinspection requested by Subcontractor
text | f8970e71-bead-59ee-98b4-ea7ac87e6977 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint-status |  |  | checkpoint | Follow up work satisfactorily
text | 1d803432-f892-5026-aa7b-a43c3d39e3c2 |  | textbox | Site Supervisor:
checkpoint-status |  |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | 71fed258-1c4a-55cd-8f7c-398d7607fdae |  | textbox | Client Representative: