## Sheet1
INSPECTION & TEST PLAN
Contract No |  | Contract Name: |  |  |  |  | Rev: | Originator | Date | Approved | Date
|  | Kiwi Rail Bridge 217 |  |  | Embankment Construction |  | 0 | Jacob Dunn | 2023-08-01
ITP No: | [6 empty] | 1
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | HOLD POINT (H) OR WITNESS POINT (W) | SIGNATURE | DATE | COMMENTS
Materials
Source material properties |  |  | PM/PE/ Engineer/ Site Supervisor | Frequency of lab testing as per Table 1.4. | Lab testing sent to Engineer for approval prior to placement of fill. Lab testing requirements as per Table 1.5 and Table 1.6, and KiwiRail standard C-ST-FO-4110.
Visual inspection of subgrade |  |  | Engineer/PE/ PM/ Site Supervisor | 100% of subgrade | Subgrade free of debris, organics and unsuitables
Installation
Proof roll |  |  | Engineer/PE/ PM/ Site Supervisor | 100% of subgrade | <5 mm deflection under a smooth drum roller
Subgrade density testing |  |  | PM/PE/ Engineer/ Site Supervisor | Scala testing every 10 m as per Section 1.5.6 | Engineer must inspect and agree required formation treatment or undercutting. CBR requirements as per Section 1.5.6.
Compaction trials |  |  | PM/PE/ Engineer/ Site Supervisor | Each fill material type | Compaction trial carried out to confirm compaction methodology and compaction standards can be met, refer Section 1.8.2.
Compaction testing |  |  | PM/PE/ Engineer/ Site Supervisor | Frequency as per Table 1.4 | Engineer notified and given the opportunity to inspect when fill testing occurs.Compaction requirements as per Table 1.3
Visual inspection of finished structural fill surface |  |  | PM/PE/ Engineer/ Site Supervisor | 100% of structural fill surface | Engineer notified and must be inspected prior to next fill layer being placed. Well compacted surface and 3% fall to outside edge
Visual inspection of finished sub-ballast level |  |  | PM/PE/ Engineer/ Site Supervisor | 100% of sub-ballast surface | Engineer notified and must be inspected prior to next fill layer being placed. Well compacted surface and 3% fall to outside edge
Level check |  |  | PM/PE/ Engineer/ Site Supervisor | Finished section of structural fill or sub-ballast level | Engineer notified and given the opportunity to inspect when level checks on finished surface are being completed
Completion
Finished Coconut matt |  |  | PM/PE/ Engineer/ Site Supervisor | 100% of batter faces | Engineer notified and should inspect completed matted/ hydroseeded area
Visual inspection of geotextiles |  |  | PM/PE/ Engineer/ Site Supervisor | Placement of all geotextile | Engineer notified and given the opportunity to inspect
Visual inspection of geogrids |  |  | PM/PE/ Engineer/ Site Supervisor | Placement of all geogrid | Engineer notified and given the opportunity to inspect
Visual inspection of drainage trenches |  |  | PM/PE/ Engineer/ Site Supervisor | All drainage trenches (subsoil drainage) | Engineer notified and must inspect prior to backfilling of the drainage trench
Visual inspection of swale |  |  | PM/PE/ Engineer/ Site Supervisor | Visual inspection of swale | Engineer notified and must inspect finished surface
Visual inspection of duct installation |  |  | PM/PE/ Engineer/ Site Supervisor | Finished section of duct prior to backfilling | Engineer notified and given the opportunity to inspect.Duct laid according to the Specification and KiwiRail Standard S-ST-CW-2140
As-builts |  |  |  |  | As-built drawings to be provided to the Engineer following completion of works. Tolerances as per the Specification. Where tolerances differ from the Specification they shall be agreed with the Engineer prior to completion of the works
Tests for aggreagte quality
Density - General Fill (GAP 100 River Run) |  |  |  | Each 20 Linear meters for each lane | Density >= 95% mean Density >= 92% minimum
Density - Structural Fill (GAP 65) |  |  |  | Each 20 Linear meters for each lane | Density >= 98% mean Density >= 95% minimum