## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Embankment Construction | itp |  |  |  |  | ITP - Embankment Construction
section | Materials
checkpoint | Source material properties
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Frequency of lab testing as per Table 1.4.
label | ACCEPTANCE CRITERIA: Lab testing sent to Engineer for approval prior to placement of fill. Lab testing requirements as per Table 1.5 and Table 1.6, and KiwiRail standard C-ST-FO-4110.
checkpoint | Visual inspection of subgrade
label | INSPECTION BY: Engineer/PE/PM/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: 100% of subgrade
label | ACCEPTANCE CRITERIA: Subgrade free of debris, organics and unsuitables
section | Installation
checkpoint | Proof roll
label | INSPECTION BY: Engineer/PE/PM/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: 100% of subgrade
label | ACCEPTANCE CRITERIA: <5 mm deflection under a smooth drum roller
checkpoint | Subgrade density testing
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Scala testing every 10 m as per Section 1.5.6
label | ACCEPTANCE CRITERIA: Engineer must inspect and agree required formation treatment or undercutting. CBR requirements as per Section 1.5.6.
checkpoint | Compaction trials
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Each fill material type
label | ACCEPTANCE CRITERIA: Compaction trial carried out to confirm compaction methodology and compaction standards can be met, refer Section 1.8.2.
checkpoint | Compaction testing
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Frequency as per Table 1.4
label | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect when fill testing occurs.Compaction requirements as per Table 1.3
checkpoint | Visual inspection of finished structural fill surface
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: 100% of structural fill surface
label | ACCEPTANCE CRITERIA: Engineer notified and must be inspected prior to next fill layer being placed. Well compacted surface and 3% fall to outside edge
checkpoint | Visual inspection of finished sub-ballast level
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: 100% of sub-ballast surface
label | ACCEPTANCE CRITERIA: Engineer notified and must be inspected prior to next fill layer being placed. Well compacted surface and 3% fall to outside edge
checkpoint | Level check
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Finished section of structural fill or sub-ballast level
label | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect when level checks on finished surface are being completed
section | Completion
checkpoint | Finished Coconut matt
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: 100% of batter faces
label | ACCEPTANCE CRITERIA: Engineer notified and should inspect completed matted/hydroseeded area
checkpoint | Visual inspection of geotextiles
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Placement of all geotextile
label | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect
checkpoint | Visual inspection of geogrids
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Placement of all geogrid
label | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect
checkpoint | Visual inspection of drainage trenches
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: All drainage trenches (subsoil drainage)
label | ACCEPTANCE CRITERIA: Engineer notified and must inspect prior to backfilling of the drainage trench
checkpoint | Visual inspection of swale
label | INSPECTION BY: PM/PE/ Engineer/ Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Visual inspection of swale
label | ACCEPTANCE CRITERIA: Engineer notified and must inspect finished surface
checkpoint | Visual inspection of duct installation
label | INSPECTION BY: PM/PE/Engineer/Site Supervisor
label | TASK TIMING OR TASK FREQUENCY: Finished section of duct prior to backfilling
label | ACCEPTANCE CRITERIA: Engineer notified and given the opportunity to inspect.Duct laid according to the Specification and KiwiRail Standard S-ST-CW-2140
checkpoint | As-builts
label | ACCEPTANCE CRITERIA: As-built drawings to be provided to the Engineer following completion of works. Tolerances as per the Specification. Where tolerances differ from the Specification they shall be agreed with the Engineer prior to completion of the works
section | Tests for aggreagte quality
checkpoint | Density - General Fill (GAP 100 River Run)
label | TASK TIMING OR TASK FREQUENCY: Each 20 Linear meters for each lane
label | ACCEPTANCE CRITERIA: Density >= 95% mean, Density >= 92% minimum
checkpoint | Density - Structural Fill (GAP 65)
label | TASK TIMING OR TASK FREQUENCY: Each 20 Linear meters for each lane
label | ACCEPTANCE CRITERIA: Density >= 98% mean, Density >= 95% minimum
section | Sign Off
checkpoint | ITP Sign Off for Construction
text | Project Engineer:
text | Date:
checkpoint | All works completed, records attached and work conforming
text | Site Engineer:
text | Date:
text | Project Engineer:
text | Date:
text | Quality Manager:
text | Date: