## WBS Expo
WORK BREAKDOWN STRUCTURE | BUILDING | LEVEL | ZONE | ROOM | ITP
Zone C | Podium | LG | Zone 07
|  | LGM | Zone 84 | T01 | *incl ITP01 Soffit Lining
*incl ITP02 Speedpanel
*incl ITP03 Plaster Walls
*incl ITP04 Ceilings (grid/sheeting)
*incl ITP05 Shaft Lining
*incl ITP06 Door Frames
T02
Bin Room
Loading Store
Comms Riser
Electrical Riser
|  |  | Zone 85 | T03
Lift Lobby (Comms)
Lift Lobby (Carpark)
Cleaners Room
Mechanical Riser
Hydraulic Riser
| Building D | Ground Floor | Zone 84
F02 - Shared Kitchenette
F03 - F&B Café
FD02 - Willim Berrbang Community Space
Circulation Space
Store Grounds & Garden
C2 Lift Lobby
Zone 85
|  | Level 1 | Zone 84
Zone 85
|  | Level 2 | Zone 84
Zone 85
|  | Level 3 | Zone 84
Zone 85
|  | Level 4 | Zone 84
Zone 85
| Building E | Level 1 | Zone 80
Zone 81
Zone 82
Zone 83
|  | Level 2 | Zone 80
Zone 81
Zone 82
Zone 83
|  | Level 3 | Zone 80
Zone 81
Zone 82
Zone 83
|  | Level 4 | Zone 80
Zone 81
Zone 82
Zone 83
|  | Level 4 | Zone 80
Zone 81
Zone 82
Zone 83

## WBS Express
LEVEL | ZONE | ROOM | ITP
Basement 1 | Zone 93 | B1.C.001
B1.C.002
B1.C.003
Lower Ground | Zone 90 | LG.C.001
LG.C.002
LG.C.003
LG.C.004
LG.C.012
LG.C.013
LG.C.017
LG.C.018
| Zone 93 | LG.C.005
LG.B.586
LG.B.587
LG.C.014
LG.C.015
LG.C.016
Lower Ground Mezzanine | Zone 90 | LM.C.003
LM.C.007
LM.C.008
LM.C.009
LM.C.012
LM.C.017
LM.C.018
LM.C.022
LM.C.023
| Zone 92 | LM.B.505
LM.B.583
| Zone 93 | LM.C.010
LM.C.011
LM.C.014
LM.C.015
LM.C.016
LM.C.019
LM.C.020
LM.C.021
Ground Floor | Zone 90 | GF.C.001
GF.C.002
GF.C.003
GF.C.004
GF.C.005
GF.C.007
GF.C.008
GF.C.009
GF.C.011
GF.C.012
GF.C.014
GF.C.015
GF.C.016
GF.C.017
GF.C.019
GF.C.021
GF.C.052
GF.C.053
GF.C.059
GF.C.101
GF.C.102
GF.C.104
GF.C.105
GF.C.107
GF.C.108
| Zone 91 | GF.C.003
GF.C.012
GF.C.022
GF.C.024
GF.C.033
GF.C.044
GF.C.045
GF.C.113
| Zone 92 | GF.C.025
GF.C.026
GF.C.027
GF.C.028
GF.C.029
GF.C.031
GF.C.042
GF.C.043
GF.C.054
| Zone 93 | GF.C.016
GF.C.023
GF.C.032
GF.C.034
GF.C.036
GF.C.037
GF.C.039
GF.C.040
GF.C.041
GF.C.050
GF.C.055
GF.C.106
GF.C.109
GF.C.115
Level 1 | Zone 93 | 01.C.004
01.C.014
01.C.029
01.C.030
Level 2 | Zone 90 | 02.C.015
02.C.018
02.C.021
02.C.022
| Zone 93 | 02.C.004
02.C.007
02.C.011
02.C.012
02.C.013
02.C.014
02.C.016
02.C.017
02.C.019
02.C.020
Level 3 | Zone 90 | 03.C.007
03.C.014
03.C.016
| Zone 93 | 02.C.011
02.C.011
02.C.012
03.C.015
03.C.031
03.C.032
Level 4 | Zone 90 | 04.C.013
04.C.052
| Zone 93 | 02.C.011
02.C.012
04.C.007
04.C.010
04.C.011
04.C.012
04.C.024
04.C.033
04.C.034

## WBS
WORK BREAKDOWN STRUCTURE |  |  |  |  | ZONE C - STRIPPING ITEMS TRACKER
Zone C | Podium | LG | Zone 05 | *incl stripping items / check box | ITEM | CHECK BOX (Y/N)
|  |  | Zone 06 | *incl stripping items / check box | GENERAL ITEMS
|  |  | Zone 07 | *incl stripping items / check box | ALL FAÇADE REBATES / CAST INS AT PERIMETER
|  |  | Zone 08 | *incl stripping items / check box | CORE LOBBY/STAIR FINISH TO ME MADE GOOD (GRINDNIG)
STRIP PRECAST/INSITU ELEVATOR SHAFTS
|  | LGM | Zone 05 | *incl stripping items / check box | FORMING ALL INSITU WALLS ON PODIUM/RACKED SLABS
|  |  | Zone 06 | *incl stripping items / check box | RECTIFY DAMAGED PRECAST PANELS
|  |  | Zone 07 | *incl stripping items / check box | INFILL TEMP PENETRATIONS FOR PRECAST PROPS IF DOUBLE HEIGHT
|  |  | Zone 08 | *incl stripping items / check box | REMOVAL OF RAPIDCRETE GEAR FROM LOWER FLOORS
GROUT ALL PT DUCTS (ALL LEVELS AND DUCTS)
|  | GF | Zone 05 | *incl stripping items / check box | INSTALL AND POUR ALIMAK PENETRATIONS
|  |  | Zone 06 | *incl stripping items / check box | BACKLOAD F700 & SUBCONTRACTOR MATERIAL AND EQUIPMENT
|  |  | Zone 07 | *incl stripping items / check box | REINSTATE HANDRAILS AROUND PUMP PENOS ONCE JUMPED PRIOR TO INFILL
|  |  | Zone 08 | *incl stripping items / check box | GRIND SLAB EDGES FOR SMOKE SEAL INSTALLATION (if required)
REMOVE FOAM AND DRY PACK AT PANEL HORIZONTAL JOINTS
| Building C | Level 1 | *incl stripping items / check box |  | COMPLETE CAULKING OF ALL PRECAST PANELS
|  | Level 2 | *incl stripping items / check box |  | GROUTING OF PRECAST PANELS AND ITP's SUBMITTED
|  | Level 3 | *incl stripping items / check box |  | REMOVE SCAFFOLD AND FORMWORK FROM CORES
|  | Level 4 | *incl stripping items / check box |  | PATCH DOOR THRESHOLDS IN CORES
FORM AND POUR PUMP PENO's
| Building D | Level 1 | *incl stripping items / check box |  | DE-NAILING AND GENERAL PATCHING ONCE STRIPPED (ESPECIALLY IN CARPARK AREAS)
|  | Level 2 | *incl stripping items / check box |  | CORE ITEMS
|  | Level 3 | *incl stripping items / check box |  | REMOVAL OF TEMPORARY STEELWORK (JUMPFORM SUPPORTS)
|  | Level 4 | *incl stripping items / check box |  | FILLING OF JUMPFORM POCKETS AND SUPPORTS
|  | Level 5 | *incl stripping items / check box |  | Z-BAR HOLE PATCHING (CRITICAL IN STAIR PRESSURISATION SHAFTS AND LIFT SHAFTS) - BOTH INSIDE AND OUT
PERMENANT HANDRAIL INSTALLATION - CHECK COMPLIANCE
| Building E | Level 1 | *incl stripping items / check box |  | CAULKING OF PRECAST DIVIDING PANELS (if applicable)
|  | Level 2 | *incl stripping items / check box |  | CAULKING OF STAIR STRINGERS
|  | Level 3 | *incl stripping items / check box |  | DE-NAILING AND GENERAL PATCHING
|  | Level 4 | *incl stripping items / check box |  | STRIPPING OF ALL HORIZONTAL PENETRATIONS
|  | Level 5 | *incl stripping items / check box |  | CORE DOOR THRESHOLDS TO BE GRINDED / PATCHED
METER MARK INSTALLED IN LOBBIES FOR KONE
SLAB ITEMS
ALL PENETRATIONS INSTALLED & SERVICE TRADES SIGNED OFF
BACKPROPPING AS PER RBG DETAILS/SKETCH
ALL FAÇADE REBATES / CAST INS AT PERIMETER
SETDOWNS INSTALLED
ASBUILTS SUBMITTED AND REVIEWED
COUPLERS INSTALLED AT TEMP PENETRATIONS FOR FUTURE INFILL
PT AND REINFORCEMENT PHOTOGRAPHED AND VIDEO PRIOR TO POUR

## Matrix
ZONE C - STRIPPING ITEMS TRACKER | LG |  |  |  | LGM |  |  |  | GF |  |  |  | L1 |  |  | L2 |  |  | L3 |  |  | L4 |  |  | L5
ITEM | Z5 | Z6 | Z7 | Z8 | Z5 | Z6 | Z7 | Z8 | Z5 | Z6 | Z7 | Z8 | Bld C | Bld D | Bld E | Bld C | Bld D | Bld E | Bld C | Bld D | Bld E | Bld C | Bld D | Bld E | Bld D | Bld E
GENERAL ITEMS
ALL FAÇADE REBATES / CAST INS AT PERIMETER
CORE LOBBY/STAIR FINISH TO ME MADE GOOD (GRINDNIG)
STRIP PRECAST/INSITU ELEVATOR SHAFTS
FORMING ALL INSITU WALLS ON PODIUM/RACKED SLABS
RECTIFY DAMAGED PRECAST PANELS
INFILL TEMP PENETRATIONS FOR PRECAST PROPS IF DOUBLE HEIGHT
REMOVAL OF RAPIDCRETE GEAR FROM LOWER FLOORS
GROUT ALL PT DUCTS (ALL LEVELS AND DUCTS)
INSTALL AND POUR ALIMAK PENETRATIONS
BACKLOAD F700 & SUBCONTRACTOR MATERIAL AND EQUIPMENT
REINSTATE HANDRAILS AROUND PUMP PENOS ONCE JUMPED PRIOR TO INFILL
GRIND SLAB EDGES FOR SMOKE SEAL INSTALLATION (if required)
REMOVE FOAM AND DRY PACK AT PANEL HORIZONTAL JOINTS
COMPLETE CAULKING OF ALL PRECAST PANELS
GROUTING OF PRECAST PANELS AND ITP's SUBMITTED
REMOVE SCAFFOLD AND FORMWORK FROM CORES
PATCH DOOR THRESHOLDS IN CORES
FORM AND POUR PUMP PENO's
DE-NAILING AND GENERAL PATCHING ONCE STRIPPED (ESPECIALLY IN CARPARK AREAS)
CORE ITEMS
REMOVAL OF TEMPORARY STEELWORK (JUMPFORM SUPPORTS)
FILLING OF JUMPFORM POCKETS AND SUPPORTS
Z-BAR HOLE PATCHING (CRITICAL IN STAIR PRESSURISATION SHAFTS AND LIFT SHAFTS) - BOTH INSIDE AND OUT
PERMENANT HANDRAIL INSTALLATION - CHECK COMPLIANCE
CAULKING OF PRECAST DIVIDING PANELS (if applicable)
CAULKING OF STAIR STRINGERS
DE-NAILING AND GENERAL PATCHING
STRIPPING OF ALL HORIZONTAL PENETRATIONS
CORE DOOR THRESHOLDS TO BE GRINDED / PATCHED
METER MARK INSTALLED IN LOBBIES FOR KONE
SLAB ITEMS
ALL PENETRATIONS INSTALLED & SERVICE TRADES SIGNED OFF
BACKPROPPING AS PER RBG DETAILS/SKETCH
ALL FAÇADE REBATES / CAST INS AT PERIMETER
SETDOWNS INSTALLED
ASBUILTS SUBMITTED AND REVIEWED
COUPLERS INSTALLED AT TEMP PENETRATIONS FOR FUTURE INFILL
PT AND REINFORCEMENT PHOTOGRAPHED AND VIDEO PRIOR TO POUR