## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-004 - Type A Fill Placement Rev3 | itp |  |  |  |  | FHC-ITP-004 - Type A Fill Placement Rev3
section | 1 - Preliminary Works
checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
note | FREQUENCY: Prior to commencing
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to Placement/ Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Verify Material
note | FREQUENCY: Prior to Placement
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive.
note | • Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075.
note | • PI between 6 and 25.
note | • Permeability of less than 5X10^-9 for capping and verge material
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec.
note | • Cl. 204.04(b)
note | • Cl. 204.06(c)
note | • Table 204.041
note | • Table 3020.052
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Record (If silt is observed)
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer & Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 Excavation Permit
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
note | • Plant and equipment shall be appropriate for the task.
note | • Excavation operations shall not disturb areas outside the limit of excavation
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Excavation permit
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Survey set-out
note | FREQUENCY: Prior to Commencing Excavation
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.
note | • The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
note | • IFC and latest available revision used
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Latest IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Survey records & pegs on the ground
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Inspection of fill area
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 204.10 (b)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Layer Thickness
note | FREQUENCY: During Excavation
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Maximum Lot Size
note | FREQUENCY: During Excavation
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Proof Roll
note | FREQUENCY: Prior to placement
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Foreman/ Superintendent
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Type A Placement
note | FREQUENCY: Prior to Placement/ Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas
note | • Any rocky material present must be uniform throughout the layer
note | • Each layer shall be kept generally parallel to the surface of subgrade
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 204.10 (d) (i).
note | • 204.10 (d) (ii).
note | • Table 3020.052
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
section | 3 - Testing
checkpoint | 3.1 Reduced Test Frequency
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification.
note | • Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Test Record
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Records
note | – – – – – – – – –
note | AP
note | – – – – – – – – –
note | RESPONSIBILITY: Project Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.2 Compaction Testing
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Compaction Test Records
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.3 Compaction Testing (Small Lots)
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area.
note | • Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 173.04 d
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Test Point
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Records, Lot Register
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: N/A
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.4 Maximum Particle Size
note | FREQUENCY: Each lot, unless reduced frequency has been approved
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec.
note | • Cl. 204.14(a)(ii)
note | • Table 204.141
note | • Table 204.041
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.5 CBR/Swell
note | FREQUENCY: First lot only
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec.
note | • Cl. 204.14(a)(i)
note | • Table 204.141
note | • Table 204.041
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: CBR/Swell Test Records
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.6 Atterberg Limit Tests
note | FREQUENCY: Each lot, unless reduced frequency has been approved
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec.
note | • Cl. 204.14(a)(ii) Table 204.141
note | • Table 204.041
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: PI Test Records
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.7 Permeability
note | FREQUENCY: Each lot, unless reduced frequency has been approved
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec.
note | • Cl. 204.14(a)(ii) Table 204.141
note | • Table 204.041
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Permeability Test Records
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.8 Material Property Testing (Scale B)
note | FREQUENCY: Each lot, unless reduced frequency has been approved
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 204.04, Cl204.14
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: NATA test report
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.9 Survey Conformance
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
note | • Scale B: Range x = +5,-25
note | • Max S = 15mm
note | • 40 measurements per lot
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 204.03
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Survey conformance point
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Survey report, Lot Register
note | – – – – – – – – –
note | WP, SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer & Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: