## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-XXX
[11 empty] | Revision : | Date : 12/05/23
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Class 3 Cement Treated Crushed Rock Placement |  | Name: | Martin Syawish | Name: |  | Patrick Fagan | Name:
Contract No: |  |  |  | Specifications: VicRoads Specification Section 173 , 306 , 815
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Verify Material |  | Each day | The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815. | Section 815 Cl 306.04 | Verify | Material certificate from supplier | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | UCS Testing |  | Each day | The Contractor shall carry out UCS testing in accordance with the test frequency specified in Table 815.141. The UCS during production shall be assessed on a ‘rolling average’ basis where the average of the most recent three UCS test results shall not be less than the minimum value specified in Table 815.101. For the purposes of UCS testing, one representative sample of fully mixed cement treated material shall be taken either from the plant or at the point of delivery in accordance with AS 5101.2.2 | Section 815 | Verify | Test Results | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | The area has been inspected and Proof rolled by MRPA and consent has been given to proceed with placement of sub-base). |  | Each lot | Sub-grade has been inspected, No visible deformation or springing in presence of Superintendent's Rep. Test rolling Plant to comply with requirements of Cl 173.03. Where any groundwater is encountered the Superintendents representative must be notified. Ensure that test results for underlying lot are available prior to placing sub-base material | Cl 173.03 | Verify | This ITP signed | HP | Fulton Hogan Engineer / MRPA |  |  | N/A
| Maximum allowable working time and moisture content |  | Each lot | The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time specified in Table 306.091. The moisture content of the material at the time of spreading and compaction shall not differ from the Modified optimum moisture content, by less than 0.5% and not more than 1.0% by mass. | Cl 306.05 Cl 306.09 | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Jointing |  | Each lot | a) material shall be spread in such a manner as to minimise the number of joints; (c) transverse joints shall be offset from one layer to the next by not less than 2 m; | Cl 306.08 | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
| Compaction Testing |  | Every Lot Every second lot (reduced frequency) | Minimum MDR of 96% using Modified compaction effort. 3 lot test (Scale B). LOT SIZE = Lesser of 4000sqm or a days production is defined as a Lot. Every Lot to be tested for surface levels and density ratio using modified compactive effort Compaction Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the requirement and then resort to one test per 2 lots . | Cl 306.09 | Test Results | This ITP signed | TP/WP | Fulton Hogan Engineer / MRPA
2.4 | Level Checking and Conformity with Drawings |  | Each lot | Sub-base shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits: Shape: no point deviation > 8mm from 3m straight edge in any direction Surface level tolerances: Range x = +6, -12mm Max S = 13 mm 40 measurements per lot (Scale B) | Cl 306.03 | Verify | Survey Report | SCP WP | Surveyor/ Fulton Hogan Engineer/ Foreman MRPA
2.6 | Final Proof Rolling |  | Proof Roll each layer | No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03. | Cl 173.03 | Visual inspection | This ITP signed | HP | Fulton Hogan Engineer / Subcontractor |  |  | N/A
2.4 | Curing and Protection of Compacted Layers |  | Each lot | The minimum compacted thickness shall be not less than 100 mm and the maximum compacted thickness shall be no more than 180 mm and constructed within the tolerances specified in Clause 306.03. (a) Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane. Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent. The subbase shall be kept in good order and condition and free from contamination. | Cl 306.11 | Verify | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.7 | Delivery Dockets |  | Each Day | FH shall make delivery dockets available for inspection on request | Cl 306.07 | Delivery Docket Submission | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.