## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-034 - Cement Treated Crushed Rock Sub-base Rev0 | itp |  |  |  |  | FHC-ITP-034 - Cement Treated Crushed Rock Sub-base Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Verify Material
note | FREQUENCY: Each day
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase.
note | • The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Section 815 Cl 306.04
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Material certificate from supplier
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 UCS Testing
note | FREQUENCY: Each day
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The Contractor shall carry out UCS testing in accordance with the test frequency specified in Table 815.141.
note | • The UCS during production shall be assessed on a ‘rolling average’ basis where the average of the most recent three UCS test results shall not be less than the minimum value specified in Table 815.101. For the purposes of UCS testing, one representative sample of fully mixed cement treated material shall be taken either from the plant or at the point of delivery in accordance with AS 5101.2.2
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Section 815
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Results
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 The area has been inspected and Proof rolled by MRPA and consent has been given to proceed with placement of sub-base).
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Sub-grade has been inspected, No visible deformation or springing in presence of Superintendent's Rep. Test rolling Plant to comply with requirements of Cl 173.03.
note | • Where any groundwater is encountered the Superintendents representative must be notified.
note | • Ensure that test results for underlying lot are available prior to placing sub-base material
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 173.03
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / MRPA
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Maximum allowable working time and moisture content
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time specified in Table 306.091.
note | • The moisture content of the material at the time of spreading and compaction shall not differ from the Modified optimum moisture content, by less than 0.5% and not more than 1.0% by mass.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 306.05, Cl 306.09
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Jointing
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: a) material shall be spread in such a manner as to minimise the number of joints;
note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 306.08
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | Compaction Testing
note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Minimum MDR of 96% using Modified compaction effort. 3 lot test (Scale B).
note | • LOT SIZE = Lesser of 4000sqm or a days production is defined as a Lot.
note | • Every Lot to be tested for surface levels and density ratio using modified compactive effort
note | • Compaction Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the requirement and then resort to one test per 2 lots .
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 306.09
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Test Results
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | TP/WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / MRPA
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Level Checking and Conformity with Drawings
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
note | • Shape: no point deviation > 8mm from 3m straight edge in any direction
note | • Surface level tolerances:
note | • Range x = +6, -12mm
note | • Max S = 13 mm
note | • 40 measurements per lot (Scale B)
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 306.03
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Survey Report
note | – – – – – – – – –
note | SCP, WP
note | – – – – – – – – –
note | RESPONSIBILITY: Surveyor/Fulton Hogan Engineer/Foreman MRPA
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Final Proof Rolling
note | FREQUENCY: Proof Roll each layer
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 173.03
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / Subcontractor
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Curing and Protection of Compacted Layers
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The minimum compacted thickness shall be not less than 100 mm and the maximum compacted thickness shall be no more than 180 mm and constructed within the tolerances specified in Clause 306.03.
note | (a) Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified:
note | • The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
note | • Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
note | • The subbase shall be kept in good order and condition and free from contamination.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 306.11
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Delivery Dockets
note | FREQUENCY: Each Day
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: FH shall make delivery dockets available for inspection on request
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Cl 306.07
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Delivery Docket Submission
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: