## PROJECT STRUCTURE
Folder Structure |  |  |  | Checklists
FLAT BUSH SCHOOL | TAMAKI HEALTH | PROJECT:KIWIRAIL
INTERIOR FITOUT
ISOLATION
|  |  | ELECTRICAL ISOLATION | ISOLATION AND DISCONNECTION
|  | ELECTRICAL INSTALLATION WORKS | ELECTRICAL INSTALLATION | 1ST FIX
2ND FIX
CONTAINMENT CONDUITS
COMMISSIONING
|  |  | COMMISSIONING - SWITCHBOARD MSB | COMMISSIONING - DISTRIBUTION BOARD

## CHECKPOINTS
TYPE | NAME
CHECKLIST | ISOLATION AND DISCONNECTION
CHECKPOINT | SAFELY ISOLATE AND LOCK OUT ALL CIRCUITS BEING WORKED ON
CHECKPOINT | REMOVAL OF EXISTING LIGHTING WHERE REQUIRED
CHECKPOINT | REMOVAL OF EXISTING POWER WHERE REQUIRED
CHECKPOINT | CHECK EXISTING CABLING FOR COMPLIANCE
CHECKPOINT | REMOVE ALL REDUNDNANT AND NON COMPLIANT CABLING
CHECKLIST | CONTAINMENT - CONDUITS
CHECKPOINT | COORDINATE SET OUT OF ALL CONDUITS WITH IMPACT AND OTHER SERVICES
CHECKPOINT | INSTALLATION OF ALL CONDUIT
CHECKLIST | 1ST FIX
CHECKPOINT | CABLING INSTALLED AS PER LGHTING AND POWER LOCATIONS REFLECTED
CHECKPOINT | CORRECT SIZE POWER/LIGHTING CABLE INSTALLED AS PER CABLE CALC TO LOADS AND VOLTAGE DROP
CHECKPOINT | MARKOUT NOGS FOR FLUSH BOXES AND SURFACE/SUSPENDED LIGHTING
CHECKPOINT | FLUSH BOXES MOUNTED AS PER ARCHITECTURAL ELEVATION
CHECKPOINT | RFIs TO SET OUT AND LOCATION ARE CONFIRMED
CHECKPOINT | FLUSH BOXES FOR ISOLATORS INSTALLED ABOVE BENCH OR AT ACCESSIABLE LOCATION TO APPLIANCE
CHECKPOINT | FEED AND SWITCH WIRES INSTALLED AND CONFIMRED FOR LIGHTING
CHECKPOINT | HOTWATER CABLE INSTALLED AND LOCATION CONFIMRED WITH PLUMBER
CHECKPOINT | APPLIANCE ISOLATORS INSTALLED A/B OR AT ACCESSIBLE LOCATION
CHECKPOINT | LCP FLUSH BOX MOUNTED AND SWITCH CONTROL WIRES INSTALLED BETWEEN LCP AND DB CONTROL
CHECKPOINT | LIGHTING LOOPS INSTALLED AS PER LIGHTING LAYOUT
CHECKPOINT | SWITCH LOCATIONS CONFIRMED AND IS ACCESSIABLE UPON ENTRY TO ROOM
CHECKPOINT | EMERGENCY CIRCUITS AND LOOPS CHECKED AND COMPLETED.
CHECKPOINT | LIGHTING AND POWER CIRCUITS CONFIRMED AND ALL LOOPS ARE CHECKED AND CONFIMRED
CHECKPOINT | BOND CABLE TO CEILING GRID/SINKS AND STRUCTURE IS RAN AND CONFIRMED
CHECKPOINT | ALL CABLES ARE CABLE TIED NEATLY ON CATENARY WIRES AND MEETS SPECIFICATION
CHECKPOINT | FLOORBOXES MARKED AND PENETRATIONS COMPLETE
CHECKLIST | 2ND FIX
CHECKPOINT | LIGHT SWITCHES INSTALLED, LEVELLED, LABELLED AND LIVE
CHECKPOINT | POWER OUTLETS INSTALLED, LEVELLED, LABELLED AND LIVE
CHECKPOINT | DATA OUTLETS INSTALLED, LEVELLED, LABELLED AND TESTED.
CHECKPOINT | SURFACE SOCKETS FITTED OFF FOR PAN FITTINGS, DOWNLIGHTS AND EMERGENCY LIGHTS
CHECKPOINT | SURFACE SOCKETS ARE LABELLED TO ALLOCATED CIRCUITS CORRECTLY
CHECKPOINT | PAN FITTINGS, DOWNLIGHTS AND EMERGENCY LIGHTS ARE INSTALLED IN CORRECT LOCATIONS.
CHECKPOINT | LCP PANEL IS FITTED OFF AND LIGHTS ARE SWITCHING CORRECTLY.
CHECKPOINT | EMERGENCY LIGHTS INSTALLED, LABELLED, LIVE AND WORKING CORRECTLY.
CHECKPOINT | TRUNKING INSTALLED PLUMMBED AND LEVEL TO MOUNTING BLOCK FOR OUTLETS WHERE REUIRED.
CHECKPOINT | CEILING GRID/SINKS/ BUILDING STRUCTURE IS BONDED AND TEST RESULTS < 0.5 OHMS TO DB
CHECKPOINT | FEATURE LIGHTS INSTALLED SECURLY SUSPENDED OR SURFACE MOUNT ONTO PLY BEHINF CEILING GRID
CHECKLIST | COMMISSIONING - DISTRIBUTION BOARD
CHECKPOINT | SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED INTO DB AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EARTHING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | TIMECLOCK TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX