## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | NEL-CNT-SDC-2990-PQA-ITP-0094 Rev 3 - Subsoil Drainage Installation | itp |  |  |  |  | NEL-CNT-SDC-2990-PQA-ITP-0094 Rev 3 - Subsoil Drainage Installation
section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint | 1.1 - Construction Package Approval
label | Resp. Person - PE
label | Specification Reference - PSDR Part F6 2 (a) to (h)
label | Acceptance Criteria - Construction Documentation shall be submitted and approved prior to commencing work at site.
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - IFU Construction Package
textbox | • InEight Reference #:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - IFC Drawings Issued
label | Resp. Person - PE
label | Specification Reference - Construction Management Plan
label | Acceptance Criteria - IFC Drawings, approved plans, technical specifications issued for construction.
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
textbox | • Design Package Number #:
checkpoint | 1.3 - All Equipment Calibrated (NATA Approved)
label | Resp. Person - PE
label | Specification Reference - CQMP Section 11.1
label | Acceptance Criteria - Equipment calibration certificates filed in InEight. Ensure all equipment associated with the relevant works is calibrated
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • InEight Reference:
bool | • Not Applicable
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Set-Out
label | Resp. Person - PS
label | Specification Reference - CQMP Survey MP
label | Acceptance Criteria - Confirm and visually inspect all survey set out points are in accordance to IFC Drawings.
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Photos of Survey Marks
bool | • Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Sub-Contractor(s) Quality Documents + Inspection Test Plans
label | Resp. Person - PE
label | Specification Reference - CQMP 8.2.2.4
label | Acceptance Criteria - Ensure Sub-Contractor(s) have submitted signed ITP’s and Checklists along with all relevant supporting documents.
label | Test Method - R
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • InEight References:
bool | • Approved ITP Review Checklist
bool | • Not Applicable
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Material Compliance
checkpoint | 2.1 - Method of Compaction
label | Resp. Person - SE
label | Specification Reference - VicRoads Section(s) 702.09
label | Acceptance Criteria - The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Nominated Authority.
label | • Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Nominated Authority which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
bool | • InEight Hold Point Reference:
textbox | • InEight Document Reference No.:
bool | • Not Applicable
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Material – Drainage pipe, granular filter and geotextile materials
label | Resp. Person - SE
label | Specification Reference - VicRoads Section(s) 702.04, 702.05, 702.06 & IFC Drawings PSDR Part B Section 5.4 and 5.5
label | Acceptance Criteria - Drainage pipes comply with specified requirements of Category 1:
label | • Perforated plastics Class 1000
label | • Precast concrete Class "2"
label | • Perforation size to be less than 1.5mm and minimum length of 150mm/m2. Drainage pipes must be made of reinforced concrete and rubber-ring jointed, or other equivalent products approved by the State. Granular filter material must be obtained from a VicRoads accredited source. No Fines concrete must meet the following requirements:
label | • Be a Type GP cement
label | • Comply with section 703
label | • W/C range of 0.35 to 0.5
label | ○ Geotextile filter to have the following characteristics:
label | • Minimum robustness G(1 ) of 900
label | • EOS(2) of 85-230 microns
label | • Minimum elongation of 45%
label | ○ Refer Table 702.131 on the last page of this ITP.
label | Test Method - V
label | Test Freq. - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Delivery Dockets for Bedding Materials
bool | • Manufacturers Compliance Certificates for pipes and geotextile materials
bool | • NATA Test Report(s)
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Construction Activities
checkpoint | 3.01 - Excavation
label | Resp. Person - SE
label | Specification Reference - VicRoads Section(s) 702.08
label | Acceptance Criteria - Trench walls excavated to allow geotextile filter to be in close contact with the wall. The bottom of the trench has been compacted and is not more than 50 mm below the specified level of the invert of the pipe.
label | • There are no departures from the grade of the base of the trench that would allow ponding of water.
label | • Excess excavation made good by backfilling with like material. Loose material has been removed.
label | • Where existing subsurface drains are intercepted, an adequate outlet has been provided for the drain.
label | • Redundant subsurface drains have been removed and backfilled with Type A per section 204, or specified pavement material when found in new road pavement.
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • InEight Hold Point Number
textbox | • Hold Point Number:
bool | • Excavation and Penetration Permit No
textbox | • Permit No:
checkpoint | 3.02 - Inspection of Base Trench
label | Resp. Person - PE
label | Specification Reference - VicRoads Section(s) 702.08
label | Acceptance Criteria - The base of the trench shall be inspected to verify compliance prior to placing bedding in completed excavations. The Nominated Authority shall be notified at least 24 hours prior to the inspection.
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
textbox | • HP Release InEight Reference #:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.03 - Subsurface drains in expansive soils
label | Resp. Person - SE
label | Specification Reference - IFC Drawings
label | Acceptance Criteria - Where subsurface drains are installed in expansive soils (swell >2.5%) the drainage pipe must not touch the expansive material. Additionally, 150mm or more of capping must be provided below the floor of the trench.
label | Test Method - V
label | Test Freq. - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Completed ITP
bool | • NATA Swell Report for Subgrade
bool | • Not Applicable
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Bedding
label | Resp. Person - SE
label | Specification Reference - VicRoads Section(s) 702.09
label | Acceptance Criteria - A bedding of granular filter material of thickness between 25 mm and 50 mm has been placed across the bottom of the trench. The bedding has been tamped and screeded or graded to level.
label | Test Method - V
label | Test Freq. - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Completed ITP
bool | • Not Applicable
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.05 - Installation
label | Resp. Person - SE
label | Specification Reference - VicRoads Section(s) 702.09
label | • VicRoads Standard Drawing 1601 IFC Drawings PSDR Part B Section 5.4 and 5.5
label | Acceptance Criteria - Subsurface drainage pipes have been laid to the depth shown on drawings. All road drainage pipes and culverts must be designed such that the top of the drain is at least 200 millimetres below the underside of pavement, except where capping or selected material is required beneath the pavement.
label | • The top of drain must be at least 200 millimetres below the underside of capping or selected material.
label | • The diameter of pipes placed under pavements must not be less than 375 millimetres and the height of box culverts must be not less than 300 millimetres.
label | • Except for drainage systems related to the Tunnel, or where agreed to by the State or the Returned Asset Owner (as applicable), all longitudinal, transverse drainage and subsurface drainage systems must be free draining.
label | • The incorporation of drainage systems that rely on pumping or siphoning is not permitted.
label | • Corrugated metal pipes, pipe arches and arches must not be used.
label | • All outlets to drainage systems must be provided by an underground
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Completed ITP
checkpoint | 3.06 - Placing Granular Filter Material and Geotextile
label | Resp. Person - SE
label | Specification Reference - VicRoads 702.09
label | Acceptance Criteria - Filter material has been placed in accordance with the approved method of placement.
label | • No segregation of no fines nor formation of a slurry at the surface. No-fines concrete placed and compacted within 1 hour of mixing.
label | • Geotextile has been lapped over granular filter material by 150mm or more as per SD1601
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Completed ITP
bool | • Compaction Test
bool | • Not Applicable
checkpoint | 3.07 - Flushing
label | Resp. Person - PE
label | Specification Reference - VicRoads 702.09
label | Acceptance Criteria - A flush test has been carried out in the presence of a representative nominated by the Nominated Authority.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
bool | • Record of flushing test
bool | • Not Applicable
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.08 - Access points & inspection openings
label | Resp. Person - SE
label | Specification Reference - VicRoads 702.10
label | Acceptance Criteria - An access point has been provided at the beginning and end of each run and an inspection point at 100-150m intervals. Where stormwater pits have been used as access points, the invert at the beginning of the run has been located above the outlet of the pit and >100mm above the outlet of the pit at the end of the run.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Completed ITP
checkpoint | 3.09 - Marker Posts
label | Resp. Person - SE
label | Specification Reference - VicRoads 702.11 PSDR Part B Section 5.4
label | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on the drawings. Posts must be 75mm diameter x 1500mm treated pine posts inserted 600mm into the ground.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Completed ITP
bool | • As Built Documents
checkpoint | 3.10 - Inspection of Subsurface Drainage Lines
label | Resp. Person - SE
label | Specification Reference - VicRoads 702.09 (i) PSDR Part B section 5.5(b)
label | Acceptance Criteria - All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | • Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Nominated Authority.
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
bool | • CCTV Report
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Post Operations (Include Inspection and Testing)
checkpoint | 4.1 - Verification and lot records Complete
label | Resp. Person - SE
label | Specification Reference - CQMP Section 8.2.6.2
label | Acceptance Criteria - Ensure completed work checklists, inspection and test results and contractor conformance records are progressively and permanently saved and stored as soon as possible after they are received. Completed construction lot records are transferred to the project Quality Team for final record verification prior to being closed
label | Test Method - V
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Lot Map Lot Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - NCR Close out (if applicable)
label | Resp. Person - PE
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - All NCR’s presented for closure
label | Test Method - R
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
textbox | • HP Release InEight Reference #
textbox | • NCR InEight Reference #:
label | • NCR Module
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Quality
checkpoint | 5.1 - Identification and control of nonconforming products or services (if applicable)
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot
label | Test Method - R
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - NCR closed with related documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Check all quality records for lot closure
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - All applicable quality records are complete
label | Test Method - R
label | Test Freq. - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Compiled documents (all data reports and records)
holdpoint | AUTHORITY HOLDPOINT