## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
613a0560-7cb0-418a-a056-3e05b0055c5b | checklist | RSA.WP17.REHAB.FIC | itp | RSA.WP17.REHAB.FIC
3550038d-7fef-4e80-ad36-25e8a9761d2f | section | FIELD INSPECTION CHECKLIST ACCESS TRACK
351ecad7-31e6-4923-a4c4-877e81b88e50 | checkpoint | Confirm set out workover rig area has been implemented by the Client
17007f09-8868-4b4d-82db-d26664da9e06 | checkpoint | Confirm pipeline entry location (GIS)
e0e67c47-0c00-414b-a007-6c5b97db7ff9 | checkpoint | ESC in working order (Ensure no sediment is past the containment point)
c9db61da-eaf0-4704-8cab-fcc0821873c6 | checkpoint | Install table drain and/or clean out (If required)
ddc681a3-d00b-4c7b-a322-76ea42b98ddb | checkpoint | Clean out shot rock sump & tidy up (if required)
46c29993-0862-461c-b777-f3c9a5f8fdda | checkpoint | Amelioration (Gypsum / Lime) (If required)
110fb906-2e9e-4152-9c8d-bb9e689ec441 | checkpoint | Rip Sub Soil Areas
f5a212f4-92f8-439c-8959-1f027d2d8188 | checkpoint | Reclaim topsoil from batters and topsoil stockpile where available
c415cae1-c223-4eaa-b91d-1ad13b679ac5 | checkpoint | Transport and Spread Topsoil
7c8ac51d-3594-41e7-bcfd-baa21be3bcfd | checkpoint | Fertiliser, Seed & Scarify
f9d88963-0b90-4242-9a3b-4633112f8d6c | checkpoint | Confirm As Con has been completed & received
e83a098a-c668-483f-8d07-1514b09efa3e | checkpoint | RSA QA Inspection
1439c76f-db60-407a-ad17-4aad8f3f48ad | signoff | HOLD POINT
8ca8a839-80d8-4f3f-9b1c-0e952dc211f9 | checklist | RSA.WP17.REHAB.ITP | itp | RSA.WP17.REHAB.ITP
5c3f7e50-b0b3-43c9-9f99-4ffda6fc915f | section | 1 - Preliminary
6a056ebe-82e0-4c48-9db3-96dc53b0382b | checkpoint | 1.1 - Access Documentation
7c6c4ed8-2681-5f13-9612-f579f2d2b33e | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client PTA / LARS Relevant Construction Work Pack
87a99484-76d9-5609-adf5-7090a8d9740f | note | Frequency - Prior to Start
5f4e0d19-3765-5d2f-9c7c-921cd57b95da | note | Test Method - Review
ef32fd03-2ccb-577b-9ed9-16e0f78ad73b | note | Acceptance Criteria - All documents in place and correct.
0451b39d-41de-5abf-a527-594cfa2ebb8e | note | Verifying Documents - Client PTA / LARS Relevant Construction Work Pack
fe5482c9-8382-53ac-84c1-5077c6e53141 | note | Responsibility: RSA - H
937faa0f-0dc1-42b8-b94f-4722c8fda1f5 | signoff | HOLD POINT
c9ff28ea-7af7-48b5-be6b-31b253d63ddd | checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
6093f83f-1adf-55f2-a6ae-669fa50a49fd | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
82fb81ef-2f74-5918-bf96-7a29bfc5b05b | note | Frequency - Prior to Start
a1539764-30cd-523c-9f65-2c8668b6688d | note | Test Method - Review
2946b4f9-28c1-5491-bcaf-3af84e7ab028 | note | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
1b48f681-d147-5a37-8e91-4fae45c9c10b | note | Verifying Documents - Weed Declaration Certificate. Appenate FFP Form
fc28dae0-b80c-572f-804c-7d75cfe6e71f | note | Responsibility: RSA - H
6b97ca15-c4eb-4ef6-97b4-890cf8ae3cc2 | signoff | HOLD POINT
471247c0-cc2c-4592-9eed-1ace7bb9dd9f | section | 2 - Lease Rehab
365fb03d-123d-431b-b69f-d26327b361fb | checkpoint | 2.1 - Confirm set out workover rig area has been implemented by the Client
27a16e2b-8f42-54c0-9c4f-54f41daf1733 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure OPS-QLDS-CI-GAR-005
9264eec1-51a4-5cd6-bf21-d87212e0f2ac | note | Frequency - Each Lease Pad
d3ff298d-e177-50e0-8403-9dd1becced0c | note | Test Method - Visual Inspection
e1ae6a4a-6122-541d-aed4-20cf6b1515a3 | note | Acceptance Criteria - As per Client Procedure
8b4f8581-b84b-5fae-ab8a-a7db0c7796cf | note | Verifying Documents - Lease Rehab FIC
9fb7a341-9b9a-5999-b128-a8d5dd2d3aaa | note | Responsibility: RSA - M
e5872289-9017-4a3e-b43b-d2a421356763 | checkpoint | 2.2 - Confirm pipeline entry location (GIS)
102d30d7-7c10-5344-9b4c-0bd2f420c9a6 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure OPS-QLDS-CI-GAR-005
173fa9a8-7ac8-539e-ae5a-5be6ed30574c | note | Frequency - Each Lease Pad
a8793191-7fcd-53d6-8681-924c8889c966 | note | Test Method - Visual Inspection
c4fd0221-377e-592a-83ad-2e5965dd7f94 | note | Acceptance Criteria - As per Client Procedure
9f39dc98-e6f3-5986-8deb-a01d640dcb6f | note | Verifying Documents - Lease Rehab FIC
fe532af7-2d16-5ff4-8778-f04698397e7c | note | Responsibility: RSA - M
caa87182-ed5d-4c8f-90dd-e2c20e2bd9a3 | checkpoint | 2.3 - ESC in working order (Ensure no sediment is past the containment point)
b7d38e7a-f2c1-5e6b-a7aa-405ee61ce651 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-003
094a620e-b71c-5ed0-bad2-771ed45cf321 | note | Frequency - Each Lease Pad
c8b545d5-e65f-55d6-8111-90f74d41b097 | note | Test Method - Visual Inspection
10c64356-21fc-5f67-a520-4c2f00264588 | note | Acceptance Criteria - As per Client Procedure
17016f7a-f476-5fde-a06f-6ce59177497c | note | Verifying Documents - Lease Rehab FIC
8423b96a-15c3-547c-831f-c8c974259b09 | note | Responsibility: RSA - M
d6e69d8a-afef-4110-b4d2-5fe0ad47e8a3 | checkpoint | 2.4 - Install table drain and/or clean out (If required)
0fdb62dd-3c21-5881-832d-a28c72dc908a | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client IFC Well Pad Cut Fill Lease Pad Layout Drawing
b5700798-a1c0-5d50-b8d4-70d96ab79d20 | note | Frequency - Each Lease Pad
eff86c0e-6395-5155-b2b9-053ab7e229e2 | note | Test Method - Visual Inspection
eb65ab5b-227e-569d-8b25-718687c092f8 | note | Acceptance Criteria - Client IFC Well Pad Cut Fill Lease Pad Layout Drawing
41f0fe1e-3b68-5d93-80b2-dfa34c733896 | note | Verifying Documents - Lease Rehab FIC
a4017539-96b2-5b44-9e96-6641b2eebd4c | note | Responsibility: RSA - M
f562990a-c2b0-4ac7-84ee-5e0d0e149b9f | checkpoint | 2.5 - Clean out shot rock sump & tidy up (if required)
75f11821-8907-5a32-b8d1-3d0062b03792 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure OPS-QLDS-CI-SPE-002
76cc3f29-c5d7-5fe7-9f98-3a4c8876f003 | note | Frequency - Each Lease Pad
1ebaca2e-cfda-59e7-b85d-13e596bf5245 | note | Test Method - Visual Inspection
826628db-8465-54c3-bc30-57bcba5c6f93 | note | Acceptance Criteria - Rock shall be no smaller than 150 millimetres and no greater than 300 millimetres and free of course to fine-grained material
e75dd16d-a5a7-56d4-9757-94a512fcb18c | note | Verifying Documents - Lease Rehab FIC
f156ee74-dfca-5e08-b12c-047e54d6a8bc | note | Responsibility: RSA - M
95092bb1-c665-4c89-8ab6-42df54e79246 | checkpoint | 2.6 - Amelioration (Gypsum / Lime) (If required)
153e7420-3f8d-5f4d-912e-d0d2a49f73aa | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client IFC Well Pad Cut Fill Lease Pad Layout Drawing
28dd7501-1955-5141-bb84-ad883a5008ab | note | Frequency - Each Lease Pad
f0188a80-26b8-594b-b9dc-cfa3c82d078e | note | Test Method - Visual Inspection
9503fc8b-e49c-5778-9486-f6476cd4c746 | note | Acceptance Criteria - As per Client Procedure
4f627d07-a29e-59a8-86fc-222cb0574e0c | note | Verifying Documents - Lease Rehab FIC
5491ac11-2e76-511a-a76e-9a417f4a129d | note | Responsibility: RSA - M
f80a3cde-56e4-435a-b6c3-1cc35f7a5e2c | checkpoint | 2.7 - Rip Sub Soil Areas
2f2fdb26-136e-5198-ad5a-8157554f6449 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002
b9eca10f-92dc-5f7b-97ad-4a88cd04abf3 | note | Frequency - Each Lease Pad
21caa1d3-3d2a-5a8a-9411-a7952967324c | note | Test Method - Visual Inspection
11dc2da2-847b-5c44-a683-4f97eb5d057f | note | Acceptance Criteria - As per Client Procedure
61b07435-8764-525d-bb47-1f5f1afa6a72 | note | Verifying Documents - Lease Rehab FIC
0a7696e3-da9b-5d82-8a5c-130cc2959ecd | note | Responsibility: RSA - M
e6971544-97dc-47f3-8b36-b9b9f6966eaf | checkpoint | 2.8 - Reclaim topsoil from batters and topsoil stock pile where available
7ddcc75c-01b2-5cdf-bda7-7077b14f90c7 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002
5ccde400-760e-5eb1-bfca-b1ab7d272d2e | note | Frequency - Each Lease Pad
12ed2646-eb7a-5060-b5ee-4718a2a96bfe | note | Test Method - Visual Inspection
91b47a49-0ded-52e4-9888-25888449fa83 | note | Acceptance Criteria - As per Client Procedure
4777c4ac-f0ed-5405-ba7d-666fc4b334e1 | note | Verifying Documents - Lease Rehab FIC
4ab4c064-b113-5c2e-9ef3-887c06ec9d8e | note | Responsibility: RSA - M
a43fdbf0-159d-4e6e-9af3-dd1535c99ea7 | checkpoint | 2.9 - Transport and Spread Topsoil
7a0db8e8-a9c5-55ae-b7ee-53a7ccd33791 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002
b51e3e11-fabf-5200-8798-d372e92f862e | note | Frequency - Each Lease Pad
e08e489d-5f57-5d4c-8597-fd5c11152f8e | note | Test Method - Visual Inspection
09b07c33-9fb8-5f42-a2ed-6316f6dd4d40 | note | Acceptance Criteria - Respread topsoil (should be a minimum depth of 150mm uncompacted, if material available). Ensure topsoil and subsoil are not mixed
93956bb8-9414-59cf-806e-a30463abdfec | note | Verifying Documents - Lease Rehab FIC
c055f025-32b0-5aac-84c9-ffacbae7cd9c | note | Responsibility: RSA - M
3e4ae3c8-e1ea-42c0-ace4-142f368bdcfc | checkpoint | 2.10 - Fertiliser, Seed & Scarify
c626b688-0689-5528-b1aa-b3658c1f246e | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002 Client LARS
97c1da7c-971d-5508-86fd-3a7419280756 | note | Frequency - Each Lease Pad
38755bfa-c8c9-5d22-aed0-385e453f39b3 | note | Test Method - Visual Inspection
c9092118-e745-59b9-936f-db41e651182d | note | Acceptance Criteria - As per Client Procedure
1cb2240e-2ba6-56e8-a9fd-3fac8116a13a | note | ○ Seed mix uses native or pasture grasses and does not contain pest species.
86ab01a4-2de7-5e2c-a241-5d3986e7b0ae | note | ○ Seed mix meets landholder requirements.
2ae0da72-4985-52d4-bbbd-6e3dde2a6e59 | note | Verifying Documents - Lease Rehab FIC
ad104881-2b63-5bad-99ac-08fc9e7fbeb6 | note | Responsibility: RSA - M
ed4d3f31-d298-4510-8ab2-d752d39fd38f | checkpoint | 2.11 - Confirm As Con Map has been completed & received
c87b1461-862b-545b-9bb4-27ae413d6e62 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Marked Drawing
b49edd54-491f-5944-aac0-a4df3df8509e | note | Frequency - Each Lease Pad
19f49c4d-6481-501f-a0a3-44d4356a24d3 | note | Test Method - Documentation
ec2147f0-ed10-51f4-b1af-194b02a75c82 | note | Acceptance Criteria - As Con Maps
b5f35005-efb7-5eeb-8080-19f08a927767 | note | Verifying Documents - Lease Rehab FIC
4c81f575-a1c5-5137-a549-208dafb5b98d | note | Responsibility: RSA - M
7e61e785-0156-4152-9948-cdbf4dfc27c1 | checkpoint | 2.12 - RSA QA inspection
3aa1af22-f516-5c33-aec9-1260f3c5ab37 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications
bd01f58a-fdbc-521d-ab66-5d731ebe9f83 | note | Frequency - Each Lease Pad
4a0bb0d1-ce2d-5ae2-9fe8-806b48cf6277 | note | Test Method - Visual Inspection
8c4e913a-8f71-5efb-915c-0a68b7cb8652 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
1f2b9e87-f883-5a20-8f4c-4f46ebe93705 | note | Verifying Documents - Lease Rehab FIC
7bb5ab0c-5018-565f-983b-e9d6e1c6013d | note | Responsibility: RSA - H
73ed2f5b-365e-454c-adba-44fafd73f38b | signoff | HOLD POINT
0ee9ab5d-06eb-4ee8-927b-17208bd34c98 | section | Reference Documents
a56b5f0c-45b0-4509-864d-23306e5a5d4c | checkpoint-no-value | Reference Documents:
d0a11dab-95fb-59b4-a524-5cb6700d9d3b | note | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
a6560c1f-efd1-5c46-9404-19e7b4cbd1ce | note | OPS-QLDS-CI-SPE-002 Rev 0 (Lease Pads, Hardstands, Access Roads Civil Specification)
8b8c582e-773a-597d-8e6f-854899b45923 | note | SENEX-QLDS-EN-PRC-002 Rev 0 (QLD Reinstatement and Rehabilitation Procedure)
c837dd6b-7f2f-5e5e-9833-34e95026a3e0 | note | OPS-QLDS-CI-GAR-001 Rev 1A (Well Lease Layout Standard Drill Rig Civil General Arrangement)
e211f5db-7550-45b3-a4a8-00049443b9b0 | section | To be completed upon completion of all work activities
2b0244c7-a6c5-4a38-b84d-160687ef619d | checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
f267cdd6-0751-5b44-a69e-336419424aa4 | note | Completed By:
93a554d7-e2d8-52b6-b42d-ee7394b448ae | textbox | Contractor Representative - Name:
67eefc2a-c431-59a7-a0be-922e3389c6d3 | textbox | Contractor Representative - Position:
04e02a4e-8dd6-5fe8-b15f-c8f8b8bae386 | textbox | Senex Construction Representative - Name:
f26d7c28-3488-5ee3-be9f-ae168765aaa7 | textbox | Senex Construction Representative - Position:
079a70e5-4416-57c9-90b2-c6ce34c9d748 | note | Approved By:
c0bf5851-ad24-5dea-90c9-b256804b27de | textbox | Client Representative - Name:
4006764f-730c-5a59-92d1-147922cab259 | textbox | Client Representative - Position:
2178f7fd-a807-5e68-8a25-9801ac3afade | date | Date:
27182873-c4e1-4e38-9726-0cd9d4cb7397 | signoff | Add Signature