## Checklist Template Builder
Component | Name | Values
checklist | Fitout- Interior Wall
section | Prestart
checkpoint | Check materials delivered (e.g. GIB toughline/Standard etc.)
checkpoint | Check Latest Architectural Drawings
checkpoint | Area clear and dry
checkpoint | Check slab levels and shear walls quality (grinded and clean)
checkpoint | Check T&B levels and drops
checkpoint | Confirm Grid lines lay-out and RL offset level clearly marked
section | Installation
section | Framing
checkpoint | DPC installed
checkpoint | check correct gauge of materials/screw used
checkpoint | Check and confirm studs and track spacing per area of installation
checkpoint | Confirm door opening with schedule
checkpoint | Check Head track installation
checkpoint | Check framing nogs installed
checkpoint | Attached SubCon QA
checkpoint | Inspect final set-out detail and check with ITP
section | Insulation
checkpoint | Check type and R value used (e.g., PINK® BATTS® R2.2).
checkpoint | Confirm proper installation, (No gaps, compression)
section | Lining
checkpoint | Inspect materials for compliance (e.g., GIB® TOUGHLINE, NOISELINE).
checkpoint | Confirm linings fixed to framing with appropriate fasteners
section | Electrical and Plumbing Penetrations:
checkpoint | check penetrations
checkpoint | Insure proper sealing around penetrations
section | Post Installation
checkpoint | Conduct overall visual inspection.
checkpoint | Check for damage, defects or poor workmanship
checkpoint | Confirm that all fire-rated walls meet the GIB specs
checkpoint | Ensure smoke-rated walls comply with the required standards.
checkpoint | Verify that fire stopping is complete and compliant for all penetrations and junctions.
checkpoint | Confirm SubCon QA signoff

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty