## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Facade - Eaves and Roof
section | Prestart
checkpoint | Steel & panel QA
checkpoint | Verify roofing system specifications and requirements.
checkpoint | Confirm delivery and quality of roofing materials
checkpoint | Ensure proper site access and safety measures.
checkpoint | Review plans for vents, electrical, mechanical, and other service penetrations.
section | Eaves
checkpoint | Framing - DPC between Timber and Steel
checkpoint | Framing - Timber frame fixings to steel frame/purlins
section | Services
checkpoint | Services signoff/QA including nogs
tickbox | i. Vents
tickbox | ii. Electrical
tickbox | iii. Mechanical
tickbox | iv. Others
checkpoint | Roof Installation
checkpoint | 1. Underlayment and Insulation:
checkpoint | Make sure roof underlayment is installed as per the manufacturer’s instructions.
checkpoint | Insulation is installed evenly with no gaps.
checkpoint | Confirm vapor barriers and moisture controls are in place.
section | 2. Roofing Membrane and Flashing:
checkpoint | Check the membrane is fully attached and seams are sealed.
checkpoint | Ensure flashing is installed around edges, vents, and chimneys.
checkpoint | Inspect parapet caps and joints for correct sealing.
section | 3. Roofing Panels:
checkpoint | Panels are aligned and fastened securely.
checkpoint | Closure strips and fasteners are correctly installed.
checkpoint | Roof edges, ridges, and valleys are properly sealed.
section | 4. Gutters and Drainage:
checkpoint | Internal gutters and downspouts are securely attached and sloped for drainage.
checkpoint | Gutters are free from obstructions.
checkpoint | Waterproofing around gutters is properly sealed.
section | 5. Skylights and Roof Penetrations:
checkpoint | Skylights and roof hatches are sealed and flashed properly.
checkpoint | Check for waterproofing around all penetrations.
section | 6. Fasteners and Fixings:
checkpoint | Correct type and size of fasteners used, installed securely.
checkpoint | Ensure no loose or missing fasteners.
section | 7. Safety Systems
checkpoint | Inspect installation of safety balustrades and maintenance walkways.
checkpoint | Ensure abseiling points and plant screens are correctly installed.
section | Council Inspection
checkpoint | Roof framing inspection report received and closeout
checkpoint | Wraps inspection report received and closeout
checkpoint | Roof Substrate inspection report received and closeout
checkpoint | Roof/deck membrane inspection report received and closeout
section | Post-Installation
checkpoint | Inspect all flashings and sealants for integrity and coverage.
checkpoint | Ensure removal of all debris and waste from the roof and site.
checkpoint | Perform water test to check for leaks and proper drainage.
checkpoint | Roof signoff/QA
checklist | Facade - External Cladding
section | Prestart
checkpoint | Verify materials specified in the plans match the delivery (e.g., timber, cladding systems, insulation).
checkpoint | Verify that materials are stored correctly to prevent damage.
checkpoint | Check that the site is safe and accessible for installation.
checkpoint | Confirm the area is clean and free of debris.
section | Pre-Installation
section | Substrate and Framework:
checkpoint | Inspect timber or steel framing (e.g., 140mm timber framing, 92mm steel stud)
checkpoint | Confirm the installation of GIB® Weatherline® or other specified internal linings as per dwg.
section | Cladding and Insulation:
checkpoint | Check that insulation values, (e.g. R3.2 insulation for wall types) are installed as specified
checkpoint | Ensure all substrate surfaces are clean and ready for cladding installation, with proper
checkpoint | Preparation of moisture barriers and flashing.
section | Fire and Acoustic Compliance:
checkpoint | Review fire rating and acoustic insulation requirements, (GIB® FYRELINE for fire-and GIB
NOISELINE for acoustic walls.)
checkpoint | Ensure fireproofing systems and expansion joints are correctly positioned as per drawings.
section | Council Hold Points
checkpoint | Council inspection wall frame and underlay report received and close-out
section | Installation
checkpoint | Cladding Panel
checkpoint | Verify that cladding materials like 3mm powder-coated aluminum and 55mm STOPOREN
render system are installed according to design intent.
checkpoint | Check for uniform panel alignment, consistent spacing, and proper attachment to the
underlying structure with specified fixings.
checkpoint | Confirm that the cavity behind the cladding (e.g., 20mm cavity for some wall types)
section | Fixings and Anchoring
checkpoint | Ensure all fasteners, anchors, and fixing systems are secured according to design.
checkpoint | Check that fixing points are properly aligned with the structural framework
section | Sealing and Flashing
checkpoint | Inspect sealant joints, weatherproofing membranes, and flashing around penetrations
checkpoint | Ensure that all exposed joints and edges are sealed to prevent water ingress
section | Council Hold Points
checkpoint | Council mid-installation inspection for cladding, insulation, and internal lining received and closeout
section | Post-Installation
checkpoint | Conduct a thorough inspection of the completed facade cladding.
checkpoint | Ensure all cladding is securely fixed and aligned.
checkpoint | Check that all joins and seals are properly completed.
checkpoint | Confirm and inspect correct primers and coat numbers for any paint finishes as per specification
checkpoint | Subcontractors QA received
section | Council Hold Points
checkpoint | Arrange a final inspection with the council to sign off the completed work.
checklist | Fitout - Interior Wall
section | Prestart
checkpoint | Check materials delivered (e.g. GIB toughline/Standard etc.)
checkpoint | Check Latest Architectural Drawings
checkpoint | Area clear and dry
checkpoint | Check slab levels and shear walls quality (grinded and clean)
checkpoint | Check T&B levels and drops
checkpoint | Confirm Grid lines lay-out and RL offset level clearly marked
section | Installation
section | Framing
checkpoint | DPC installed
checkpoint | Check correct gauge of materials/screw used
checkpoint | Check and confirm studs and track spacing per area of installation
checkpoint | Confirm door opening with schedule
checkpoint | Check Head track installation
checkpoint | Check framing nogs installed
checkpoint | Attached SubCon QA
checkpoint | Inspect final set-out detail and check with ITP
section | Insulation
checkpoint | Check type and R value used (e.g., PINK® BATTS® R2.2).
checkpoint | Confirm proper installation, (No gaps, compression)
section | Lining
checkpoint | Inspect materials for compliance (e.g., GIB® TOUGHLINE, NOISELINE).
checkpoint | Confirm linings fixed to framing with appropriate fasteners
section | Electrical and Plumbing Penetrations:
checkpoint | Check penetrations
checkpoint | Insure proper sealing around penetrations
section | Post Installation
checkpoint | Conduct overall visual inspection.
checkpoint | Check for damage, defects or poor workmanship
checkpoint | Confirm that all fire-rated walls meet the GIB specs
checkpoint | Ensure smoke-rated walls comply with the required standards.
checkpoint | Verify that fire stopping is complete and compliant for all penetrations and junctions.
checkpoint | Confirm SubCon QA signoff
checklist | Fitout - Internal Waterproofing
section | Pre-start
checkpoint | Floor cleared from waste materials and are in correct locaion, flush and grinded down
checkpoint | Confirm primer used to floors and walls as per specification; curing time
checkpoint | Check correct fall and levelling compound are available
checkpoint | Confirm RL's on levelling compound in relation falls and door clearance
section | Installation
checkpoint | Confirm correct mixing ratios of materials
checkpoint | Check for uniform application without gaps or bubble
checkpoint | Ensure proper curing time is followed
section | Joint Sealing
checkpoint | Inspect all joints sealing and proper sealing used
section | Flood testing
checkpoint | Perform 24 hrs flood test
checkpoint | Observed signs of leakage or water penerations
checkpoint | If found with leaks - reflood, and retest
checkpoint | Subcon to submit QA checkilst report